## Sheet1
Sr no | Module | Defects | Priority | Issue reported | Testing Remark
1 | MASTERS | Though not edited, successful message when navigated to back page. | Low | No | Informed verbally
2 | MASTERS | Data found pop up message when the page opened. | Low | No | Informed verbally
3 | VENDOR MASTER | Showing invalid mail ID when the mail ID provided in caps. | Medium | No | Informed verbally
4 | VENDOR MASTER | In edit, the beneficiary's name can be edited. | Medium | Not a bug | Not an issue. This authority based.
5 | BILL CHECKING TRANSACTION | Payment history button is showing twice and blocker. | High | No | This issue was not occured while testing last week. Currentlt facing same issue.
6 | BILL CHECKING TRANSACTION | Bill history button is missing. | High | No | This issue was not occured while testing last week. Currentlt facing same issue.
7 | BILL CHECKING TRANSACTION | View and edit - even though 1 iteration, showing multiple iterations in the data below. | Medium | NA | Scenario not tested. In this case bill creator, assigned to person and approver is a same user.
8 | BILL CHECKING TRANSACTION | Double successful pop ups when bill approved. | Low | No | Informed verbally
9 | BILL CHECKING TRANSACTION | When bill is rejected, the creator is getting the option to approve/ reject the bill. | Medium | No | Scenario not tested. In this case bill creator, assigned to person and approver is a same user.
10 | BILL CHECKING TRANSACTION | When the bill completes the entire approval process, the assigned person is getting the option to approve/ reject the bill. | Medium | No | Scenario not tested. In this case bill creator, assigned to person and approver is a same user.
11 | BILL CHECKING TRANSACTION | When bill checking transaction page refreshed, the pop up - bill successfully updated message is displayed. | Low | No | Informed verbally
12 | BILL CHECKING TRANSACTION | When searched through filter and canceled bill, in the history, the record is displayed 3 times. | Medium | Not a bug | Issue not found. Do refer the recording.
13 | APPROVAL SETTINGS | TDS Constitution authority is not working. | High | NA | Not in scope
14 | APPROVAL SETTINGS | Unable to update the payment status, even though update payment details authority provided. The data is not getting submitted. | High | Not a bug | Issue not found. Do refer the recording.
15 | APPROVAL SETTINGS | Unable to update the payment status, even though payment status release authority provided. The data is not getting submitted. | High | Not a bug | Issue not found. Do refer the recording.
16 | APPROVAL SETTINGS | When 2 authorities, update payment details and payment status release authorities provided. The system is accepting only the latest authority provided, but not the merging of the authorities. | High | NA | Not in scope as there are 5 setting related to payment details page. These conbinations were not cleared earlier and were not awared about these combinations.
17 | APPROVAL SETTINGS | Showing invalid sub-module name in the grid view. | Medium | No | Priority could be Low
18 | APPROVAL SETTINGS | Record room authority is not working. | High | NA | Not in scope
19 | APPROVAL SETTINGS | Pre-pone payment date authority is not working. | High | Not a bug | Issue not found. Do refer the recording.