## data
Sr no | sprint Name | Sprint Start date | Sprint End Date | Task Name | Task Users | Task Start Date | Task End Date | Task actual completed date | Task scheduled hours | Task actual hours played | Task status | Actual status
1 | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation module bug solving | Asmita Margaje | 2024-10-03 | 2024-10-03 |  | 04:00:00 | 18:31:46 | IN_PROGRESS | DELAY
2 | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for automation | Amreen Shaikh | 2024-10-04 | 2024-10-04 | 2024-10-09 16:55:03 | 00:00:00 |  | COMPLETED | DELAY
3 | E2E Testing | 2024-09-30 | 2024-10-12 | Retesting Documentation Module | Swapnil Ramdasi | 2024-10-03 | 2024-10-03 |  | 03:00:00 |  | TO_DO | DELAY
4 | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil - report preparation | Amreen Shaikh | 2024-10-03 | 2024-10-03 | 2024-10-09 16:57:49 | 00:00:00 |  | COMPLETED | DELAY
5 | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for document module | Amreen Shaikh | 2024-10-03 | 2024-10-03 | 2024-10-09 16:55:48 | 00:00:00 |  | COMPLETED | DELAY
6 | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for document module | Swapnil Ramdasi | 2024-10-03 | 2024-10-03 | 2024-10-09 16:55:48 | 00:00:00 |  | COMPLETED | DELAY
7 | E2E Testing | 2024-09-30 | 2024-10-12 | test | Swapnil Ramdasi | 2024-10-03 | 2024-10-03 | 2024-09-27 17:54:38 | 00:00:00 |  | COMPLETED | IN_TIME
8 | E2E Testing | 2024-09-30 | 2024-10-12 | Doc Module Sync call | Priyanka Gole | 2024-10-01 | 2024-10-04 | 2024-10-04 18:26:18 | 01:00:00 | 00:55:31 | COMPLETED | IN_TIME
9 | E2E Testing | 2024-09-30 | 2024-10-12 | Doc Module Sync call | Asmita Margaje | 2024-10-01 | 2024-10-04 | 2024-10-04 18:26:18 | 01:00:00 | 00:54:45 | COMPLETED | IN_TIME
10 | E2E Testing | 2024-09-30 | 2024-10-12 | Doc Module Sync call | Swapnil Ramdasi | 2024-10-01 | 2024-10-04 | 2024-10-04 18:26:18 | 01:00:00 |  | COMPLETED | IN_TIME
11 | E2E Testing | 2024-09-30 | 2024-10-12 | Bugs Solving | Reshma Gawade | 2024-10-03 | 2024-10-08 | 2024-10-08 18:28:38 | 01:18:00 | 01:13:52 | COMPLETED | IN_TIME