## Summary
Version History | [5 empty] | Iteration Summary
Date | Author | Version | Approved by | Total Tcs. | Remark | Sub Module | Iteration category | Iteration Count | Start Date | End Date | Total Tcs | Total Defects | Remark
14/10/2024 |  | V1.1 |  |  | Initial draft | Branchwise Counterwise Item Mapping | Initial Phase | 1 | 14/10/2024 | 14/10/2024

## Report
Test execution report | Status Dt 9/10/2024 | [5 empty] | Tester Status 09/12/2024 | (Multiple Items)
Submodule | Fail | NA | Pass | Suggestion | Grand Total
Consolidated View | 14 | 6 | 13 | 1 | 34 |  | Count of Sr No | Severity
General Setting | 1 |  | 1 | 1 | 3 |  | Priority | High | Low | Medium | Grand Total
Grand Total | 15 | 6 | 14 | 2 | 37 |  | High | 3 | 1 | 2 | 6
Status Dt 9/10/2024 | Fail | [5 empty] | Medium |  | 2 | 4 | 6
[7 empty] | Grand Total | 3 | 3 | 6 | 12
Severity
| High | Medium | Grand Total
Test execution report | 11 | 4 | 15
[6 empty] | Status Dt 9/2/2024 | Fail
[6 empty] | Count of Case ID | Severity
[6 empty] | Submodule | High | Low | Medium | Grand Total
Daily Summary Report - 6/10/2024 | [5 empty] | Consolidated View | 6 | 1 | 9 | 16
[6 empty] | General setting |  |  | 1 | 1
Submodule | Test case execution status |  |  |  |  | Grand Total | 6 | 1 | 10 | 17
Consolidated View | 39
Grand Total | 39

## Consolidated Report (hidden)
Date | Failed test case status report - 9/3/2024 | [5 empty] | Remark | Date | Failed test case status report - 9/12/2024 | [5 empty] | Remark
2024-09-03 | Very High | High | Medium | Low | Grand Total |  |  | 2024-09-12 | Very High | High | Medium | Low | Grand Total
|  | 6 | 10 | 1 | 17 |  |  |  |  | 11 | 4 |  | 15
| Defect Status report - 9/3/2024 | [5 empty] | Remark |  | Defect Status report - 9/12/2024 | [5 empty] | Remark
| Severity / Priority | High | Medium | Low | Very High | Grand Total |  |  | Severity / Priority | High | Medium | Low | Very High | Grand Total
| High | 1 |  | 2 |  | 3 |  |  | High | 3 | 2 | 1 |  | 6
| Medium |  | 7 |  |  | 7 |  |  | Medium |  | 4 | 2 |  | 6
| Low |  |  |  |  | 0 |  |  | Low |  |  |  |  | 0
| Very High |  |  |  |  | 0 |  |  | Very High |  |  |  |  | 0
| Grand Total | 1 | 7 | 2 | 0 | 10 |  |  | Grand Total | 3 | 6 | 3 | 0 | 12
| Test case execution status Report - 9/3/2024 | [5 empty] | Remark |  | Test case execution status Report - 9/12/2024 | [5 empty] | Remark
| TCs Status / Submodules | Pass Tcs | Fail Tcs | Other / Not Executed | Total Tcs |  |  |  | TCs Status / Submodules | Pass Tcs | Fail Tcs | Other / Not Executed | Total Tcs
| Consolidated View | 13 | 16 |  | 29 |  |  |  | Consolidated View | 13 | 14 | 8 | 35 |  | Out of 8 not executed cases : 2 are suggestion and 6 are NA cases
| General setting |  | 1 |  | 1 |  |  |  | General setting | 1 | 1 |  | 2
| Grand Total | 13 | 17 | 0 | 30 | [7 empty] | 0
[9 empty] | Grand Total | 14 | 15 | 8 | 37

## TPM_Sheet
Ticket ID | TT21405 | Released Version
Project live Date |  | Project Name | Connect us 1.0
Module Name | Sales Incentive | Test Cases Reviewed By | Amreen
Testing Owner | Digvijay Tulse | Ticket Owner | Priyanka Gole | #######
Testing URL | http://10.2.11.40/connectus-testing/admin/ | Email / User Name | Haridas | 123456
Password
Description | Counter employee mapping by excel uploading in sales incentive flow
| 6 | 6 | 6 | 0 | 0 |  |  | 1 | 1 | 1 | 26 |  | 26 | 26 | 2
26 | 20 | 20 | 20 | 26 | 26 |  |  | 25 | 25 | 25 | 0 |  | 0 | 0 | 24
Case ID | Module | Submodule | Req Id | Function | Testing Type | Platform | Field | Test Description | Test steps | Expected Result | Actual Result | Screen Shot | Status Dt 9/2/2024 | Priority | Severity | Written Date | Review Remark | BA Remark | Developer Remark | Last Updated Date
TC_01 | Sales Incentive | Branchwise Counterwise Item Mapping | BR001 --In the sales Incentive download template for counter wise item mapping. | Download | UI | Web |  | Verify whether the headers are in given sequence | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Move to the path of downloaded template. 8.Open the excel sheet. | All headers i.e target group,branch,counter,item,remark should be in a sequence. |  |  |  |  | Medium
TC_02 | Sales Incentive | Branchwise Counterwise Item Mapping | BR001 --In the sales Incentive download template for counter wise item mapping. | Download | Usability | Web | Download | Verify whether the download template button is enabled | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button | Once user press the button , excel template should start downloading and get stored on the defined path. |  |  |  |  | High
TC_03 |  |  |  | Download | Functionality | Web |  | Verify whether the file is getting downloaded in .csv extension. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button | Downloaded file should be in .csv format |  |  |  |  | Medium
TC_03 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Usability | Web | Upload | Verify whether the upload button is enabled | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Press on upload button. | Error message should be thrown - please select the valid file |  |  |  |  | High
TC_04 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Functionality | Web |  | Verify whether the user is able to upload the excel file (.xlsx)with valid mapped data. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add valid data with correct mapping and save in .xlsx file extension. 8.Upload the excel file. | Excel file should get uploaded successfully. 1. Uploaded data get reflected under specific column header at grid view |  |  |  |  | High
TC_05 | Sales Incentive | Branchwise Counterwise Item Mapping | BR001 --In the sales Incentive download template for counter wise item mapping. | Download | Functionality | Web |  | Verify user is able to download the file in CSV format | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button | 1) Downloaded file should be in CSV format 2) Download template should be displayed with following headers - Sr. no, Target group , Branch , Counter , Item , Remark. 2)This template should be editable. |  |  |  |  | High
TC_06 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web |  | Verify whether Target group , Branch , Counter , Item fields are mandatory. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Open the downloaded excel file. 7.Don't add the data in the Target group ,Branch ,Counter , Item block. 8.Upload the excel file. | Valid error message should be thrown when we upload this file without mandatory field. |  |  |  |  | Medium
TC_07 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web | Target Group | Verify whether Target group field is active. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Open the downloaded excel file. 7.Check status from master and add active files. 8.Upload the excel file. | File should get uploaded successfully if the field is active |  |  |  |  | Medium
TC_08 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web |  | Verify whether Branch field is active. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Open the downloaded excel file. 7.Check status from master and add active files. 8.Upload the excel file. | File should get uploaded successfully if the field is active |  |  |  |  | High
TC_09 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web |  | Verify whether Counter field is active. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Open the downloaded excel file. 7.Check status from master and add active files. 8.Upload the excel file. | File should get uploaded successfully if the field is active |  |  |  |  | High
TC_10 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web |  | Verify whether Item field is active. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Open the downloaded excel file. 7.Check status from master and add active files. 8.Upload the excel file. | File should get uploaded successfully if the field is active |  |  |  |  | High
TC_11 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web |  | Verify whether the remark field is optional | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Open the downloaded excel file. 7.Do not add the data in the remark field and add valid data in all the other fields. 8.Upload the excel file. | The file should upload successfully and display a success message without any error for remark field |  |  |  |  | Medium
TC_08 |  |  |  | Upload | Validation | Web |  | Verify whether all columns accepts space, special characters. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Open the downloaded excel file. 7.Add space and $ in all blocks and upload the excel | Error message should be thrown after uploading the file |  |  |  |  | Medium
TC_12 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web |  | Verify whether the user is able to upload excel file containing the valid data | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Add Valid data in all the fields. 7.Upload the excel file. | The file should upload successfully and display a success message |  |  |  |  | High
TC_13 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Validation | Web |  | Verify whether the user is able to upload empty excel file . | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Do not add the data in all the blocks. 7.Upload the excel file. | The file should not get uploaded and an error message should be thrown. |  |  |  |  | High
TC_14 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | upload | Validation | Web |  | Verify whether the user is able to upload file with other extensions like - .doc, .docx, .pdf, .pptx, .png, .jpeg, .mp4 | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Now add the file types with following extensions- .doc, .docx, .pdf, .pptx, .png, .jpeg, .mp4 | No any file should get uploaded. |  |  |  |  | High
TC_15 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | upload | Validation | Web |  | Verify user is able to upload the file size >=5 MB | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Upload the excel file with size greater than the allowed size. | File should not get uploaded and an error message should be thrown indicating the allowed size |  |  |  |  | Medium
TC_16 | Sales Incentive | Branchwise Counterwise Item Mapping | BR001 --In the sales Incentive download template for counter wise item mapping. | View | UI | Web |  | Verify the spelling of Headers | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Move to the path of downloaded template. 8.Open the excel sheet. | All the headers should be spelled properly. |  |  |  |  | Medium
TC_17 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Functionality | Web |  | Verify whether the user is able to upload the excel file (.csv) with valid mapped data. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add valid data with correct mapping and save in .csv file extension. 8.Upload the excel file. | 1.Excel file should get uploaded successfully. 2.Uploaded data must get reflected under specific column header at grid view.
TC_18 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Functionality | Web |  | Verify whether the user is able to upload the excel file (.xls)with valid mapped data. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add valid data with correct mapping and save in .xlsx file extension. 8.Upload the excel file. | 0 |  |  |  |  | High
TC_19 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Functionality | Web |  | Verify whether system accepts unmapped data with active status | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add valid(active) data with incorrect mapping and save in .xlsx file extension. 8.Upload the excel file. | 1.Excel file should not get uploaded successfully . 2.Valid error should be thrown indicating that the added data is not mapped. |  |  |  |  | High
TC_20 | Sales Incentive | Branchwise Counterwise Item Mapping | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. | Upload | Functionality | Web |  | Verify whether system accepts mapped data with active status. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add data with correct mapping and save in .xlsx file extension. 8.Upload the excel file. | 1.Excel file should get uploaded successfully . |  |  |  |  | High
TC_10 |  |  |  | Upload | Functionality | Web |  | Verify system behaviour where from master deactive whether deleted data from master is getting uploaded. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add data which is deleted from master and save in .xlsx file extension. 8.Upload the excel file. | Error should be thrown indicating that the data is invalid. |  |  |  |  | Medium
TC_11 |  |  |  | Upload | Functionality | Web |  | Verify whether the data in file is matching the data in master(including spaces , special characters) | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add field value same from master with space and special charater and save in .xlsx file extension. 8.Upload the excel file. | File should get uploaded successfully without any error.
TC_12 |  |  |  | Upload | Functionality | Web |  | Verify file not get uploaded in case user tried to upload the data which is already present in the grid view | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add data with correct mapping and save in .xlsx file extension. 8.Upload the excel file. 9.Again upload the same file. | 1.Error file with duplicate data/already exist should be thrown and file should not get uploaded . 2.If data is repeated twice in excel file then that data should be shown only once in grid view once the file gets uploaded. 3.If we add Deactive data from grid view then that data must be shown active once the file gets uploaded. |  |  |  |  | Medium
TC_13 |  |  |  | Upload | Functionality | Web |  | Verify whether the system don't upload the file if user press cancel after pressing the upload button. Verify File not get uploaded in case user cancel while uploading the file | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add data with correct mapping and save in .xlsx file extension. 8.Upload the excel file and simultaneously stop the uploading | 1.File should not get uploaded and data should not get stored. 2.Upon click on cancel button user landed to "Branchwise Counterwise Item Mapping " page -grid view |  |  |  |  | Medium
TC_14 |  |  |  | Upload | Functionality | Web |  | Verify file not get uploaded in case internet is off | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add data with correct mapping and save in .xlsx file extension. 8.Upload the excel file and simultaneously put off the network connection. | File should not get uploaded successfully. |  |  |  |  | Medium
TC_15 |  |  |  | Upload | Functionality | Web |  | Verify file not uploaded in case branch is marked as without Incentive | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Open the excel file. 7.Add branch to which incentive is not applicable. 8.Upload the excel file and simultaneously stop the uploading | 1.File should not get uploaded . 2.Error message should be thrown as - Sales incemntive is not applicable to the added branch . |  |  |  |  | Medium
TC_21 | Sales Incentive | Branchwise Counterwise Item Mapping | BR001 --In the sales Incentive download template for counter wise item mapping. | Download | Usability | Web |  | Verify whether the headers of the template are in title case. | 1. Click on the URL- http://10.2.11.40/connectus-testing/admin 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Sales Incentive" menu 5. Click on Sales Mapping > Branchwise Counterwise Item Mapping 6.Click on Download Template button 7.Move to the path of downloaded template. 8.Open the excel sheet. | All headers should be in Title case. |  |  |  |  | Medium
Note on K25: user: Query - Are the special characters allowed in Target group , Branch,counter ,item ?
Note on K29: user: Please mention the allowed size of excel file

## TPM_MISC
Testing Type | Status | Priority / Severity | Tester remark | Developer remark | BA Remark | Functions | Req id | Req desc | Platform
Functionality | Pass | High | Closed | Resolved | Closed | Add | BR001 - In the sales Incentive download template for counter wise item mapping. |  | App
Intergration | Fail | Medium | Pending | Not a bug | Re-open | Edit | BR002 - In the sales Incentive bulk upload counter wise item mapping by excel sheet. |  | Website
Validation | Not Executed | Low | Re-open | Deffered | Deffered | View |  |  | Web Application
UI | Under Development | Very High | Blocker | In-Progress | Not a bug | Delete
Usability | Suggestion |  | Re-Test | Development Completed |  | Search
Compatibilty | NA |  |  |  |  | Gird view
Security | Next Phase |  |  |  |  | Export
Performance | [5 empty] | Custom Export
Load | [5 empty] | Filter
Pre-requisitis
download

## Sheet4 (hidden)
Count of Case ID | Severity
Priority | High | Low | Medium | Grand Total
(blank) | 16 | 1 | 14 | 31
Grand Total | 16 | 1 | 14 | 31

## Sheet2 (hidden)
Count of Defect ID | Severity
Priority | High | Low | Medium | Grand Total
High | 2 | 2 |  | 4
Medium |  | 4 | 9 | 13
Grand Total | 2 | 6 | 9 | 17
Count of Case ID | Status Dt 9/2/2024
Submodule | Fail | Pass | Grand Total
Consolidated View | 16 | 23 | 39
General setting | 1 | 1 | 2
Grand Total | 17 | 24 | 41

## Defect log
Sr No | Defect ID | Raise on Date | Module | Sub Module | Function | Severity | Priority | Defect Description | Assign To | Tester Status | Tester Status 09/12/2024 | Defect status - 9/24/2024 | Defect status - 10/13/2024 | Tester comment | Dev Status(10/10/24) | Dev comment | BA comment
1 | TT24427_01 | 2024-02-09 | Project Management | Consolidated View | View | Medium | Medium | "Please Select Module or Submodule to Filter The Documents" Note displayed at document upload page Whereas Note message should not be displayed to the user. |  | New | Repoen | Reopen | As per the agreement with BA . Design document which says this statement would removed now changed to say that this would be available at upload document page. | 9/2/2024 Note message should not be displayed to the user. 9/12/2024 Note still displayed in the 3rd secion of the upload document page. 9/24/2024: Issue still persist | Not a bug
2 | TT24427_02 | 2024-02-09 | Project Management | Consolidated View | View | High | High | System must display the notification message when uploading the file size contaning the size 200 MB |  | New | Closed |  |  | 9/2/2024 Sytem Getting stuck after uploading 200 MB file
3 | TT24427_03 | 2024-02-09 | Project Management | Consolidated View | View | Medium | Medium | System allow to the user for uploading mp3 , webp, Fig, HTML files. |  | New | Closed |  |  | 9/2/2024 Multiple extension files are allowed by the system to upload against the project, module and submodule 9/12/2024 Retested and closed
4 | TT24427_04 | 2024-02-09 | Project Management | Consolidated View | View | Medium | Medium | After click on show to all check box, File dispalyed on the get reomved, user need to refresh the page to view other files. |  | New | Repoen | Reopen |  | 9/2/2024 When user logined with "Show To ALL" persmisssion Go to consolidated view Select any project and select any file by checkbox 9/12/2024 Still issue open Steps to reproduce 1. Click on the project icon of "Ticketing System" 2. select "Test cases" module 3. Select submodule" My Module" 4. check the "show to all" checkmark | Resolved
5 | TT24427_05 | 2024-02-09 | Project Management | Consolidated View | View | Medium | Medium | After deselecting show to all check box, File dispalyed on the grid get reomved, user need to refresh the page to view other files. |  | New | Repoen | Closed |  | 9/2/2024 When user logined with "Show To ALL" persmisssion Go to consolidated view Select any project and deselect any file by checkbox 9/12/2024 Still issue open Steps to reproduce 1. Click on the project icon of "Ticketing System" 2. select "Test cases" module 3. Select submodule" My Module" 4. check the "show to all" checkmark | Resolved
6 | TT24427_06 | 2024-02-09 | Project Management | Consolidated View | View | Medium | Medium | System must throw the error message when uploading the file size greater than 50 MB against project, Module / Submodule |  | New | Closed |  |  | 9/2/2024 Sytem Getting stuck after uploading 50 MB file and notfication not throwed by syetem 9/12/2024 Retested and closed
7 | TT24427_07 | 2024-02-09 | Project Management | Consolidated View | View | Medium | Medium | After inserting the record user need to refresh the webpage to see all the uploaded document. |  | New | Closed |  |  | 9/2/2024 Uploaded file are not displayed to the user 9/12/2024 Retested and closed
8 | TT24427_08 | 2024-02-09 | Project Management | Consolidated View | View | Medium | Medium | Recently Inserted Document record not updated on the first line against project. |  | New | Closed |  |  | 9/2/2024 record not found on the top row of the lsit of records 9/12/2024 Retested and closed
9 | TT24427_09 | 2024-02-09 | Project Management | Consolidated View | View | Low | Medium | Back button not found in the document upload page and History page. |  | New | Repoen | Reopen | Closed | 9/2/2024 Back button not displayed to the user on history page and upload document page 9/12/2024 Back button not found on the document upload page but On history page back button found. 10/13/2024: Retest and closed successfully. | Resolved
10 | TT24427_10 | 2024-02-09 | Project Management | Consolidated View | View | Low | Medium | Page header not displayed as " Upload document" on the document upload page. |  | New | Repoen | Reopen | Closed | 9/2/2024 Page heading as upload document is not found when user redirected ducument upload page. 9/12/2024 Page header not displayed on Upload document page. 10/13/2024: Retested and closed successfully. | Resolved
11 | TT24427_11 | 2024-02-09 | Project Management | Consolidated View | View | Low | High | Deactive subModule are getting dispayed in Module dropdown at upload document page ( issue observed while user transverse through Consolidated view via click on icon through Project view) |  | New | Closed |  |  | 9/2/2024 Deactive submodule module should not displayed to the user when accessing module from document upload page 9/12/2024 Retetsed and closed
12 | TT24427_12 | 2024-02-09 | Project Management | Consolidated View | View | Low | High | Deactive Module are gedtting dispayed in Module dropdown at upload document page ( issue observed while user transverse through Consolidated view via click on icon through Project view) |  | New | Repoen | Closed |  | 9/2/2024 Deactive module should not displayed to the user when accessing module from document upload page 9/12/2024 Deactive module displayed in the module dropdown. | Resolved
13 | TT24427_13 | 2024-12-09 | Project Management | Consolidated View | View | High | High | User is unable to upload file of 50 MB. Sytem is throwing the error after uploading 50 MB file |  |  | New |  |  | 9/12/2024 Sytem is throwing the error after uploading 50 MB file | Resolved
14 | TT24427_14 | 2024-12-09 | Project Management | Consolidated View | View | Medium | Medium | Succseefull toastify messages displayed at 2 times, after uploading the document. |  |  | New | Closed |  | 9/12/2024 Toastify message should be displayed only one time after uploading the document. | Resolved
15 | TT24427_15 | 2024-12-09 | Project Management | Consolidated View | View | Medium | High | MP4 extension file should be uploaded from document upload page. |  |  | New | NA |  | 9/12/2024 MP4 video files should be uploaded successfully through document upload page. | Not a bug
16 | TT24427_16 | 2024-12-09 | Project Management | Consolidated View | View | Medium | High | Mutiple notification message for updating records displayed mutiple times without any valid actions. |  |  | New | Closed |  | 9/12/2024 Steps: 1. Go to consolidated view 2. select module "Test cases" from module dropdown 3. select submodule "My module" 4. delete any file 5. CLick on the active button 6. Click on deactive button 7. observe the mnotification message. | Resolved
17 | TT24427_17 | 2024-12-09 | Project Management | Consolidated View | View | High | High | User can not upload the document against the any active module. |  |  | New | Closed |  | 9/12/2024 Steps: 1. Go to consolidated view 2. select module "Test cases" from module dropdown 3. select submodule "My module" 4. upload any file valid file 5. observe the document upload screen User should see the recent uploaded file against the "Test case"module. | Resolved
18 | TT24427_18 | 2024-12-09 | Project Management | Consolidated View | View | High | High | Latest record not displayed at the top. It getting displayed at the last |  |  | New | Closed |  | 9/24/2024: Retested and closed | Resolved
19 | TT24427_19 | 2024-09-23 | Project Management | Consolidated View | View | Low | Low | Project owner 1. While moving to upload document through Consolidated view - icon , Upon Deleting the files while uncheck the 'show to all' checkbox, user redirected to previous page with radio button selected as "Deactive". Here Add Files got disabled even through user switched to Active radio button....High |  |  |  | New | Reopen | 10/13/2024: Partially resolved. Still below issue persist hence reduce the priority. Upon Deleting the files while uncheck the 'show to all' checkbox, user redirected to previous page with radio button selected as "Deactive". | Resolved
20 | TT24427_20 | 2024-09-23 | Project Management | Consolidated View | View | High | High | Project owner 2. While moving to upload document through Consolidated view - icon , Select Module and submodule ,Upon Deleting the files against submodule or module , Deleted files are not visible. |  |  |  | New | Reopen | 10/13/2024: Retest failed. Issue persist. | Resolved
21 | TT24427_21 | 2024-09-23 | Project Management | Consolidated View | View | High | High | Project owner 3. Upon deleting the files , restore button is not visible- |  |  |  | New | Closed | 10/13/2024: Retested successfully and closed | Resolved
23 | TT24427_23 | 2024-09-23 | Project Management | Consolidated View | View | High | High | Project Owner 5. While moving to upload document through Consolidated view - icon, Upon click on history -back button via deactive doc grid view , user redirected to upload document where radio button is Active selected. |  |  |  | New | Reopen | 10/13/2024: Issue still persist. upon moving from deactive doc grid view -history , click on back button expected to take user to dective grid view page . Here at this moment user redirected to upload document page where below project name ,module name is reflected and module dropdown as well as submodule dropdown depicted with no option. Here add files button got disabled | Not a bug
24 | TT24427_24 | 2024-09-23 | Project Management | Consolidated View | View | Low | Low | Project Owner 6. While uploading the document against project at grid view Module header is not populated with " No Module " -Low |  |  |  | New | Reopen | 10/13/2024: Retest failed. Issue persist. | Resolved
25 | TT24427_25 | 2024-09-23 | Project Management | Consolidated View | View | Low | Low | Project Owner 7. While uploading the document against project at grid view SubModule header is populated with " No Sub Module " , expected to display with "No SubModule" -Low ( Consistency need to be maintained) |  |  |  | New | Closed | 10/13/2024: Retested successfully and closed | Resolved
26 | TT24427_26 | 2024-09-24 | Project Management | Consolidated View | View | Low | Low | 8. At upload document Submodule dropdown label expected to displayed as "SubModule" as per consistency - Low |  |  |  | New | Closed |  | Resolved
27 | TT24427_27 | 2024-09-24 | Project Management | Consolidated View | View | Medium | Medium | 9. After uncheck the checkbox of show to all by PO, checkbox remain as checked. |  |  |  | New | Closed |  | Resolved
28 | TT24427_28 | 2024-09-24 | Project Management | Consolidated View | View | High | High | User neither having "show all" nor "Delete All" Access (DemoUser1) While moving to upload document through Consolidated view - icon , user able to view all files |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser1) | Resolved
29 | TT24427_29 | 2024-09-24 | Project Management | Consolidated View | View | High | High | User neither having "show all" nor "Delete All" Access (DemoUser1) 2. While moving to upload document through Consolidated view - icon ,Upon adding the files against Submodule , system throws message as " Record inserted and updated " however inserted file is not visible at grid view.-High |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser1) | Resolved
30 | TT24427_30 | 2024-09-24 | Project Management | Consolidated View | View | Medium | Medium | User neither having "show all" nor "Delete All" Access (DemoUser1) 3. While moving to upload document through Consolidated view - icon , upon selecting the file delete button appears however it is disabled - Medium |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser1) | Resolved
31 | TT24427_31 | 2024-09-24 | Project Management | Consolidated View | View | Low | Low | User neither having "show all" nor "Delete All" Access (DemoUser1) 4. While moving to upload document through Consolidated view - icon , Restore button is visible upon selecting the Deactive icon.-Low |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser1) | Resolved
32 | TT24427_32 | 2024-09-24 | Project Management | Consolidated View | View | Low | Low | User neither having "show all" nor "Delete All" Access (DemoUser1) 5. While moving to upload document through Consolidated view - icon , Without selecting the module , Submodule is populated as "Sales Bill" - Low |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser1) | Resolved
33 | TT24427_33 | 2024-09-24 | Project Management | Consolidated View | View | High | High | User neither having "show all" nor "Delete All" Access (DemoUser1) 6. While moving to upload document through Consolidated view - icon , Upon switching from Deactive to Active radio button - Documents are not visible - High |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser1) | Resolved
34 | TT24427_34 | 2024-09-24 | Project Management | Consolidated View | View | High | High | User neither having "show all" nor "Delete All" Access (DemoUser1) 7. While moving to upload document through Consolidated view - icon , Even though document unchecked with show all option still it is visible to user ( without show all & delete access), This issue observed for document against Project , module, sub module -High |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser2) | Resolved
35 | TT24427_35 | 2024-09-24 | Project Management | Consolidated View | View | High | High | User neither having "show all" nor "Delete All" Access (DemoUser1) 8. While moving to upload document through Module-Submodule , Even though document unchecked with show all option still it is visible to user ( without show all & delete access), This issue observed for document against Project , module, sub module -High |  |  |  | New |  | User neither having "show all" nor "Delete All" Access (DemoUser3) | Resolved
36 | TT24427_36 | 2024-09-24 | Project Management | Consolidated View | View | High | High | 1.Through project icon user can not delete the file which is uploaded against the submodule. |  |  |  | New |  | User having delete doc access (DemoUser2) | Resolved
37 | TT24427_37 | 2024-09-24 | Project Management | Consolidated View | View | Medium | Medium | 2. Through project icon, after deleting the document in submodule user need to refresh to view the files. |  |  |  | New |  | User having delete doc access (DemoUser2) | Resolved

## Test Case Quality (hidden)
Attribute | Count | Percentage Completed | Percentage pending
TC Count | 26
Module | 20 | 76.92 | 23.08
Req Id | 20 | 76.92 | 23.08
Function | 26 | 100 | 0
Testing Type | 26 | 100 | 0
Test Description | 25 | 96.15 | 3.85
Test steps | 25 | 96.15 | 3.85
Expected Result | 25 | 96.15 | 3.85
Actual Result | 0 | 0 | 100
Priority | 0 | 0 | 100
Severity | 24 | 92.31 | 7.69
TC count as per the standards
%ofTest Cases | TCs Count | %
Functionality | 13 | 50
Usability | 1 | 3.85
UI/UX | 0 | 0