## URD Exchange & Purchase Test Ca
SrNo | Project | Module | Submodule | Platform | Function | Field | Testing Type | Testing Group | Severity | Test Description | Steps | Expected Result | Actual Result | Status:10/08/2024 | ss
TC_01 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | Add |  | UI | Smoke | Low | Verify Spelling Mistake on Create estimate page |  | The correct spelling should be displayed instead of any misspelled words. | There is Spelling mistake for CREATE ADVANCE button | Fail | SS!A1
TC_02 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | Add |  | Functional | Regression | High | Verify URD Purchase Estimate Button |  | URD Purchase Estimate Button Should be clickable and after clicking user should navigate to Creating Invoice Page. | As Expected | Pass
TC_03 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | UI | Smoke | Low | Verify UI of URD Advance(Purchase)page. |  | After Clicking On URD Advance button User will get Following Options on URD Advance Page: 1.Grid View with Following options:Select, Purchase Id, Date, Item Type ,Item Id ,Purity, Pcs ,Gross Wt, Rate ,Net Wt ,Stone ,Pcs, Stone Wt(CT), Stone Name, Stone, Rate, Amount. 2.Create Voucher Button | As Expected | Pass
TC_04 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Customer Details | Validations | Regression | Low | Verify Customer Details functionality |  | On clicking on customer name pop up should be displayed with below details:Customer name, Customer mobile number, Customer Address. | User can extend/Increase POPUP size | Fail | SS!A1009
TC_05 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Validations | Regression | Medium | Verify Select All Checkbox |  | The select all option to select all the records with the single tick,If the user unselects the select all, all the check boxes should get unselected. | As Expected | Pass
TC_06 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Purchase ID | Validations | Regression | Medium | Verify Purchase ID field for Gold Ornament |  | It should be auto fetched from D> Jewelry> Old Gold Note,It should be read only | As Expected | Pass
TC_07 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Date | Validations | Regression | Medium | Verify Date field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | Wrong time is reflecting(For all orders 12:00PM) | Fail | SS!A140
TC_08 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Item Name | Validations | Regression | Medium | Verify Item Name field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | In Item Name Field-Item Type Value is reflecting | Fail | SS!A938
TC_09 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Item Type | Validations | Regression | Medium | Verify Item Type field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | In Item Type Field-Item Name Value is reflecting | Fail | SS!A938
TC_10 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Purity | Validations | Regression | Medium | Verify Purity field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | In D365-reflecting as a carat and forPOS reflecting in The purity percentage | Fail | SS!A938
TC_11 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Gross Weight | Validations | Regression | Low | Verify Gross Weight field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | In D365 value is 50.00 and POS value-50(not reflecting decimal values in POS) | Fail | SS!A938
TC_12 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | pcs | Validations | Regression | Low | Verify PCS field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | As Expected | Pass | SS!A321
TC_13 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Rate | Validations | Regression | Low | Verify Rate field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | Comma's Are missing in POS for rate amount | Fail | SS!A938
TC_14 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Amount | Functional | Regression | Low | Verify Amount field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | Comma's Are missing in POS for amount | Fail | SS!U369
TC_15 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Net weight | Validations | Regression | Low | Verify Net Weight field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | In D365 value is 50.00 and POS value-50(not reflecting decimal values in POS) | Fail | SS!U369
TC_16 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Stone pcs | Validations | Regression | Medium | Verify Stone PCS field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | As Expected | Pass
TC_17 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Stone rate | Validations | Regression | Medium | Verify Stone Rate field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | As Expected | Pass
TC_18 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Stone name | Validations | Regression | Medium | Verify Stone Name field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | As Expected | Pass
TC_19 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us > Gold Bullion >Below Field should be autofetched from Jewellery >Old Gold Note 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name 13.Amount |  | It should be autofetched from > Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365-reflecting as a carat and forPOS reflecting in The purity percentage 7.Comma's Are missing in POS for rate amount 13.Comma's Are missing in POS for amount | Fail | SS!P414
TC_20 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us/other > Gold ornament >Below Field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name 13.Amount |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5 In D365-reflecting as a carat and forPOS reflecting in The purity percentage for purchase from us only 7.Comma's Are missing in POS for rate amount 13.Comma's Are missing in POS for amount | Fail | SS!S454
TC_21 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us/other > Silver ornament >Below Field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name 13. Amount |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | Fail | SS!C536
TC_22 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us/other > platinum ornament >Below Field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name 13.Amount |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | Fail | SS!C591
TC_23 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us/other > Diamond Jewellery ornament >Below Field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name 13.Amount |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | .Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | Fail | SS!C656
TC_24 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us/other > Sterlling Silver Jewellery ornament >Below Field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | unable to test because of can not add purch transe amount from D365 | Blocker | SS!C717
TC_25 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us/other > Gold Bullion >Below Field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | Fail | SS!A789
TC_26 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us -Gold Ornament >purchase from other -Gold Bullion below field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | Fail | SS!A789
TC_27 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from us -Silver Ornament >purchase from other -Silver Bullion below field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name 13.Amount |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | Fail | SS!A850
TC_28 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View |  | Functional | Regression | Low | Verify that purchase from other >Diamond Jewellery below field should be autofetched from D 1.Purchase ID 2.Date 3.Item Name 4.Item Type 5.Purity 6.Gross Weight 7.Rate 8.Net weight 9.pcs 10.Stone pcs 11.Stone rate 12.Stone name 13.Amount |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | Fail | SS!A850
TC_29 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | View | Stone Weight | Validations | Regression | Medium | Verify Stone Weight field for Gold Ornament |  | It should be autofetched from D> Jewelry> Old Gold Note,It should be read-only | As Expected | Pass
TC_30 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Create advance Button Functionality |  | After clicking on create voucher Advance should be created for all line details against the purchase ID selected and user will navigate to Payment Page will get folloeing options: Advance ,Cash ,IMPS, Attachment, Total Amount, Remaining amount ,Action, Sr no ,Payment Type, Amount ,Save and Print . | As Expected | Pass
TC_31 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | Add |  | Functional | Regression | High | Verify Create advance Button Functionality if payment is above 2 lakh |  | After clicking on crate voucher user should be redirected to the Tax Information page, where user needs to compulsory fill any of the below details: PAN details, Form 60, Form 61 Once the details are filled and validated, user should be able to create advance and redirected to the payment page. | As Expected | Pass
TC_32 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Payment by cash Functionality |  | User Should able to do 10000 amount only by cash | As Expected | Pass
TC_33 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Payment by cash more than 10000 |  | User should'nt perform more than 10000 by cash | As Expected | Pass
TC_34 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify User perform Payment by IMPS |  | Users needs to fill the customer bank details and the amount will be transferred to customer bank account and UTR number will be generated for the same, which can be validated through Jewelry> Customer Advance UTR Payment. | Due to posting error unable to test | Blocker | SS!A892
TC_35 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | verify Credit/Advance Functionality |  | Amount can be kept as Credit/Advance against the customer account as well by using Advance button. | There should be proper diffrence should be shown User can't Makeout Exactly CREDIT Functionality | Confirmation By BA
TC_36 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify cash Payment reflection |  | The IMPS details should be saved against the customer in customer master. If the customer revisits, the details should be autofetched, Once the cash Payment is done, the UTR will be generated and can be validated from D> Jewelry> Customer Advance UTR Payment | Due to posting error unable to test | Blocker | SS!A892
TC_37 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | Add |  | Validations | Regression | Medium | Verify Save And Submit Button |  | Min one payment should be to selected, else the button should not be active. | As Expected | Pass
TC_38 | Microsoft Dynamic D365 | URD Advance | URD-Purchase | Web | Add |  | Functional | Regression | High | Verify print button functionality |  | After click on print invoice button invoice receipt should be generated | Currently PDF format invoice receipt not generated and showing blank page | Fail | SS!A213
TC_39 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify user can perform IMPS,Credit and Cash in one transaction |  | User should able to do all three actions in one transaction | As Expected | Pass
TC_40 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify IMPS Payment for Purchase from Us for all product group(Excluding MRP,Forming) |  | User Should be able to perform IMPS Payment for purchase from us for all product group | As Expected | Pass
TC_41 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify IMPS Payment for Purchase from Other for all product group(Excluding MRP,Forming) |  | User Should be able to perform IMPS Payment for purchase from Other for all product group | As Expected | Pass
TC_42 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify IMPS Payment+CASH for Purchase from Us for all product group(Excluding MRP,Forming) |  | User Should be able to perform IMPS Payment +CASH for purchase from us for all product group | As Expected | Pass
TC_43 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify IMPS Payment+CASH for Purchase from Other for all product group(Excluding MRP,Forming) |  | User Should be able to perform IMPS Payment+CASH for purchase from Other for all product group | As Expected | Pass
TC_44 | Microsoft Dynamic D365 | URD Advance |  | Web |  |  | Integration | Regression | High | Verify created URD purchase advance D- reflection on POS for the customer |  | User should get Added URD details on D for that customer in POS(Purchase) | Due to posting error unable to test | Blocker | SS!A892
TC_45 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Payment Mode -Cash |  | User should be able to make payment by cash | As Expected | Pass
TC_46 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Payment Mode -Credit |  | User should able to do credit amount for that customer | WILL CONSIDER IN NEXT PHASE:Discussed with BA | Blocker | SS!A892
TC_47 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Payment Mode -IMPS |  | Below fields should be displayed once the user selects the IMPS payment type: 1.Payment Amount - Amount to be transferred should be entered 2.Customer name - It should be autofetched and disable 3.IFSC Code- IFSC Code should be text field where user can input the code 4.Bank Name - It should be dropdown field fetched from Bank master 5.Bank Branch - Text box to enter the bank branch 6.Account Number - It will be text field where user can enter the Account number. 7.Confirm Account number - It will be text field where user needs to confirm the account number. If the account no does not match error should be displayed with red color. 8.Chose Files - User should be able to upload supporting document and view the uploaded document as well. Below file format should be supported : .jpg, .png, .pdf, .heic, .jpeg 9.Capture - User should be able to capture the image and upload it in system. 10.Save - On clicking on save button, the details should be saved against customer and the pop up should be closed. | 2.While doing IMPS Payment Customer name is not Auto fetched. 8.attachement -Choose File and View Image buttons UI is not loaded properly(Showing empty check box on button) | Fail | SS!AV10
TC_48 | Microsoft Dynamic D365 | URD Advance | Purchase | Web |  |  | Validations | Regression | High | Verify Pan Number |  | 1.User should be able to enter 10 digit alphanumeric PAN No. 2.It includes first five letters, followed by 4 numbers and last character. 3.In case of invalid pan card number format, it should display error message as “Invalid pan number”. | As Expected | Pass
TC_49 | Microsoft Dynamic D365 | URD Advance | Purchase | Web |  |  | Validations | Regression | High | Verify Pan attachement |  | 1.User should be able to attach file from the system. 2.It should accept attachment of maximum 2MB size with jpeg, jpg, png, pdf, heic extensions | As Expected | Pass
TC_50 | Microsoft Dynamic D365 | URD Advance | Purchase | Web |  |  | Validations | Regression | Medium | Validate View process |  | By clicking on view action, pop up with attachments added should be opened. | As Expected | Pass
TC_51 | Microsoft Dynamic D365 | URD Advance | Purchase | Web |  |  | Validations | Regression | High | Verify Name as per PAN Card Feild |  | Once the user validates the PAN Card, Name as per card should be updated. | As Expected | Pass
TC_52 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | UI | Regression | High | Verify Attachement Process UI |  | User should be able to attach supporting documents by clicking through this button. User should be to upload and view below documents: 1.Bill details - Bill Copy, Affidavit 2.Personal Photo - Personal Photo 3.D Proof- Adhar card, PAN Card, Driving Licence Address Proof- Electricity Bill, Ration card | For Choose File and View Button options-->are not displaying/loading properly(getting blank checkbox on buttons) | Fail | SS!AW126
TC_53 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Attachement Process |  | User should be able to attach supporting documents by clicking through this button. User should be to upload and view below documents: 1.Bill details - Bill Copy, Affidavit 2.Personal Photo - Personal Photo 3.ID Proof- Adhar card, PAN Card, Driving Licence Address Proof- Electricity Bill, Ration card | As Expected | Pass
TC_54 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Bill details DRP |  | It will be drop-down where user can upload copy of Bill and affidavit by clicking on upload file button. | Suggetion:There is usability issue After uploading image user can't makeout easily that image is added | Pass
TC_55 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify personal Photo Drp |  | It will be drop-down where user can upload copy of photo by clicking on upload file button. | Suggetion:There is usability issue After uploading image user can't makeout easily that image is added | Pass
TC_56 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify ID Proof drp |  | It will be dropdown where user can upload copy of adhar card, pan card, driving licence by clicking on upload file button. | Suggetion:There is usability issue After uploading image user can't makeout easily that image is added | Pass
TC_57 | Microsoft Dynamic D365 | URD Advance | Payment | Web |  |  | Functional | Regression | High | Verify Adress Proof drp |  | It will be dropdown where user can upload copy of Electricity and ration card by clicking on upload file button. | Suggetion:There is usability issue After uploading image user can't makeout easily that image is added | Pass

## Report
URD Purchase Test Summery Report | Severity
Status:10/08/2024 | High | Low | Medium | Grand Total
Blocker | 2 | 3 | 4 | 9
Fail | 4 | 12 | 6 | 22
Not executed | 1 |  |  | 1
Pass | 18 | 2 | 3 | 23
Grand Total | 25 | 17 | 13 | 55
Failed Test Case Report | Severity
Status:10/08/2024 | High | Low | Medium | Grand Total
Fail | 4 | 12 | 6 | 22
Grand Total | 4 | 12 | 6 | 22
Defect Status | Severity
Priority | High | Low | Medium | Grand Total
High | 4 |  |  | 4
Low |  | 12 |  | 12
Medium |  |  | 6 | 6
Grand Total | 4 | 12 | 6 | 22

## Defect Log
Sr No | Defect ID | Raise on Date | Module | Sub Module | Product Group | Severity | Priority | Defect Description | Screenshot | Assign To | Defect Status | Tester comment | Dev Status | Dev comment | BA comment
1 | TC_01 | 2024-10-10 | URD Advance | URD-Purchase | Gold Bullion | Low | Low | There is Spelling mistake for CREATE ADVANCE button | SS!A1 |  | New
2 | TC_04 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Medium | Medium | User can extend/Increase POPUP size | SS!A1009 |  | Closed
3 | TC_07 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Medium | Medium | Wrong time is reflecting(For all orders 12:00PM) | SS!A140 |  | New
4 | TC_08 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Medium | Medium | In Item Name Field-Item Type Value is reflecting for Gold Ornament | SS!A140 |  | New
5 | TC_09 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Medium | Medium | In Item Type Field-Item Name Value is reflecting for Gold Ornament | SS!A140 |  | New
6 | TC_10 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Medium | Medium | In D365-reflecting as a carat and forPOS reflecting in The purity percentage for Gold Ornament | SS!A140 |  | New
7 | TC_11 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Low | Low | In D365 value is 50.00 and POS value-50(not reflecting decimal values in POS) Gold Ornament | SS!A140 |  | New
8 | TC_13 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Low | Low | Comma's Are missing in POS for rate amount for Gold Ornament | SS!A140 |  | New
9 | TC_14 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Low | Low | Comma's Are missing in POS for amount for Gold Ornament | SS!U369 |  | New
10 | TC_15 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Low | Low | In D365 value is 50.00 and POS value-50(not reflecting decimal values in POS) Gold Ornament | SS!A140 |  | New
11 | TC_19 | 2024-10-10 | URD Advance | URD-Purchase | Gold Bullion | Low | Low | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365-reflecting as a carat and forPOS reflecting in The purity percentage 7.Comma's Are missing in POS for rate amount 13.Comma's Are missing in POS for amount | SS!P414 |  | New
12 | TC_20 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Low | Low | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5 In D365-reflecting as a carat and forPOS reflecting in The purity percentage for purchase from us only 7.Comma's Are missing in POS for rate amount 13.Comma's Are missing in POS for amount | SS!S454 |  | New
13 | TC_21 | 2024-10-10 | URD Advance | URD-Purchase | Silver Ornament | Low | Low | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | SS!C536 |  | New
14 | TC_22 | 2024-10-10 | URD Advance | URD-Purchase | Platinum Ornament | Low | Low | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | SS!C591 |  | New
15 | TC_25 | 2024-10-10 | URD Advance | URD-Purchase | Gold Bullion | Low | Low | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | SS!A789 |  | New
16 | TC_26 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Low | Low | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | SS!A789 |  | New
17 | TC_27 | 2024-10-10 | URD Advance | URD-Purchase | Silver Ornament | Low | Low | 2.Wrong time is reflecting(For all orders 12:00PM) 3.In Item Name Field-Item Type Value is reflecting 4.In Item Type Field-Item Name Value is reflecting 5.In D365 value is 10.00 and POS value-10(not reflecting decimal values in POS) 7.Comma's Are missing in POS for rate 13.Comma's Are missing in POS for amount | SS!A850 |  | New
18 | TC_31 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | High | High | 1.If One pan card entered and validated legal name after that user is able to add another user's pan card also and able to proceed 2.Bydefault attached image is getting 3.Back option is not awaialable |  |  | Closed
19 | TC_38 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | High | High | Currently PDF format invoice receipt not generated and showing blank page | SS!A213 |  | New
20 | TC_47 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | High | High | 2.While doing IMPS Payment Customer name is not Auto fetched. 8.attachement -Choose File and View Image buttons UI is not loaded properly(Showing empty check box on button) | SS!AV10 |  | New
21 | TC_50 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | Medium | Medium | Bydefault one attachement is showing after clicking on view |  |  | Closed
22 | TC_52 | 2024-10-10 | URD Advance | URD-Purchase | Gold Ornament | High | High | For Choose File and View Button options-->are not displaying/loading properly(getting blank checkbox on buttons) | SS!AW126 |  | New