## Summary (hidden)
Version History | [5 empty] | Iteration Summary
Date | Author | Version | Approved by | Total Tcs. | Remark | Sub Module | Iteration category | Iteration Count | Start Date | End Date | Total Tcs | Total Defects | Remark
2024-09-02 |  | V0.1 |  | 31 | Initial draft | Consolidated View | Initial Phase | 1 | 2024-09-02 | 2024-09-02 | 39 | 17
2024-09-03 |  | V0.2 |  | 41 | Incorporated with missing scenarios , 12 missing scenarios are identified | General Setting | Initial Phase | 1 | 2024-09-02 | 2024-09-03 | 2 | 0
#N/A
#N/A
#N/A

## Report (hidden)
Test execution report | Status Dt 9/2/2024 |  |  |  |  | Tester Status | New
Submodule | Fail | Pass | Grand Total
Consolidated View | 16 | 13 | 29 |  |  | Count of Defect ID | Severity
General setting | 1 |  | 1 |  |  | Priority | High | Low | Medium | Grand Total
Grand Total | 17 | 13 | 30 |  |  | High | 1 | 2 |  | 3
[6 empty] | Medium |  |  | 7 | 7
[6 empty] | Grand Total | 1 | 2 | 7 | 10
Count of Case ID | Severity
Status Dt 9/2/2024 | High | Low | Medium | Grand Total
Fail | 6 | 1 | 10 | 17
Pass | 10 |  | 14 | 24
Grand Total | 16 | 1 | 24 | 41 | Status Dt 9/2/2024 | Fail
[5 empty] | Count of Case ID | Severity
[5 empty] | Submodule | High | Low | Medium | Grand Total
Daily Summary Report - 6/10/2024 |  |  |  |  | Consolidated View | 6 | 1 | 9 | 16
[5 empty] | General setting |  |  | 1 | 1
Submodule | Test case execution status |  |  |  | Grand Total | 6 | 1 | 10 | 17
Consolidated View | 39
Grand Total | 39

## Consolidated Report (hidden)
Date | Failed test case status report - 9/3/2024 | [5 empty] | Remark | Date | Failed test case status report - 6/1/2024 | [5 empty] | Remark | Date | Failed test case status report - 6/1/2024 | [5 empty] | Remark
2024-09-03 | Very High | High | Medium | Low | Grand Total |  |  | 2024-06-01 | Very High | High | Medium | Low | Grand Total |  |  | 2024-06-01 | Very High | High | Medium | Low | Grand Total
|  | 6 | 10 | 1 | 17 | [7 empty] | 0 | [7 empty] | 0
| Defect Status report - 9/3/2024 | [5 empty] | Remark |  | Defect Status report - 6/1/2024 | [5 empty] | Remark |  | Defect Status report - 6/1/2024 | [5 empty] | Remark
| Severity / Priority | High | Medium | Low | Very High | Grand Total |  |  | Severity / Priority | High | Medium | Low | Very High | Grand Total |  |  | Severity / Priority | High | Medium | Low | Very High | Grand Total
| High | 1 |  | 2 |  | 3 |  |  | High |  |  |  |  | 0 |  |  | High |  |  |  |  | 0
| Medium |  | 7 |  |  | 7 |  |  | Medium |  |  |  |  | 0 |  |  | Medium |  |  |  |  | 0
| Low |  |  |  |  | 0 |  |  | Low |  |  |  |  | 0 |  |  | Low |  |  |  |  | 0
| Very High |  |  |  |  | 0 |  |  | Very High |  |  |  |  | 0 |  |  | Very High |  |  |  |  | 0
| Grand Total | 1 | 7 | 2 | 0 | 10 |  |  | Grand Total | 0 | 0 | 0 | 0 | 0 |  |  | Grand Total | 0 | 0 | 0 | 0 | 0
| Test case execution status Report - 9/3/2024 | [5 empty] | Remark |  | Test case execution status Report - 6/1/2024 | [5 empty] | Remark |  | Test case execution status Report - 6/1/2024 | [5 empty] | Remark
| TCs Status / Submodules | Pass Tcs | Fail Tcs | Other / Not Executed | Total Tcs |  |  |  | TCs Status / Submodules | Pass Tcs | Fail Tcs | Other / Not Executed | Total Tcs |  |  |  | TCs Status / Submodules | Pass Tcs | Fail Tcs | Other / Not Executed | Total Tcs
| Consolidated View | 13 | 16 |  | 29 | [7 empty] | 0 | [7 empty] | 0
| General setting |  | 1 |  | 1 | [7 empty] | 0 | [7 empty] | 0
| Grand Total | 13 | 17 | 0 | 30 | [7 empty] | 0 | [7 empty] | 0
[9 empty] | Grand Total | 0 | 0 | 0 | 0 |  |  |  | Grand Total | 0 | 0 | 0 | 0

## TPM_Sheet
Ticket ID | TT24427 | Released Version
Project live Date |  | Project Name | Connect us 2.0
Module Name | Project Master | Test Cases Reviewed By
Testing Owner | Swapnil Ramdasi | Ticket Owner | Priyanka Gole | #######
Testing URL | http://3.108.206.34/2_Testing/TechTicket | Email / User Name | Preetib | abcd1234
Password
Description | Uploading of documents
| 0 | 0 | 26 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 35 | 0
35 | 35 | 35 | 9 | 35 | 35 |  |  | 35 | 35 | 35 | 35 |  | 35 | 0 | 35
Case ID | Module | Submodule | Req Id | Function | Testing Type | Platform | Field | Test Description | Test steps | Expected Result | Actual Result | Screen Shot | Status Dt 9/2/2024 | Priority | Severity | Written Date | Review Remark | BA Remark | Developer Remark | Last Updated Date
TC_01 | Project Management | Consolidated View | BR001 - Require Icon on the consolidated view to upload project wise Attachment. | View | UI | Web |  | Verify the document upload page through consolidated view - icon | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. observe he details at document upload page 8. | Upon successful login user redirected to document upload page , Pg is divided into 4 sections and displayed with below details Project section( 1st section) 1. Project name with icon ( displayed at centre) 2. Pending tickets, completed tickets , Pending Tasks, Delayed Tasks Add files with status(2nd section) 1. Module( dropdown)- single selection 2. Submodule(dropdown)- single selection 3. Status( radio button) - Active , Deactive 4. Add Files (button) Note: ( 3rd section) 1) Please Select Documents for Delete and Restore 2) Please Select Deactive To Check Deleted Documents Document details in grid view( 4th section) 1. Check box ( by default unchecked) 2. Sr. no 3. Show to all ( checkbox) 4. Actions ( History, download) 5. File Name 6. Project Name 7. Module Name 8. SubModule Name | 9/2/2024 All fields are present as per the expected result except the filter message As per the requirement No. BR006 Note message should not displayed to the user. Note 3 : "3) Please Select Module or Submodule to Filter The Documents" should be removed. |  | Fail |  | High | 2024-09-02
TC_02 | Project Management | Consolidated View |  | View | UI | Web |  | Verify the document upload page through consolidated view - Module | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. observe he details at document upload page 8. | Upon successful logon user redirected to document upload page , Pg is divided into 4 sections and displayed with below details Project section( 1st section) 1. Project name with icon ( displayed at centre) 2. Pending tickets, completed tickets , Pending Tasks, Delayed Tasks Add files with status(2nd section) 1. Module( dropdown)- single selection-prepopulated with module name 2. Submodule(dropdown)- single selection 3. Status( radio button) - Active , Deactive 4. Add Files (button) Note: ( 3rd section) 1) Please Select Documents for Delete and Restore 2) Please Select Deactive To Check Deleted Documents 3) Please Select Module or Submodule to Filter The Documents Document details in grid view( 4th section) 1. Check box ( by default unchecked) 2. Sr. no 3. Show to all ( checkbox) 4. Actions ( History, download) 5. File Name 6. Project Name 7. Module Name 8. SubModule Name | 9/2/2024 All fields are present as per the expected result except the filter message As per the requirement No. BR006 Note message should not displayed to the user. Note 3 : "3) Please Select Module or Submodule to Filter The Documents" should be removed. |  | Fail |  | High | 2024-09-02
TC_03 | Project Management | Consolidated View | BR002 - Upload document against project. | View | Functionality | Web |  | Verify user is able to upload the document( Pdf) through Consolidated view - icon | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. Click on Add File 8. Choose file 9. Click on Submit button | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Latest records gets displayed at Top 4. Project, Module &Submodule won't populated | 9/2/2024 PDF uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. It getting displayed at the last |  | Fail |  | High | 2024-09-02
TC_04 | Project Management | Consolidated View | BR001 - Require Icon on the consolidated view to upload project wise Attachment. | View | Functionality | Web |  | Verify user is able to upload the document( Jpeg) through Consolidated view - icon | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. Click on Add File 8. Choose file 9. Click on Submit button | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Latest records gets displayed at Top 4. Project, Module &Submodule won't populated | 9/2/2024 jepg uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. It getting displayed at the last |  | Fail |  | High | 2024-09-02
TC_05 | Project Management | Consolidated View | BR001 - Require Icon on the consolidated view to upload project wise Attachment. | View | Functionality | Web |  | Verify user is able to upload the document( Png) through Consolidated view - icon | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. Click on Add File 8. Choose file 9. Click on Submit button | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Latest records gets displayed at Top 4. Project, Module &Submodule won't populated | 9/2/2024 png uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. It getting displayed at the last |  | Fail |  | High | 2024-09-02
TC_06 | Project Management | Consolidated View | BR001 - Require Icon on the consolidated view to upload project wise Attachment. | View | Functionality | Web |  | Verify user is able to upload the document( doc/docx) through Consolidated view - icon | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. Click on Add File 8. Choose file 9. Click on Submit button | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Latest records gets displayed at Top 4. Project, Module &Submodule won't populated | 9/2/2024 doc and docx file uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. It getting displayed at the last |  | Fail |  | High | 2024-09-02
TC_07 | Project Management | Consolidated View | BR001 - Require Icon on the consolidated view to upload project wise Attachment. | View | Functionality | Web |  | Verify user is able to upload the document( pptx) through Consolidated view - icon | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. Click on Add File 8. Choose file 9. Click on Submit button | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Latest records gets displayed at Top 4. Project, Module &Submodule won't populated | 9/2/2024 PPTX file uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. It getting displayed at the last |  | Pass |  | High | 2024-09-02
TC_08 | Project Management | Consolidated View | BR002 - Require Icon on the consolidated view to upload project wise Attachment. | View | Functionality | Web |  | Verify user is able to upload the document( mp4) through Consolidated view - icon | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. Click on Add File 8. Choose file 9. Click on Submit button | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Latest records gets displayed at Top 4. Project, Module &Submodule won't populated | 9/2/2024 mp4 file uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. It getting displayed at the last |  | Pass |  | High | 2024-09-02
TC_09 | Project Management | Consolidated View |  | View | Usability | Web |  | Verify that last uploaded files displayed at top in grid view | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Project Name 7. Click on Add File 8. Choose file 9. Click on Submit button 10.observe the grid view | Last added file should displayed at top | 9/2/2024 Sample file uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. |  | Fail |  | Low | 2024-09-02
TC_10 | Project Management | Consolidated View |  | View | Functionality | Web |  | Verify user is able to upload the document through Consolidated view-Module | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.Click on Add File 9. Choose file 10. Click on Submit button 10.observe the grid view | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Project, (Module,Submodule won't Prepopulated) however the selected module is available against Module dropdown as option. 3. Latest records gets displayed at Top | 9/2/2024 Sample file uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. |  | Pass |  | Medium | 2024-09-02
TC_11 | Project Management | Consolidated View | BR003-Provision to upload Sub module wise document | View | Functionality | Web |  | Verify user is able to upload the document against submodule wise through Consolidated view-Module | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.Click on Add File 9. Choose file 10. Click on Submit button 10.observe the grid view | 1.System should throw acknowledgement message for succesfully inserted the same file. 2. Uploaded file details are displayed in 4th section . 3. Project, (Module,Submodule won't Prepopulated) however the selected module is available against Module dropdown as option and Submodule dropdown is populated with submodule mapped to module. 3. Latest records gets displayed at Top | 9/2/2024 Sample file uploaded to the system but Success message dispalyaed at 2 time Latest record not displayed at the top. |  | Pass |  | Medium | 2024-09-02
TC_12 | Project Management | Consolidated View | BR004-Active records History button should show document name, uploaded by, uploaded at date time. | View | Functionality | Web |  | Verify History page for active records | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.Click on history icon under action column against file name 9. observe the history page details | History page is populated with details under below fields 1. Sr ( Serial no ) 2. Document Name 3. Status ( Active/Deactive) 4. Host name (Ip address) 5. Updated By 6. Updtaed At 7. Deleted By 8. Deleted At | 9/2/2024 As expected |  | Pass |  | High | 2024-09-02
TC_13 | Project Management | Consolidated View | BR005-Deactive records History button should show document name, uploaded by, uploaded at date time, deleted by, deleted at date time | View | Functionality | Web |  | Verify history page for deactive records | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.Click on history icon under action column against file name 9. observe the history page details | History page is populated with details under below fields 1. Sr ( Serial no ) 2. Document Name 3. Status ( Active/Deactive) 4. Host name 5. Updated By 6. Updated At 7. Deleted by 8. Deleted at | 9/2/2024 As expected |  | Pass |  | High | 2024-09-02
TC_14 | Project Management | Consolidated View |  | View | Functionality | Web |  | Verify Document with show all access is able to view the document by all users | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.Select the checkbox ( show all) against file name 9. | All users whomever has Consolidated menu access is able to view the document with Show all access | 9/2/2024 As expected |  | Pass |  | High | 2024-09-02
TC_15 | Project Management | Consolidated View |  | View | Functionality | Web |  | Verify document without show all ( check box unchecked) is unable to view by users other than project owner | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.DeSelect the checkbox ( show all) against file name 9. | Only project owner can view this document and all users is unable to view the same. | 9/2/2024 As expected |  | Pass |  | High | 2024-09-02
TC_16 | Project Management | Consolidated View |  | View | Functionality | Web |  | Verify document without show all ( check box unchecked) is unable to download the document by users other than project owner | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.DeSelect the checkbox ( show all) against file name 9. | Only project owner can view and download this document and all users is unable to view the same.hence unable to download | 9/2/2024 As expected After checkmarking on chech box all files getting hide. |  | Pass |  | High | 2024-09-02
TC_17 | Project Management | Consolidated View |  | View | Functionality | Web |  | Verify user with "delete doc" access is able to delete the documents | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.Select the checkbox against file name 9. click on Delete button | System should throw the Successful deletion message . | 9/2/2024 As expected |  | Pass |  | High | 2024-09-02
TC_18 | Project Management | Consolidated View |  | View | Functionality | Web |  | Verify all users able to view and download the document | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module & submodule 8.Click on download icon against document name | The selected file get downloaded | 9/2/2024 As expected |  | Pass |  | High | 2024-09-02
TC_19 | Project Management | Consolidated View |  | View | Functionality | Web |  | Verify that "Delete DOC" authority persons having the authority to delete the document | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Select tthe module 8.Select the checkbox against file name 9. click on Delete button | The selected file get deleted | 9/2/2024 As expected |  | Pass |  | High | 2024-09-02
TC_20 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify user is able to upload the file with 201MB size against project | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Click on thee Add files 8. upload the document | System should throw error message | 9/2/2024 Not as expected System gets stuck after uploading the file. Error message disssplayed to the user |  | Fail |  | Medium | 2024-09-02
TC_21 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify user is able to upload the document file size grater than 201 MB against module | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Click on thee Add files 8. upload the document | System should throw error message | 9/2/2024 Not as expected System gets stuck after uploading the file. |  | Fail |  | Medium | 2024-09-02
TC_22 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify user is able to upload the document file size grater than 201MB against submodule | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Click on thee Add files 8. upload the document | System should throw error message | 9/2/2024 Not as expected System gets stuck after uploading the file. |  | Fail |  | Medium | 2024-09-02
TC_23 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify system should not allow to upload the file other than .doc, .docx, .pdf, .pptx, .png, .jpeg, .mp4 etention | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Clickon the add Files 8. upload the document | System should throw error message | 9/2/2024 Not As expected System is accepting the all the file extensions And Not throwing any error message |  | Fail |  | Medium | 2024-09-02
TC_24 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify user is able to upload the file equal to 200MB size against project | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon to upload document 7. Click on thee Add files 8. upload the document | System should throw successful acknowledgement | 9/2/2024 Not As expected System getting stuck while uploading 200 mb file nonotifiation displayed for the progress of uploading |  | Fail |  | Medium | 2024-09-02
TC_25 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify user is able to upload the document file size equal to 200MB against module | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to Module 7. Click on thee Add files 8. upload the document | System should throw successful acknowledgement | 9/2/2024 Not As expected System getting stuck while uploading 200 mb file nonotifiation displayed for the progress of uploading |  | Fail |  | Medium | 2024-09-02
TC_26 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify user is able to upload the document file size equal to 200MB against submodule | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to sub module Module 7. Click on thee Add files 8. upload the document | System should throw successful acknowledgement | 9/2/2024 Not As expected System getting stuck while uploading 200 mb file nonotifiation displayed for the progress of uploading |  | Fail |  | Medium | 2024-09-02
TC_27 | Project Management | Consolidated View |  | View | Validation | Web |  | Verify "is show to all " checkbox by default behaviour | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Logon - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to sub module Module 7. upload the document | " Is show to all " field is by default populated with Yes | 9/2/2024 As expected |  | Pass |  | Medium | 2024-09-02
TC_28 | Project Management | Consolidated View |  | View | Usability | Web |  | Verify back button to take user to previous page 1. From History page to document upload page 2. From Document upload page to consolidated page | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to sub module Module 7. Click on thee Add files 8. upload the document | Back button take user to previous page 1. From History page to document upload page 2. From Document upload page to consolidated page | 9/2/2024 Not as expected Button is not present on the history page. Button not found document upload page. |  | Fail |  | Medium | 2024-09-02
TC_29 | Project Management | Consolidated View |  | View | Usability | Web |  | Verify page header get displayed upon redirecting to Upload document page | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Click on icon next to sub module Module 7. Click on thee Add files 8. upload the document | Page header get displayed as " Upload document" | 9/2/2024 Not as expected Upload Document Heading not found on the header part of document upload page |  | Fail |  | Medium | 2024-09-02
TC_30 | Settings | General setting |  | Add | Usability | Web |  | Verify Select user dropdown is populated with user name with emp id to differentiate the employee of same name | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on "Setting " menu 5. Click on Add Setting 6. observe the select user drop down | Dropdown should be displayed with user name and employee id | 9/2/2024 Not as expected User can see the users along with employee id |  | Fail |  | Medium | 2024-09-02
TC_31 | Settings | General setting |  | Edit | Functionality | Web |  | Deactive users won't populate while selecting user from select user dropdown | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on "Setting " menu 5. Click on show to all 6. Check the selected user | Deactive users won't populate in Select user dropdown | 9/2/2024 As Expected |  | Pass |  | Medium | 2024-09-02
TC_32 | Project Management | Consolidated View |  | Add | Functionality | Web |  | Verify that a user can upload a document to against module by clicking the project icon. | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Select the module 7. upload the document | Document should be uploaded against the module and can viewed by clicking on the project icon | 9/2/2024 As Expected |  | Pass |  | Medium
TC_33 | Project Management | Consolidated View |  | Add | Functionality | Web |  | Verify that a user can upload a document to against submodule by clicking the project icon. | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Select the module 7. select the sub module 8. upload the document | Document should be uploaded against the submodule and can viewed by clicking on the project icon | 9/2/2024 As Expected |  | Pass |  | Medium
TC_34 | Project Management | Consolidated View |  | Add | Functionality | Web |  | Verify that a user can upload a document to against module by via view module. | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Select the module 7. upload the document | The document should be uploaded against the module and accessible via the view module. | 9/2/2024 As Expected |  | Pass |  | Medium
TC_35 | Project Management | Consolidated View |  | Add | Functionality | Web |  | Verify that a user can upload a document to against sub module by via view module. | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Select the module 7. select the sub module 8. upload the document | The docuemnt should be uploaded against submodule and accessible via module view | 9/2/2024 As Expected |  | Pass |  | Medium
TC_36 | Project Management | Consolidated View |  | Add | Functionality | Web |  | Verify user is able to view the document uploaded against submodule via click on Icon ( besideProject name) can accessible via view module | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Select the module 7. select the sub module 8. upload the document | User should able to view the document uploaded against submodule via click on Icon ( besideProject name) can accessible via view module | 9/2/2024 As Expected |  | Pass |  | Medium
TC_37 | Project Management | Consolidated View |  | Add | Functionality | Web |  | Verify user is able to view the document uploaded against module click on Icon ( besideProject name) can accessible via view module | 1. Click on the URL- http://3.108.206.34/2_Testing/TechTicket 2. Login - enter the username & password 3. Click on Sign In 4. Click on " Project Management " menu 5. Click on Conslidated Menu 6. Select the module 7. select the sub module 8. upload the document | User should able to view the document uploaded against submodule via click on Icon ( besideProject name) can accessible via view module | 9/2/2024 As Expected |  | Pass |  | Medium
Note on I64: Amruta Kore:

## TPM_MISC (hidden)
Testing Type | Status | Priority / Severity | Tester remark | Developer remark | BA Remark | Functions | Req id | Req desc | Platform
Functionality | Pass | High | Closed | Resolved | Closed | Add | BR001 - Require Icon on the consolidated view to upload project wise Attachment. |  | App
Intergration | Fail | Medium | Pending | Not a bug | Re-open | Edit | BR002 - Upload document against project. |  | Website
Validation | Not Executed | Low | Re-open | Deffered | Deffered | View | BR003-Provision to upload Sub module wise document |  | Web Application
UI | Under Development | Very High | Blocker | In-Progress | Not a bug | Delete | BR004-Active records History button should show document name, uploaded by, uploaded at date time.
Usability | Suggestion |  | Re-Test | Development Completed |  | Search | BR005-Deactive records History button should show document name, uploaded by, uploaded at date time, deleted by, deleted at date time
Compatibilty | NA |  |  |  |  | Gird view | BR006-Remove filter note (3) as system showing all documents/attachments
Security | Next Phase |  |  |  |  | Export
Performance | [5 empty] | Custom Export
Load | [5 empty] | Filter
Pre-requisitis

## Sheet4 (hidden)
Count of Case ID | Severity
Priority | High | Low | Medium | Grand Total
(blank) | 16 | 1 | 14 | 31
Grand Total | 16 | 1 | 14 | 31

## Sheet2 (hidden)
Count of Defect ID | Severity
Priority | High | Low | Medium | Grand Total
High | 2 | 2 |  | 4
Medium |  | 4 | 9 | 13
Grand Total | 2 | 6 | 9 | 17
Count of Case ID | Status Dt 9/2/2024
Submodule | Fail | Pass | Grand Total
Consolidated View | 16 | 23 | 39
General setting | 1 | 1 | 2
Grand Total | 17 | 24 | 41

## Defect log
Sr No | Defect ID | Raise on Date | Module | Sub Module | Function | Severity | Priority | Defect Description | Assign To | Tester Status | Tester comment | Dev Status | Dev comment | BA comment
1 | TC_01 | 2024-09-02 | Project Management | Consolidated View | View | Medium | Medium | "Please Select Module or Submodule to Filter The Documents" Note displayed at document upload page Whereas Note message should not be displayed to the user. |  | New | 9/2/2024 Note message should not be displayed to the user.
2 | TC_02 | 2024-09-02 | Project Management | Consolidated View | View | High | High | System must display the notification message when uploading the file size contaning the size 200 MB |  | New | 9/2/2024 Sytem Getting stuck after uploading 200 MB file
3 | TC_03 | 2024-09-02 | Project Management | Consolidated View | View | Medium | Medium | System allow to the user for uploading mp3 , webp, Fig, HTML files. |  | New | 9/2/2024 Multiple extension files are allowed by the system to upload against the project, module and submodule
4 | TC_04 | 2024-09-02 | Project Management | Consolidated View | View | Medium | Medium | After click on show to all check box, File dispalyed on the get reomved, user need to refresh the page to view other files. |  | New | 9/2/2024 When user logined with "Show To ALL" persmisssion Go to consolidated view Select any project and select any file by checkbox
5 | TC_05 | 2024-09-02 | Project Management | Consolidated View | View | Medium | Medium | After deselecting show to all check box, File dispalyed on the get reomved, user need to refresh the page to view other files. |  | New | 9/2/2024 When user logined with "Show To ALL" persmisssion Go to consolidated view Select any project and deselect any file by checkbox
6 | TC_06 | 2024-09-02 | Project Management | Consolidated View | View | Medium | Medium | System must throw the error message when uploading the file size greater than 200 MB against project, Module / Submodule |  | New | 9/2/2024 Sytem Getting stuck after uploading 300 MB file and notfication not throwed by syetem
7 | TC_07 | 2024-09-02 | Project Management | Consolidated View | View | Medium | Medium | After inserting the record user need to refresh the webpage to see all the uploaded document. |  | New | 9/2/2024 Uploaded file are not displayed to the user
8 | TC_08 | 2024-09-02 | Project Management | Consolidated View | View | Medium | Medium | Recently Inserted Document record not updated on the first line against project. |  | New | 9/2/2024 record not found on the top row of the lsit of records
9 | TC_09 | 2024-09-02 | Project Management | Consolidated View | View | Low | Medium | Back button not found in the document upload page and History page. |  |  | 9/2/2024 Back button not displayed to the user on history page and upload document page
10 | TC_10 | 2024-09-02 | Project Management | Consolidated View | View | Low | Medium | Page header not displayed as " Upload document" on the document upload page. |  |  | 9/2/2024 Page heading as upload document is not found when user redirected ducument upload page.
11 | TC_11 | 2024-09-02 | Project Management | Consolidated View | View | Low | High | Deactive subModule are gedtting dispayed in Module dropdown at upload document page ( issue observed while user transverse through Consolidated view via click on icon through Project view) |  | New | 9/2/2024 Deactive submodule module should not displayed to the user when accessing module from document upload page
12 | TC_12 | 2024-09-02 | Project Management | Consolidated View | View | Low | High | Deactive Module are gedtting dispayed in Module dropdown at upload document page ( issue observed while user transverse through Consolidated view via click on icon through Project view) |  | New | 9/2/2024 Deactive module should not displayed to the user when accessing module from document upload page

## Test Case Quality (hidden)
Attribute | Count | Percentage Completed | Percentage pending
TC Count | 35
Module | 35 | 100 | 0
Req Id | 9 | 25.71 | 74.29
Function | 35 | 100 | 0
Testing Type | 35 | 100 | 0
Test Description | 35 | 100 | 0
Test steps | 35 | 100 | 0
Expected Result | 35 | 100 | 0
Actual Result | 35 | 100 | 0
Priority | 0 | 0 | 100
Severity | 35 | 100 | 0
TC count as per the standards
%ofTest Cases | TCs Count | %
Functionality | 17 | 48.57
Usability | 1 | 2.86
UI/UX | 0 | 0