## data
sr | ticket_id | task_owner | task_name | task_start_Date | task_scheduled_Hours | task_schedule_hours_min | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at
36 | TT15299 | Rushikesh Harkare | Code Review and live support | 2023-10-02 | 20:00 | 1200 | 21:31:35 | 2023-10-06 |  | COMPLETED | DELAYED | 2023-10-09 07:38:35 | 2023-10-09 07:38:35
37 | TT15299 | Rushikesh Harkare | Bill Type Master Add Functionality and Edit Functionality Development | 2023-10-02 | 08:00 | 480 | 08:10:44 | 2023-10-03 |  | COMPLETED | DELAYED | 2023-10-05 09:55:52 | 2023-10-05 09:55:52
38 | TT15299 | Rushikesh Harkare | Bill Type Master Bugs Solving ADD and Edit Functionality | 2023-10-04 | 07:00 | 420 | 05:06:09 | 2023-10-05 |  | COMPLETED | DELAYED | 2023-10-09 07:38:48 | 2023-10-09 07:38:48
39 | TT15299 | Rushikesh Harkare | Fun Friday 06 Oct | 2023-10-06 | 01:00 | 60 | 00:00:00 | 2023-10-06 |  | COMPLETED | DELAYED | 2023-10-09 07:38:27 | 2023-10-09 07:38:27
40 | TT15299 | Rushikesh Harkare | Bill Type Master Retested Bugs Solving and deployment | 2023-10-06 | 02:30 | 150 | 04:15:45 | 2023-10-06 |  | COMPLETED | DELAYED | 2023-10-11 18:06:12 | 2023-10-11 18:06:12
41 | TT16541 | Rushikesh Harkare | test | 2023-10-09 | 00:20 | 20 | 00:00:00 | 2023-10-10 |  | COMPLETED | COMPLETED | 2023-10-09 07:49:31 | 2023-10-09 07:49:31
42 | TT15299 | Rushikesh Harkare | Review code and live support | 2023-10-09 | 20:00 | 1200 | 21:12:54 | 2023-10-13 |  | COMPLETED | DELAYED | 2023-10-14 10:38:06 | 2023-10-14 10:38:06
43 | TT15299 | Rushikesh Harkare | Daily sync call | 2023-10-09 | 01:15 | 75 | 00:36:37 | 2023-10-13 |  | COMPLETED | DELAYED | 2023-10-14 10:37:18 | 2023-10-14 10:37:18
44 | TT15299 | Rushikesh Harkare | Fun friday 13oct | 2023-10-13 | 01:00 | 60 | 00:00:00 | 2023-10-13 |  | COMPLETED | DELAYED | 2023-10-14 10:37:10 | 2023-10-14 10:37:10
45 | TT15299 | Rushikesh Harkare | Unit Testing of Bill Type master for crud operation | 2023-10-09 | 04:00 | 240 | 04:26:43 | 2023-10-10 |  | COMPLETED | DELAYED | 2023-10-11 18:06:03 | 2023-10-11 18:06:03
46 | TT15299 | Rushikesh Harkare | Code Merging into Testing Server and SoftLaunch | 2023-10-09 | 05:00 | 300 | 04:59:15 | 2023-10-13 |  | COMPLETED | COMPLETED | 2023-10-11 18:05:44 | 2023-10-11 18:05:44
47 | TT15299 | Rushikesh Harkare | Bill Checking Authority Mapping bugs Solving | 2023-10-13 | 01:00 | 60 | 03:24:38 | 2023-10-13 |  | COMPLETED | COMPLETED | 2023-10-13 14:12:17 | 2023-10-13 14:12:17
48 | TT15299 | Rushikesh Harkare | Bill checking ADD EDIT VIEW Bugs Solving | 2023-10-13 | 04:00 | 240 | 03:51:35 | 2023-10-13 |  | COMPLETED | DELAYED | 2023-10-14 10:37:03 | 2023-10-14 10:37:03
49 | TT15299 | Rushikesh Harkare | Interviews | 2023-10-14 | 07:00 | 420 | 06:28:26 | 2023-10-14 |  | COMPLETED | COMPLETED | 2023-10-14 19:08:46 | 2023-10-14 19:08:46
50 | TT15299 | Rushikesh Harkare | Code Review and Live Support | 2023-10-16 | 20:00 | 1200 | 21:56:24 | 2023-10-20 |  | COMPLETED | DELAYED | 2023-10-27 18:27:01 | 2023-10-27 18:27:01
51 | TT15299 | Rushikesh Harkare | Technical Documentation Meeting | 2023-10-16 | 02:00 | 120 | 02:14:50 | 2023-10-16 |  | COMPLETED | COMPLETED | 2023-10-16 18:25:04 | 2023-10-16 18:25:04
52 | TT15299 | Rushikesh Harkare | Code Merging into Live code | 2023-10-16 | 05:00 | 300 | 05:42:20 | 2023-10-20 |  | COMPLETED | COMPLETED | 2023-10-20 16:25:20 | 2023-10-20 16:25:20
53 | TT15299 | Rushikesh Harkare | Resolve Bugs of Go-Live Modules | 2023-10-17 | 08:00 | 480 | 07:33:32 | 2023-10-20 |  | COMPLETED | COMPLETED | 2023-10-20 16:25:09 | 2023-10-20 16:25:09
54 | TT15299 | Rushikesh Harkare | Code Review and KT to Radhika | 2023-10-23 | 30:00 | 1800 | 29:50:30 | 2023-10-27 |  | COMPLETED | COMPLETED | 2023-10-27 18:26:54 | 2023-10-27 18:26:54
55 | TT15299 | Rushikesh Harkare | Bill Checking Live Bugs and Deployment | 2023-10-23 | 03:00 | 180 | 03:21:52 | 2023-10-24 |  | COMPLETED | COMPLETED | 2023-10-23 18:10:22 | 2023-10-23 18:10:22
56 | TT15299 | Rushikesh Harkare | PO Point explaination KT | 2023-10-25 | 00:30 | 30 | 00:15:02 | 2023-10-25 |  | COMPLETED | COMPLETED | 2023-10-25 18:09:36 | 2023-10-25 18:09:36
57 | TT16866 | Rushikesh Harkare | Ticket against Added task not showing in user task report . | 2023-10-23 | 00:30 | 30 | 00:00:00 | 2023-10-25 |  | COMPLETED | COMPLETED | 2023-10-26 16:26:53 | 2023-10-24 17:11:50
58 | TT16866 | Rushikesh Harkare | Regularization Request Time calculation showing Wrong | 2023-10-23 | 01:00 | 60 | 00:00:00 | 2023-10-25 |  | COMPLETED | COMPLETED | 2023-10-26 16:26:53 | 2023-10-24 17:11:37
59 | TT15299 | Rushikesh Harkare | TTD Meeting With all non-d developers | 2023-10-26 | 01:00 | 60 | 03:13:38 | 2023-10-26 |  | COMPLETED | COMPLETED | 2023-10-26 14:44:20 | 2023-10-26 14:44:20
60 | TT15994 | Rushikesh Harkare | Code Review 30Oct - 03Nov | 2023-10-30 | 30:00 | 1800 | 16:27:43 | 2023-11-03 |  | COMPLETED | DELAYED | 2023-11-06 10:11:11 | 2023-11-06 10:11:11
61 | TT15994 | Rushikesh Harkare | create Technica DOC for complete Bill checking , Test Cases and Forgot Pass, and Sign In | 2023-10-30 | 10:00 | 600 | 07:31:35 | 2023-11-03 |  | COMPLETED | DELAYED | 2023-11-06 10:11:06 | 2023-11-06 10:11:06
62 | TT15299 | Rushikesh Harkare | Code Review 06Nov - 09Nov | 2023-11-06 | 16:00 | 960 | 14:54:44 | 2023-11-09 |  | COMPLETED | COMPLETED | 2023-11-09 13:57:39 | 2023-11-09 13:57:39
63 | TT15299 | Rushikesh Harkare | Review the Technical Doc of Complete Bill Checking and Complete Ticketing Sysytem | 2023-11-08 | 06:00 | 360 | 05:55:04 | 2023-11-10 |  | COMPLETED | COMPLETED | 2023-11-09 13:57:25 | 2023-11-09 13:57:25
64 | TT15299 | Rushikesh Harkare | Fun Friday - 10-11-2023 | 2023-11-10 | 01:00 | 60 | 00:30:38 | 2023-11-10 |  | COMPLETED | COMPLETED | 2023-11-10 17:36:54 | 2023-11-10 17:36:54
65 | TT18190 | Rushikesh Harkare | test | 2023-12-06 | 00:20 | 20 | 00:00:00 | 2023-12-07 |  | COMPLETED | COMPLETED | 2023-12-04 10:36:23 | 2023-12-04 10:36:23
66 | TT18190 | Rushikesh Harkare | DOC Reading For New Development | 2023-12-13 | 01:00 | 60 | 03:55:13 | 2023-12-13 |  | COMPLETED | COMPLETED | 2023-12-13 17:22:11 | 2023-12-13 17:22:11
67 | TT18190 | Rushikesh Harkare | KT New Dev Meeting | 2023-12-13 | 01:00 | 60 | 15:58:44 | 2023-12-13 |  | COMPLETED | DELAYED | 2023-12-14 09:20:37 | 2023-12-14 09:20:37
68 | TT18190 | Rushikesh Harkare | Test case Module KT | 2023-12-13 | 01:00 | 60 | 01:36:42 | 2023-12-13 |  | COMPLETED | COMPLETED | 2023-12-13 17:22:01 | 2023-12-13 17:22:01
69 | TT18190 | Rushikesh Harkare | KT to react team, code review, and Support | 2023-12-18 | 40:00 | 2400 | 17:21:12 | 2023-12-22 |  | COMPLETED | DELAYED | 2023-12-26 09:18:58 | 2023-12-26 09:18:58
70 | TT18190 | Rushikesh Harkare | KT to react team, code review, and Support - 26/12/2023 | 2023-12-26 | 30:00 | 1800 | 28:50:04 | 2023-12-29 |  | COMPLETED | COMPLETED | 2023-12-29 17:19:52 | 2023-12-29 17:19:52