## data
sr | ticket_id | task_owner | task_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Remark
17 | TT10647 | Amruta Kore | Understanding the flow of Customer view | 2024-01-15 | 00:30 | 00:48:56 | 2024-01-15 |  | COMPLETED | COMPLETED | 2024-01-15 17:38:53 | 2024-01-15 17:38:53 | Done
18 | TT10647 | Amruta Kore | Test Execution - Self admin role ( Tenant Employee as admin) | 2024-01-15 | 02:00 | 01:00:26 | 2024-01-15 |  | IN_PROGRESS | DELAYED | 2024-01-15 09:53:05 |  | Done
19 | TT10647 | Amruta Kore | Test execution - Super admin role execution | 2024-01-15 | 01:00 | 03:03:21 | 2024-01-15 |  | COMPLETED | COMPLETED | 2024-01-15 17:38:41 | 2024-01-15 17:38:41 | Done
20 | TT10647 | Amruta Kore | Retesting - Super admin, Self Admin, Tenant end user | 2024-01-15 | 02:00 | 00:44:52 | 2024-01-15 |  | IN_PROGRESS | DELAYED | 2024-01-15 09:53:57 |  | Done
21 | TT10647 | Amruta Kore | TT10647: Test Execution( Tenant master add/edit/view, Tenant employee(Admin)- user creation, Query type, role master, Dynamic form , Customer Mapping) | 2024-01-15 | 02:00 | 00:39:49 | 2024-01-15 |  | IN_PROGRESS | DELAYED | 2024-01-15 09:53:36 |  | Done
22 | TT16817 | Amruta Kore | General discussion Morning | 2024-01-15 | 01:15 | 00:36:03 | 2024-01-19 |  | IN_PROGRESS | IN_PROGRESS |  |  | Done
23 | TT16817 | Amruta Kore | General Discussion - Evening | 2024-01-15 | 01:15 | 00:00:03 | 2024-01-19 |  | IN_PROGRESS | IN_PROGRESS |  |  | Done
24 | TT16817 | Amruta Kore | KT/Self improvement | 2024-01-16 | 04:00 | 00:00:00 | 2024-01-19 |  | TO_DO | TO_DO
25 | TT16817 | Amruta Kore | Fun Friday/ rescheduling | 2024-01-19 | 01:30 | 00:00:00 | 2024-01-19 |  | TO_DO | TO_DO
26 | TT14739 | Amruta Kore | Retesting of All masters- add edit, view, Tenant's self admin' login, master admin, super admin | 2024-01-16 | 04:00 | 00:00:00 | 2024-01-16 |  | COMPLETED | COMPLETED | 2024-01-15 12:12:13 | 2024-01-15 12:12:13
27 | TT14739 | Amruta Kore | Test Execution- Retesting of Edit ticket, view ticket create ticket, query type customer mapping approach | 2024-01-16 | 02:30 | 00:00:00 | 2024-01-16 |  | COMPLETED | COMPLETED | 2024-01-15 12:12:31 | 2024-01-15 12:12:31
28 | TT14739 | Amruta Kore | End to end test execution customer view- 6hrs | 2024-01-17 | 06:00 | 00:00:00 | 2024-01-17 |  | COMPLETED | COMPLETED | 2024-01-15 12:12:00 | 2024-01-15 12:12:00
29 | TT10647 | Amruta Kore | TT10647: All masters- add edit, view, Tenant's self admin' login,) master admin, super admin | 2024-01-16 | 04:00 | 00:00:00 | 2024-01-16 |  | TO_DO | TO_DO
30 | TT10647 | Amruta Kore | TT10647: Retesting of All masters- add edit, view, Tenant's self admin' login, master admin, super admin | 2024-01-16 | 02:30 | 00:00:00 | 2024-01-16 |  | TO_DO | TO_DO | 2024-01-15 12:19:34
31 | TT10647 | Amruta Kore | End to end test execution customer view | 2024-01-17 | 06:30 | 00:00:00 | 2024-01-17 |  | TO_DO | TO_DO
32 | TT10647 | Amruta Kore | Test execution | 2024-01-15 | 00:10 | 00:00:00 | 2024-01-15 |  | TO_DO | DELAYED |  |  | Done