## data
sr | ticket_id | task_owner | sprint_name | sprint_start_date | sprint_end_date | task_name | type_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at
1 | TT21914 | Amreen Shaikh | - | - | - | Support from Preeti Ma'am. | Query clarification | 2024-09-02 | 02:30:00 | 03:43:21 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-08 23:15:06 | 2024-09-06 19:27:58
2 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Tester interview | Interview | 2024-09-30 | 12:00:00 | 13:07:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:20 | 2024-10-01 19:34:20
3 | TT21405 | Amreen Shaikh | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | Scheduling | Task Scheduling | 2024-10-11 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-11 18:07:05 | 2024-10-11 18:07:05
4 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Issue explanation to developer | Brainstorming with DEV Team \BA | 2024-09-26 | 00:30:00 | 01:26:40 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 19:48:57 | 2024-09-26 19:48:57
5 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Logic building guidence | Technical guidance/Process Input | 2024-09-18 | 02:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:05 | 2024-09-20 20:38:05
6 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48
7 | TT21405 | Amreen Shaikh | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | Estimation | Estimate the requirement | 2024-10-11 | 00:15:00 | 00:13:20 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-11 14:11:55 | 2024-10-11 14:11:55
8 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | E2E retesting - Bill transaction | E2E Testing. | 2024-09-26 | 12:00:00 | 11:39:15 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-08 17:12:40 | 2024-10-08 17:12:40
9 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Query clarification | 2024-09-09 | 03:45:00 | 02:53:19 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:22 | 2024-09-13 20:10:22
10 | TT20736 | Amreen Shaikh | - | - | - | Customer mapping - Explain issue to dev | Explore the existing system. | 2024-08-29 | 00:30:00 | 00:23:00 | 2024-08-29 |  | COMPLETED | IN_TIME | 2024-08-29 19:17:08 | 2024-08-29 19:17:08
11 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Amreen - Support from Preeti Ma'am. | Query clarification | 2024-09-30 | 02:00:00 | 00:40:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:56 | 2024-10-04 20:47:56
12 | TT21405 | Amreen Shaikh | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | Document reading | Document Reading | 2024-10-10 | 01:00:00 | 01:05:09 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 15:00:45 | 2024-10-10 15:00:45
13 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | E2E testing - Bill transaction | E2E Testing. | 2024-09-23 | 18:00:00 | 16:11:19 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 11:35:41 | 2024-09-26 11:35:41
14 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Logic building guidence | Technical guidance/Process Input | 2024-09-09 | 03:45:00 | 02:42:35 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:15 | 2024-09-13 20:10:15
15 | TT21914 | Amreen Shaikh | - | - | - | Support from Preeti Ma'am. | Query clarification | 2024-08-28 | 01:30:00 | 03:39:12 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 20:33:42 | 2024-08-30 20:33:42
16 | TT21405 | Amreen Shaikh | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | KT for item Counter mapping Bulk upload at 3.30pm | KT Session | 2024-10-11 | 01:00:00 | 00:50:34 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-11 13:24:06 | 2024-10-11 13:24:06
17 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | E2E testing - Bill transaction - add, edit, view, grid view, approval & rejection cycle. + Payment details page. | E2E Testing. | 2024-09-21 | 00:00:00 | 00:00:00 | 2024-09-21 |  | COMPLETED | DELAY | 2024-09-25 13:57:11 | 2024-09-25 13:57:11
18 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-09 | 05:00:00 | 03:54:18 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:03 | 2024-09-13 20:10:03
19 | TT19645 | Amreen Shaikh | - | - | - | AS Bill Checking RAD | RAD Testing | 2024-08-28 | 12:00:00 | 13:17:24 | 2024-09-02 |  | COMPLETED | DELAY | 2024-09-23 16:42:43 | 2024-09-23 16:42:43
20 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05
21 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Issue explaination | Requirement gathering | 2024-09-02 | 00:30:00 | 00:33:52 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 15:25:44 | 2024-09-02 15:25:44
22 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-04 | 03:00:00 | 02:58:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:20:39 | 2024-09-06 18:20:39
23 | TT23294 | Amreen Shaikh | - | - | - | Support for Time regularization | Mentoring | 2024-08-26 | 00:30:00 | 00:24:20 | 2024-08-26 |  | COMPLETED | DELAY | 2024-08-27 08:16:07 | 2024-08-27 08:16:07
24 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:54:27 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09
25 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Sprint plaaning | Task Scheduling | 2024-10-09 | 01:15:00 | 01:19:06 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 16:38:35 | 2024-10-09 16:38:35
26 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | TS BC Queries | General meeting | 2024-08-22 | 00:30:00 | 00:18:44 | 2024-08-22 |  | COMPLETED | IN_TIME | 2024-08-22 15:53:34 | 2024-08-22 15:53:34
27 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-03 | 01:00:00 | 00:48:00 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-06 17:35:09 | 2024-09-03 22:03:33
28 | TT19645 | Amreen Shaikh | - | - | - | AS BC Retesting | Bugs Retesting | 2024-08-26 | 04:00:00 | 06:09:40 | 2024-08-27 |  | COMPLETED | IN_TIME | 2024-08-27 09:02:00 | 2024-08-27 09:02:00
29 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:44:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31
30 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website test case review | Review Test cases | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-09 19:12:18 | 2024-10-09 19:12:18
31 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | TS BC issue explanation and Positive E2E flow execution. | Retesting | 2024-08-12 | 11:00:00 | 10:41:58 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-14 19:29:43 | 2024-08-14 19:29:43
32 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Logic building guidence | Technical guidance/Process Input | 2024-09-02 | 02:15:00 | 02:28:04 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:18:48 | 2024-09-06 20:18:48
33 | TT24437 | Amreen Shaikh | - | - | - | Regularization CR KT - go through recording | Explore the existing system. | 2024-08-26 | 00:30:00 | 00:00:00 | 2024-08-26 |  | COMPLETED | DELAY | 2024-08-30 20:36:16 | 2024-08-30 20:36:16
34 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 30 Sept - 4 oct | Task Scheduling | 2024-09-27 | 00:30:00 | 01:45:14 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:50:31 | 2024-09-27 20:50:31
35 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Scheduling for upcoming week | Task Scheduling | 2024-10-08 | 00:30:00 | 00:53:43 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 19:59:16 | 2024-10-08 19:59:16
36 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Vendor master edit - Automation scripting | Development | 2024-08-06 | 00:00:00 | 00:00:00 | 2024-08-06 |  | COMPLETED | IN_TIME | 2024-08-02 20:35:20 | 2024-08-02 20:35:20
37 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Script review | 2024-09-02 | 02:15:00 | 02:46:39 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:18:42 | 2024-09-06 20:18:42
38 | TT24437 | Amreen Shaikh | - | - | - | Regularization CR KT | KT Session | 2024-08-21 | 01:08:00 | 00:00:00 | 2024-08-21 |  | COMPLETED | IN_TIME | 2024-08-21 19:14:34 | 2024-08-21 19:14:34
39 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 01:12:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40
40 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-09 16:55:48 | 2024-10-09 16:55:48
41 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website - Validation review | Test Case Review | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-09 19:10:56 | 2024-10-09 19:10:56
42 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Payment template master (Add, View, Grid view & Edit) Automation Scripting | Development | 2024-08-01 | 06:30:00 | 05:20:17 | 2024-08-02 |  | COMPLETED | IN_TIME | 2024-08-02 20:36:48 | 2024-08-02 20:36:48
43 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Script review | 2024-08-26 | 05:00:00 | 04:47:01 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 21:34:42 | 2024-08-30 21:34:42
44 | TT24452 | Amreen Shaikh | - | - | - | TR KT and Discussion: Show played and paused tasks of a user | KT Session | 2024-08-20 | 00:45:00 | 00:49:20 | 2024-08-20 |  | COMPLETED | IN_TIME | 2024-08-20 20:54:22 | 2024-08-20 20:54:22
45 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 23 Sept - 27 sept | Task Scheduling | 2024-09-20 | 00:30:00 | 00:44:13 | 2024-09-20 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-23 16:42:05 | 2024-09-23 16:42:05
46 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-08 15:07:54 | 2024-10-08 15:07:54
47 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 04:02:53 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31
48 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Test script review | 2024-08-20 | 04:00:00 | 02:19:37 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 22:43:59 | 2024-08-23 22:43:59
49 | TT19645 | Amreen Shaikh | - | - | - | GRN history + PO closer edit + history - retesting | Retesting | 2024-08-19 | 04:00:00 | 04:38:52 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 11:42:49 | 2024-08-23 11:42:49
50 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:15:00 | 00:40:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39
51 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website scheduling | Task Scheduling | 2024-10-11 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | DELAY
52 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil - report preparation | Daily Summary report | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-09 16:57:49 | 2024-10-09 16:57:49
53 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS KT Session | KT Session | 2024-09-26 | 01:30:00 | 01:29:36 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:12:46 | 2024-09-27 15:12:46
54 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 9 Sept - 13 sept | Task Scheduling | 2024-09-06 | 00:30:00 | 00:29:14 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:12:26 | 2024-09-06 20:12:26
55 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | My CS APP Daily Sync call 23-27 | Daily Sync Call | 2024-09-23 | 00:50:00 | 00:18:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:07:41 | 2024-09-27 17:07:41
56 | TT19645 | Amreen Shaikh | - | - | - | GRN restesting - add + Edit + View | Retesting | 2024-08-19 | 03:00:00 | 02:43:17 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 11:44:07 | 2024-08-23 11:44:07
57 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 16 Sept - 20 sept | Task Scheduling | 2024-09-13 | 00:30:00 | 00:25:49 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:32 | 2024-09-13 20:08:32
58 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, Default setting, header, Reflection on website - testcase writing | Test Case Writing | 2024-10-11 | 00:00:00 | 04:18:39 | 2024-10-11 |  | IN_PROGRESS | DELAY
59 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for automation | Query clarification | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-09 16:55:03 | 2024-10-09 16:55:03
60 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS - KT Session | KT Session | 2024-09-26 | 01:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:16 | 2024-09-20 20:38:16
61 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support for task scheduling for swapnil | Task Scheduling | 2024-08-26 | 00:30:00 | 00:27:28 | 2024-08-26 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-27 08:16:34 | 2024-08-27 08:16:34
62 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Validation updation | Validation updation | 2024-09-09 | 00:20:00 | 00:20:10 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:03:18 | 2024-09-09 19:03:18
63 | TT21819 | Amreen Shaikh | - | - | - | Task scheduling 26 - 30 aug | Task Scheduling | 2024-08-23 | 00:30:00 | 00:30:08 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 22:43:41 | 2024-08-23 22:43:41
64 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:14:50 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40
65 | TT21819 | Amreen Shaikh | - | - | - | Meeting with Preeti maam | General meeting | 2024-08-09 | 00:55:00 | 00:50:08 | 2024-08-09 |  | COMPLETED | IN_TIME | 2024-08-09 17:43:17 | 2024-08-09 17:43:17
66 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Report preparation. | Daily Summary report | 2024-09-13 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:00 | 2024-09-13 20:11:00
67 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Query clarification | 2024-09-18 | 01:30:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:04:45 | 2024-09-20 22:04:45
68 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 2 Sept - 6 sept | Task Scheduling | 2024-08-30 | 00:30:00 | 00:53:17 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 20:35:25 | 2024-08-30 20:35:25
69 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Test case modification | Test case updation\modification | 2024-09-13 | 01:00:00 | 02:02:29 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-20 19:54:36 | 2024-09-20 19:54:36
70 | TT21819 | Amreen Shaikh | - | - | - | Support to Swapnil 19/08/2024 - 23/08/2024 | Mentoring | 2024-08-19 | 04:00:00 | 06:05:02 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 20:00:22 | 2024-08-23 20:00:22
71 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25
72 | TT21819 | Amreen Shaikh | - | - | - | Support to Swapnil 12/08/2024 - 16/08/2024 | Mentoring | 2024-08-12 | 07:30:00 | 06:23:00 | 2024-08-16 |  | COMPLETED | IN_TIME | 2024-08-16 20:56:35 | 2024-08-16 20:56:35
73 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Bill checking KT scheduling | Task Scheduling | 2024-10-11 | 00:30:00 | 00:19:58 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-11 18:58:36 | 2024-10-11 18:58:36
74 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Report preparation | Daily Summary report | 2024-09-12 | 00:15:00 | 00:17:26 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 19:37:16 | 2024-09-12 19:37:16
75 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website - Document reading | Document Reading | 2024-09-26 | 01:00:00 | 02:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 13:41:43 | 2024-09-26 13:41:43
76 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task type KT | KT Session | 2024-08-22 | 00:30:00 | 01:03:47 | 2024-08-22 |  | COMPLETED | IN_TIME | 2024-08-22 18:42:05 | 2024-08-22 18:42:05
77 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Testcase writing | Test case writing- | 2024-09-09 | 03:30:00 | 02:33:13 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-13 16:29:19 | 2024-09-13 16:29:19
78 | TT19645 | Amreen Shaikh | - | - | - | Issue explanation to dev | Requirement gathering | 2024-08-13 | 00:30:00 | 00:27:12 | 2024-08-13 |  | COMPLETED | IN_TIME | 2024-08-13 19:18:35 | 2024-08-13 19:18:35
79 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02
80 | TT23530 | Amreen Shaikh | - | - | - | CS website KT from sanika | KT Session | 2024-08-12 | 00:00:00 | 00:00:00 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-14 12:45:43 | 2024-08-14 12:45:43
81 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01
82 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Support to Swapnil | Query clarification | 2024-09-10 | 01:00:00 | 01:09:55 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:38 | 2024-09-13 20:10:38
83 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Malfunctioning discussion with Gaurav sir | General meeting | 2024-08-14 | 00:45:00 | 00:45:00 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-16 15:25:02 | 2024-08-14 17:16:55
84 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Scheme - Daily sync call | Sync call with BA | 2024-09-09 | 00:50:00 | 17:19:08 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:15:56 | 2024-09-13 19:15:56
85 | TT21819 | Amreen Shaikh | - | - | - | Task scheduling | Task Scheduling | 2024-08-19 | 00:30:00 | 00:33:17 | 2024-08-19 |  | COMPLETED | IN_TIME | 2024-08-19 12:57:39 | 2024-08-19 12:57:39
86 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Automation Scheduling - support to Swapnil | Support. | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:12:44 | 2024-09-06 20:12:44
87 | TT23530 | Amreen Shaikh | - | - | - | CS Website estimation | Estimate calculation | 2024-08-12 | 00:00:00 | 00:00:00 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-14 12:45:56 | 2024-08-14 12:45:56
88 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT - Customer view | Internal KT/cross KT | 2024-09-02 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-08-30 20:15:30 | 2024-08-30 20:15:30
89 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:26:29 | 2024-09-06 18:26:29
90 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Query clarification | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-09 18:59:53 | 2024-09-09 18:59:53
91 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Testing - Report preparation | Daily Summary report | 2024-10-08 | 00:00:00 | 00:00:00 | 2024-10-08 |  | COMPLETED | DELAY | 2024-10-09 15:25:35 | 2024-10-09 15:25:35
92 | TT22309 | Amreen Shaikh | - | - | - | Framework understanding | Automation | 2024-08-19 | 03:00:00 | 01:18:24 | 2024-08-19 |  | COMPLETED | DELAY | 2024-08-22 20:29:38 | 2024-08-22 20:29:38
93 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module - Document reading. | Document Reading | 2024-08-26 | 00:30:00 | 00:31:30 | 2024-08-26 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 17:11:00 | 2024-08-30 17:11:00
94 | TT23530 | Amreen Shaikh | - | - | - | CS website document reading | Documentation Reading | 2024-08-12 | 00:00:00 | 00:00:00 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-14 12:46:12 | 2024-08-14 12:46:12
95 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT | Internal KT/cross KT | 2024-08-26 | 05:00:00 | 05:58:19 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 19:40:35 | 2024-08-30 19:40:35
96 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Review and update test cases on TS | Test Case Review | 2024-09-03 | 00:45:00 | 01:00:54 | 2024-09-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-04 20:09:41 | 2024-09-04 20:09:41
97 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Mentoring | 2024-09-03 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:37:15 | 2024-09-06 16:37:15
98 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Preeti Maam | General meeting | 2024-08-12 | 00:18:00 | 00:40:42 | 2024-08-12 |  | COMPLETED | IN_TIME | 2024-08-12 19:42:54 | 2024-08-12 19:42:54
99 | TT23294 | Amreen Shaikh | - | - | - | Time regularization - test case review | Test Case Review | 2024-08-13 | 00:20:00 | 00:23:59 | 2024-08-13 |  | COMPLETED | DELAY | 2024-08-14 19:29:34 | 2024-08-14 19:29:34
100 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module KT - go through recording | Explore the existing system. | 2024-08-26 | 00:30:00 | 00:13:36 | 2024-08-26 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 20:36:00 | 2024-08-30 20:36:00
101 | TT20736 | Amreen Shaikh | - | - | - | Customer view KT from Preeti maam | KT Session | 2024-08-07 | 02:00:00 | 01:55:00 | 2024-08-07 |  | COMPLETED | IN_TIME | 2024-08-07 20:56:27 | 2024-08-07 20:56:27
102 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT | KT Session | 2024-08-20 | 02:00:00 | 01:22:08 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 15:47:50 | 2024-08-23 15:47:50
103 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-02 | 00:44:00 | 00:34:46 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-03 19:29:26 | 2024-09-03 19:29:26
104 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CSM + Website Validation updation | Validation updation | 2024-10-10 | 01:30:00 | 01:44:02 | 2024-10-11 |  | COMPLETED | DELAY | 2024-10-13 16:40:16 | 2024-10-13 16:40:16
105 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Scheme Testing | Testing. | 2024-09-25 | 02:00:00 | 02:36:34 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 15:24:16 | 2024-10-09 15:24:16
106 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module KT | KT Session | 2024-08-20 | 00:30:00 | 00:00:36 | 2024-08-20 |  | COMPLETED | IN_TIME | 2024-08-20 15:30:48 | 2024-08-20 15:30:48
107 | TT21914 | Amreen Shaikh | - | - | - | Login jar issue resolving | General meeting | 2024-08-07 | 01:00:00 | 01:20:00 | 2024-08-07 |  | COMPLETED | IN_TIME | 2024-08-08 13:14:13 | 2024-08-07 19:49:57
108 | TT24208 | Amreen Shaikh | Testing_DPOS_Practice_Oct24_WK1 | 2024-09-30 | 2024-10-06 | Sale bill (Gold item) - Estimate + invoice. Practice | D Practice | 2024-08-23 | 02:30:00 | 01:13:12 | 2024-08-23 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-09 21:43:21 | 2024-09-09 21:43:21
109 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - report review | Reporting Review | 2024-09-02 | 00:15:00 | 00:53:10 | 2024-09-02 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-03 20:42:38 | 2024-09-03 20:42:38
110 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Sync call | Sync call with BA | 2024-08-30 | 00:30:00 | 00:38:18 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 20:34:28 | 2024-08-30 20:34:28
111 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Validation writing | Validation writing | 2024-09-05 | 00:30:00 | 00:42:50 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 20:14:18 | 2024-09-05 20:14:18
112 | TT23530 | Amreen Shaikh | - | - | - | CS Website Sync call | General meeting | 2024-08-07 | 00:30:00 | 00:30:55 | 2024-08-07 |  | COMPLETED | IN_TIME | 2024-08-07 19:54:49 | 2024-08-07 19:54:49
113 | TT24208 | Amreen Shaikh | Testing_DPOS_Practice_Oct24_WK1 | 2024-09-30 | 2024-10-06 | New P2P practice & item creation practice | D Practice | 2024-08-22 | 05:00:00 | 04:36:51 | 2024-08-23 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-04 15:57:22 | 2024-09-04 15:57:22
114 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - report preparation | Daily Summary report | 2024-09-04 | 00:20:00 | 00:24:54 | 2024-09-04 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-06 17:07:04 | 2024-09-06 17:07:04
115 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | DSC - CMS | Daily Sync Call | 2024-09-02 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:16:17 | 2024-09-06 17:16:17
116 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Scheme Enrollment - Daily sync call | Daily Sync Call | 2024-09-06 | 01:15:00 | 00:41:15 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-06 19:34:56 | 2024-09-06 19:34:56
117 | TT20736 | Amreen Shaikh | - | - | - | Customer mapping E2E Testing ( Bulk upload wise ) | Testing | 2024-08-09 | 03:00:00 | 00:04:24 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-14 17:02:19 | 2024-08-14 17:02:19
118 | TT24208 | Amreen Shaikh | Testing_DPOS_Practice_Oct24_WK1 | 2024-09-30 | 2024-10-06 | POS New P2P process recording understanding | D Practice | 2024-08-21 | 01:00:00 | 00:56:17 | 2024-08-21 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-22 13:33:00 | 2024-08-22 13:33:00
119 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to Swapnil for Consolidated report | Query clarification | 2024-09-02 | 01:30:00 | 01:59:48 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:31 | 2024-09-06 17:05:31
120 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website - Estimation | Estimate the requirement | 2024-10-09 | 02:00:00 | 05:30:00 | 2024-10-09 |  | COMPLETED | DELAY | 2024-10-10 17:29:51 | 2024-10-10 17:10:39
121 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | New scheme Enrollment Brain storming | Brainstorming | 2024-09-05 | 00:30:00 | 00:50:05 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 17:48:00 | 2024-09-05 17:48:00
122 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am | Query clarification | 2024-09-23 | 02:30:00 | 03:48:53 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:51:17 | 2024-09-27 20:51:17
123 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | documentation module query clearification | Brainstorming with DEV Team \BA | 2024-08-29 | 00:30:00 | 00:00:00 | 2024-08-29 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 18:59:49 | 2024-08-30 18:59:49
124 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS Meeting - Plan of action | General meeting | 2024-08-29 | 01:00:00 | 01:09:58 | 2024-08-29 |  | COMPLETED | IN_TIME | 2024-08-29 17:44:36 | 2024-08-29 17:44:36
125 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01
126 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Prepare estimation | Estimate the requirement | 2024-09-05 | 00:30:00 | 00:45:14 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 20:14:24 | 2024-09-05 20:14:24
127 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-18 | 01:30:00 | 01:18:49 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:59:00 | 2024-09-20 20:59:00
128 | TT20736 | Amreen Shaikh | - | - | - | Customer mapping E2E testing ( Sub tenant ( customer view- 6 approaches) | Testing | 2024-08-06 | 04:00:00 | 05:54:08 | 2024-08-09 |  | COMPLETED | IN_TIME | 2024-08-09 13:35:03 | 2024-08-09 13:35:03
129 | TT24216 | Amreen Shaikh | Testing_Skill Upgrade_Oct24_Wk1 | 2024-09-30 | 2024-10-04 | Automation Planning - support to Swapnil | Planning | 2024-09-13 | 00:30:00 | 00:23:28 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:17:42 | 2024-09-13 20:17:42
130 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Go through the recording | Explore the existing system. | 2024-09-04 | 00:40:00 | 00:50:25 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:47 | 2024-09-04 19:41:47
131 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, Default setting page & tenant master page - Testing | Unit Testing | 2024-10-02 | 00:00:00 | 00:00:00 | 2024-10-02 |  | COMPLETED | IN_TIME | 2024-09-27 19:26:44 | 2024-09-27 19:26:44
132 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | Document reading | Document Reading | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-08 17:57:30 | 2024-10-08 17:57:30
133 | TT19645 | Amreen Shaikh | - | - | - | AS BC retesting. | Bug Retesting | 2024-09-18 | 03:30:00 | 04:34:29 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-23 16:39:51 | 2024-09-23 16:39:51
134 | TT20736 | Amreen Shaikh | - | - | - | customer mapping E2E Testing ( Main tenant - 6 approaches) | E2E Testing | 2024-08-05 | 04:00:00 | 05:11:45 | 2024-08-06 |  | COMPLETED | IN_TIME | 2024-08-06 21:46:33 | 2024-08-06 21:46:33
135 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Go through the document | Document Reading | 2024-09-04 | 00:40:00 | 00:45:42 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:52 | 2024-09-04 19:41:52
136 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, Default setting page & tenant master page - Test case writing | Test case writing- | 2024-08-27 | 00:15:00 | 00:13:32 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-01 15:05:57 | 2024-09-27 19:06:50
137 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | QR Code Generation - HRMS - document reading | Document Reading | 2024-08-28 | 00:00:00 | 00:00:00 | 2024-08-28 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 19:35:55 | 2024-08-30 19:35:55
138 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-09 | 02:30:00 | 00:29:56 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:19 | 2024-09-13 20:11:19
139 | TT23294 | Amreen Shaikh | - | - | - | Time Regularization CR KT | KT Session | 2024-08-05 | 00:30:00 | 01:00:00 | 2024-08-05 |  | COMPLETED | IN_TIME | 2024-09-13 14:43:51 | 2024-08-05 17:03:13
140 | TT24216 | Amreen Shaikh | Testing_Skill Upgrade_Oct24_Wk1 | 2024-09-30 | 2024-10-04 | Automation Planning - support to Swapnil | Planning | 2024-09-06 | 00:30:00 | 00:27:35 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:39:52 | 2024-09-06 20:39:52
141 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Daily Sync Call | Daily Sync Call | 2024-08-26 | 00:00:00 | 00:00:00 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 17:55:13 | 2024-08-30 17:55:13
142 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | KT Session - QR Code Generation - HRMS | KT from BA | 2024-08-28 | 00:00:00 | 00:00:00 | 2024-08-28 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 19:36:13 | 2024-08-30 19:36:13
143 | TT23294 | Amreen Shaikh | - | - | - | Regularization - Report Preparation | Daily Summary report | 2024-09-09 | 00:15:00 | 00:00:00 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 21:42:56 | 2024-09-09 21:42:56
144 | TT21819 | Amreen Shaikh | - | - | - | Framework - extent report Documentation | Documentation | 2024-08-06 | 00:00:00 | 00:00:00 | 2024-08-06 |  | COMPLETED | IN_TIME | 2024-08-03 10:27:09 | 2024-08-03 10:27:09
145 | TT24216 | Amreen Shaikh | Testing_Skill Upgrade_Oct24_Wk1 | 2024-09-30 | 2024-10-04 | Support to swapnil - unpass ticket practise | Query clarification | 2024-08-27 | 00:30:00 | 00:00:00 | 2024-08-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-29 19:09:01 | 2024-08-29 19:09:01
146 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS-Menu header meeting with all stakeholders | KT Session | 2024-08-23 | 00:30:00 | 01:13:11 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 18:09:13 | 2024-08-23 18:09:13
147 | TT23294 | Amreen Shaikh | - | - | - | Support for Regularization | Query clarification | 2024-09-09 | 00:30:00 | 00:47:01 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 17:55:43 | 2024-09-09 17:55:43
148 | TT21819 | Amreen Shaikh | - | - | - | Meeting with Gaurav Sir 12/08/2024 | General meeting | 2024-08-12 | 01:00:00 | 01:50:17 | 2024-08-12 |  | COMPLETED | IN_TIME | 2024-08-12 19:28:27 | 2024-08-12 19:28:27
149 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Knowledge transfer to Preeti ma'am. | Brainstorming | 2024-08-23 | 00:30:00 | 00:18:02 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 19:59:55 | 2024-08-23 19:59:55
150 | TT23932 | Amreen Shaikh | Sprint 1 | 2024-07-30 | 2024-08-31 | AS BC DIS GS PS | General meeting | 2024-09-12 | 00:30:00 | 00:27:33 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 19:58:04 | 2024-09-12 19:58:04
151 | TT21914 | Amreen Shaikh | - | - | - | Automation code test round - nirgun | Interview | 2024-09-06 | 01:30:00 | 01:22:16 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:09:40 | 2024-09-06 19:09:40
152 | TT21819 | Amreen Shaikh | - | - | - | Nemgiri go through CR Document | Documentation Reading | 2024-08-05 | 00:30:00 | 00:28:27 | 2024-08-05 |  | COMPLETED | IN_TIME | 2024-08-05 17:18:06 | 2024-08-05 17:18:06
153 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Sync Call | Daily Sync Call | 2024-08-23 | 01:00:00 | 00:58:06 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 14:09:31 | 2024-08-23 14:09:31
154 | TT23932 | Amreen Shaikh | Sprint 1 | 2024-07-30 | 2024-08-31 | AS BC Discussions | General meeting | 2024-09-06 | 00:30:00 | 00:29:19 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 14:16:41 | 2024-09-06 14:16:41
155 | TT20736 | Amreen Shaikh | - | - | - | Issue explanation to dev | Requirement gathering | 2024-09-03 | 00:30:00 | 00:34:21 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 17:09:31 | 2024-09-03 17:09:31
156 | TT21819 | Amreen Shaikh | - | - | - | Support to Swapnil 05/08/2024 - 09/08/2024 | Mentoring | 2024-08-05 | 15:00:00 | 13:07:52 | 2024-08-09 |  | COMPLETED | IN_TIME | 2024-08-09 21:36:19 | 2024-08-09 21:36:19
157 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website KT from sanika | KT Session | 2024-08-21 | 01:00:00 | 00:52:01 | 2024-08-21 |  | COMPLETED | IN_TIME | 2024-08-21 17:10:47 | 2024-08-21 17:10:47
158 | TT23932 | Amreen Shaikh | Sprint 1 | 2024-07-30 | 2024-08-31 | Team Activity | Brainstorming | 2024-08-27 | 01:00:00 | 01:15:22 | 2024-08-27 |  | COMPLETED | IN_TIME | 2024-08-27 15:12:47 | 2024-08-27 15:12:47
159 | TT19645 | Amreen Shaikh | - | - | - | AS report preparation | Daily Summary report | 2024-09-02 | 00:15:00 | 00:00:05 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:03:01 | 2024-09-06 19:03:01
160 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Branch visit meeting with HR | HR meeting | 2024-10-10 | 01:00:00 | 00:54:45 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 15:36:25 | 2024-10-10 15:36:25
161 | TT23674 | Amreen Shaikh | - | - | - | Nemgiri KT to Team Members | KT Session | 2024-08-05 | 01:00:00 | 00:25:58 | 2024-08-05 |  | COMPLETED | IN_TIME | 2024-08-05 16:29:18 | 2024-08-05 16:29:18
162 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website estimation | Estimate calculation | 2024-08-21 | 00:30:00 | 01:13:37 | 2024-08-21 |  | COMPLETED | IN_TIME | 2024-08-21 20:00:58 | 2024-08-21 20:00:58
163 | TT24437 | Amreen Shaikh | - | - | - | Regularization - validation review | Review. | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:26 | 2024-09-06 17:23:26
164 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Bill checking - KT plan of action | Planning | 2024-10-09 | 01:00:00 | 00:13:07 | 2024-10-09 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-10 00:12:02 | 2024-10-10 00:12:02
165 | TT21819 | Amreen Shaikh | - | - | - | Support to Swapnil 31/07/2024 - 02/08/2024 | Mentoring | 2024-07-31 | 06:00:00 | 05:36:52 | 2024-08-02 |  | COMPLETED | IN_TIME | 2024-08-02 19:50:02 | 2024-08-02 19:50:02
166 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website document reading | Documentation Reading | 2024-08-21 | 00:30:00 | 00:32:21 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 16:57:18 | 2024-09-06 16:57:18
167 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for automation multiple line | Query clarification | 2024-10-08 | 02:00:00 | 00:59:08 | 2024-10-09 |  | COMPLETED | DELAY | 2024-10-10 00:11:30 | 2024-10-10 00:11:30
168 | TT24437 | Amreen Shaikh | - | - | - | Support to swapnil - regularization | Query clarification | 2024-09-06 | 00:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:40 | 2024-09-06 17:23:40
169 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Testing team sync call | Testing Team Meeting | 2024-10-08 | 02:00:00 | 03:33:02 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-11 18:05:23 | 2024-10-11 18:05:23
170 | TT26067 | Amreen Shaikh | Salary Slip Download Issue in IOS My CS App | 2024-10-08 | 2024-10-12 | Kindly test the MY CS Application on IOS Application for Salary Slip Generation & Download | E2E Testing | 2024-10-10 | 03:00:00 | 02:02:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-10 19:27:29 | 2024-10-10 19:27:29
171 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Bill checking test on Live server | E2E Testing. | 2024-09-29 | 02:30:00 | 02:36:52 | 2024-09-29 |  | IN_PROGRESS | DELAY
172 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-19 | 01:00:00 | 00:53:41 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 21:52:24 | 2024-09-20 21:52:24
173 | TT24437 | Amreen Shaikh | - | - | - | Regularization - validation writing | Validation writing | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:51 | 2024-09-06 17:23:51
174 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA-KPI : Self improvement meeting | Query clarification | 2024-10-08 | 00:15:00 | 00:21:34 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:21:33 | 2024-10-08 16:21:33
175 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CSJ meeting with Gaurav Sir | General meeting | 2024-08-05 | 02:00:00 | 01:27:06 | 2024-08-05 |  | COMPLETED | IN_TIME | 2024-08-05 21:58:13 | 2024-08-05 21:58:13
176 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Script review | 2024-09-18 | 02:00:00 | 00:48:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:00 | 2024-09-20 20:38:00
177 | TT19645 | Amreen Shaikh | - | - | - | As BC Retesting | Testing. | 2024-09-02 | 04:00:00 | 02:10:25 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:09:15 | 2024-09-06 19:09:15
178 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Amreen | Query clarification | 2024-10-08 | 01:00:00 | 04:44:25 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-11 20:36:51 | 2024-10-11 20:36:51
179 | TT21405 | Amreen Shaikh | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | Task Scheduling Item counter mapping at 6.00 | Task Scheduling | 2024-10-11 | 01:08:00 | 00:45:25 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-11 19:10:07 | 2024-10-11 19:10:07
180 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Support to swapnil | Query clarification | 2024-09-23 | 02:30:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-08 17:58:26 | 2024-10-08 17:58:26
181 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS KT Session | KT Session | 2024-09-26 | 01:30:00 | 01:30:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:12:46 | 2024-09-27 15:12:46
182 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore & practice the connect us 2.0( Tenant Master, Dynamic Dropdown, Dynamic Form and Query Type Master) | Explore the existing system. | 2024-09-24 | 01:00:00 | 01:14:09 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 22:57:56 | 2024-09-24 22:57:56
183 | TT21819 | Swapnil Ramdasi | - | - | - | Meeting with Preeti maam | General meeting | 2024-08-09 | 00:55:00 | 00:50:42 | 2024-08-09 |  | COMPLETED | IN_TIME | 2024-08-09 17:43:17 | 2024-08-09 17:43:17
184 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-02 | 00:44:00 | 00:37:07 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-03 19:29:26 | 2024-09-03 19:29:26
185 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Query clarification | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-09 18:59:53 | 2024-09-09 18:59:53
186 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil( Tenant Master, Dynamic form, Dropdown master, Query Type Master) | Internal KT/cross KT | 2024-09-24 | 02:00:00 | 00:27:31 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:03:39 | 2024-09-24 19:03:39
187 | TT21819 | Swapnil Ramdasi | - | - | - | User master grid view page scripting | Automate test script | 2024-08-14 | 03:00:00 | 01:26:53 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-14 23:16:58 | 2024-08-14 23:16:58
188 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Support to Swapnil for Consolidated report | Query clarification | 2024-09-02 | 01:30:00 | 00:24:07 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:31 | 2024-09-06 17:05:31
189 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Mentoring | 2024-09-03 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:37:15 | 2024-09-06 16:37:15
190 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore & practice the connect us 2.0( User master, customer master, Role master and designation Master) | Explore the existing system. | 2024-09-23 | 01:00:00 | 01:05:27 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:06:43 | 2024-09-23 23:06:43
191 | TT21819 | Swapnil Ramdasi | - | - | - | User master edit page scripting | Automate test script | 2024-08-12 | 06:00:00 | 03:46:49 | 2024-08-13 |  | COMPLETED | DELAY | 2024-08-14 23:17:10 | 2024-08-14 23:17:10
192 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module Testing | Testing | 2024-09-02 | 02:30:00 | 04:00:10 | 2024-09-02 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-03 11:53:14 | 2024-09-03 11:53:14
193 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CSM + Website Validation writing | Validation writing | 2024-09-27 | 03:00:00 | 03:00:00 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-01 15:05:56 | 2024-09-29 23:02:40
194 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil (User Master, Customer Master, Role Master, Designation Master) | Internal KT/cross KT | 2024-09-23 | 02:00:00 | 00:41:06 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 12:18:43 | 2024-09-23 12:18:43
195 | TT23550 | Swapnil Ramdasi | - | - | - | PAN File not Working | Application Support | 2024-08-07 | 01:00:00 | 00:30:00 | 2024-08-07 |  | COMPLETED | DELAY | 2024-08-09 19:54:06 | 2024-08-09 19:54:06
196 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | documentation module query clearification | Brainstorming with DEV Team \BA | 2024-08-29 | 00:30:00 | 00:00:00 | 2024-08-29 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 18:59:49 | 2024-08-30 18:59:49
197 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Estimation KT to Swapnil | Internal KT/cross KT | 2024-09-06 | 00:45:00 | 00:42:10 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:53:10 | 2024-09-06 18:53:10
198 | TT23530 | Swapnil Ramdasi | - | - | - | CS Website Sync call | General meeting | 2024-08-07 | 00:30:00 | 00:18:19 | 2024-08-07 |  | COMPLETED | IN_TIME | 2024-08-07 19:54:49 | 2024-08-07 19:54:49
199 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | documentation module Estimation | Estimate the requirement | 2024-08-29 | 00:30:00 | 00:55:48 | 2024-08-29 |  | COMPLETED | IN_TIME | 2024-08-29 22:03:58 | 2024-08-29 22:03:58
200 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore and Practice connect us 2.0(Reports-user task, resource planning, Variance) | Explore the existing system. | 2024-10-01 | 04:00:00 | 00:00:09 | 2024-10-13 |  | COMPLETED | IN_TIME | 2024-10-08 19:48:15 | 2024-10-08 19:48:15
201 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | DSC - CMS | Daily Sync Call | 2024-09-02 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:16:17 | 2024-09-06 17:16:17
202 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01
203 | TT24006 | Swapnil Ramdasi | - | - | - | PAN File not Working | Application Support | 2024-08-06 | 00:00:00 | 00:00:00 | 2024-08-07 |  | COMPLETED | DELAY | 2024-08-08 12:44:01 | 2024-08-08 12:44:01
204 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module - Document reading | Documentation Reading | 2024-08-27 | 00:30:00 | 00:22:51 | 2024-08-27 |  | COMPLETED | IN_TIME | 2024-08-27 22:50:20 | 2024-08-27 22:50:20
205 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS Meeting - Plan of action | General meeting | 2024-08-29 | 01:00:00 | 01:11:01 | 2024-08-29 |  | COMPLETED | IN_TIME | 2024-08-29 17:44:36 | 2024-08-29 17:44:36
206 | TT23294 | Swapnil Ramdasi | - | - | - | Time regularization - history - Testing | Testing | 2024-08-09 | 03:00:00 | 00:57:04 | 2024-08-09 |  | COMPLETED | IN_TIME | 2024-08-09 20:39:48 | 2024-08-09 20:39:48
207 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module KT - go through recording. | KT Session | 2024-08-27 | 00:30:00 | 00:33:00 | 2024-08-27 |  | COMPLETED | IN_TIME | 2024-08-27 22:50:27 | 2024-08-27 22:50:27
208 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Daily Sync Call | Daily Sync Call | 2024-08-26 | 00:00:00 | 00:00:00 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 17:55:13 | 2024-08-30 17:55:13
209 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT - Customer view | Internal KT/cross KT | 2024-09-02 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-08-30 20:15:30 | 2024-08-30 20:15:30
210 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module KT | KT Session | 2024-08-20 | 00:30:00 | 00:10:57 | 2024-08-20 |  | COMPLETED | IN_TIME | 2024-08-20 15:30:48 | 2024-08-20 15:30:48
211 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | KT Session - CMS | KT Session | 2024-08-21 | 00:45:00 | 00:46:24 | 2024-08-21 |  | COMPLETED | IN_TIME | 2024-08-21 19:23:33 | 2024-08-21 19:23:33
212 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module kt | KT Session | 2024-08-29 | 00:30:00 | 00:47:37 | 2024-08-29 |  | COMPLETED | IN_TIME | 2024-08-29 13:07:37 | 2024-08-29 13:07:37
213 | TT21819 | Swapnil Ramdasi | - | - | - | Nemgiri - (Donation , Yearly donation, Room registration) System exploration | Explore the existing system | 2024-08-06 | 05:00:00 | 05:02:47 | 2024-08-07 |  | COMPLETED | IN_TIME | 2024-08-07 17:31:54 | 2024-08-07 17:31:54
214 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS - Document Go through | Documentation Reading | 2024-09-23 | 01:00:00 | 00:46:26 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:07:54 | 2024-09-23 23:07:54
215 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT | Internal KT/cross KT | 2024-08-26 | 05:00:00 | 01:55:42 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 19:40:35 | 2024-08-30 19:40:35
216 | TT21819 | Swapnil Ramdasi | - | - | - | Sprint planning - System exploration | Explore the existing system | 2024-08-06 | 00:00:00 | 00:00:00 | 2024-08-07 |  | COMPLETED | IN_TIME | 2024-08-02 19:24:29 | 2024-08-02 19:24:29
217 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT | KT Session | 2024-08-20 | 02:00:00 | 00:00:00 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-23 15:47:50 | 2024-08-23 15:47:50
218 | TT21819 | Swapnil Ramdasi | - | - | - | User master integration in DTO | Automate test script | 2024-08-08 | 04:00:00 | 08:03:06 | 2024-08-09 |  | COMPLETED | IN_TIME | 2024-08-09 20:41:31 | 2024-08-09 20:41:31
219 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT | KT Session | 2024-08-19 | 00:00:00 | 00:00:00 | 2024-08-23 |  | COMPLETED | IN_TIME | 2024-08-20 12:46:59 | 2024-08-20 12:46:59
220 | TT21819 | Swapnil Ramdasi | - | - | - | User master scripting | Automate test script | 2024-08-07 | 00:00:00 | 01:02:19 | 2024-08-08 |  | COMPLETED | IN_TIME | 2024-08-08 13:07:43 | 2024-08-08 13:07:43
221 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT | KT Session | 2024-08-12 | 04:00:00 | 01:15:55 | 2024-08-16 |  | COMPLETED | IN_TIME | 2024-08-16 23:03:47 | 2024-08-16 23:03:47
222 | TT21819 | Swapnil Ramdasi | - | - | - | Meeting with Gaurav Sir 12/08/2024 | General meeting | 2024-08-12 | 01:00:00 | 01:50:43 | 2024-08-12 |  | COMPLETED | IN_TIME | 2024-08-12 19:28:27 | 2024-08-12 19:28:27
223 | TT21819 | Swapnil Ramdasi | - | - | - | Customer mapping integration in DTO | Automate test script | 2024-08-07 | 03:00:00 | 03:17:34 | 2024-08-08 |  | COMPLETED | IN_TIME | 2024-08-08 20:19:10 | 2024-08-08 20:19:10
224 | TT21819 | Swapnil Ramdasi | - | - | - | Customer mapping scripting | Automate test script | 2024-08-05 | 03:30:00 | 03:30:00 | 2024-08-06 |  | COMPLETED | IN_TIME | 2024-08-06 18:19:12 | 2024-08-06 18:19:12
225 | TT23294 | Swapnil Ramdasi | - | - | - | Time Regularization CR KT | KT Session | 2024-08-05 | 00:30:00 | 00:23:50 | 2024-08-05 |  | COMPLETED | IN_TIME | 2024-09-13 14:43:51 | 2024-08-05 17:03:13
226 | TT21819 | Swapnil Ramdasi | - | - | - | Cross KT | KT Session | 2024-08-05 | 03:30:00 | 03:43:20 | 2024-08-09 |  | COMPLETED | IN_TIME | 2024-08-09 20:40:12 | 2024-08-09 20:40:12
227 | TT21819 | Swapnil Ramdasi | - | - | - | Framework - DTO understatnding | General meeting | 2024-08-01 | 02:30:00 | 02:30:00 | 2024-08-01 |  | COMPLETED | IN_TIME | 2024-08-01 23:06:04 | 2024-08-01 23:06:04
228 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01
229 | TT21819 | Swapnil Ramdasi | - | - | - | Integration of create ticket into DTO concept + DTO practise | Development | 2024-08-02 | 03:30:00 | 03:29:14 | 2024-08-02 |  | COMPLETED | IN_TIME | 2024-08-02 16:19:48 | 2024-08-02 16:19:48
230 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | Document reading | Document Reading | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-08 17:57:30 | 2024-10-08 17:57:30
231 | TT21819 | Swapnil Ramdasi | - | - | - | CS Jewel - website - Comapatibility test case writing. | Test Case Writing | 2024-08-01 | 00:00:00 | 00:00:00 | 2024-08-01 |  | COMPLETED | IN_TIME | 2024-07-31 19:31:59 | 2024-07-31 19:31:59
232 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | test | Application Support | 2024-10-03 | 00:40:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-04 20:50:51 | 2024-10-04 20:50:51
233 | TT21819 | Swapnil Ramdasi | - | - | - | Sprint - KT | KT Session | 2024-08-01 | 01:00:00 | 00:37:58 | 2024-08-01 |  | COMPLETED | IN_TIME | 2024-08-01 19:27:03 | 2024-08-01 19:27:03
234 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | QR Code Generation - HRMS - document reading | Document Reading | 2024-08-28 | 00:00:00 | 00:00:00 | 2024-08-28 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 19:35:55 | 2024-08-30 19:35:55
235 | TT21819 | Swapnil Ramdasi | - | - | - | Automate - Create ticket (Customer mapping : assign ticket to self) | Development | 2024-07-19 | 02:00:00 | 00:17:20 | 2024-08-02 |  | COMPLETED | IN_TIME | 2024-08-02 16:20:16 | 2024-08-02 16:20:16
236 | TT21819 | Swapnil Ramdasi | - | - | - | Sprint - Go through document | Brainstorming | 2024-08-01 | 01:00:00 | 00:31:01 | 2024-08-01 |  | COMPLETED | IN_TIME | 2024-08-01 19:26:48 | 2024-08-01 19:26:48
237 | TT23294 | Swapnil Ramdasi | - | - | - | End to End testing for Time Regularization | E2E Testing. | 2024-09-09 | 04:00:00 | 03:58:31 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-10 04:53:21 | 2024-09-10 04:53:21
238 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | KT Session - QR Code Generation - HRMS | KT from BA | 2024-08-28 | 00:00:00 | 00:00:00 | 2024-08-28 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 19:36:13 | 2024-08-30 19:36:13
239 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA KPI - go through recording | Internal KT/cross KT | 2024-09-30 | 01:00:00 | 00:00:00 | 2024-09-30 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-04 20:49:11 | 2024-10-04 20:49:11
240 | TT24216 | Swapnil Ramdasi | Testing_Skill Upgrade_Oct24_Wk1 | 2024-09-30 | 2024-10-04 | My tickets - unpassed ticket tab, pass/unpass/reject process practice. | Explore the existing system | 2024-08-27 | 03:00:00 | 03:05:24 | 2024-08-29 |  | COMPLETED | IN_TIME | 2024-08-29 18:52:33 | 2024-08-29 18:52:33
241 | TT21819 | Swapnil Ramdasi | - | - | - | Nemgiri Go through document | KT Session | 2024-08-02 | 02:30:00 | 02:41:12 | 2024-08-06 |  | COMPLETED | DELAY | 2024-08-07 12:53:52 | 2024-08-07 12:53:52
242 | TT21914 | Swapnil Ramdasi | - | - | - | Task Scheduling for 9 to 13 Sept | Task Scheduling | 2024-09-06 | 00:30:00 | 00:14:11 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-10 04:53:43 | 2024-09-10 04:53:43
243 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling | Task Scheduling | 2024-09-06 | 00:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:26:17 | 2024-09-06 20:26:17
244 | TT21819 | Swapnil Ramdasi | - | - | - | Nemgiri go through recording - KT | KT Session | 2024-08-06 | 01:00:00 | 00:31:07 | 2024-08-06 |  | COMPLETED | IN_TIME | 2024-08-06 19:11:14 | 2024-08-06 19:11:14
245 | TT24437 | Swapnil Ramdasi | - | - | - | Regularization - Estimation | Estimate the requirement | 2024-09-03 | 00:00:00 | 00:00:00 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-06 17:27:39 | 2024-09-06 17:27:39
246 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Customer mapping - Add + edit + reflection on Grid | Test Script Preparation | 2024-09-10 | 00:00:00 | 00:00:00 | 2024-09-12 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-16 11:15:59 | 2024-09-16 11:15:59
247 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:12:47 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40
248 | TT21819 | Swapnil Ramdasi | - | - | - | Nemgiri KT | KT Session | 2024-08-02 | 01:00:00 | 00:50:00 | 2024-08-02 |  | COMPLETED | IN_TIME | 2024-08-02 21:36:57 | 2024-08-02 21:36:57
249 | TT23294 | Swapnil Ramdasi | - | - | - | Time regularization - Report preparation | Daily Summary report | 2024-08-26 | 00:15:00 | 00:36:14 | 2024-08-26 |  | COMPLETED | DELAY | 2024-08-27 04:48:46 | 2024-08-27 04:48:46
250 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Customer mapping test case writing | Test Case Writing | 2024-09-09 | 01:00:00 | 10:46:38 | 2024-09-09 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-10 10:53:46 | 2024-09-10 10:53:46
251 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25
252 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Doc Module Sync call | Daily Sync Call | 2024-10-01 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:26:18 | 2024-10-04 18:26:18
253 | TT24437 | Swapnil Ramdasi | - | - | - | Regularization CR KT - go through recording. | Explore the existing system. | 2024-08-27 | 00:30:00 | 01:07:52 | 2024-08-27 |  | COMPLETED | DELAY | 2024-08-28 20:13:21 | 2024-08-28 20:13:21
254 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Automation Script for reading Tool tip text | Test Script Preparation | 2024-09-06 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-12 15:42:11 | 2024-09-12 15:42:11
255 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02
256 | TT24452 | Swapnil Ramdasi | - | - | - | TR KT and Discussion: Show played and paused tasks of a user | KT Session | 2024-08-20 | 00:43:00 | 00:53:48 | 2024-08-20 |  | COMPLETED | IN_TIME | 2024-08-20 19:28:11 | 2024-08-20 19:28:11
257 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | test | Application Support | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-09-27 17:54:38 | 2024-09-27 17:54:38
258 | TT23294 | Swapnil Ramdasi | - | - | - | RAD Time regularization | RAD | 2024-08-26 | 04:00:00 | 03:13:23 | 2024-08-26 |  | COMPLETED | DELAY | 2024-08-27 04:48:56 | 2024-08-27 04:48:56
259 | TT23932 | Swapnil Ramdasi | Sprint 1 | 2024-07-30 | 2024-08-31 | Project work flow Activity | Exploration | 2024-08-27 | 01:00:00 | 01:00:00 | 2024-08-27 |  | COMPLETED | HIGHLY_DELAY | 2024-08-28 18:30:49 | 2024-08-28 11:15:28
260 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Customer Master Add Data preparation Add, Edit, View | Test case writing- | 2024-09-06 | 01:30:00 | 02:05:55 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:25:11 | 2024-09-06 20:25:11
261 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 2 Sept - 6 sept. | Task Scheduling | 2024-08-30 | 00:30:00 | 00:00:00 | 2024-08-30 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-31 00:07:26 | 2024-08-31 00:07:26
262 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 00:00:00 | 00:07:50 | 2024-09-16 |  | COMPLETED | IN_TIME | 2024-09-13 16:08:19 | 2024-09-13 16:08:19
263 | TT19295 | Swapnil Ramdasi | - | - | - | Sprint Testing | Functional Testing | 2024-08-13 | 02:00:00 | 02:39:45 | 2024-08-13 |  | COMPLETED | DELAY | 2024-08-15 19:34:36 | 2024-08-15 19:34:36
264 | TT24437 | Swapnil Ramdasi | - | - | - | Regularization CR KT | KT Session | 2024-08-21 | 01:08:00 | 00:33:10 | 2024-08-21 |  | COMPLETED | IN_TIME | 2024-08-21 19:14:34 | 2024-08-21 19:14:34
265 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | User Master Add edit negative Scripting | Test Script Preparation | 2024-09-02 | 06:00:00 | 03:42:45 | 2024-09-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-20 19:24:50 | 2024-09-20 19:24:50
266 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task type KT | KT Session | 2024-08-22 | 00:30:00 | 01:04:06 | 2024-08-22 |  | COMPLETED | IN_TIME | 2024-08-22 18:42:05 | 2024-08-22 18:42:05
267 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Country Master , State Master , City Master Add + Reflection on Grid | Test Script Preparation | 2024-09-19 | 07:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-24 16:22:16 | 2024-09-24 16:22:16
268 | TT23294 | Swapnil Ramdasi | - | - | - | TR Sync Call | Daily Sync Call | 2024-08-13 | 00:30:00 | 00:33:41 | 2024-08-14 |  | COMPLETED | DELAY | 2024-08-16 14:48:34 | 2024-08-16 14:48:34
269 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-09 16:55:48 | 2024-10-09 16:55:48
270 | TT23294 | Swapnil Ramdasi | - | - | - | Time Regularization New CR Testing | Functional Testing | 2024-08-21 | 05:00:00 | 05:45:40 | 2024-08-22 |  | COMPLETED | DELAY | 2024-08-23 12:52:42 | 2024-08-23 12:52:42
271 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Variance Report Jar Creation | Test Script Preparation | 2024-08-30 | 03:30:00 | 03:08:49 | 2024-08-30 |  | COMPLETED | IN_TIME | 2024-08-30 21:09:42 | 2024-08-30 21:09:42
272 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Preeti Maam | General meeting | 2024-08-12 | 00:18:00 | 00:40:22 | 2024-08-12 |  | COMPLETED | IN_TIME | 2024-08-12 19:42:54 | 2024-08-12 19:42:54
273 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Country Master , State Master , City Master test case Writing | Test Case Writing | 2024-09-12 | 01:30:00 | 00:00:00 | 2024-09-12 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-23 23:03:41 | 2024-09-23 23:03:41
274 | TT23294 | Swapnil Ramdasi | - | - | - | TR Sync Call | Daily Sync Call | 2024-08-12 | 00:51:00 | 00:00:00 | 2024-08-16 |  | COMPLETED | IN_TIME | 2024-08-13 12:18:05 | 2024-08-13 12:18:05
275 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Retesting Documentation Module | Bug Retesting | 2024-10-03 | 03:00:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY
276 | TT24452 | Swapnil Ramdasi | - | - | - | Time regularization history - estimation | Estimate calculation | 2024-08-20 | 00:30:00 | 00:20:19 | 2024-08-20 |  | COMPLETED | IN_TIME | 2024-08-20 20:54:30 | 2024-08-20 20:54:30
277 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | User Master Scenario writing for Add ,Edit and View | Data Preparation | 2024-08-26 | 02:00:00 | 03:36:10 | 2024-08-26 |  | COMPLETED | SLIGHTLY_DELAY | 2024-08-30 19:38:49 | 2024-08-27 16:35:46
278 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil(Reports- user task , variance, Resource planning) | Internal KT/cross KT | 2024-09-27 | 02:00:00 | 00:50:24 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-29 23:01:25 | 2024-09-29 23:01:25
279 | TT23674 | Swapnil Ramdasi | - | - | - | Nemgiri - Room registration & respective report testing | Testing | 2024-08-16 | 02:30:00 | 03:09:45 | 2024-08-16 |  | COMPLETED | IN_TIME | 2024-08-16 22:56:17 | 2024-08-16 22:56:17
280 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 12:00:00 | 05:45:26 | 2024-10-04 |  | IN_PROGRESS | DELAY | 2024-09-27 20:27:44
281 | TT24452 | Swapnil Ramdasi | - | - | - | Time Regularization New CR Testing | Functional Testing | 2024-08-20 | 00:00:00 | 00:00:00 | 2024-08-20 |  | COMPLETED | IN_TIME | 2024-08-20 18:52:11 | 2024-08-20 18:52:11
282 | TT15425 | Swapnil Ramdasi | Sprint 1 | 2023-08-30 | 2024-12-31 | Bill checking transaction - filter testing | Unit Testing | 2024-09-25 | 01:30:00 | 05:01:52 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:55:59 | 2024-09-25 22:55:59
283 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | User master script execution | Script Execution/ Modification | 2024-08-19 | 10:30:00 | 19:15:23 | 2024-08-28 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-16 15:25:34 | 2024-09-16 15:25:34
284 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore and Practice (My Ticket) | Explore the existing system. | 2024-09-26 | 04:00:00 | 04:53:32 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 23:22:18 | 2024-09-26 23:22:18
285 | TT23674 | Swapnil Ramdasi | - | - | - | Nemgiri test case writing | Test Case Writing | 2024-08-16 | 03:00:00 | 04:29:40 | 2024-08-16 |  | COMPLETED | IN_TIME | 2024-08-16 22:56:24 | 2024-08-16 22:56:24
286 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | RAD for Documentation Module | RAD Testing | 2024-09-16 | 03:00:00 | 04:14:42 | 2024-09-16 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-27 17:15:40 | 2024-09-27 17:15:40
287 | TT15425 | Swapnil Ramdasi | Sprint 1 | 2023-08-30 | 2024-12-31 | Vendor master, Approval setting page, Payment template master -Testing | Unit Testing | 2024-09-23 | 08:00:00 | 11:25:51 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 22:58:14 | 2024-09-24 22:58:14
288 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil(My Ticket) | Internal KT/cross KT | 2024-09-26 | 01:30:00 | 00:47:13 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 14:12:21 | 2024-09-26 14:12:21
289 | TT21819 | Swapnil Ramdasi | - | - | - | Customer master add- Scripting | Test Script Preparation | 2024-08-22 | 04:00:00 | 04:23:47 | 2024-08-29 |  | COMPLETED | IN_TIME | 2024-08-29 18:52:55 | 2024-08-29 18:52:55
290 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module Retesting | Retesting | 2024-09-10 | 02:30:00 | 03:28:18 | 2024-09-10 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-27 10:00:55 | 2024-09-13 07:41:09
291 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, page master, section type master, page section master, page content master, Setting master, - Test case writing | Test Case Writing | 2024-09-30 | 03:30:00 | 01:33:54 | 2024-09-30 |  | COMPLETED | DELAY | 2024-10-11 12:10:55 | 2024-10-11 12:10:55
292 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore & practice the connect us 2.0( Customer Mapping , Create Ticket) | Explore the existing system. | 2024-09-25 | 04:00:00 | 01:56:18 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:55:44 | 2024-09-25 22:55:44
293 | TT23294 | Swapnil Ramdasi | - | - | - | Test Case Writing for new CR in Time Regularization | Test Case Writing | 2024-08-12 | 01:00:00 | 01:49:08 | 2024-08-12 |  | COMPLETED | IN_TIME | 2024-08-12 19:42:34 | 2024-08-12 19:42:34
294 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:26:29 | 2024-09-06 18:26:29
295 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-08 15:07:54 | 2024-10-08 15:07:54
296 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil (Customer Mapping , Create Ticket) | Internal KT/cross KT | 2024-09-25 | 01:30:00 | 01:27:01 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:54:56 | 2024-09-25 22:54:56
297 | TT23294 | Swapnil Ramdasi | - | - | - | Time regularization | Functional Testing | 2024-08-13 | 04:00:00 | 02:22:36 | 2024-08-14 |  | COMPLETED | IN_TIME | 2024-08-14 23:19:09 | 2024-08-14 23:19:09
298 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Document module Test case modification | Test case updation\modification | 2024-09-03 | 02:00:00 | 02:39:17 | 2024-09-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-06 15:13:08 | 2024-09-06 15:13:08