## data
sr | ticket_id | task_owner | task_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Remark
12 | TT16817 | Amruta Kore | KT/Self Improvement | 2024-01-01 | 05:00 | 01:54:43 | 2024-01-05 |  | IN_PROGRESS | IN_PROGRESS |  |  | done for today
13 | TT16817 | Amruta Kore | General Discussion - Morning | 2024-01-01 | 01:15 | 00:40:35 | 2024-01-05 |  | IN_PROGRESS | IN_PROGRESS |  |  | done for today
14 | TT16817 | Amruta Kore | General Discussion - Evening | 2024-01-01 | 01:15 | 00:04:34 | 2024-01-05 |  | IN_PROGRESS | IN_PROGRESS |  |  | done for today
15 | TT16817 | Amruta Kore | Scheduling Fun Friday | 2024-01-05 | 01:30 | 00:00:00 | 2024-01-05 |  | TO_DO | TO_DO |  |  | In progress
16 | TT11135 | Amruta Kore | TT11135 -Test Execution | 2024-01-04 | 04:00 | 00:00:00 | 2024-01-04 |  | TO_DO | TO_DO |  |  | In progress
17 | TT11135 | Amruta Kore | TT11135 -Test Execution 5Jan | 2024-01-05 | 04:00 | 00:00:00 | 2024-01-05 |  | TO_DO | TO_DO
18 | TT11135 | Amruta Kore | Modify the testcase | 2024-01-01 | 01:30 | 01:42:53 | 2024-01-01 |  | COMPLETED | COMPLETED | 2024-01-01 18:05:25 | 2024-01-01 18:05:25 | Done
19 | TT16817 | Amruta Kore | API Testing | 2024-01-01 | 03:00 | 02:22:45 | 2024-01-01 |  | COMPLETED | COMPLETED | 2024-01-01 19:19:15 | 2024-01-01 19:19:15 | Done
20 | TT16817 | Amruta Kore | Material Issue Scripting | 2024-01-01 | 02:00 | 00:21:19 | 2024-01-01 |  | COMPLETED | COMPLETED | 2024-01-01 19:40:29 | 2024-01-01 19:40:29 | Done
21 | TT16817 | Amruta Kore | Material Issue Scripting | 2024-01-02 | 02:00 | 01:07:46 | 2024-01-02 |  | COMPLETED | COMPLETED | 2024-01-02 19:51:21 | 2024-01-02 19:51:21 | Done
22 | TT10647 | Amruta Kore | TT10647: Test Execution( Tenant master add/edit/view, Tenant employee(Admin)- user creation, Query type, role master, Dynamic form , Customer Mapping) | 2024-01-02 | 04:30 | 04:43:21 | 2024-01-02 |  | IN_PROGRESS | DELAYED |  |  | Done(Smoke testing done)