## data
sr | ticket_id | task_owner | task_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Remark
20 | TT16817 | Amruta Kore | KT/Self Improvement | 2024-01-01 | 05:00 | 02:18:43 | 2024-01-05 |  | IN_PROGRESS | IN_PROGRESS |  |  | Done
21 | TT16817 | Amruta Kore | General Discussion - Morning | 2024-01-01 | 01:15 | 00:40:40 | 2024-01-05 |  | IN_PROGRESS | IN_PROGRESS |  |  | Done
22 | TT16817 | Amruta Kore | General Discussion - Evening | 2024-01-01 | 01:15 | 00:56:17 | 2024-01-05 |  | IN_PROGRESS | IN_PROGRESS |  |  | Done
23 | TT16817 | Amruta Kore | Scheduling Fun Friday | 2024-01-05 | 01:30 | 00:00:00 | 2024-01-05 |  | TO_DO | TO_DO
24 | TT11135 | Amruta Kore | TT11135 -Test Execution | 2024-01-04 | 04:00 | 02:31:13 | 2024-01-04 |  | IN_PROGRESS | IN_PROGRESS |  |  | Done(4 major bugs found)
25 | TT11135 | Amruta Kore | TT11135 -Test Execution 5Jan | 2024-01-05 | 04:00 | 00:00:07 | 2024-01-05 |  | IN_PROGRESS | IN_PROGRESS
26 | TT11135 | Amruta Kore | Modify the testcase | 2024-01-01 | 01:30 | 01:42:53 | 2024-01-01 |  | COMPLETED | COMPLETED | 2024-01-01 18:05:25 | 2024-01-01 18:05:25
27 | TT16817 | Amruta Kore | API Testing | 2024-01-01 | 03:00 | 02:22:45 | 2024-01-01 |  | COMPLETED | COMPLETED | 2024-01-01 19:19:15 | 2024-01-01 19:19:15
28 | TT16817 | Amruta Kore | Material Issue Scripting | 2024-01-01 | 02:00 | 00:21:19 | 2024-01-01 |  | COMPLETED | COMPLETED | 2024-01-01 19:40:29 | 2024-01-01 19:40:29
29 | TT16817 | Amruta Kore | Material Issue Scripting | 2024-01-02 | 02:00 | 01:07:46 | 2024-01-02 |  | COMPLETED | COMPLETED | 2024-01-02 19:51:21 | 2024-01-02 19:51:21
30 | TT10647 | Amruta Kore | TT10647: Test Execution( Tenant master add/edit/view, Tenant employee(Admin)- user creation, Query type, role master, Dynamic form , Customer Mapping) | 2024-01-02 | 04:30 | 04:43:21 | 2024-01-02 |  | COMPLETED | DELAYED | 2024-01-03 16:42:31 | 2024-01-03 16:42:31
31 | TT11135 | Amruta Kore | Test Execution - 3 Jan | 2024-01-03 | 04:30 | 02:09:50 | 2024-01-03 |  | COMPLETED | COMPLETED | 2024-01-03 19:56:55 | 2024-01-03 19:56:55
32 | TT16817 | Amruta Kore | KT on report by Preeti Mam | 2024-01-03 | 00:30 | 00:54:57 | 2024-01-03 |  | COMPLETED | COMPLETED | 2024-01-03 17:14:39 | 2024-01-03 17:14:39
33 | TT16817 | Amruta Kore | meeting with Gourav Sir | 2024-01-03 | 01:07 | 10:11:53 | 2024-01-03 |  | COMPLETED | COMPLETED | 2024-01-03 19:41:26 | 2024-01-03 19:41:26
34 | TT10647 | Amruta Kore | Explore customer View | 2024-01-03 | 00:30 | 00:18:41 | 2024-01-03 |  | COMPLETED | COMPLETED | 2024-01-03 19:56:13 | 2024-01-03 19:56:13
35 | TT13906 | Amruta Kore | Test Execution -Upload document | 2024-01-04 | 02:30 | 00:31:48 | 2024-01-04 |  | IN_PROGRESS | IN_PROGRESS |  |  | Upload test case on ticketing system
36 | TT16807 | Amruta Kore | Meeting with Gaurav Sir | 2024-01-04 | 00:30 | 04:39:05 | 2024-01-04 |  | COMPLETED | COMPLETED | 2024-01-04 15:17:13 | 2024-01-04 15:17:13 | Done
37 | TT16817 | Amruta Kore | Function point KT by Preeti Mam | 2024-01-04 | 00:45 | 07:36:44 | 2024-01-04 |  | COMPLETED | COMPLETED | 2024-01-04 17:57:14 | 2024-01-04 17:57:14 | Done
38 | TT11135 | Amruta Kore | TT11135 - Negative test Execution 4 Jan | 2024-01-04 | 01:00 | 00:00:00 | 2024-01-04 |  | IN_PROGRESS | IN_PROGRESS |  |  | This task is created to execute test case on ticketing