## Sheet2
sr | ticket_id | task_owner | sprint_name | sprint_start_date | sprint_end_date | task_name | type_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Scheduled hrs | Actual hrs
14 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website - Estimation | Estimate the requirement | 2024-10-09 | 02:00:00 | 00:00:00 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-08 15:14:56 |  | 2 | 0
87 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Bill checking test on Live server | E2E Testing. | 2024-09-29 | 02:30:00 | 02:36:52 | 2024-09-29 |  | IN_PROGRESS | DELAY |  |  | 2.5 | 2.61
306 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Parallel run process Exporation | Explore New things\other | 2024-10-09 | 02:00:00 | 01:14:36 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-09 12:04:44 |  | 2 | 1.24
477 | TT25148 | Maruti Hakke | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Estimate the requirement -Sales Return | Estimate the requirement | 2024-10-09 | 00:30:00 | 00:09:51 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-09 12:20:58 |  | 0.5 | 0.16
604 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance support to prathamesh | Query clarification | 2024-10-07 | 03:00:00 | 02:58:23 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-08 17:45:24 |  | 3 | 2.97
610 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance scripting | Test Script Preparation | 2024-09-30 | 19:00:00 | 11:28:36 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-09 18:44:14 |  | 19 | 11.48
655 | TT21914 | Preeti Bokade | - | - | - | Prepare the Function point on Ticketing system ( Reusable purpose) | Estimate the requirement | 2024-09-26 | 04:00:00 | 00:14:17 | 2024-09-30 |  | IN_PROGRESS | DELAY |  |  | 4 | 0.24
896 | TT24670 | Sayali Vyawahare | - | - | - | customer advance support to prathamesh | Query clarification | 2024-10-07 | 03:00:00 | 02:58:17 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-08 17:45:24 |  | 3 | 2.97
913 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 12:00:00 | 05:45:26 | 2024-10-04 |  | IN_PROGRESS | DELAY | 2024-09-27 20:27:44 |  | 12 | 5.76
944 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, page master, section type master, page section master, page content master, Setting master, - Test case writing | Test Case Writing | 2024-09-30 | 03:30:00 | 01:33:54 | 2024-09-30 |  | IN_PROGRESS | DELAY | 2024-09-27 20:33:10 |  | 3.5 | 1.57

## Sheet3
sr | ticket_id | task_owner | sprint_name | sprint_start_date | sprint_end_date | task_name | type_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Scheduled hrs | Actual hrs
256 | TT26038 | Gokul Bhoi | - | - | - | TT26038-P2P process bugsheet review(Platinum, DJ, Silver) | Reporting Review | 2024-10-09 | 01:00:00 | 00:00:00 | 2024-10-09 |  | TO_DO | DELAY | 2024-10-09 15:50:54 |  | 1 | 0
474 | TT25148 | Maruti Hakke | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Sales return Estimation Review | Estimation Review | 2024-10-09 | 00:15:00 | 00:00:00 | 2024-10-09 |  | TO_DO | DELAY |  |  | 0.25 | 0
911 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Retesting Documentation Module | Bug Retesting | 2024-10-03 | 03:00:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY |  |  | 3 | 0

## Sheet1
task_delivery_scheduled | (Multiple Items) |  |  |  | task_delivery_scheduled | (Multiple Items)
Count of task_name | task_status |  |  |  | Count of task_name | task_actual_status
task_owner | COMPLETED | IN_PROGRESS | TO_DO | Grand Total | task_owner | TO_DO | IN_TIME | IN_PROGRESS | DELAY | SLIGHTLY_DELAY | Grand Total
Amreen Shaikh | 99 | 2 |  | 101 | Amreen Shaikh | 3.571% | 42.86% | 14.29% | 35.71% | 3.571% | 100%
Amruta Kore | 101 |  |  | 101 | Amruta Kore | 0% | 64.29% | 28.57% | 3.571% | 3.571% | 100%
Digvijay Tulse | 1 |  |  | 1 | Digvijay Tulse | 0% | 100% | 0% | 0% | 0% | 100%
Gokul Bhoi | 154 | 1 | 1 | 156 | Gokul Bhoi | 0% | 77.78% | 15.56% | 4.444% | 2.222% | 100%
Kiran Dhanepkar | 70 |  |  | 70 | Kiran Dhanepkar | 0% | 76.19% | 19.05% | 4.762% | 0% | 100%
Maruti Hakke | 78 | 1 | 1 | 80 | Maruti Hakke | 3.846% | 65.38% | 15.38% | 11.54% | 3.846% | 100%
Prathamesh Kulkarni | 65 | 2 |  | 67 | Prathamesh Kulkarni | 0% | 71.43% | 19.05% | 9.524% | 0% | 100%
Preeti Bokade | 74 | 1 |  | 75 | Preeti Bokade | 9.677% | 64.52% | 19.35% | 6.452% | 0% | 100%
Saurabh Shelke | 75 |  |  | 75 | Saurabh Shelke | 0% | 74.07% | 25.93% | 0% | 0% | 100%
Sayali Vyawahare | 105 | 1 |  | 106 | Sayali Vyawahare | 2.703% | 70.27% | 18.92% | 8.108% | 0% | 100%
Swapnil Ramdasi | 50 | 2 | 1 | 53 | Swapnil Ramdasi | 0% | 40% | 0% | 50% | 10% | 100%
Vaishnavi Khandwe | 64 |  |  | 64 | Vaishnavi Khandwe | 0% | 73.91% | 17.39% | 4.348% | 4.348% | 100%
Grand Total | 936 | 10 | 3 | 949 | Grand Total | 2.013% | 67.45% | 18.46% | 10.07% | 2.013% | 100%
task_delivery_scheduled | (Multiple Items)
sprint_name | -
task_owner | ticket_id | Distinct Count of ticket_id
Amreen Shaikh |  | 1
| TT26067 | 1
Amruta Kore |  | 9
| TT21945 | 1
| TT22163 | 1
| TT22785 | 1
| TT22830 | 1
| TT24674 | 1
| TT24774 | 1
| TT26038 | 1
| TT21899 | 1
| TT23053 | 1
Gokul Bhoi |  | 10
| TT21945 | 1
| TT22163 | 1
| TT22830 | 1
| TT24674 | 1
| TT26038 | 1
| TT23053 | 1
| TT23985 | 1
| TT17156 | 1
| TT18255 | 1
| TT22810 | 1
Kiran Dhanepkar |  | 3
| TT22830 | 1
| TT17156 | 1
| TT22810 | 1
Maruti Hakke |  | 1
| TT24598 | 1
Prathamesh Kulkarni |  | 1
| TT24670 | 1
Preeti Bokade |  | 1
| TT23155 | 1
Saurabh Shelke |  | 7
| TT21945 | 1
| TT22785 | 1
| TT22830 | 1
| TT26038 | 1
| TT21899 | 1
| TT23053 | 1
| TT23985 | 1
Sayali Vyawahare |  | 3
| TT24670 | 1
| TT22442 | 1
| TT24598 | 1
Vaishnavi Khandwe |  | 4
| TT21945 | 1
| TT22830 | 1
| TT26038 | 1
| TT18255 | 1
Grand Total |  | 18

## data
sr | ticket_id | task_owner | sprint_name | sprint_start_date | sprint_end_date | task_name | type_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Scheduled hrs | Actual hrs
1 | TT21405 | Amreen Shaikh | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | KT for item Counter mapping Bulk upload at 3.30pm | KT Session | 2024-10-10 | 01:00:00 | 00:00:00 | 2024-10-10 |  | TO_DO | TO_DO | 2024-10-09 18:41:52 |  | 1 | 0
2 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website - Document reading | Document Reading | 2024-09-26 | 01:00:00 | 02:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 13:41:43 | 2024-09-26 13:41:43 | 1 | 2
3 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
4 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Query clarification | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-09 18:59:53 | 2024-09-09 18:59:53 | 0 | 0
5 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT - Customer view | Internal KT/cross KT | 2024-09-02 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-08-30 20:15:30 | 2024-08-30 20:15:30 | 0 | 0
6 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Mentoring | 2024-09-03 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:37:15 | 2024-09-06 16:37:15 | 1 | 0
7 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CSM + Website Validation updation | Validation updation | 2024-10-10 | 01:30:00 | 00:26:33 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-09 19:09:41 |  | 1.5 | 0.44
8 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Testing team sync call | Testing Team Meeting | 2024-10-08 | 01:30:00 | 02:10:51 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 17:07:38 |  | 1.5 | 2.18
9 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-09 16:55:48 | 2024-10-09 16:55:48 | 0 | 0
10 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | DSC - CMS | Daily Sync Call | 2024-09-02 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:16:17 | 2024-09-06 17:16:17 | 2 | 0
11 | TT26067 | Amreen Shaikh | - | - | - | Kindly test the MY CS Application on IOS Application for Salary Slip Generation & Download | E2E Testing | 2024-10-10 | 01:30:00 | 00:11:23 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-10 15:51:20 |  | 1.5 | 0.19
12 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA-KPI : Self improvement meeting | Query clarification | 2024-10-08 | 00:15:00 | 00:21:34 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:21:33 | 2024-10-08 16:21:33 | 0.25 | 0.36
13 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil - report preparation | Daily Summary report | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-09 16:57:49 | 2024-10-09 16:57:49 | 0 | 0
14 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website - Estimation | Estimate the requirement | 2024-10-09 | 02:00:00 | 00:00:00 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-08 15:14:56 |  | 2 | 0
15 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am | Query clarification | 2024-09-23 | 02:30:00 | 03:48:53 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:51:17 | 2024-09-27 20:51:17 | 2.5 | 3.81
16 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Amreen | Query clarification | 2024-10-08 | 00:45:00 | 03:06:12 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.75 | 3.1
17 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for automation multiple line | Query clarification | 2024-10-08 | 02:00:00 | 00:59:08 | 2024-10-09 |  | COMPLETED | DELAY | 2024-10-10 00:11:30 | 2024-10-10 00:11:30 | 2 | 0.99
18 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for automation | Query clarification | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-09 16:55:03 | 2024-10-09 16:55:03 | 0 | 0
19 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, Default setting page & tenant master page - Testing | Unit Testing | 2024-10-02 | 00:00:00 | 00:00:00 | 2024-10-02 |  | COMPLETED | IN_TIME | 2024-09-27 19:26:44 | 2024-09-27 19:26:44 | 0 | 0
20 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-18 | 01:30:00 | 01:18:49 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:59:00 | 2024-09-20 20:59:00 | 1.5 | 1.31
21 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Tester interview | Interview | 2024-09-30 | 12:00:00 | 13:07:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:20 | 2024-10-01 19:34:20 | 12 | 13.13
22 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-19 | 01:00:00 | 00:53:41 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 21:52:24 | 2024-09-20 21:52:24 | 1 | 0.89
23 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Branch visit meeting with HR | HR meeting | 2024-10-10 | 01:00:00 | 00:54:45 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 15:36:25 | 2024-10-10 15:36:25 | 1 | 0.91
24 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, Default setting page & tenant master page - Test case writing | Test case writing- | 2024-08-27 | 00:00:00 | 00:12:32 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-01 15:05:57 | 2024-09-27 19:06:50 | 0 | 0.21
25 | TT19645 | Amreen Shaikh | - | - | - | AS BC retesting. | Bug Retesting | 2024-09-18 | 03:30:00 | 04:34:29 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-23 16:39:51 | 2024-09-23 16:39:51 | 3.5 | 4.57
26 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0
27 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Script review | 2024-09-18 | 02:00:00 | 00:48:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:00 | 2024-09-20 20:38:00 | 2 | 0.8
28 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Report preparation. | Daily Summary report | 2024-09-13 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:00 | 2024-09-13 20:11:00 | 0 | 0
29 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-09 | 02:30:00 | 00:29:56 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:19 | 2024-09-13 20:11:19 | 2.5 | 0.5
30 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Amreen - Support from Preeti Ma'am. | Query clarification | 2024-09-30 | 02:00:00 | 00:40:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:56 | 2024-10-04 20:47:56 | 2 | 0.68
31 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Logic building guidence | Technical guidance/Process Input | 2024-09-18 | 02:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:05 | 2024-09-20 20:38:05 | 2 | 0
32 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Report preparation | Daily Summary report | 2024-09-12 | 00:15:00 | 00:17:26 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 19:37:16 | 2024-09-12 19:37:16 | 0.25 | 0.29
33 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Bill checking - KT plan of action | Planning | 2024-10-09 | 01:00:00 | 00:13:07 | 2024-10-09 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-10 00:12:02 | 2024-10-10 00:12:02 | 1 | 0.22
34 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website document reading | Documentation Reading | 2024-08-21 | 00:00:00 | 00:00:00 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 16:57:18 | 2024-09-06 16:57:18 | 0 | 0
35 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Script review | 2024-09-02 | 02:15:00 | 02:46:39 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:18:42 | 2024-09-06 20:18:42 | 2.25 | 2.78
36 | TT23294 | Amreen Shaikh | - | - | - | Regularization - Report Preparation | Daily Summary report | 2024-09-09 | 00:15:00 | 00:00:00 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 21:42:56 | 2024-09-09 21:42:56 | 0.25 | 0
37 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0
38 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review and provide remark/suggestion on Swapnils automation code | Query clarification | 2024-09-09 | 03:45:00 | 02:53:19 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:22 | 2024-09-13 20:10:22 | 3.75 | 2.89
39 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Support to Swapnil | Query clarification | 2024-09-10 | 01:00:00 | 01:09:55 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:38 | 2024-09-13 20:10:38 | 1 | 1.17
40 | TT24216 | Amreen Shaikh | Testing_Skill Upgrade_Oct24_Wk1 | 2024-09-30 | 2024-10-04 | Automation Planning - support to Swapnil | Planning | 2024-09-13 | 00:30:00 | 00:23:28 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:17:42 | 2024-09-13 20:17:42 | 0.5 | 0.39
41 | TT23294 | Amreen Shaikh | - | - | - | Support for Regularization | Query clarification | 2024-09-09 | 00:30:00 | 00:47:01 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 17:55:43 | 2024-09-09 17:55:43 | 0.5 | 0.78
42 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:54:27 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 2.91
43 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Logic building guidence | Technical guidance/Process Input | 2024-09-09 | 03:45:00 | 02:42:35 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:15 | 2024-09-13 20:10:15 | 3.75 | 2.71
44 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:26:29 | 2024-09-06 18:26:29 | 0.75 | 0
45 | TT24216 | Amreen Shaikh | Testing_Skill Upgrade_Oct24_Wk1 | 2024-09-30 | 2024-10-04 | Automation Planning - support to Swapnil | Planning | 2024-09-06 | 00:30:00 | 00:27:35 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:39:52 | 2024-09-06 20:39:52 | 0.5 | 0.46
46 | TT21914 | Amreen Shaikh | - | - | - | Automation code test round - nirgun | Interview | 2024-09-06 | 01:30:00 | 01:22:16 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:09:40 | 2024-09-06 19:09:40 | 1.5 | 1.37
47 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:44:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.74
48 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-09 | 05:00:00 | 03:54:18 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:03 | 2024-09-13 20:10:03 | 5 | 3.91
49 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - Review and update test cases on TS | Test Case Review | 2024-09-03 | 00:45:00 | 01:00:54 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-04 20:09:41 | 2024-09-04 20:09:41 | 0.75 | 1.02
50 | TT20736 | Amreen Shaikh | - | - | - | Issue explanation to dev | Requirement gathering | 2024-09-03 | 00:30:00 | 00:34:21 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 17:09:31 | 2024-09-03 17:09:31 | 0.5 | 0.57
51 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 30 Sept - 4 oct | Task Scheduling | 2024-09-27 | 00:30:00 | 01:45:14 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:50:31 | 2024-09-27 20:50:31 | 0.5 | 1.75
52 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-04 | 03:00:00 | 02:58:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:20:39 | 2024-09-06 18:20:39 | 3 | 2.98
53 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-02 | 00:44:00 | 00:34:46 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-03 19:29:26 | 2024-09-03 19:29:26 | 0.73 | 0.58
54 | TT19645 | Amreen Shaikh | - | - | - | AS report preparation | Daily Summary report | 2024-09-02 | 00:15:00 | 00:00:05 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:03:01 | 2024-09-06 19:03:01 | 0.25 | 0
55 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 01:12:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 1.2
56 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to D team for Automation | Technical guidance/Process Input | 2024-09-03 | 01:00:00 | 00:48:00 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-06 17:35:09 | 2024-09-03 22:03:33 | 1 | 0.8
57 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - report review | Reporting Review | 2024-09-02 | 00:15:00 | 00:53:10 | 2024-09-02 |  | COMPLETED | DELAY | 2024-09-03 20:42:38 | 2024-09-03 20:42:38 | 0.25 | 0.89
58 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 23 Sept - 27 sept | Task Scheduling | 2024-09-20 | 00:30:00 | 00:44:13 | 2024-09-20 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-23 16:42:05 | 2024-09-23 16:42:05 | 0.5 | 0.74
59 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Logic building guidence | Technical guidance/Process Input | 2024-09-02 | 02:15:00 | 02:28:04 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:18:48 | 2024-09-06 20:18:48 | 2.25 | 2.47
60 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Document module - report preparation | Daily Summary report | 2024-09-04 | 00:20:00 | 00:24:54 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 17:07:04 | 2024-09-06 17:07:04 | 0.33 | 0.42
61 | TT24437 | Amreen Shaikh | - | - | - | Regularization - validation review | Review. | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:26 | 2024-09-06 17:23:26 | 0 | 0
62 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:15:00 | 00:40:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1.25 | 0.67
63 | TT24427 | Amreen Shaikh | E2E Testing | 2024-09-30 | 2024-10-12 | Support to Swapnil for Consolidated report | Query clarification | 2024-09-02 | 01:30:00 | 01:59:48 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:31 | 2024-09-06 17:05:31 | 1.5 | 2
64 | TT24437 | Amreen Shaikh | - | - | - | Support to swapnil - regularization | Query clarification | 2024-09-06 | 00:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:40 | 2024-09-06 17:23:40 | 0.5 | 0
65 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 16 Sept - 20 sept | Task Scheduling | 2024-09-13 | 00:30:00 | 00:25:49 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:32 | 2024-09-13 20:08:32 | 0.5 | 0.43
66 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | My CS APP Daily Sync call 23-27 | Daily Sync Call | 2024-09-23 | 00:50:00 | 00:18:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:07:41 | 2024-09-27 17:07:41 | 0.83 | 0.31
67 | TT24437 | Amreen Shaikh | - | - | - | Regularization - validation writing | Validation writing | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:51 | 2024-09-06 17:23:51 | 0 | 0
68 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:14:50 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40 | 0.17 | 0.25
69 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Validation updation | Validation updation | 2024-09-09 | 00:20:00 | 00:20:10 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:03:18 | 2024-09-09 19:03:18 | 0.33 | 0.34
70 | TT19645 | Amreen Shaikh | - | - | - | As BC Retesting | Testing. | 2024-09-02 | 04:00:00 | 02:10:25 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:09:15 | 2024-09-06 19:09:15 | 4 | 2.17
71 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Test case modification | Test case updation\modification | 2024-09-13 | 01:00:00 | 02:02:29 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-20 19:54:36 | 2024-09-20 19:54:36 | 1 | 2.04
72 | TT21914 | Amreen Shaikh | - | - | - | Support from Preeti Ma'am. | Query clarification | 2024-09-02 | 02:30:00 | 03:43:21 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-08 23:15:06 | 2024-09-06 19:27:58 | 2.5 | 3.72
73 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
74 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Testcase writing | Test case writing- | 2024-09-09 | 03:30:00 | 02:33:13 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-13 16:29:19 | 2024-09-13 16:29:19 | 3.5 | 2.55
75 | TT19645 | Amreen Shaikh | - | - | - | AS Bill Checking RAD | RAD Testing | 2024-08-28 | 04:00:00 | 00:00:00 | 2024-09-02 |  | COMPLETED | DELAY | 2024-09-23 16:42:43 | 2024-09-23 16:42:43 | 4 | 0
76 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
77 | TT23932 | Amreen Shaikh | Sprint 1 | 2024-07-30 | 2024-08-31 | AS BC DIS GS PS | General meeting | 2024-09-12 | 00:30:00 | 00:27:33 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 19:58:04 | 2024-09-12 19:58:04 | 0.5 | 0.46
78 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Scheme - Daily sync call | Sync call with BA | 2024-09-09 | 00:50:00 | 17:19:08 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:15:56 | 2024-09-13 19:15:56 | 0.83 | 17.32
79 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Automation Scheduling - support to Swapnil | Support. | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:12:44 | 2024-09-06 20:12:44 | 0 | 0
80 | TT23932 | Amreen Shaikh | Sprint 1 | 2024-07-30 | 2024-08-31 | AS BC Discussions | General meeting | 2024-09-06 | 00:30:00 | 00:29:19 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 14:16:41 | 2024-09-06 14:16:41 | 0.5 | 0.49
81 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Testing - Report preparation | Daily Summary report | 2024-10-08 | 00:00:00 | 00:00:00 | 2024-10-08 |  | COMPLETED | DELAY | 2024-10-09 15:25:35 | 2024-10-09 15:25:35 | 0 | 0
82 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 04:02:53 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 4.05
83 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | MyCS Scheme Testing | Testing. | 2024-09-25 | 02:00:00 | 02:36:34 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 15:24:16 | 2024-10-09 15:24:16 | 2 | 2.61
84 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling 9 Sept - 13 sept | Task Scheduling | 2024-09-06 | 00:30:00 | 00:29:14 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:12:26 | 2024-09-06 20:12:26 | 0.5 | 0.49
85 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Validation writing | Validation writing | 2024-09-05 | 00:30:00 | 00:42:50 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 20:14:18 | 2024-09-05 20:14:18 | 0.5 | 0.71
86 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Scheme Enrollment - Daily sync call | Daily Sync Call | 2024-09-06 | 01:15:00 | 00:41:15 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-06 19:34:56 | 2024-09-06 19:34:56 | 1.25 | 0.69
87 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Bill checking test on Live server | E2E Testing. | 2024-09-29 | 02:30:00 | 02:36:52 | 2024-09-29 |  | IN_PROGRESS | DELAY |  |  | 2.5 | 2.61
88 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Sprint plaaning | Task Scheduling | 2024-10-09 | 01:15:00 | 01:19:06 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 16:38:35 | 2024-10-09 16:38:35 | 1.25 | 1.32
89 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | New scheme Enrollment Brain storming | Brainstorming | 2024-09-05 | 00:30:00 | 00:50:05 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 17:48:00 | 2024-09-05 17:48:00 | 0.5 | 0.83
90 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01 | 0 | 0
91 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Support to swapnil | Query clarification | 2024-09-23 | 02:30:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-08 17:58:26 | 2024-10-08 17:58:26 | 2.5 | 0
92 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website test case review | Review Test cases | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-09 19:12:18 | 2024-10-09 19:12:18 | 0 | 0
93 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Prepare estimation | Estimate the requirement | 2024-09-05 | 00:30:00 | 00:45:14 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 20:14:24 | 2024-09-05 20:14:24 | 0.5 | 0.75
94 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | Document reading | Document Reading | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-08 17:57:30 | 2024-10-08 17:57:30 | 0 | 0
95 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Issue explanation to developer | Brainstorming with DEV Team \BA | 2024-09-26 | 00:30:00 | 01:26:40 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 19:48:57 | 2024-09-26 19:48:57 | 0.5 | 1.44
96 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Scheduling for upcoming week | Task Scheduling | 2024-10-08 | 00:30:00 | 00:53:43 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 19:59:16 | 2024-10-08 19:59:16 | 0.5 | 0.9
97 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Go through the recording | Explore the existing system. | 2024-09-04 | 00:40:00 | 00:50:25 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:47 | 2024-09-04 19:41:47 | 0.67 | 0.84
98 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | E2E retesting - Bill transaction | E2E Testing. | 2024-09-26 | 12:00:00 | 11:39:15 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-08 17:12:40 | 2024-10-08 17:12:40 | 12 | 11.65
99 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS Website - Validation review | Test Case Review | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-09 19:10:56 | 2024-10-09 19:10:56 | 0 | 0
100 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Go through the document | Document Reading | 2024-09-04 | 00:40:00 | 00:45:42 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:52 | 2024-09-04 19:41:52 | 0.67 | 0.76
101 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | E2E testing - Bill transaction | E2E Testing. | 2024-09-23 | 18:00:00 | 16:11:19 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 11:35:41 | 2024-09-26 11:35:41 | 18 | 16.19
102 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-08 15:07:54 | 2024-10-08 15:07:54 | 0 | 0
103 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | E2E testing - Bill transaction - add, edit, view, grid view, approval & rejection cycle. + Payment details page. | E2E Testing. | 2024-09-21 | 00:00:00 | 00:00:00 | 2024-09-21 |  | COMPLETED | DELAY | 2024-09-25 13:57:11 | 2024-09-25 13:57:11 | 0 | 0
104 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS KT Session | KT Session | 2024-09-26 | 01:30:00 | 01:29:36 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:12:46 | 2024-09-27 15:12:46 | 1.5 | 1.49
105 | TT15425 | Amreen Shaikh | Sprint 1 | 2023-08-30 | 2024-12-31 | Issue explaination | Requirement gathering | 2024-09-02 | 00:30:00 | 00:33:52 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 15:25:44 | 2024-09-02 15:25:44 | 0.5 | 0.56
106 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS - KT Session | KT Session | 2024-09-26 | 01:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:16 | 2024-09-20 20:38:16 | 1 | 0
107 | TT21405 | Amreen Shaikh | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | Document reading | Document Reading | 2024-10-10 | 01:00:00 | 01:05:09 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 15:00:45 | 2024-10-10 15:00:45 | 1 | 1.09
108 | TT23495 | Amreen Shaikh | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Query clarification | 2024-09-18 | 01:30:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:04:45 | 2024-09-20 22:04:45 | 1.5 | 0
109 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 01:30:00 | 01:27:19 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 1.5 | 1.46
110 | TT21945 | Amruta Kore | - | - | - | Platinum P2P process testing | E2E Testing | 2024-10-09 | 00:00:00 | 00:00:00 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-07 17:03:10 | 2024-10-07 17:03:10 | 0 | 0
111 | TT24772 | Amruta Kore | - | - | - | Designer Master Testcase writing | Test case writing- | 2024-09-11 | 01:00:00 | 01:28:33 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 13:15:51 | 2024-09-11 13:15:51 | 1 | 1.48
112 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:37 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
113 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | Task scheduling 19 to 20 Sept | Task Scheduling | 2024-09-19 | 01:00:00 | 01:19:22 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:57:59 | 2024-09-20 23:57:59 | 1 | 1.32
114 | TT21945 | Amruta Kore | - | - | - | Sterling Silver - P2P process testing | E2E Testing | 2024-10-04 | 03:00:00 | 04:04:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:24:34 | 2024-10-04 23:24:34 | 3 | 4.07
115 | TT23423 | Amruta Kore | - | - | - | SSRS report Estimation - 5 reports | Estimate calculation | 2024-09-10 | 01:15:00 | 00:25:54 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 22:50:01 | 2024-09-10 22:50:01 | 1.25 | 0.43
116 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Branch visit meeting with HR | HR meeting | 2024-10-10 | 01:00:00 | 01:19:25 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 15:36:25 | 2024-10-10 15:36:25 | 1 | 1.32
117 | TT22163 | Amruta Kore | - | - | - | offline tagging Estimation merge with gr wt adjustment | Estimate calculation | 2024-09-10 | 00:15:00 | 00:40:24 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 22:49:32 | 2024-09-10 22:49:32 | 0.25 | 0.67
118 | TT22455 | Amruta Kore | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Support from Gokul - For Gift Voucher Script | Technical guidance/Process Input | 2024-09-11 | 01:30:00 | 00:50:43 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 21:22:32 | 2024-09-13 21:22:32 | 1.5 | 0.85
119 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 01:00:00 | 00:21:43 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 19:18:04 |  | 1 | 0.36
120 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:39:51 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.66
121 | TT21945 | Amruta Kore | - | - | - | Silver - P2P process testing | E2E Testing | 2024-10-03 | 03:00:00 | 05:39:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 23:20:25 | 2024-10-03 23:20:25 | 3 | 5.67
122 | TT22823 | Amruta Kore | - | - | - | Karagir Nave jama new CR estimation | Estimate calculation | 2024-09-09 | 00:30:00 | 00:38:08 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 12:46:20 | 2024-09-09 12:46:20 | 0.5 | 0.64
123 | TT22455 | Amruta Kore | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Gift Voucher Automation script for 10 Testcase | Automate test script | 2024-09-11 | 12:00:00 | 12:58:42 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 00:04:32 | 2024-09-21 00:04:32 | 12 | 12.98
124 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
125 | TT21945 | Amruta Kore | - | - | - | Gold - P2P process Testing | E2E Testing | 2024-10-10 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-07 17:02:30 | 2024-10-07 17:02:30 | 0 | 0
126 | TT14931 | Amruta Kore | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:21 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
127 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:37:10 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.62
128 | TT22785 | Amruta Kore | - | - | - | Lot Tag BrainStroming - | Brainstorming - Internal ( Within Team member) | 2024-09-27 | 00:30:00 | 00:54:12 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:45:04 | 2024-09-27 19:45:04 | 0.5 | 0.9
129 | TT22830 | Amruta Kore | - | - | - | Kariger requirement discussion | Requirement gathering | 2024-09-04 | 02:00:00 | 01:54:04 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 18:00:50 | 2024-09-04 18:00:50 | 2 | 1.9
130 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:44:19 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.74
131 | TT24683 | Amruta Kore | - | - | - | Pcs adjustment in offline tagging - document reading | Document Reading | 2024-09-26 | 00:45:00 | 00:34:13 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 20:25:59 | 2024-09-26 20:25:59 | 0.75 | 0.57
132 | TT24678 | Amruta Kore | - | - | - | Testcase writing - Making charges Master | Test case writing- | 2024-09-05 | 01:30:00 | 01:32:45 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 18:51:12 | 2024-09-09 18:51:12 | 1.5 | 1.55
133 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 02:04:01 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 2.07
134 | TT24680 | Amruta Kore | - | - | - | Support from gokul for Subsmith master script | Technical guidance/Process Input | 2024-09-30 | 00:30:00 | 00:20:55 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:17:23 | 2024-09-30 19:17:23 | 0.5 | 0.35
135 | TT24772 | Amruta Kore | - | - | - | Estimation of Designer master | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:07:44 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 11:04:55 | 2024-09-04 11:04:55 | 0.25 | 0.13
136 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:49 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 0.28
137 | TT24680 | Amruta Kore | - | - | - | Sub smith master - Automation script(Positive Flow) | Automate test script | 2024-09-30 | 01:30:00 | 04:26:20 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:41:12 | 2024-09-30 19:41:12 | 1.5 | 4.44
138 | TT24647 | Amruta Kore | - | - | - | BDD estimation | Estimate the requirement | 2024-09-04 | 00:30:00 | 00:37:55 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 21:55:59 | 2024-09-04 21:55:59 | 0.5 | 0.63
139 | TT24769 | Amruta Kore | - | - | - | Wastage code master - Estimation | Estimate the requirement | 2024-09-05 | 00:15:00 | 00:23:10 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 11:20:29 | 2024-09-05 11:20:29 | 0.25 | 0.39
140 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:54:15 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.9
141 | TT24674 | Amruta Kore | - | - | - | Support from gokul | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 00:29:21 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:59:58 | 2024-09-27 16:59:58 | 0.5 | 0.49
142 | TT24647 | Amruta Kore | - | - | - | BDD Cross KT | KT Session | 2024-09-03 | 00:45:00 | 00:33:21 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:40 | 2024-09-03 22:23:40 | 0.75 | 0.56
143 | TT24770 | Amruta Kore | - | - | - | Sub category Master - Estimation | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:10:31 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 11:42:53 | 2024-09-04 11:42:53 | 0.25 | 0.18
144 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:30:54 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.52
145 | TT24674 | Amruta Kore | - | - | - | Weight range master scripting | Automate test script | 2024-09-26 | 03:00:00 | 02:36:37 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 23:56:55 | 2024-09-27 23:56:55 | 3 | 2.61
146 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 6 Sept | Technical guidance/Process Input | 2024-09-06 | 00:30:00 | 00:46:52 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:17 | 2024-09-06 20:14:17 | 0.5 | 0.78
147 | TT24778 | Amruta Kore | - | - | - | Item Type Master Estimation - | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:14:12 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 12:07:54 | 2024-09-04 12:07:54 | 0.25 | 0.24
148 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
149 | TT22785 | Amruta Kore | - | - | - | Lot tag testcase writing | Test case writing- | 2024-09-27 | 02:00:00 | 01:22:11 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 23:04:00 | 2024-09-30 23:04:00 | 2 | 1.37
150 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 5 Sept | Technical guidance/Process Input | 2024-09-05 | 00:30:00 | 00:10:34 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 22:54:47 | 2024-09-05 22:54:47 | 0.5 | 0.18
151 | TT24776 | Amruta Kore | - | - | - | Agent Master - Estimation | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:10:37 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 12:18:47 | 2024-09-04 12:18:47 | 0.25 | 0.18
152 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
153 | TT24683 | Amruta Kore | - | - | - | Pcs adjustment in offline tagging - Testcase writing | Test case writing- | 2024-09-26 | 02:00:00 | 01:47:54 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:54:29 | 2024-09-27 23:54:29 | 2 | 1.8
154 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 4 Sept | Technical guidance/Process Input | 2024-09-04 | 00:30:00 | 00:16:25 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 21:42:25 | 2024-09-04 21:42:25 | 0.5 | 0.27
155 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 01:26:08 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 1.44
156 | TT24683 | Amruta Kore | - | - | - | PCS adjustment in offline tagging - Brainstroming | Brainstorming - Internal ( Within Team member) | 2024-09-26 | 00:30:00 | 00:20:36 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:51:21 | 2024-09-27 16:51:21 | 0.5 | 0.34
157 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 3 Sept | Technical guidance/Process Input | 2024-09-03 | 00:30:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:09 | 2024-09-03 22:23:09 | 0.5 | 0.43
158 | TT24672 | Amruta Kore | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | Configuration Master Testing | E2E Testing | 2024-09-30 | 01:00:00 | 01:04:49 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 12:28:28 | 2024-09-30 12:28:28 | 1 | 1.08
159 | TT24777 | Amruta Kore | - | - | - | QC Setup Master - Estimation | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:13:08 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 11:53:56 | 2024-09-04 11:53:56 | 0.25 | 0.22
160 | TT24206 | Amruta Kore | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
161 | TT22785 | Amruta Kore | - | - | - | Lot tag document reading | Document Reading | 2024-09-24 | 00:30:00 | 00:35:52 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 17:06:09 | 2024-09-24 17:06:09 | 0.5 | 0.6
162 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 2 Sept | Technical guidance/Process Input | 2024-09-02 | 00:30:00 | 00:12:30 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:44:17 | 2024-09-02 19:44:17 | 0.5 | 0.21
163 | TT24672 | Amruta Kore | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | Support from gokul - Configuration master script | Technical guidance/Process Input | 2024-09-27 | 00:30:00 | 00:20:32 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:12:38 | 2024-09-27 20:12:38 | 0.5 | 0.34
164 | TT24674 | Amruta Kore | - | - | - | Weight Range master - Testcase writing | Test case writing- | 2024-09-24 | 01:00:00 | 01:18:06 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 16:52:05 | 2024-09-24 16:52:05 | 1 | 1.3
165 | TT22163 | Amruta Kore | - | - | - | Support from gokul - Gr wt adjustment in offline tagging | Technical guidance/Process Input | 2024-09-23 | 01:30:00 | 00:29:32 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:10:16 | 2024-09-25 23:10:16 | 1.5 | 0.49
166 | TT24647 | Amruta Kore | - | - | - | BDD Module - Automation Script(Positive Testing) | Automate test script | 2024-09-02 | 28:00:00 | 25:34:17 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 22:49:49 | 2024-09-10 22:49:49 | 4 | 1.57
167 | TT24672 | Amruta Kore | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | configuration master - Automation script | Automate test script | 2024-09-27 | 03:00:00 | 02:38:42 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:39:27 | 2024-09-27 23:39:27 | 3 | 2.65
168 | TT24674 | Amruta Kore | - | - | - | Weight range master - Document reading | Document Reading | 2024-09-23 | 00:15:00 | 00:16:41 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 15:07:26 | 2024-09-23 15:07:26 | 0.25 | 0.28
169 | TT22163 | Amruta Kore | - | - | - | Gross wt Adjustment in offline tagging- Automation script | Automate test script | 2024-09-23 | 12:00:00 | 10:51:07 | 2024-09-30 |  | COMPLETED | DELAY | 2024-10-07 16:45:17 | 2024-10-07 16:45:17 | 12 | 10.85
170 | TT24390 | Amruta Kore | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Supprot from Gokul | Support. | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:06:31 | 2024-09-18 17:06:31 | 0 | 0
171 | TT23782 | Amruta Kore | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
172 | TT24672 | Amruta Kore | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | Configuration master - Document reading | Documentation Reading | 2024-09-10 | 00:15:00 | 00:18:59 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 12:45:07 | 2024-09-10 12:45:07 | 0.25 | 0.32
173 | TT24678 | Amruta Kore | - | - | - | Making Charges Master - Testing | Testing | 2024-09-24 | 02:30:00 | 04:27:53 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 12:46:10 | 2024-09-26 12:46:10 | 2.5 | 4.46
174 | TT24774 | Amruta Kore | - | - | - | KT New development-HM pcs adjustment field in RNG Process | KT Session | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 12:26:03 | 2024-09-26 12:26:03 | 0 | 0
175 | TT24390 | Amruta Kore | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Set Tag Module - Script(As per testcase) | Automate test script | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:05:58 | 2024-09-18 17:05:58 | 0 | 0
176 | TT23782 | Amruta Kore | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
177 | TT24672 | Amruta Kore | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | Modification testcase of configuration master | Test case updation\modification | 2024-09-10 | 00:30:00 | 00:32:01 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 13:17:46 | 2024-09-10 13:17:46 | 0.5 | 0.53
178 | TT24678 | Amruta Kore | - | - | - | Making charges Master Testcase Modification | Test case updation\modification | 2024-09-23 | 00:30:00 | 00:42:46 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:16:56 | 2024-09-23 23:16:56 | 0.5 | 0.71
179 | TT24683 | Amruta Kore | - | - | - | PCS Adjustment in offline tagging estimation | Estimate calculation | 2024-09-20 | 00:15:00 | 00:12:25 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:45:59 | 2024-09-20 23:45:59 | 0.25 | 0.21
180 | TT22785 | Amruta Kore | - | - | - | Lot Tag KT | KT Session | 2024-09-19 | 00:30:00 | 00:40:14 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 20:31:42 | 2024-09-19 20:31:42 | 0.5 | 0.67
181 | TT22163 | Amruta Kore | - | - | - | Gross wt Adjustment - Retesting | Retesting | 2024-09-19 | 04:00:00 | 04:32:43 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-25 10:50:41 | 2024-09-22 18:29:17 | 4 | 4.55
182 | TT24683 | Amruta Kore | - | - | - | PCS Adjustment KT by snehal | KT Session | 2024-09-23 | 01:00:00 | 00:49:34 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 13:58:07 | 2024-09-23 13:58:07 | 1 | 0.83
183 | TT24920 | Amruta Kore | - | - | - | Support from Gokul - Set tag Module | Technical guidance/Process Input | 2024-09-20 | 00:30:00 | 00:38:21 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:58:11 | 2024-09-20 23:58:11 | 0.5 | 0.64
184 | TT22163 | Amruta Kore | - | - | - | Offline Tagging Script | Automate test script | 2024-10-08 | 07:30:00 | 09:08:13 | 2024-10-15 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 17:21:26 |  | 7.5 | 9.14
185 | TT24920 | Amruta Kore | - | - | - | Set tag - Automation script as per Testcases | Script Execution/ Modification | 2024-09-20 | 04:00:00 | 03:30:13 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:19:43 | 2024-09-23 23:19:43 | 4 | 3.5
186 | TT26038 | Amruta Kore | - | - | - | Support from Saurabh - P2P process testing (platinum, SS) | Query clarification | 2024-10-10 | 00:20:00 | 00:00:00 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 18:55:14 |  | 0.33 | 0
187 | TT26038 | Amruta Kore | - | - | - | Sprint Sathi Discussion & Sprint Define For Ticket | Estimate calculation | 2024-10-10 | 01:00:00 | 00:54:02 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 0.9
188 | TT21899 | Amruta Kore | - | - | - | Set Tag Module - Script(As per testcase) | Script Execution/ Modification | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-18 17:10:34 | 2024-09-18 17:10:34 | 0 | 0
189 | TT26038 | Amruta Kore | - | - | - | Sterling silver - P2P testing | E2E Testing | 2024-10-10 | 02:30:00 | 01:49:31 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 2.5 | 1.83
190 | TT26038 | Amruta Kore | - | - | - | Task Schedule With Team | General meeting | 2024-10-09 | 00:45:00 | 00:25:49 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 19:12:03 | 2024-10-09 19:12:03 | 0.75 | 0.43
191 | TT24769 | Amruta Kore | - | - | - | Testcase writing - Wastage code master | Test case writing- | 2024-09-20 | 01:00:00 | 00:54:35 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 13:14:15 | 2024-09-20 13:14:15 | 1 | 0.91
192 | TT26038 | Amruta Kore | - | - | - | Platinum - P2P process testing | E2E Testing | 2024-10-08 | 05:00:00 | 04:28:37 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 12:22:36 | 2024-10-09 12:22:36 | 5 | 4.48
193 | TT24674 | Amruta Kore | - | - | - | Weight range master Testcase Modification | Test case updation\modification | 2024-10-08 | 00:45:00 | 00:25:49 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 18:39:10 | 2024-10-08 18:39:10 | 0.75 | 0.43
194 | TT24774 | Amruta Kore | - | - | - | Testcase writing Hallmarking master | Test case writing- | 2024-09-19 | 01:00:00 | 00:37:42 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 22:27:00 | 2024-09-19 22:27:00 | 1 | 0.63
195 | TT22163 | Amruta Kore | - | - | - | Support from gokul - Code Merged P2P process | Query clarification | 2024-10-05 | 01:00:00 | 01:40:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:24:33 | 2024-10-05 23:24:33 | 1 | 1.68
196 | TT24680 | Amruta Kore | - | - | - | Test cases writing of sub smith master | Test case writing- | 2024-09-20 | 01:00:00 | 00:33:59 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 13:50:11 | 2024-09-20 13:50:11 | 1 | 0.57
197 | TT23053 | Amruta Kore | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 01:19:06 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 1.32
198 | TT22163 | Amruta Kore | - | - | - | Support from Gokul - Offline Tagging Automation Script | Query clarification | 2024-10-08 | 01:00:00 | 00:19:54 | 2024-10-15 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 17:22:35 |  | 1 | 0.33
199 | TT24774 | Amruta Kore | - | - | - | Automation Script of HallMarking Master | Automate test script | 2024-09-18 | 04:00:00 | 03:26:06 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 22:35:11 | 2024-09-19 22:35:11 | 4 | 3.44
200 | TT22785 | Amruta Kore | - | - | - | Lot Tag Testcase Modification | Test case updation\modification | 2024-10-01 | 01:00:00 | 00:39:32 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 23:33:30 | 2024-10-01 23:33:30 | 1 | 0.66
201 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - BDD Scheme Script | Technical guidance/Process Input | 2024-09-09 | 01:00:00 | 02:18:47 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:38:14 | 2024-09-10 19:38:14 | 1 | 2.31
202 | TT24774 | Amruta Kore | - | - | - | HallMarking Master Scripting - 100% | Automate test script | 2024-10-08 | 02:03:00 | 02:23:13 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 15:23:49 |  | 2.05 | 2.39
203 | TT24773 | Amruta Kore | - | - | - | QC setting master - Testcase writing | Test case writing- | 2024-09-13 | 01:30:00 | 00:59:52 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 09:54:24 | 2024-09-13 09:54:24 | 1.5 | 1
204 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:18:20 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 11:33:31 |  | 2 | 0.31
205 | TT21899 | Amruta Kore | - | - | - | Support from gokul - Set tag module | Query clarification | 2024-09-30 | 01:00:00 | 00:39:13 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:05 | 2024-10-01 19:34:05 | 1 | 0.65
206 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:50:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 1.84
207 | TT21899 | Amruta Kore | - | - | - | Set Tag Module Scripting - 100 percent | Automate test script | 2024-09-30 | 08:00:00 | 13:56:31 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 10:52:25 | 2024-10-04 10:52:25 | 8 | 13.94
208 | TT24776 | Amruta Kore | - | - | - | Agent master - Testcase writing | Test case writing- | 2024-09-12 | 01:00:00 | 00:46:54 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 12:50:15 | 2024-09-12 12:50:15 | 1 | 0.78
209 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | Scheduling | Task Scheduling | 2024-10-03 | 01:00:00 | 00:11:57 | 2024-10-04 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-07 09:26:42 | 2024-10-07 09:26:42 | 1 | 0.2
210 | TT22830 | Amruta Kore | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
211 | TT24777 | Amruta Kore | - | - | - | QC ssetup master - Testcase writing | Test case writing- | 2024-09-13 | 01:00:00 | 00:51:20 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 09:54:37 | 2024-09-13 09:54:37 | 1 | 0.86
212 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | Task scheduling | Task Scheduling | 2024-09-12 | 00:30:00 | 00:42:07 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:57:02 | 2024-09-13 18:57:02 | 0.5 | 0.7
213 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | Task scheduling 26 to 27 Sept | Task Scheduling | 2024-09-26 | 01:00:00 | 01:14:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:56:23 | 2024-09-27 23:56:23 | 1 | 1.24
214 | TT21945 | Amruta Kore | - | - | - | Support from Gokul -P2P process(SS, SB) | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-07 17:03:35 | 2024-10-07 17:03:35 | 0 | 0
215 | TT24778 | Amruta Kore | - | - | - | Item type master - Testcase writing | Test case writing- | 2024-09-12 | 01:00:00 | 00:59:57 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 22:08:56 | 2024-09-12 22:08:56 | 1 | 1
216 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | Scheduling | Task Scheduling | 2024-09-05 | 00:30:00 | 00:31:35 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 21:02:32 | 2024-09-06 21:02:32 | 0.5 | 0.53
217 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:38:21 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.64
218 | TT21945 | Amruta Kore | - | - | - | Support from Gokul - P2P process (Gold, Silver, Platinum) | Query clarification | 2024-10-01 | 01:00:00 | 00:52:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:33:21 | 2024-10-04 22:33:21 | 1 | 0.88
219 | TT24681 | Amruta Kore | - | - | - | Ornament Number Sequence Master | Test case writing- | 2024-09-11 | 01:30:00 | 01:29:26 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 19:09:42 | 2024-09-11 19:09:42 | 1.5 | 1.49
220 | TT23932 | Amruta Kore | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:00:00 | 01:45:36 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2 | 1.76
221 | TT24206 | Digvijay Tulse | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Digvijay about connect us 2.0 (Masters , except customer mapping ) | Internal KT/cross KT | 2024-10-07 | 04:00:00 | 03:10:54 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 19:47:56 | 2024-10-08 19:47:56 | 4 | 3.18
222 | TT22454 | Gokul Bhoi | - | - | - | Review customer order repair testing | Reporting Review | 2024-09-24 | 00:45:00 | 00:34:56 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 16:55:20 | 2024-09-26 16:55:20 | 0.75 | 0.58
223 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:20 | 2024-10-06 23:45:20 | 0 | 0
224 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | Modification and Update of Generic Method in Framework | Modify test script | 2024-09-25 | 04:00:00 | 14:07:49 | 2024-09-27 |  | COMPLETED | HIGHLY_DELAY | 2024-09-29 23:25:05 | 2024-09-29 23:25:05 | 4 | 14.13
225 | TT23985 | Gokul Bhoi | - | - | - | TT23985 -Review- Stock Repair Positive flow Scripting (50% TC Cover) | Test script review | 2024-10-07 | 01:36:00 | 00:22:09 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 16:20:00 |  | 1.6 | 0.37
226 | TT14931 | Gokul Bhoi | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:21 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
227 | TT14931 | Gokul Bhoi | - | - | - | Review Customer order testing 23 sep | Reporting Review | 2024-09-23 | 01:00:00 | 00:37:42 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 23:45:01 | 2024-09-24 23:45:01 | 1 | 0.63
228 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 01:00:00 | 00:09:19 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 23:48:07 |  | 1 | 0.16
229 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling | Task Scheduling | 2024-09-26 | 01:00:00 | 00:42:40 | 2024-09-27 |  | COMPLETED | HIGHLY_DELAY | 2024-09-29 23:25:36 | 2024-09-29 23:25:36 | 1 | 0.71
230 | TT21945 | Gokul Bhoi | - | - | - | TT21945 -Review- QC Process (PR , DC , QC) TC Scripting | Test script review | 2024-09-23 | 00:30:00 | 00:15:17 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 20:04:02 | 2024-09-23 20:04:02 | 0.5 | 0.25
231 | TT17156 | Gokul Bhoi | - | - | - | Automation Support | Technical guidance/Process Input | 2024-09-09 | 02:30:00 | 02:56:48 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:25:13 | 2024-09-13 18:25:13 | 2.5 | 2.95
232 | TT22163 | Gokul Bhoi | - | - | - | Support from gokul - Gr wt adjustment in offline tagging | Technical guidance/Process Input | 2024-09-23 | 01:30:00 | 00:29:29 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:10:16 | 2024-09-25 23:10:16 | 1.5 | 0.49
233 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:47 | 2024-10-06 23:46:47 | 0 | 0
234 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 26:36:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.61
235 | TT24674 | Gokul Bhoi | - | - | - | Support from gokul | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 00:29:15 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:59:58 | 2024-09-27 16:59:58 | 0.5 | 0.49
236 | TT24683 | Gokul Bhoi | - | - | - | KT - PCS Adjustment Sub Module to developer and tester | KT Session | 2024-09-06 | 01:13:00 | 01:06:13 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:16:03 | 2024-09-06 19:16:03 | 1.22 | 1.1
237 | TT18255 | Gokul Bhoi | - | - | - | Support From Gokul URD | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:40:43 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 19:21:47 | 2024-09-23 19:21:47 | 0.5 | 0.68
238 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:59 | 2024-10-06 23:46:59 | 0 | 0
239 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling | Task Scheduling | 2024-09-19 | 01:00:00 | 01:18:17 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:47:16 | 2024-09-20 23:47:16 | 1 | 1.3
240 | TT22163 | Gokul Bhoi | - | - | - | Support from Gokul - Offline Tagging Automation Script | Query clarification | 2024-10-08 | 01:00:00 | 00:19:54 | 2024-10-15 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 17:22:35 |  | 1 | 0.33
241 | TT14931 | Gokul Bhoi | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:01 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
242 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 01:30:00 | 01:35:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 1.5 | 1.59
243 | TT22163 | Gokul Bhoi | - | - | - | Support from gokul - Code Merged P2P process | Query clarification | 2024-10-05 | 01:00:00 | 01:40:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:24:33 | 2024-10-05 23:24:33 | 1 | 1.68
244 | TT22455 | Gokul Bhoi | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Review Gift voucher Automation script | Test script review | 2024-09-11 | 03:00:00 | 01:30:07 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 23:49:50 | 2024-09-13 23:49:50 | 3 | 1.5
245 | TT21914 | Gokul Bhoi | - | - | - | support to Gokul | Query clarification | 2024-09-02 | 02:30:00 | 00:36:59 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:29:04 | 2024-09-06 19:29:04 | 2.5 | 0.62
246 | TT23985 | Gokul Bhoi | - | - | - | Support From Gokul | Technical guidance/Process Input | 2024-10-03 | 01:00:00 | 00:49:16 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:58 | 2024-10-04 19:41:58 | 1 | 0.82
247 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:43:31 | 2024-10-06 23:43:31 | 1 | 0
248 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:39:51 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.66
249 | TT18255 | Gokul Bhoi | - | - | - | Support from Gokul URD Silver | Support. | 2024-10-05 | 01:00:00 | 00:59:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:22:37 | 2024-10-05 23:22:37 | 1 | 1
250 | TT22455 | Gokul Bhoi | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Support from Gokul - For Gift Voucher Script | Technical guidance/Process Input | 2024-09-11 | 01:30:00 | 00:47:30 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 21:22:32 | 2024-09-13 21:22:32 | 1.5 | 0.79
251 | TT14931 | Gokul Bhoi | - | - | - | Customer order Automation Scripting (Positive flow) | Automate test script | 2024-09-04 | 02:30:00 | 03:34:35 | 2024-09-05 |  | COMPLETED | DELAY | 2024-09-06 17:20:06 | 2024-09-06 17:20:06 | 2.5 | 3.58
252 | TT21945 | Gokul Bhoi | - | - | - | Automation support from gokul | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:24:53 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-25 14:04:22 | 2024-09-25 14:04:22 | 0.5 | 0.41
253 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
254 | TT23053 | Gokul Bhoi | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 03:08:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 3.15
255 | TT23436 | Gokul Bhoi | - | - | - | PadmStockBalance API Testing | Api Testing | 2024-09-06 | 01:30:00 | 01:34:27 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-09 16:36:46 | 2024-09-09 16:36:46 | 1.5 | 1.57
256 | TT26038 | Gokul Bhoi | - | - | - | TT26038-P2P process bugsheet review(Platinum, DJ, Silver) | Reporting Review | 2024-10-09 | 01:00:00 | 00:00:00 | 2024-10-09 |  | TO_DO | DELAY | 2024-10-09 15:50:54 |  | 1 | 0
257 | TT24760 | Gokul Bhoi | - | - | - | Automation Support From Gokul Bank Master | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 01:32:31 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 18:48:38 | 2024-09-26 18:48:38 | 0.5 | 1.54
258 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:49 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
259 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling 6-9-2024 | Task Scheduling | 2024-09-05 | 01:00:00 | 01:00:14 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 23:58:01 | 2024-09-06 23:58:01 | 1 | 1
260 | TT21945 | Gokul Bhoi | - | - | - | P2P Process - Support from Gokul | Support. | 2024-10-08 | 00:30:00 | 00:00:00 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:49:54 | 2024-10-08 16:49:54 | 0.5 | 0
261 | TT23436 | Gokul Bhoi | - | - | - | PadmStockBalance API Test case writing | Test Case Writing | 2024-09-03 | 01:25:00 | 01:21:04 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:09:37 | 2024-09-03 23:09:37 | 1.42 | 1.35
262 | TT26038 | Gokul Bhoi | - | - | - | Task Schedule With Team | General meeting | 2024-10-09 | 00:45:00 | 00:27:07 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 19:12:03 | 2024-10-09 19:12:03 | 0.75 | 0.45
263 | TT22454 | Gokul Bhoi | - | - | - | Support From Gokul(Customer order repair) | Query clarification | 2024-09-24 | 00:45:00 | 03:12:15 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:30:23 | 2024-09-25 19:30:23 | 0.75 | 3.2
264 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
265 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:18:57 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 2.32
266 | TT18255 | Gokul Bhoi | - | - | - | Support from Gokul URD Automation | Query clarification | 2024-10-03 | 01:00:00 | 00:23:06 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:23 | 2024-10-04 19:08:23 | 1 | 0.39
267 | TT24647 | Gokul Bhoi | - | - | - | Review Stock transfer Automation Scripting | Review | 2024-09-02 | 02:30:00 | 01:44:15 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:13:45 | 2024-09-06 20:13:45 | 2.5 | 1.74
268 | TT24674 | Gokul Bhoi | - | - | - | Weight range Master testcase review | Review updated Test cases | 2024-10-08 | 00:30:00 | 00:24:42 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 23:11:19 | 2024-10-08 23:11:19 | 0.5 | 0.41
269 | TT14931 | Gokul Bhoi | - | - | - | Support from Gokul(customer order) | Query clarification | 2024-09-23 | 00:30:00 | 00:27:36 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:42:41 | 2024-09-24 19:42:41 | 0.5 | 0.46
270 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Walk in interview support | Interview | 2024-09-30 | 12:00:00 | 05:22:43 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 12 | 5.38
271 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:18 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
272 | TT17156 | Gokul Bhoi | - | - | - | Support from gokul(Stock Transfer-Transfer) | Query clarification | 2024-10-08 | 00:30:00 | 00:36:15 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 18:52:37 | 2024-10-08 18:52:37 | 0.5 | 0.6
273 | TT24647 | Gokul Bhoi | - | - | - | Review BDD module Automation Scripting | Review | 2024-09-02 | 02:30:00 | 01:47:46 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 23:44:27 | 2024-09-06 23:44:27 | 2.5 | 1.8
274 | TT24683 | Gokul Bhoi | - | - | - | PCS Adjustment in offline tagging estimation | Estimate calculation | 2024-09-20 | 00:15:00 | 00:12:33 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:45:59 | 2024-09-20 23:45:59 | 0.25 | 0.21
275 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:22:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0.38
276 | TT14720 | Gokul Bhoi | - | - | - | review estimation of RNG | Review | 2024-09-02 | 00:15:00 | 00:10:13 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:56:33 | 2024-09-02 19:56:33 | 0.25 | 0.17
277 | TT24774 | Gokul Bhoi | - | - | - | KT New development-HM pcs adjustment field in RNG Process | KT Session | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 12:26:03 | 2024-09-26 12:26:03 | 0 | 0
278 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:20:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.34
279 | TT22810 | Gokul Bhoi | - | - | - | Automation Support From gokul(RNG) | Query clarification | 2024-10-03 | 02:00:00 | 02:21:28 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:29:18 | 2024-10-07 19:29:18 | 2 | 2.36
280 | TT24772 | Gokul Bhoi | - | - | - | Designer master - Estimation Review | Review | 2024-09-04 | 00:15:00 | 00:07:26 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:59:58 | 2024-09-04 19:59:58 | 0.25 | 0.12
281 | TT24683 | Gokul Bhoi | - | - | - | PCS Adjustment KT by snehal | KT Session | 2024-09-23 | 00:00:00 | 00:00:00 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 13:58:07 | 2024-09-23 13:58:07 | 0 | 0
282 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:30:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0.5
283 | TT14931 | Gokul Bhoi | - | - | - | Cutomer order and customer order repair bugs explain by gokul sir | General meeting | 2024-09-28 | 00:30:00 | 00:45:15 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 18:23:11 | 2024-09-28 18:23:11 | 0.5 | 0.75
284 | TT24769 | Gokul Bhoi | - | - | - | Wastage code master Estimation - Review | Review | 2024-09-05 | 00:15:00 | 00:06:57 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 11:41:05 | 2024-09-05 11:41:05 | 0.25 | 0.12
285 | TT24920 | Gokul Bhoi | - | - | - | Set Tag Automation Script Review | Test script review | 2024-09-23 | 00:30:00 | 00:00:00 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:15:37 | 2024-09-23 23:15:37 | 0.5 | 0
286 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:28:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 2.47
287 | TT24678 | Gokul Bhoi | - | - | - | Making charges Master bugsheet Review | Reporting Review | 2024-09-28 | 00:30:00 | 00:27:04 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 18:22:51 | 2024-09-28 18:22:51 | 0.5 | 0.45
288 | TT18255 | Gokul Bhoi | - | - | - | Support for automation URD from Gokul | Technical guidance/Process Input | 2024-09-19 | 01:00:00 | 02:10:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:24 | 2024-09-20 19:48:24 | 1 | 2.18
289 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 01:00:00 | 00:16:27 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 13:31:36 |  | 1 | 0.27
290 | TT18255 | Gokul Bhoi | - | - | - | Support From Gokul URD | Test Script Preparation | 2024-10-07 | 01:00:00 | 01:00:34 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:19:07 | 2024-10-08 16:19:07 | 1 | 1.01
291 | TT14931 | Gokul Bhoi | - | - | - | Support(Customer order ) | Query clarification | 2024-09-11 | 00:30:00 | 00:23:21 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:06:31 | 2024-09-13 12:06:31 | 0.5 | 0.39
292 | TT24920 | Gokul Bhoi | - | - | - | Support from Gokul - Set tag Module | Technical guidance/Process Input | 2024-09-20 | 00:30:00 | 00:38:21 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:58:11 | 2024-09-20 23:58:11 | 0.5 | 0.64
293 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
294 | TT22830 | Gokul Bhoi | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 0
295 | TT24770 | Gokul Bhoi | - | - | - | Sub category Master - Estimation review | Review | 2024-09-04 | 00:15:00 | 00:07:05 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:54:07 | 2024-09-04 19:54:07 | 0.25 | 0.12
296 | TT14931 | Gokul Bhoi | - | - | - | Customer order Scripting as Per test cases(40%) | Automate test script | 2024-09-20 | 03:30:00 | 03:02:30 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-30 01:50:15 | 2024-09-30 01:50:15 | 3.5 | 3.04
297 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 02:00:01 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 2
298 | TT21945 | Gokul Bhoi | - | - | - | Support from Gokul - P2P process (Gold, Silver, Platinum) | Query clarification | 2024-10-01 | 01:00:00 | 00:52:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:33:21 | 2024-10-04 22:33:21 | 1 | 0.88
299 | TT24778 | Gokul Bhoi | - | - | - | Item Type Master Estimation - Review | Review | 2024-09-04 | 00:15:00 | 00:08:12 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:10 | 2024-09-04 19:41:10 | 0.25 | 0.14
300 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:48 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
301 | TT22200 | Gokul Bhoi | - | - | - | Items Category code modification | Automate test script | 2024-09-18 | 06:00:00 | 05:26:23 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 21:21:12 | 2024-09-19 21:21:12 | 6 | 5.44
302 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 01:08:10 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 1.14
303 | TT21945 | Gokul Bhoi | - | - | - | P2P Process Support from Gokul | Query clarification | 2024-10-03 | 01:00:00 | 00:09:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:47 | 2024-10-04 19:08:47 | 1 | 0.16
304 | TT24777 | Gokul Bhoi | - | - | - | QC Setup Master - Estimation Review | Review | 2024-09-04 | 00:15:00 | 00:13:07 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:50:52 | 2024-09-04 19:50:52 | 0.25 | 0.22
305 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support By Preeti ma'am | Mentoring | 2024-09-02 | 02:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-02 14:41:34 | 2024-09-02 14:41:34 | 2.5 | 0
306 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Parallel run process Exporation | Explore New things\other | 2024-10-09 | 02:00:00 | 01:14:36 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-09 12:04:44 |  | 2 | 1.24
307 | TT22810 | Gokul Bhoi | - | - | - | Support form gokul(RNG) | Technical guidance/Process Input | 2024-09-18 | 00:15:00 | 00:35:46 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 19:18:21 | 2024-09-18 19:18:21 | 0.25 | 0.6
308 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:52:24 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.87
309 | TT24672 | Gokul Bhoi | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | Configuration Master - Script review | Script review | 2024-09-27 | 00:30:00 | 00:28:54 | 2024-09-27 |  | COMPLETED | DELAY | 2024-09-29 23:54:45 | 2024-09-29 23:54:45 | 0.5 | 0.48
310 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 6 Sept | Technical guidance/Process Input | 2024-09-06 | 00:30:00 | 00:46:52 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:17 | 2024-09-06 20:14:17 | 0.5 | 0.78
311 | TT22785 | Gokul Bhoi | - | - | - | Lot Tag BrainStroming - | Brainstorming - Internal ( Within Team member) | 2024-09-27 | 00:30:00 | 00:54:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:45:04 | 2024-09-27 19:45:04 | 0.5 | 0.9
312 | TT24776 | Gokul Bhoi | - | - | - | Agent Master Review | Review | 2024-09-04 | 00:15:00 | 00:13:03 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:33:44 | 2024-09-04 19:33:44 | 0.25 | 0.22
313 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:07:59 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.13
314 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Mulitple line data send Generic method modification | Automate test script | 2024-10-08 | 04:00:00 | 03:11:24 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 19:52:54 | 2024-10-08 19:52:54 | 4 | 3.19
315 | TT14931 | Gokul Bhoi | - | - | - | Review customer order testing | Reporting Review | 2024-09-19 | 01:00:00 | 00:40:14 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-23 19:41:03 | 2024-09-23 19:41:03 | 1 | 0.67
316 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 01:02:44 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 1.05
317 | TT24672 | Gokul Bhoi | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | Support from gokul - Configuration master script | Technical guidance/Process Input | 2024-09-27 | 00:30:00 | 00:20:32 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:12:38 | 2024-09-27 20:12:38 | 0.5 | 0.34
318 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 5 Sept | Technical guidance/Process Input | 2024-09-05 | 00:30:00 | 00:10:34 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 22:54:47 | 2024-09-05 22:54:47 | 0.5 | 0.18
319 | TT24777 | Gokul Bhoi | - | - | - | QC Setup Master script Review | Script review | 2024-09-27 | 00:30:00 | 00:21:32 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:51:58 | 2024-09-27 19:51:58 | 0.5 | 0.36
320 | TT24771 | Gokul Bhoi | - | - | - | Review of Size master | Review | 2024-09-03 | 00:10:00 | 00:06:03 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:08:16 | 2024-09-03 23:08:16 | 0.17 | 0.1
321 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Weekly meeting with gaurav sir 20th Sep | Weekly sync call | 2024-09-20 | 01:00:00 | 00:59:39 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:50:01 | 2024-09-20 20:50:01 | 1 | 0.99
322 | TT14931 | Gokul Bhoi | - | - | - | Support from gokul(Customer order) | Query clarification | 2024-09-19 | 00:30:00 | 01:03:37 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:56:13 | 2024-09-20 22:56:13 | 0.5 | 1.06
323 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:15:00 | 01:09:45 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1.25 | 1.16
324 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 4 Sept | Technical guidance/Process Input | 2024-09-04 | 00:30:00 | 00:16:25 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 21:42:25 | 2024-09-04 21:42:25 | 0.5 | 0.27
325 | TT24777 | Gokul Bhoi | - | - | - | Qc setup Master Support from gokul | Query clarification | 2024-09-27 | 00:30:00 | 00:56:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:04:11 | 2024-09-27 17:04:11 | 0.5 | 0.93
326 | TT24680 | Gokul Bhoi | - | - | - | Review estimation of sub-smith master | Review | 2024-09-03 | 00:10:00 | 00:08:39 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:08:49 | 2024-09-03 23:08:49 | 0.17 | 0.14
327 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 01:27:33 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 1.46
328 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | p2p scripting modification | Modify test script | 2024-10-07 | 01:00:00 | 01:13:27 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 23:05:43 | 2024-10-07 23:05:43 | 1 | 1.22
329 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 3 Sept | Technical guidance/Process Input | 2024-09-03 | 00:30:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:09 | 2024-09-03 22:23:09 | 0.5 | 0.43
330 | TT24678 | Gokul Bhoi | - | - | - | Making charges master - bugsheet Review | Reporting Review | 2024-09-25 | 00:30:00 | 00:14:16 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:59:36 | 2024-09-25 23:59:36 | 0.5 | 0.24
331 | TT24647 | Gokul Bhoi | - | - | - | BDD Estimation Review | Review. | 2024-09-04 | 00:30:00 | 00:24:10 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 23:12:47 | 2024-09-04 23:12:47 | 0.5 | 0.4
332 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 02:27:19 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 2.46
333 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Code modification PADM customer order status | Automate test script | 2024-10-05 | 03:00:00 | 00:00:00 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:32:22 | 2024-10-05 23:32:22 | 3 | 0
334 | TT24774 | Gokul Bhoi | - | - | - | Code Review - HallMarking automation script | Test script review | 2024-09-19 | 00:30:00 | 00:23:32 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 23:44:38 | 2024-09-19 23:44:38 | 0.5 | 0.39
335 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:27:43 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.46
336 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 2 Sept | Technical guidance/Process Input | 2024-09-02 | 00:30:00 | 00:12:13 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:44:17 | 2024-09-02 19:44:17 | 0.5 | 0.2
337 | TT24206 | Gokul Bhoi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
338 | TT22830 | Gokul Bhoi | - | - | - | Karagir nave Jama Scripting Support By Gokul | Technical guidance/Process Input | 2024-09-24 | 02:00:00 | 01:56:36 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 16:04:23 | 2024-09-27 16:04:23 | 2 | 1.94
339 | TT24647 | Gokul Bhoi | - | - | - | BDD Cross KT | KT Session | 2024-09-03 | 00:45:00 | 00:33:15 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:40 | 2024-09-03 22:23:40 | 0.75 | 0.55
340 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Padm Labour charges Automation scripting | Automate test script | 2024-10-03 | 08:00:00 | 07:20:10 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-03 13:21:32 | 2024-10-03 13:21:32 | 8 | 7.34
341 | TT17156 | Gokul Bhoi | - | - | - | Review code-Transfer order -Document scan/Old metal copy scan | Test script review | 2024-09-19 | 00:30:00 | 00:51:08 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-23 16:39:33 | 2024-09-23 16:39:33 | 0.5 | 0.85
342 | TT23782 | Gokul Bhoi | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
343 | TT25654 | Gokul Bhoi | - | - | - | TT25654 Review Script (Pending vendor Invoices) | Script review | 2024-09-25 | 00:30:00 | 00:35:19 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:17:51 | 2024-09-25 23:17:51 | 0.5 | 0.59
344 | TT17156 | Gokul Bhoi | - | - | - | Automation support | Technical guidance/Process Input | 2024-09-02 | 02:30:00 | 02:40:02 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:51 | 2024-09-06 20:14:51 | 2.5 | 2.67
345 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Generic Methods for Framework Automation Scripting | Automate test script | 2024-10-03 | 08:00:00 | 04:54:44 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:32:18 | 2024-10-04 23:32:18 | 8 | 4.91
346 | TT17156 | Gokul Bhoi | - | - | - | Automation Support(Transfer Order-Document scan and old metal copy ) | Technical guidance/Process Input | 2024-09-19 | 00:30:00 | 01:12:04 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-21 11:59:37 | 2024-09-21 11:59:37 | 0.5 | 1.2
347 | TT25654 | Gokul Bhoi | - | - | - | Support From Gokul (Pending vendor Invoices) | Technical guidance/Process Input | 2024-09-25 | 00:30:00 | 00:21:55 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:18:12 | 2024-09-25 19:18:12 | 0.5 | 0.37
348 | TT24647 | Gokul Bhoi | - | - | - | Review BDD Automation scripting | Test script review | 2024-09-09 | 01:30:00 | 01:02:57 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-11 11:37:36 | 2024-09-11 11:37:36 | 1.5 | 1.05
349 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | P2P process code merge | Automate test script | 2024-09-28 | 05:00:00 | 04:53:49 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 23:17:09 | 2024-09-28 23:17:09 | 5 | 4.9
350 | TT24678 | Gokul Bhoi | - | - | - | Making charge master Automation scripting | Automate test script | 2024-09-13 | 05:00:00 | 05:40:13 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-14 14:58:14 | 2024-09-14 14:58:14 | 5 | 5.67
351 | TT22454 | Gokul Bhoi | - | - | - | Customer Order Repair bug sheet review | Review | 2024-09-02 | 01:15:00 | 01:12:49 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 21:10:29 | 2024-09-02 21:10:29 | 1.25 | 1.21
352 | TT25655 | Gokul Bhoi | - | - | - | TT25655 Script Review Post Product Receipt | Script review | 2024-09-24 | 00:30:00 | 00:31:42 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 16:18:17 | 2024-09-25 16:18:17 | 0.5 | 0.53
353 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - BDD Scheme Script | Technical guidance/Process Input | 2024-09-09 | 01:00:00 | 01:00:57 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:38:14 | 2024-09-10 19:38:14 | 1 | 1.02
354 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Supprot from Gokul | Support. | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:06:31 | 2024-09-18 17:06:31 | 0 | 0
355 | TT21914 | Gokul Bhoi | - | - | - | support to gokul | Query clarification | 2024-09-09 | 02:30:00 | 02:27:38 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:36:02 | 2024-09-13 22:36:02 | 2.5 | 2.46
356 | TT23782 | Gokul Bhoi | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:01 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
357 | TT25655 | Gokul Bhoi | - | - | - | Support from gokul (Post product receipt ) | Technical guidance/Process Input | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 11:14:00 | 2024-09-25 11:14:00 | 0.5 | 0
358 | TT23423 | Gokul Bhoi | - | - | - | SSRS report Estimation - 5 reports - Review | Review | 2024-09-10 | 00:30:00 | 00:13:14 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 23:43:34 | 2024-09-10 23:43:34 | 0.5 | 0.22
359 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Review code - Set Tag Module Atomation Script | Test script review | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:05:27 | 2024-09-18 17:05:27 | 0 | 0
360 | TT22454 | Gokul Bhoi | - | - | - | Customer order repair Test case SCRIPTING | Automate test script | 2024-09-09 | 07:00:00 | 07:05:36 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:35:28 | 2024-09-13 22:35:28 | 7 | 7.09
361 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | P2P Process automation scripting demo | Demo | 2024-10-07 | 00:30:00 | 01:28:46 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 15:26:06 | 2024-10-07 15:26:06 | 0.5 | 1.48
362 | TT22163 | Gokul Bhoi | - | - | - | Review - offline tagging Estimation merge with gr wt adjustment | Review | 2024-09-10 | 00:15:00 | 00:19:26 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 23:26:26 | 2024-09-10 23:26:26 | 0.25 | 0.32
363 | TT24206 | Gokul Bhoi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
364 | TT21945 | Gokul Bhoi | - | - | - | Review -HM Centre & PO check Positive Flow Scripting | Test script review | 2024-09-11 | 01:30:00 | 02:24:35 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:07:22 | 2024-09-13 22:07:22 | 1.5 | 2.41
365 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Testing team sync call | Testing Team Meeting | 2024-10-08 | 01:30:00 | 01:56:15 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 17:07:38 |  | 1.5 | 1.94
366 | TT24760 | Gokul Bhoi | - | - | - | TT24760 -Review Bank Master Automation Scripting | Script review | 2024-09-26 | 00:30:00 | 00:43:54 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 19:19:05 | 2024-09-26 19:19:05 | 0.5 | 0.73
367 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:31:14 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 11:33:31 |  | 2 | 0.52
368 | TT22810 | Gokul Bhoi | - | - | - | Review test case of RNG | Test Case Review | 2024-09-09 | 00:30:00 | 00:44:08 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-13 17:41:36 | 2024-09-13 17:41:36 | 0.5 | 0.74
369 | TT21945 | Gokul Bhoi | - | - | - | Review -HM , LM Stage (QC process) Positive flow Scripting | Test script review | 2024-09-09 | 01:00:00 | 01:09:25 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-11 11:30:42 | 2024-09-11 11:30:42 | 1 | 1.16
370 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Selef improvement discussion- Gokul | Testing Team Meeting | 2024-10-08 | 00:15:00 | 00:13:32 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 22:51:20 | 2024-10-08 22:51:20 | 0.25 | 0.23
371 | TT18255 | Gokul Bhoi | - | - | - | TT18255 -Review URD Scripting 50 Percent coverage | Script review | 2024-09-23 | 00:30:00 | 00:30:49 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:15:07 | 2024-09-23 23:15:07 | 0.5 | 0.51
372 | TT14931 | Gokul Bhoi | - | - | - | Review customer order testing | Review | 2024-09-12 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:10 | 2024-09-13 12:08:10 | 0 | 0
373 | TT17156 | Gokul Bhoi | - | - | - | Review Transfer Order Automation Scripting | Test script review | 2024-09-09 | 03:45:00 | 01:24:21 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 23:50:31 | 2024-09-13 23:50:31 | 3.75 | 1.41
374 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflit meeting against task scheduling | Testing Team Meeting | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:07:17 | 2024-10-07 19:07:17 | 0.5 | 0
375 | TT21914 | Gokul Bhoi | - | - | - | KRA -KPI relevant action plan with Gokul & Sayali | Explore Team capability/Improvement plan | 2024-09-23 | 02:00:00 | 00:56:14 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 20:31:38 | 2024-09-24 20:31:38 | 2 | 0.94
376 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 00:44:23 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 0.74
377 | TT24674 | Gokul Bhoi | - | - | - | Weight range master script review | Test script review | 2024-09-26 | 00:30:00 | 00:21:09 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 23:56:47 | 2024-09-27 23:56:47 | 0.5 | 0.35
378 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 01:00:00 | 00:38:04 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 19:18:04 |  | 1 | 0.63
379 | TT21914 | Gokul Bhoi | - | - | - | Support to Gokul | Query clarification | 2024-09-23 | 02:30:00 | 00:43:06 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:53:43 | 2024-09-27 19:53:43 | 2.5 | 0.72
380 | TT14931 | Gokul Bhoi | - | - | - | Review customer order update test case | Test Case Review | 2024-09-11 | 00:15:00 | 00:20:00 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 19:03:28 | 2024-09-11 19:03:28 | 0.25 | 0.33
381 | TT24674 | Gokul Bhoi | - | - | - | Weight range master - testcase review | Test Case Review | 2024-09-24 | 00:30:00 | 00:17:05 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 17:27:15 | 2024-09-25 17:27:15 | 0.5 | 0.28
382 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
383 | TT24678 | Gokul Bhoi | - | - | - | Review - Making charges Master Testcase After Modification | Review updated Test cases | 2024-09-23 | 00:15:00 | 00:14:42 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 23:57:33 | 2024-09-24 23:57:33 | 0.25 | 0.25
384 | TT14931 | Gokul Bhoi | - | - | - | Estimate Review - Customer Order | Review | 2024-09-06 | 00:15:00 | 00:16:57 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:15:40 | 2024-09-06 20:15:40 | 0.25 | 0.28
385 | TT24683 | Gokul Bhoi | - | - | - | PCS adjustment in offline tagging - Brainstroming | Brainstorming - Internal ( Within Team member) | 2024-09-26 | 00:30:00 | 00:20:36 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:51:21 | 2024-09-27 16:51:21 | 0.5 | 0.34
386 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:10 | 2024-10-06 23:45:10 | 0 | 0
387 | TT23932 | Gokul Bhoi | Sprint 1 | 2024-07-30 | 2024-08-31 | Task rescheduling | Task Scheduling | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 23:51:57 | 2024-09-24 23:51:57 | 0.5 | 0
388 | TT22163 | Gokul Bhoi | - | - | - | TT22163 -Review -Gross wt Adjustment in offline tagging- Automation script | Test script review | 2024-09-23 | 01:30:00 | 01:05:59 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:10:05 | 2024-09-25 23:10:05 | 1.5 | 1.1
389 | TT24678 | Gokul Bhoi | - | - | - | Making charges master - Testcase Review | Test Case Review | 2024-09-09 | 00:30:00 | 00:40:42 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-10 10:54:12 | 2024-09-10 10:54:12 | 0.5 | 0.68
390 | TT22454 | Kiran Dhanepkar | - | - | - | Customer order repair retesting(All type) | E2E Testing. | 2024-09-24 | 07:00:00 | 07:02:46 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:28:50 | 2024-09-25 19:28:50 | 7 | 7.05
391 | TT22454 | Kiran Dhanepkar | - | - | - | Support From Gokul(Customer order repair) | Query clarification | 2024-09-24 | 00:45:00 | 00:40:30 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:30:23 | 2024-09-25 19:30:23 | 0.75 | 0.68
392 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:31:14 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 11:33:31 |  | 2 | 0.52
393 | TT14931 | Kiran Dhanepkar | - | - | - | Support from gokul(Customer order) | Query clarification | 2024-09-19 | 00:30:00 | 00:47:33 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:56:13 | 2024-09-20 22:56:13 | 0.5 | 0.79
394 | TT14931 | Kiran Dhanepkar | - | - | - | Customer order retesting according to new CR(MRP,Forming ,Gold Bullion and Silver Bullion) | E2E Testing. | 2024-09-23 | 06:30:00 | 06:42:20 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:42:49 | 2024-09-24 19:42:49 | 6.5 | 6.71
395 | TT24207 | Kiran Dhanepkar | Testing_D365_Practice_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Update test cases Karagir Jama(QC,DC,LM,HM,Hm center and PO check) | Test case updation\modification | 2024-10-08 | 02:00:00 | 01:57:35 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 17:07:26 | 2024-10-08 17:07:26 | 2 | 1.96
396 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:50:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 1.84
397 | TT14931 | Kiran Dhanepkar | - | - | - | Customer order retesting according to new CR(Gold, Silver, platinum and diamond jewellery) | E2E Testing. | 2024-09-19 | 07:30:00 | 07:32:38 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 13:22:27 | 2024-09-21 13:22:27 | 7.5 | 7.54
398 | TT14931 | Kiran Dhanepkar | - | - | - | Customer order bugs discussion | Testing | 2024-09-23 | 00:30:00 | 00:20:36 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 19:20:21 | 2024-09-23 19:20:21 | 0.5 | 0.34
399 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | Scheduling 4 Oct | Task Scheduling | 2024-10-03 | 01:00:00 | 00:50:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:32:22 | 2024-10-04 23:32:22 | 1 | 0.84
400 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Support(Transfer Order-Document scan and old metal copy ) | Technical guidance/Process Input | 2024-09-19 | 00:30:00 | 01:12:04 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-21 11:59:37 | 2024-09-21 11:59:37 | 0.5 | 1.2
401 | TT14931 | Kiran Dhanepkar | - | - | - | Support from Gokul(customer order) | Query clarification | 2024-09-23 | 00:30:00 | 00:35:51 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:42:41 | 2024-09-24 19:42:41 | 0.5 | 0.6
402 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | Scheduling | Task Scheduling | 2024-09-25 | 01:00:00 | 00:50:52 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 16:02:00 | 2024-09-30 16:02:00 | 1 | 0.85
403 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Scripting by DTO(Transfer Order-Document scan and Old Metal copy ) | Test Script Preparation | 2024-09-19 | 04:00:00 | 05:02:12 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-21 13:24:46 | 2024-09-21 13:24:46 | 4 | 5.04
404 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 01:30:00 | 01:49:26 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 1.5 | 1.82
405 | TT14931 | Kiran Dhanepkar | - | - | - | Update customer order test cases according to new changes | Test case updation\modification | 2024-09-11 | 01:00:00 | 01:10:01 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-12 15:54:45 | 2024-09-12 15:54:45 | 1 | 1.17
406 | TT22810 | Kiran Dhanepkar | - | - | - | Support form gokul(RNG) | Technical guidance/Process Input | 2024-09-18 | 00:15:00 | 00:35:56 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 19:18:21 | 2024-09-18 19:18:21 | 0.25 | 0.6
407 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 01:30:00 | 01:35:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 1.5 | 1.59
408 | TT14931 | Kiran Dhanepkar | - | - | - | Estimation of Customer order | Estimate calculation | 2024-09-06 | 00:30:00 | 00:30:34 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:30 | 2024-09-06 17:05:30 | 0.5 | 0.51
409 | TT22810 | Kiran Dhanepkar | - | - | - | Automation script RNG As per test cases | Test Script Preparation | 2024-09-18 | 03:00:00 | 03:08:24 | 2024-09-18 |  | COMPLETED | DELAY | 2024-09-19 17:10:04 | 2024-09-19 17:10:04 | 3 | 3.14
410 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | Scheduling 20 sep | Task Scheduling | 2024-09-19 | 01:00:00 | 00:54:50 | 2024-09-20 |  | COMPLETED | HIGHLY_DELAY | 2024-09-21 10:44:39 | 2024-09-21 10:44:39 | 1 | 0.91
411 | TT14931 | Kiran Dhanepkar | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:21 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
412 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:39:51 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.66
413 | TT24683 | Kiran Dhanepkar | - | - | - | KT - PCS Adjustment Sub Module to developer and tester | KT Session | 2024-09-06 | 01:13:00 | 01:06:13 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:16:03 | 2024-09-06 19:16:03 | 1.22 | 1.1
414 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | Scheduling 12 sep | Task Scheduling | 2024-09-12 | 01:00:00 | 00:57:35 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:24:41 | 2024-09-13 18:24:41 | 1 | 0.96
415 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Support | Technical guidance/Process Input | 2024-09-09 | 02:30:00 | 03:30:07 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:25:13 | 2024-09-13 18:25:13 | 2.5 | 3.5
416 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | Scheduling 6 September | Task Scheduling | 2024-09-05 | 01:00:00 | 00:50:32 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:12:09 | 2024-09-06 18:12:09 | 1 | 0.84
417 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Scripting by DTO(Tag/Bulk tag-transfer order-Branch to branch and State to state) | Test Script Preparation | 2024-09-09 | 21:00:00 | 22:15:06 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 16:57:55 | 2024-09-18 16:57:55 | 21 | 22.25
418 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:16:28 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 2.27
419 | TT14931 | Kiran Dhanepkar | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
420 | TT17156 | Kiran Dhanepkar | - | - | - | Estimation of E-way bill added in E-Invoice | Estimate calculation | 2024-09-03 | 00:15:00 | 00:15:34 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:53:41 | 2024-09-03 14:53:41 | 0.25 | 0.26
421 | TT23932 | Kiran Dhanepkar | Sprint 1 | 2024-07-30 | 2024-08-31 | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:37 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
422 | TT14931 | Kiran Dhanepkar | - | - | - | Support(Customer order ) | Query clarification | 2024-09-11 | 00:30:00 | 00:23:33 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:06:31 | 2024-09-13 12:06:31 | 0.5 | 0.39
423 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 01:00:00 | 00:41:52 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 19:18:04 |  | 1 | 0.7
424 | TT24771 | Kiran Dhanepkar | - | - | - | Estimation of Size master | Estimate calculation | 2024-09-03 | 00:15:00 | 00:16:45 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:53:04 | 2024-09-03 14:53:04 | 0.25 | 0.28
425 | TT24206 | Kiran Dhanepkar | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
426 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
427 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
428 | TT24680 | Kiran Dhanepkar | - | - | - | Estimation of sub-smith master | Estimate calculation | 2024-09-03 | 00:15:00 | 00:12:29 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:53:16 | 2024-09-03 14:53:16 | 0.25 | 0.21
429 | TT24206 | Kiran Dhanepkar | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
430 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:37:28 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.62
431 | TT24774 | Kiran Dhanepkar | - | - | - | Estimation of hallmarking master | Estimate calculation | 2024-09-03 | 00:30:00 | 00:26:33 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:52:52 | 2024-09-03 14:52:52 | 0.5 | 0.44
432 | TT17156 | Kiran Dhanepkar | - | - | - | Support from gokul(Stock Transfer-Transfer) | Query clarification | 2024-10-08 | 00:30:00 | 00:36:15 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 18:52:37 | 2024-10-08 18:52:37 | 0.5 | 0.6
433 | TT24674 | Kiran Dhanepkar | - | - | - | Estimation of weight range master | Estimate calculation | 2024-09-02 | 00:15:00 | 00:13:53 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 18:23:37 | 2024-09-02 18:23:37 | 0.25 | 0.23
434 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:37 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
435 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Scripting Stock transfer(Transfer 100%) | Automate test script | 2024-10-08 | 04:00:00 | 04:46:18 | 2024-10-13 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 22:38:38 |  | 4 | 4.77
436 | TT14720 | Kiran Dhanepkar | - | - | - | Estimation of RNG | Estimate calculation | 2024-09-02 | 00:15:00 | 00:31:32 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 18:23:24 | 2024-09-02 18:23:24 | 0.25 | 0.53
437 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 00:45:00 | 01:21:23 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 0.75 | 1.36
438 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point karagir Jama to Kiran | Query clarification | 2024-10-07 | 00:30:00 | 01:22:19 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 18:52:21 |  | 0.5 | 1.37
439 | TT17156 | Kiran Dhanepkar | - | - | - | Automation support | Technical guidance/Process Input | 2024-09-02 | 02:30:00 | 02:39:45 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:51 | 2024-09-06 20:14:51 | 2.5 | 2.66
440 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:31 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 0.28
441 | TT22810 | Kiran Dhanepkar | - | - | - | Automation Support From gokul(RNG) | Query clarification | 2024-10-03 | 02:00:00 | 02:21:28 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:29:18 | 2024-10-07 19:29:18 | 2 | 2.36
442 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Scripting by DTO(Stock Transfer counter to counter positive flow) | Test Script Preparation | 2024-09-02 | 23:15:00 | 25:23:09 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-10 17:02:31 | 2024-09-10 17:02:31 | 23.25 | 1.39
443 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:54:24 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.91
444 | TT23782 | Kiran Dhanepkar | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
445 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:30:36 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.51
446 | TT22810 | Kiran Dhanepkar | - | - | - | RNG process Scripting(100%) | Automate test script | 2024-10-03 | 12:00:00 | 12:58:45 | 2024-10-07 |  | COMPLETED | DELAY | 2024-10-09 17:28:18 | 2024-10-09 17:28:18 | 12 | 12.98
447 | TT22810 | Kiran Dhanepkar | - | - | - | Test case writing RNG Process(gold,silver, platinum and diamond jewellery) | Test Case Writing | 2024-09-09 | 02:30:00 | 02:32:38 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:56:45 | 2024-09-10 19:56:45 | 2.5 | 2.54
448 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
449 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point to Kiran Karagir jama | Query clarification | 2024-10-03 | 01:00:00 | 00:26:51 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:36 | 2024-10-04 19:41:36 | 1 | 0.45
450 | TT22810 | Kiran Dhanepkar | - | - | - | Estimation of Hall marking RNG | Estimate calculation | 2024-09-03 | 00:00:00 | 00:00:00 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 11:47:31 | 2024-09-03 11:47:31 | 0 | 0
451 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
452 | TT22830 | Kiran Dhanepkar | - | - | - | karagir jama (QC Process - HM Centre,LM & PO check) TC Writing | Test Case Writing | 2024-10-04 | 03:00:00 | 02:34:47 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:31:42 | 2024-10-04 23:31:42 | 3 | 2.58
453 | TT23782 | Kiran Dhanepkar | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
454 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 03:28:08 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 3.47
455 | TT22830 | Kiran Dhanepkar | - | - | - | karagir jama (QC Process - DC,QC,HM) TC Writing | Test Case Writing | 2024-10-03 | 02:30:00 | 02:25:48 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:28:06 | 2024-10-03 18:28:06 | 2.5 | 2.43
456 | TT14931 | Kiran Dhanepkar | - | - | - | Customer Order retesting(Gold and silver) | E2E Testing | 2024-09-12 | 01:30:00 | 01:04:41 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:00:02 | 2024-09-13 12:00:02 | 1.5 | 1.08
457 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point to Kiran Karagir Nave | Support. | 2024-10-01 | 00:30:00 | 00:27:02 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:43 | 2024-10-01 19:02:43 | 0.5 | 0.45
458 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Nave TC Writting and updation | Test Case Writing | 2024-10-01 | 04:30:00 | 04:00:41 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:53 | 2024-10-01 19:02:53 | 4.5 | 4.01
459 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Nave BrainStroming | Brainstorming with DEV Team/BA | 2024-09-30 | 00:15:00 | 00:13:17 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 15:35:06 | 2024-09-30 15:35:06 | 0.25 | 0.22
460 | TT24776 | Kiran Dhanepkar | - | - | - | Support from Saurabh(Agent Master) | Query clarification | 2024-09-30 | 00:30:00 | 00:22:31 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:56:57 | 2024-09-30 19:56:57 | 0.5 | 0.38
461 | TT24776 | Kiran Dhanepkar | - | - | - | Agent Master Automation Scripting-Positive flow | Automate test script | 2024-09-30 | 03:45:00 | 03:40:38 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 20:08:35 | 2024-09-30 20:08:35 | 3.75 | 3.68
462 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Jama Brainstorming | Brainstorming with DEV Team/BA | 2024-10-03 | 00:45:00 | 00:39:24 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:47:04 | 2024-10-03 18:47:04 | 0.75 | 0.66
463 | TT22830 | Kiran Dhanepkar | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
464 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:41:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.7
465 | TT25975 | Maruti Hakke | Scheme Discount Bifurcation | 2024-10-07 | 2024-10-08 | Scheme Discount Bifurcation KT to Dev & Testers | KT Session | 2024-10-09 | 00:30:00 | 00:43:37 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 16:46:27 | 2024-10-09 16:46:27 | 0.5 | 0.73
466 | TT24670 | Maruti Hakke | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 0.43
467 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (18th - 20th Sep) | Sync call with Team | 2024-09-18 | 01:30:00 | 00:14:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:26:13 | 2024-09-20 22:26:13 | 1.5 | 0.24
468 | TT22394 | Maruti Hakke | - | - | - | URD Purchase Exchange KT | KT Session | 2024-09-03 | 00:45:00 | 00:31:22 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:41:20 | 2024-09-03 18:41:20 | 0.75 | 0.52
469 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Script report demo to Gaurav Sir | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:14 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:39:57 | 2024-09-20 19:39:57 | 1 | 0.27
470 | TT23939 | Maruti Hakke | - | - | - | POS Sync Call 0209 to 0609 | Daily Sync Call | 2024-09-02 | 02:00:00 | 02:20:07 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:13:52 | 2024-09-06 18:13:52 | 2 | 2.34
471 | TT25148 | Maruti Hakke | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Sales return Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-10-09 | 01:00:00 | 00:35:21 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 20:43:41 | 2024-10-09 20:43:41 | 1 | 0.59
472 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (9th Sep - 13th Sep) | Sync call with Team | 2024-09-09 | 01:15:00 | 01:57:49 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:23 | 2024-09-13 19:33:23 | 1.25 | 1.96
473 | TT23939 | Maruti Hakke | - | - | - | Task Scheduling for 06 Next Week | Task Scheduling | 2024-09-06 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:23:33 | 2024-09-06 19:23:33 | 1 | 0
474 | TT25148 | Maruti Hakke | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Sales return Estimation Review | Estimation Review | 2024-10-09 | 00:15:00 | 00:00:00 | 2024-10-09 |  | TO_DO | DELAY |  |  | 0.25 | 0
475 | TT24390 | Maruti Hakke | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Automation Support By SV | Query clarification | 2024-09-26 | 04:00:00 | 09:11:46 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-28 23:01:07 | 2024-09-28 23:01:07 | 4 | 9.2
476 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
477 | TT25148 | Maruti Hakke | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Estimate the requirement -Sales Return | Estimate the requirement | 2024-10-09 | 00:30:00 | 00:09:51 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-09 12:20:58 |  | 0.5 | 0.16
478 | TT24390 | Maruti Hakke | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Automation test case discussion meeting with team | Test Script Preparation | 2024-09-02 | 01:00:00 | 00:40:48 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:58 | 2024-09-02 19:54:58 | 1 | 0.68
479 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
480 | TT25148 | Maruti Hakke | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Sales Return Figma KT to Developers & Testers | KT Session | 2024-09-12 | 00:10:00 | 00:07:36 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 15:10:15 | 2024-09-12 15:10:15 | 0.17 | 0.13
481 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (2th Sep - 6th Sep) | Sync call with Team | 2024-09-02 | 01:15:00 | 00:49:37 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:00:01 | 2024-09-06 13:00:01 | 1.25 | 0.83
482 | TT24208 | Maruti Hakke | Testing_DPOS_Practice_Oct24_WK1 | 2024-09-30 | 2024-10-06 | CRM AND KARAGIR REPAIR PRACTICE | D Practice | 2024-09-02 | 01:15:00 | 00:56:40 | 2024-09-02 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-03 10:58:12 | 2024-09-03 10:58:12 | 1.25 | 0.94
483 | TT22455 | Maruti Hakke | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Gift Voucher Sale Bill Code Review | Code Review | 2024-10-09 | 01:00:00 | 00:00:00 | 2024-10-12 |  | TO_DO | TO_DO |  |  | 1 | 0
484 | TT22455 | Maruti Hakke | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Gift Voucher Test case modification review | Review updated Test cases | 2024-09-27 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-01 19:30:00 | 2024-10-01 19:30:00 | 0 | 0
485 | TT22455 | Maruti Hakke | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Gift Voucher Test case review | Review Test cases | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-24 14:48:48 | 2024-09-24 14:48:48 | 0 | 0
486 | TT22455 | Maruti Hakke | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Gift Card document reading | Document Reading | 2024-09-24 | 01:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 09:24:44 | 2024-09-25 09:24:44 | 1 | 0
487 | TT22455 | Maruti Hakke | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Gift Voucher-Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-24 16:22:06 | 2024-09-24 16:22:06 | 0 | 0
488 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD Report Modification | Automation Script Execution/modification | 2024-10-03 | 01:15:00 | 01:18:47 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 20:06:02 | 2024-10-03 20:06:02 | 1.25 | 1.31
489 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | Sprint Planning | General meeting | 2024-10-09 | 00:30:00 | 00:42:17 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 15:18:45 | 2024-10-09 15:18:45 | 0.5 | 0.7
490 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD purchase test script | Script Execution/ Modification | 2024-09-28 | 07:00:00 | 07:11:35 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 22:58:42 | 2024-09-28 22:58:42 | 7 | 7.19
491 | TT22402 | Maruti Hakke | - | - | - | SWGP Scheme New CR KT | KT Session | 2024-09-27 | 00:33:00 | 00:38:57 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:17:47 | 2024-09-27 15:17:47 | 0.55 | 0.65
492 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD Support from Sayali Script | Query clarification | 2024-10-07 | 00:30:00 | 00:15:55 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 21:33:39 | 2024-10-07 21:33:39 | 0.5 | 0.27
493 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD Purchase Test Script | Script Execution/ Modification | 2024-09-25 | 19:00:00 | 09:43:52 | 2024-09-27 |  | COMPLETED | DELAY | 2024-09-28 23:00:09 | 2024-09-28 23:00:09 | 19 | 9.73
494 | TT25629 | Maruti Hakke | - | - | - | Lumsam and mrp, Sterling rate | Demo | 2024-09-26 | 00:30:00 | 00:21:58 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 17:01:38 | 2024-09-26 17:01:38 | 0.5 | 0.37
495 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD purchase Test script E2E | Test Automation Script Preparation | 2024-10-07 | 09:00:00 | 05:33:23 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS |  |  | 9 | 5.56
496 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD IMPS Flow Support By MK | Query clarification | 2024-09-25 | 01:00:00 | 00:21:48 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 17:38:46 | 2024-09-25 17:38:46 | 1 | 0.36
497 | TT18735 | Maruti Hakke | - | - | - | Bil to Bil adjustment receipt scripts | Test Script Preparation | 2024-09-27 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-24 14:45:37 | 2024-09-24 14:45:37 | 0 | 0
498 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD Purchase support | Query clarification | 2024-10-09 | 01:00:00 | 01:06:44 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 20:43:24 | 2024-10-09 20:43:24 | 1 | 1.11
499 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD Purchase Data creation Scripting | Test Script Preparation | 2024-09-24 | 05:45:00 | 06:57:44 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 10:30:39 | 2024-09-25 10:30:39 | 5.75 | 6.96
500 | TT18735 | Maruti Hakke | - | - | - | Receipt Module Scripts | Script Execution/ Modification | 2024-09-23 | 00:00:00 | 00:49:52 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-23 23:50:07 | 2024-09-23 23:50:07 | 0 | 0.83
501 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD purchase Bugs Review and Reporting | Reporting Review | 2024-10-10 | 02:00:00 | 06:44:10 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 21:34:34 |  | 2 | 6.74
502 | TT22442 | Maruti Hakke | - | - | - | TT22442 - Invoice Script Code Review | Script review | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-24 14:47:57 | 2024-09-24 14:47:57 | 0 | 0
503 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD Purchase Test case 1 to 5 Execute Script | Automation Script Execution/modification | 2024-10-04 | 06:15:00 | 04:32:21 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:59:07 | 2024-10-04 22:59:07 | 6.25 | 4.54
504 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | Test case Modification Review | Review updated Test cases | 2024-09-23 | 00:00:00 | 00:00:00 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 11:36:44 | 2024-09-24 11:36:44 | 0 | 0
505 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Test case Execution | Testing. | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-24 14:41:57 | 2024-09-24 14:41:57 | 0 | 0
506 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | Urd purchase test case modification review | Review updated Test cases | 2024-09-19 | 00:30:00 | 00:25:43 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 18:59:29 | 2024-09-19 18:59:29 | 0.5 | 0.43
507 | TT24598 | Maruti Hakke | - | - | - | Customer Creation test case modification | Test case updation\modification | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 14:42:05 | 2024-09-24 14:42:05 | 0 | 0
508 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:45:43 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 2 | 0.76
509 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD purchase test case review | Test Case Review | 2024-09-19 | 02:00:00 | 02:13:40 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 09:42:47 | 2024-09-19 09:42:47 | 2 | 2.23
510 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 2 | 0
511 | TT23819 | Maruti Hakke | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | TT23819 - URD exchange and purchase brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:00:00 | 01:11:21 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 16:20:37 | 2024-09-11 16:20:37 | 1 | 1.19
512 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-23 | 01:00:00 | 00:47:19 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 01:40:00 | 2024-09-24 01:40:00 | 1 | 0.79
513 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 0
514 | TT18735 | Maruti Hakke | - | - | - | Cash receipt module script updation | Script Execution/ Modification | 2024-09-20 | 02:30:00 | 05:11:36 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 00:05:41 | 2024-09-21 00:05:41 | 2.5 | 5.19
515 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Branch visit meeting with HR | HR meeting | 2024-10-10 | 01:00:00 | 00:50:54 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 15:36:25 | 2024-10-10 15:36:25 | 1 | 0.85
516 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS sync call | Daily Sync Call | 2024-09-30 | 01:30:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 1.5 | 0
517 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Test case writing | Test case writing- | 2024-10-03 | 04:00:00 | 06:38:38 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 19:56:02 | 2024-10-04 19:56:02 | 4 | 6.64
518 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 2309 to 2709 | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:16:12 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:30 | 2024-09-27 19:54:30 | 2.5 | 3.27
519 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Document Reading | Document Reading | 2024-09-19 | 01:00:00 | 00:27:05 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 17:33:27 | 2024-09-20 17:33:27 | 1 | 0.45
520 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Discussion with preeti ma'am | Conflict resolution meeting | 2024-10-09 | 00:30:00 | 00:00:00 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 20:26:19 | 2024-10-09 20:26:19 | 0.5 | 0
521 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for next week | Task Scheduling | 2024-09-27 | 01:00:00 | 01:52:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:58:39 | 2024-09-27 19:58:39 | 1 | 1.88
522 | TT18735 | Maruti Hakke | - | - | - | TT18735 - Receipt module Test Script Preparation | Test Script Preparation | 2024-09-12 | 07:15:00 | 23:15:11 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 14:33:14 | 2024-09-18 14:33:14 | 7.25 | 23.25
523 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Estimate | Estimate the requirement | 2024-09-19 | 01:00:00 | 01:00:28 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:38:49 | 2024-09-20 17:38:49 | 1 | 1.01
524 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | daily sync call POS testers | Sync call with Team | 2024-10-07 | 01:00:00 | 00:26:13 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 16:19:46 |  | 1 | 0.44
525 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for next week | Task Scheduling | 2024-09-20 | 01:00:00 | 01:29:35 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 19:57:00 | 2024-09-21 19:57:00 | 1 | 1.49
526 | TT22442 | Maruti Hakke | - | - | - | Tax Page Scripting (all module ) | Test Script Preparation | 2024-09-10 | 11:00:00 | 14:54:27 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-14 16:22:44 | 2024-09-14 16:22:44 | 11 | 14.91
527 | TT23350 | Maruti Hakke | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:25:07 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.42
528 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
529 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 1809 to 2009 | Daily Sync Call | 2024-09-18 | 01:30:00 | 00:54:24 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:25:59 | 2024-09-20 22:25:59 | 1.5 | 0.91
530 | TT22402 | Maruti Hakke | - | - | - | Scheme creation and Installment TPOS Brainstorming and scenario listing | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:30:00 | 00:25:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:59:50 | 2024-09-11 17:59:50 | 1.5 | 0.43
531 | TT24598 | Maruti Hakke | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:41:29 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0.69
532 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
533 | TT14931 | Maruti Hakke | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
534 | TT24670 | Maruti Hakke | - | - | - | customer advance brainstorming | Brainstorming | 2024-09-19 | 00:30:00 | 00:44:25 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:04 | 2024-09-19 17:01:04 | 0.5 | 0.74
535 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:51:08 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 1 | 0.85
536 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:50:08 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.84
537 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for Next Week | Task Scheduling | 2024-09-13 | 01:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 18:43:15 | 2024-09-16 18:43:15 | 1 | 0
538 | TT22456 | Maruti Hakke | - | - | - | Karagir repair sale bill test script execution | Script Execution/ Modification | 2024-09-05 | 12:00:00 | 13:48:45 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-12 11:43:36 | 2024-09-12 11:43:36 | 12 | 13.81
539 | TT22442 | Maruti Hakke | - | - | - | Tax Page Test Script Modification | Script Execution/ Modification | 2024-09-18 | 03:00:00 | 03:39:21 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 22:32:02 | 2024-09-18 22:32:02 | 3 | 3.66
540 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Walk in interview support | Interview | 2024-09-30 | 12:00:00 | 22:10:55 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 12 | 22.18
541 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
542 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 0909 to 1309 | Daily Sync Call | 2024-09-09 | 02:30:00 | 01:39:24 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:52 | 2024-09-13 18:56:52 | 2.5 | 1.66
543 | TT25976 | Maruti Hakke | Rate Display on POS Document Creation | 2024-10-07 | 2024-10-08 | Rate Display on TPOS KT to Testers | KT Session | 2024-10-09 | 00:12:00 | 00:06:46 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 17:19:37 | 2024-10-09 17:19:37 | 0.2 | 0.11
544 | TT18735 | Maruti Hakke | - | - | - | TT18735 - Receipt Module Test Script Execution | Script Execution/ Modification | 2024-09-13 | 03:45:00 | 02:38:02 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 22:44:53 | 2024-09-18 22:44:53 | 3.75 | 2.63
545 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Sprint KT to team | KT from BA | 2024-09-24 | 00:34:00 | 00:17:34 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:24:50 | 2024-09-24 18:24:50 | 0.57 | 0.29
546 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Karagir repair KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:23:42 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:39 | 2024-09-02 19:54:39 | 1 | 0.4
547 | TT22456 | Maruti Hakke | - | - | - | Karagir repair sale bill test script preparation | Test Script Preparation | 2024-09-02 | 09:15:00 | 08:08:58 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 19:19:10 | 2024-09-06 19:19:10 | 9.25 | 8.15
548 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (23rd - 27th Sep) | Sync call with Team | 2024-09-23 | 01:15:00 | 00:50:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:04:20 | 2024-09-27 20:04:20 | 1.25 | 0.84
549 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | CRM KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:11:05 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:40:58 | 2024-09-02 23:40:58 | 1 | 0.18
550 | TT22402 | Maruti Hakke | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
551 | TT25148 | Prathamesh Kulkarni | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Sales Return Figma KT to Developers & Testers | KT Session | 2024-09-12 | 00:10:00 | 00:07:36 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 15:10:15 | 2024-09-12 15:10:15 | 0.17 | 0.13
552 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (9th Sep - 13th Sep) | Sync call with Team | 2024-09-09 | 01:15:00 | 00:48:09 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:23 | 2024-09-13 19:33:23 | 1.25 | 0.8
553 | TT23350 | Prathamesh Kulkarni | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:25:07 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.42
554 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
555 | TT24598 | Prathamesh Kulkarni | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:49:04 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0.82
556 | TT22455 | Prathamesh Kulkarni | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Gift Voucher-Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-24 16:22:06 | 2024-09-24 16:22:06 | 0 | 0
557 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (2th Sep - 6th Sep) | Sync call with Team | 2024-09-02 | 01:15:00 | 01:08:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:00:01 | 2024-09-06 13:00:01 | 1.25 | 1.14
558 | TT24670 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Support. | 2024-09-20 | 00:45:00 | 00:21:27 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:26:33 | 2024-09-20 19:26:33 | 0.75 | 0.36
559 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance positive flow scripting | Test script execution | 2024-09-20 | 03:00:00 | 03:08:17 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 09:16:46 | 2024-09-24 09:16:46 | 3 | 3.14
560 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance testcase writing | Test Case Writing | 2024-09-19 | 03:00:00 | 02:37:36 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 18:44:04 | 2024-09-20 18:44:04 | 3 | 2.63
561 | TT24208 | Prathamesh Kulkarni | Testing_DPOS_Practice_Oct24_WK1 | 2024-09-30 | 2024-10-06 | CRM and karargir repair practice | D Practice | 2024-09-02 | 01:15:00 | 00:35:43 | 2024-09-02 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-04 09:48:31 | 2024-09-04 09:48:31 | 1.25 | 0.6
562 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance brainstorming | Brainstorming | 2024-09-19 | 00:30:00 | 00:44:25 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:04 | 2024-09-19 17:01:04 | 0.5 | 0.74
563 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme creation and installment execution | Testing | 2024-09-19 | 04:30:00 | 04:27:06 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 20:07:50 | 2024-09-19 20:07:50 | 4.5 | 4.45
564 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:46:45 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 2 | 0.78
565 | TT22402 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Mentoring | 2024-09-18 | 00:30:00 | 00:10:48 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 22:00:49 | 2024-09-18 22:00:49 | 0.5 | 0.18
566 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 1809 to 2009 | Daily Sync Call | 2024-09-18 | 01:30:00 | 01:01:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:25:59 | 2024-09-20 22:25:59 | 1.5 | 1.02
567 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 2 | 0
568 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for Next Week | Task Scheduling | 2024-09-13 | 01:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 18:43:15 | 2024-09-16 18:43:15 | 1 | 0
569 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 01:48:09 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 1.8
570 | TT22442 | Prathamesh Kulkarni | - | - | - | TT22442-Estimate Module Data Preparation | Data Preparation | 2024-09-18 | 01:00:00 | 01:00:29 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 18:03:26 | 2024-09-18 18:03:26 | 1 | 1.01
571 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 0909 to 1309 | Daily Sync Call | 2024-09-09 | 02:30:00 | 01:20:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:52 | 2024-09-13 18:56:52 | 2.5 | 1.33
572 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
573 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS sync call | Daily Sync Call | 2024-09-30 | 02:00:00 | 00:25:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 2 | 0.43
574 | TT22402 | Prathamesh Kulkarni | - | - | - | Scheme creation and installment test case modification | Test Case Writing | 2024-09-18 | 02:00:00 | 02:15:55 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 23:15:56 | 2024-09-18 23:15:56 | 2 | 2.27
575 | TT23819 | Prathamesh Kulkarni | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | TT23819 - URD exchange and purchase brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:00:00 | 01:00:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 16:20:37 | 2024-09-11 16:20:37 | 1 | 1.01
576 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
577 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 2309 to 2709 | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:17:08 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:30 | 2024-09-27 19:54:30 | 2.5 | 3.29
578 | TT22442 | Prathamesh Kulkarni | - | - | - | TT22442-Data Preparation For Estimate Module For Different Product groups | Data Preparation | 2024-09-13 | 00:45:00 | 00:34:32 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 14:52:15 | 2024-09-16 14:52:15 | 0.75 | 0.58
579 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Karagir repair KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:23:42 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:39 | 2024-09-02 19:54:39 | 1 | 0.4
580 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for next week | Task Scheduling | 2024-09-27 | 01:00:00 | 01:52:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:58:39 | 2024-09-27 19:58:39 | 1 | 1.88
581 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme creation and installment test case writing | Test Case Writing | 2024-09-12 | 04:00:00 | 03:55:54 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:15 | 2024-09-13 18:56:15 | 4 | 3.93
582 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | CRM KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:11:05 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:40:58 | 2024-09-02 23:40:58 | 1 | 0.18
583 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for next week | Task Scheduling | 2024-09-20 | 01:00:00 | 01:31:09 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 19:57:00 | 2024-09-21 19:57:00 | 1 | 1.52
584 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme creation and installment go through KT session recording | KT Session | 2024-09-12 | 00:30:00 | 00:26:06 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-13 09:12:32 | 2024-09-13 09:12:32 | 0.5 | 0.44
585 | TT22402 | Prathamesh Kulkarni | - | - | - | Scheme creation and Installment TPOS Brainstorming and scenario listing | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:30:00 | 00:25:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:59:50 | 2024-09-11 17:59:50 | 1.5 | 0.43
586 | TT14931 | Prathamesh Kulkarni | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
587 | TT22442 | Prathamesh Kulkarni | - | - | - | Estimate module automation using DTO | Automation. | 2024-09-02 | 22:45:00 | 21:52:17 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-17 10:12:38 | 2024-09-17 10:12:38 | 22.75 | 21.87
588 | TT22402 | Prathamesh Kulkarni | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
589 | TT24670 | Prathamesh Kulkarni | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 0.43
590 | TT22394 | Prathamesh Kulkarni | - | - | - | URD Purchase Exchange KT | KT Session | 2024-09-03 | 00:45:00 | 00:31:22 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:41:20 | 2024-09-03 18:41:20 | 0.75 | 0.52
591 | TT23939 | Prathamesh Kulkarni | - | - | - | POS Sync Call 0209 to 0609 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:10:12 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:13:52 | 2024-09-06 18:13:52 | 2.5 | 2.17
592 | TT24390 | Prathamesh Kulkarni | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Automation test case discussion meeting with team | Test Script Preparation | 2024-09-02 | 01:00:00 | 00:40:48 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:58 | 2024-09-02 19:54:58 | 1 | 0.68
593 | TT23939 | Prathamesh Kulkarni | - | - | - | Task Scheduling for 06 Next Week | Task Scheduling | 2024-09-06 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:23:33 | 2024-09-06 19:23:33 | 1 | 0
594 | TT24390 | Prathamesh Kulkarni | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to Prathamesh from sayali | Support. | 2024-09-03 | 04:00:00 | 02:56:21 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:32:49 | 2024-09-06 17:32:49 | 4 | 2.94
595 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Branch visit meeting with HR | HR meeting | 2024-10-10 | 01:00:00 | 00:50:54 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 15:36:25 | 2024-10-10 15:36:25 | 1 | 0.85
596 | TT25961 | Prathamesh Kulkarni | Gift card Redeem 1 | 2024-10-07 | 2024-10-31 | gift voucher redemption execution | E2E Testing | 2024-10-10 | 03:00:00 | 02:50:20 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 3 | 2.84
597 | TT25961 | Prathamesh Kulkarni | Gift card Redeem 1 | 2024-10-07 | 2024-10-31 | gift voucher redemption test case modification | Test Case Writing | 2024-10-09 | 02:00:00 | 02:53:03 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 22:48:51 | 2024-10-09 22:48:51 | 2 | 2.88
598 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | daily sync call POS testers | Sync call with Team | 2024-10-07 | 01:00:00 | 00:41:27 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 16:19:46 |  | 1 | 0.69
599 | TT25961 | Prathamesh Kulkarni | Gift card Redeem 1 | 2024-10-07 | 2024-10-31 | gift voucher redemption test case writing | Testing | 2024-10-08 | 04:30:00 | 03:29:46 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 19:39:31 | 2024-10-08 19:39:31 | 4.5 | 3.5
600 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
601 | TT25961 | Prathamesh Kulkarni | Gift card Redeem 1 | 2024-10-07 | 2024-10-31 | gift voucher redemption estimation | Estimate calculation | 2024-10-07 | 00:45:00 | 00:28:14 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:23:17 | 2024-10-07 19:23:17 | 0.75 | 0.47
602 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
603 | TT25629 | Prathamesh Kulkarni | - | - | - | Lumsam and mrp, Sterling rate | Demo | 2024-09-26 | 00:30:00 | 00:21:58 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 17:01:38 | 2024-09-26 17:01:38 | 0.5 | 0.37
604 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance support to prathamesh | Query clarification | 2024-10-07 | 03:00:00 | 02:58:23 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-08 17:45:24 |  | 3 | 2.97
605 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:51:08 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 0.75 | 0.85
606 | TT22453 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Technical guidance/Process Input | 2024-09-25 | 03:00:00 | 01:12:36 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:57:16 | 2024-09-27 19:57:16 | 3 | 1.21
607 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance retesting 1 | Bug Retesting | 2024-10-09 | 03:00:00 | 00:15:57 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-10 16:29:17 |  | 3 | 0.27
608 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Sprint KT to team | KT from BA | 2024-09-24 | 00:34:00 | 00:17:34 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:24:50 | 2024-09-24 18:24:50 | 0.57 | 0.29
609 | TT22453 | Prathamesh Kulkarni | - | - | - | customer order automation | Test Script Preparation | 2024-09-23 | 27:30:00 | 26:03:53 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-03 11:29:00 | 2024-10-03 11:29:00 | 3.5 | 2.06
610 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance scripting | Test Script Preparation | 2024-09-30 | 19:00:00 | 11:28:36 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-09 18:44:14 |  | 19 | 11.48
611 | TT25976 | Prathamesh Kulkarni | Rate Display on POS Document Creation | 2024-10-07 | 2024-10-08 | Rate Display on TPOS KT to Testers | KT Session | 2024-10-09 | 00:12:00 | 00:06:46 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 17:19:37 | 2024-10-09 17:19:37 | 0.2 | 0.11
612 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (23rd - 27th Sep) | Sync call with Team | 2024-09-23 | 01:15:00 | 00:50:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:04:20 | 2024-09-27 20:04:20 | 1.25 | 0.84
613 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme sale bill retesting | Testing | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-25 19:35:12 | 2024-09-25 19:35:12 | 0 | 0
614 | TT24670 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Query clarification | 2024-10-03 | 02:00:00 | 01:40:38 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:19:19 | 2024-10-04 20:19:19 | 2 | 1.68
615 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:41:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.7
616 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme estimate retesting | Testing. | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:36:03 | 2024-09-25 19:36:03 | 0 | 0
617 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (18th - 20th Sep) | Sync call with Team | 2024-09-18 | 01:30:00 | 00:14:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:26:13 | 2024-09-20 22:26:13 | 1.5 | 0.24
618 | TT24670 | Prathamesh Kulkarni | - | - | - | Customer advance test case modification | Test Case Writing | 2024-09-23 | 01:30:00 | 01:43:59 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 12:55:49 | 2024-09-23 12:55:49 | 1.5 | 1.73
619 | TT25975 | Prathamesh Kulkarni | Scheme Discount Bifurcation | 2024-10-07 | 2024-10-08 | Scheme Discount Bifurcation KT to Dev & Testers | KT Session | 2024-10-09 | 00:30:00 | 00:43:37 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 16:46:27 | 2024-10-09 16:46:27 | 0.5 | 0.73
620 | TT22402 | Prathamesh Kulkarni | - | - | - | SWGP Scheme New CR KT | KT Session | 2024-09-27 | 00:33:00 | 00:38:57 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:17:47 | 2024-09-27 15:17:47 | 0.55 | 0.65
621 | TT25148 | Prathamesh Kulkarni | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Sales return Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-10-09 | 01:00:00 | 00:35:21 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 20:43:41 | 2024-10-09 20:43:41 | 1 | 0.59
622 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | support to prathamesh | Technical guidance/Process Input | 2024-09-11 | 02:00:00 | 00:25:11 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:02 | 2024-09-13 19:33:02 | 2 | 0.42
623 | TT24670 | Prathamesh Kulkarni | - | - | - | Customer advance test case execution | Testing. | 2024-09-24 | 04:30:00 | 00:22:11 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 11:38:03 | 2024-09-24 11:38:03 | 4.5 | 0.37
624 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Self development Discussion- sayali | Testing Team Meeting | 2024-10-08 | 00:15:00 | 00:23:09 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:44:36 | 2024-10-08 16:44:36 | 0.25 | 0.39
625 | TT21914 | Preeti Bokade | - | - | - | support to sayali | Query clarification | 2024-09-02 | 02:30:00 | 01:32:12 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:04:13 | 2024-09-06 18:04:13 | 2.5 | 1.54
626 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA-KPI : Self improvement meeting | Query clarification | 2024-10-08 | 00:15:00 | 00:16:04 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:21:33 | 2024-10-08 16:21:33 | 0.25 | 0.27
627 | TT22402 | Preeti Bokade | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
628 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflit meeting against task scheduling | Testing Team Meeting | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:07:17 | 2024-10-07 19:07:17 | 0.5 | 0
629 | TT24670 | Preeti Bokade | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 02:56:46 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 2.95
630 | TT24427 | Preeti Bokade | E2E Testing | 2024-09-30 | 2024-10-12 | Doc Module Sync call | Daily Sync Call | 2024-09-26 | 00:30:00 | 01:37:11 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:48:06 | 2024-09-27 18:48:06 | 0.5 | 1.62
631 | TT24207 | Preeti Bokade | Testing_D365_Practice_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Going through Masters KT- recording listening | Explore the existing system. | 2024-09-06 | 00:40:00 | 01:13:56 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:31:58 | 2024-09-06 16:31:58 | 0.67 | 1.23
632 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
633 | TT21914 | Preeti Bokade | - | - | - | Support from Preeti Ma'am. | Query clarification | 2024-09-02 | 02:30:00 | 04:45:39 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-08 23:15:06 | 2024-09-06 19:27:58 | 2.5 | 4.76
634 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 01:00:00 | 00:07:47 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 23:48:07 |  | 1 | 0.13
635 | TT21914 | Preeti Bokade | - | - | - | Support from Gaurav sir | Query clarification | 2024-08-30 | 09:30:00 | 17:06:26 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 23:03:49 | 2024-09-30 23:03:49 | 9.5 | 17.11
636 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:47 | 2024-10-06 23:46:47 | 0 | 0
637 | TT23782 | Preeti Bokade | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 01:17:59 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 1.3
638 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:20 | 2024-10-06 23:45:20 | 0 | 0
639 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:10 | 2024-10-06 23:45:10 | 0 | 0
640 | TT24216 | Preeti Bokade | Testing_Skill Upgrade_Oct24_Wk1 | 2024-09-30 | 2024-10-04 | Explore BDD concept through Youtube | Explore New things\other | 2024-09-10 | 02:00:00 | 01:20:12 | 2024-09-11 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-16 07:32:05 | 2024-09-16 07:32:05 | 2 | 1.34
641 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:59 | 2024-10-06 23:46:59 | 0 | 0
642 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:43:31 | 2024-10-06 23:43:31 | 1 | 0
643 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Sayali | Query clarification | 2024-10-07 | 01:00:00 | 03:04:30 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 3.08
644 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Query clarification with BA | Brainstorming with DEV Team \BA | 2024-09-19 | 00:15:00 | 00:13:36 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 15:36:18 | 2024-09-19 15:36:18 | 0.25 | 0.23
645 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | My CS Test case review | Review Test cases | 2024-09-13 | 01:00:00 | 05:40:46 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 14:07:25 | 2024-09-16 14:07:25 | 1 | 5.68
646 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Amreen | Query clarification | 2024-10-08 | 00:45:00 | 02:01:54 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.75 | 2.03
647 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Review estimation | Estimation Review | 2024-09-05 | 00:30:00 | 00:31:44 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:50:07 | 2024-09-05 19:50:07 | 0.5 | 0.53
648 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 03:19:24 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 3.32
649 | TT23155 | Preeti Bokade | - | - | - | Power BI meeting | General meeting | 2024-10-08 | 00:20:00 | 00:56:28 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:41:36 | 2024-10-08 16:41:36 | 0.33 | 0.94
650 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:45 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
651 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | New scheme Enrollment Brain storming | Brainstorming | 2024-09-05 | 00:30:00 | 00:50:05 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 17:48:00 | 2024-09-05 17:48:00 | 0.5 | 0.83
652 | TT24148 | Preeti Bokade | - | - | - | Regularization issue testing task | Application Support | 2024-09-25 | 01:00:00 | 00:33:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 18:07:35 | 2024-09-25 18:07:35 | 1 | 0.55
653 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
654 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | Go through the document | Document Reading | 2024-09-03 | 00:40:00 | 01:12:51 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 20:34:42 | 2024-09-03 20:34:42 | 0.67 | 1.21
655 | TT21914 | Preeti Bokade | - | - | - | Prepare the Function point on Ticketing system ( Reusable purpose) | Estimate the requirement | 2024-09-26 | 04:00:00 | 00:14:17 | 2024-09-30 |  | IN_PROGRESS | DELAY |  |  | 4 | 0.24
656 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Walk in Drive - Interview ( Automation Tester) | Interview | 2024-09-30 | 14:00:00 | 10:07:17 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:21:45 | 2024-10-04 20:21:45 | 14 | 10.12
657 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | 2024-10-01 | 2024-10-31 | New scheme Enrollment KT | KT Session | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:26:28 | 2024-09-04 13:26:28 | 0.75 | 0
658 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:22:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0.38
659 | TT21914 | Preeti Bokade | - | - | - | KRA -KPI relevant action plan with Gokul & Sayali | Explore Team capability/Improvement plan | 2024-09-23 | 02:00:00 | 00:56:14 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 20:31:38 | 2024-09-24 20:31:38 | 2 | 0.94
660 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Amreen - Support from Preeti Ma'am. | Query clarification | 2024-09-30 | 02:00:00 | 00:03:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:56 | 2024-10-04 20:47:56 | 2 | 0.06
661 | TT21914 | Preeti Bokade | - | - | - | Automation Tester Interview | Interview | 2024-09-23 | 05:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:00:18 | 2024-09-27 23:00:18 | 5 | 0
662 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | General discussion on Dashboard(Power BI Report) | Explore the existing system | 2024-09-26 | 00:27:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 18:52:44 | 2024-09-26 18:52:44 | 0.45 | 0
663 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Digvijay about connect us 2.0 (Masters , except customer mapping ) | Internal KT/cross KT | 2024-10-07 | 04:00:00 | 25:55:13 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 19:47:56 | 2024-10-08 19:47:56 | 4 | 1.92
664 | TT21914 | Preeti Bokade | - | - | - | Support to Gokul | Query clarification | 2024-09-23 | 02:30:00 | 00:43:06 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:53:43 | 2024-09-27 19:53:43 | 2.5 | 0.72
665 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0
666 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil(Reports- user task , variance, Resource planning) | Internal KT/cross KT | 2024-09-27 | 02:00:00 | 00:44:03 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-29 23:01:25 | 2024-09-29 23:01:25 | 2 | 0.73
667 | TT21914 | Preeti Bokade | - | - | - | Support to Sayali | Query clarification | 2024-09-23 | 02:30:00 | 00:21:15 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:39 | 2024-09-27 19:54:39 | 2.5 | 0.35
668 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Weekly sync call with Gaurav sir | Weekly sync call | 2024-10-09 | 01:00:00 | 00:52:32 | 2024-10-09 |  | COMPLETED | DELAY | 2024-10-10 12:17:16 | 2024-10-10 12:17:16 | 1 | 0.88
669 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:04:06 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 3.07
670 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil(My Ticket) | Internal KT/cross KT | 2024-09-26 | 01:30:00 | 00:46:54 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 14:12:21 | 2024-09-26 14:12:21 | 1.5 | 0.78
671 | TT21914 | Preeti Bokade | - | - | - | Amreen - Support from Preeti ma'am | Query clarification | 2024-09-23 | 02:30:00 | 03:45:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:51:17 | 2024-09-27 20:51:17 | 2.5 | 3.75
672 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Resource planning Report analysis | Performance analysis and improvement plan | 2024-10-07 | 01:36:00 | 00:57:15 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 15:00:48 |  | 1.6 | 0.95
673 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 01:00:00 | 00:16:27 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 13:31:36 |  | 1 | 0.27
674 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil (Customer Mapping , Create Ticket) | Internal KT/cross KT | 2024-09-25 | 01:30:00 | 01:26:26 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:54:56 | 2024-09-25 22:54:56 | 1.5 | 1.44
675 | TT24598 | Preeti Bokade | - | - | - | estimation review | Estimation Review | 2024-09-19 | 00:30:00 | 00:43:03 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 20:41:40 | 2024-09-20 20:41:40 | 0.5 | 0.72
676 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:37:53 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.63
677 | TT23495 | Preeti Bokade | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Review estimation | Estimation Review | 2024-10-10 | 01:00:00 | 00:00:00 | 2024-10-10 |  | TO_DO | TO_DO | 2024-10-09 19:11:44 |  | 1 | 0
678 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:38 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
679 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil( Tenant Master, Dynamic form, Dropdown master, Query Type Master) | Internal KT/cross KT | 2024-09-24 | 02:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:03:39 | 2024-09-24 19:03:39 | 2 | 0
680 | TT21914 | Preeti Bokade | - | - | - | Automation Tester Interview | Interview | 2024-09-19 | 00:45:00 | 01:07:23 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:45:16 | 2024-09-19 17:45:16 | 0.75 | 1.12
681 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support By Preeti ma'am | Mentoring | 2024-09-02 | 02:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-02 14:41:34 | 2024-09-02 14:41:34 | 2.5 | 0
682 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Support from Gaurav sir | Query clarification | 2024-10-07 | 01:36:00 | 00:00:00 | 2024-10-31 |  | TO_DO | TO_DO |  |  | 1.6 | 0
683 | TT23495 | Preeti Bokade | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Footer / Setting Discussion KT | KT Session | 2024-10-07 | 00:30:00 | 00:58:55 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:21:38 | 2024-10-07 13:21:38 | 0.5 | 0.98
684 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 01:08:10 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 1.14
685 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil (User Master, Customer Master, Role Master, Designation Master) | Internal KT/cross KT | 2024-09-23 | 02:00:00 | 00:41:06 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 12:18:43 | 2024-09-23 12:18:43 | 2 | 0.69
686 | TT23350 | Preeti Bokade | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:21:23 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.36
687 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
688 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Resource planning report analysis | Performance analysis and improvement plan | 2024-10-03 | 01:00:00 | 01:13:23 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-06 00:19:32 | 2024-10-06 00:19:32 | 1 | 1.22
689 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 02:19:28 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 2.32
690 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Estimation KT to Swapnil | Internal KT/cross KT | 2024-09-06 | 00:45:00 | 00:50:56 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:53:10 | 2024-09-06 18:53:10 | 0.75 | 0.85
691 | TT24598 | Preeti Bokade | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:00:00 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0
692 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Weekly meeting with gaurav sir 20th Sep | Weekly sync call | 2024-09-20 | 01:00:00 | 00:00:36 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:50:01 | 2024-09-20 20:50:01 | 1 | 0.01
693 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Weekly sync call with Gaurav sir | Weekly sync call | 2024-09-25 | 01:00:00 | 01:24:13 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-27 19:32:25 | 2024-09-27 19:32:25 | 1 | 1.4
694 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:15:00 | 00:56:30 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1.25 | 0.94
695 | TT23932 | Preeti Bokade | Sprint 1 | 2024-07-30 | 2024-08-31 | AS BC Discussions | General meeting | 2024-09-06 | 00:30:00 | 00:29:19 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 14:16:41 | 2024-09-06 14:16:41 | 0.5 | 0.49
696 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
697 | TT21914 | Preeti Bokade | - | - | - | Sayali - Support task | Query clarification | 2024-09-19 | 01:00:00 | 00:02:03 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:40:40 | 2024-09-20 20:40:40 | 1 | 0.03
698 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 03:23:12 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 3.39
699 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Weekly sync call with Gaurav sir | Meeting with PH | 2024-09-18 | 01:00:00 | 00:44:26 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 17:32:12 | 2024-09-18 17:32:12 | 1 | 0.74
700 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:13:01 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40 | 0.17 | 0.22
701 | TT21914 | Preeti Bokade | - | - | - | Automation interview - 16sept | Interview | 2024-09-16 | 01:30:00 | 01:37:37 | 2024-09-16 |  | COMPLETED | DELAY | 2024-09-18 15:32:49 | 2024-09-18 15:32:49 | 1.5 | 1.63
702 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Weekly sync call with Gaurav sir | Meeting with PH | 2024-09-11 | 01:00:00 | 00:04:03 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 23:29:13 | 2024-09-11 23:29:13 | 1 | 0.07
703 | TT21914 | Preeti Bokade | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-18 | 01:30:00 | 00:50:22 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:59:00 | 2024-09-20 20:59:00 | 1.5 | 0.84
704 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Weekly sync Report preparation | Weekly sync call report | 2024-09-11 | 01:00:00 | 02:59:46 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 23:29:56 | 2024-09-11 23:29:56 | 1 | 3
705 | TT21914 | Preeti Bokade | - | - | - | support to gokul | Query clarification | 2024-09-09 | 02:30:00 | 02:50:18 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:36:02 | 2024-09-13 22:36:02 | 2.5 | 2.84
706 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Resource planning task analysis | Explore Team capability/Improvement plan | 2024-09-09 | 01:00:00 | 02:13:52 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 15:41:29 | 2024-09-09 15:41:29 | 1 | 2.23
707 | TT21914 | Preeti Bokade | - | - | - | support to sayali | Query clarification | 2024-09-09 | 02:00:00 | 01:52:46 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:43 | 2024-09-13 19:33:43 | 2 | 1.88
708 | TT21405 | Preeti Bokade | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | Go through the document | Document Reading | 2024-10-10 | 00:40:00 | 00:31:55 | 2024-10-10 |  | COMPLETED | IN_TIME | 2024-10-10 13:59:10 | 2024-10-10 13:59:10 | 0.67 | 0.53
709 | TT21914 | Preeti Bokade | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-09 | 02:30:00 | 23:11:49 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:19 | 2024-09-13 20:11:19 | 2.5 | 23.2
710 | TT21405 | Preeti Bokade | Sprint 1 for phase 1 | 2024-10-07 | 2024-10-14 | KT for item Counter mapping Bulk upload at 3.30pm | KT Session | 2024-10-10 | 01:00:00 | 00:00:00 | 2024-10-10 |  | TO_DO | TO_DO | 2024-10-09 18:41:52 |  | 1 | 0
711 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Testing team sync call | Testing Team Meeting | 2024-10-08 | 01:30:00 | 02:10:31 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 17:07:38 |  | 1.5 | 2.18
712 | TT21914 | Preeti Bokade | - | - | - | support to Gokul | Query clarification | 2024-09-02 | 02:30:00 | 01:00:09 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:29:04 | 2024-09-06 19:29:04 | 2.5 | 1
713 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Selef improvement discussion- Gokul | Testing Team Meeting | 2024-10-08 | 00:15:00 | 00:20:23 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 22:51:20 | 2024-10-08 22:51:20 | 0.25 | 0.34
714 | TT18255 | Saurabh Shelke | - | - | - | Support Point To vaishnavi | Technical guidance/Process Input | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:16:14 | 2024-09-09 19:16:14 | 0 | 0
715 | TT24771 | Saurabh Shelke | - | - | - | Support from Saurabh(Size master) | Query clarification | 2024-09-19 | 00:30:00 | 00:25:09 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 18:28:15 | 2024-09-19 18:28:15 | 0.5 | 0.42
716 | TT21899 | Saurabh Shelke | - | - | - | (Iteration 2) Set Tag Retesting | Retesting | 2024-09-11 | 04:30:00 | 04:05:47 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:14:12 | 2024-09-13 19:14:12 | 4.5 | 4.1
717 | TT24760 | Saurabh Shelke | - | - | - | Support from saurabh | Query clarification | 2024-09-20 | 00:15:00 | 00:20:35 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 18:11:21 | 2024-09-20 18:11:21 | 0.25 | 0.34
718 | TT26038 | Saurabh Shelke | - | - | - | Sprint Sathi Discussion & Sprint Define For Ticket | Estimate calculation | 2024-10-10 | 01:00:00 | 01:07:50 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 1.13
719 | TT21945 | Saurabh Shelke | - | - | - | LM PO check Positive Flow Scripting | Automate test script | 2024-09-11 | 12:40:00 | 14:22:22 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 11:05:41 | 2024-09-16 11:05:41 | 12.67 | 14.37
720 | TT23985 | Saurabh Shelke | - | - | - | Iteration 2 Stock Repair Retesting | Retesting | 2024-09-20 | 03:30:00 | 02:39:09 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:41:17 | 2024-09-20 19:41:17 | 3.5 | 2.65
721 | TT26038 | Saurabh Shelke | - | - | - | Support from Saurabh - P2P process testing (platinum, SS) | Query clarification | 2024-10-10 | 00:20:00 | 00:00:00 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 18:55:14 |  | 0.33 | 0
722 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair retesting | Retesting | 2024-09-10 | 03:00:00 | 02:37:03 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-12 12:07:21 | 2024-09-12 12:07:21 | 3 | 2.62
723 | TT22911 | Saurabh Shelke | - | - | - | Batch Registration Positive Flow Scripting | Automate test script | 2024-09-18 | 11:15:00 | 11:28:46 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:39:36 | 2024-09-20 19:39:36 | 11.25 | 11.48
724 | TT23053 | Saurabh Shelke | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 01:45:56 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 1.77
725 | TT21945 | Saurabh Shelke | - | - | - | HM , LM Stage (QC process) Positive flow Scripting | Automate test script | 2024-09-09 | 08:30:00 | 07:55:26 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-11 15:39:48 | 2024-09-11 15:39:48 | 8.5 | 7.92
726 | TT22823 | Saurabh Shelke | - | - | - | Karagir nave jama new CR estimation - Review | Review | 2024-09-09 | 00:30:00 | 00:42:42 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:45:00 | 2024-09-09 19:45:00 | 0.5 | 0.71
727 | TT21945 | Saurabh Shelke | - | - | - | P2P Process - Support from Saurabh | Support. | 2024-10-07 | 00:30:00 | 00:34:08 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:07:51 | 2024-10-07 19:07:51 | 0.5 | 0.57
728 | TT22785 | Saurabh Shelke | - | - | - | Lot tag testcase review | Review Test cases | 2024-10-01 | 00:45:00 | 00:32:39 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:47:43 | 2024-10-01 15:47:43 | 0.75 | 0.54
729 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair retesting | Retesting | 2024-10-10 | 01:30:00 | 01:53:01 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 18:49:36 |  | 1.5 | 1.88
730 | TT22830 | Saurabh Shelke | - | - | - | Kariger requirement discussion | Requirement gathering | 2024-09-04 | 02:00:00 | 01:51:02 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 18:00:50 | 2024-09-04 18:00:50 | 2 | 1.85
731 | TT22830 | Saurabh Shelke | - | - | - | Support Point to Kiran Karagir jama | Query clarification | 2024-10-03 | 01:00:00 | 00:24:40 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:36 | 2024-10-04 19:41:36 | 1 | 0.41
732 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair TC Scripting (60 %) | Automate test script | 2024-10-07 | 05:45:00 | 03:05:31 | 2024-10-13 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-10 16:41:23 |  | 5.75 | 3.09
733 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair Retesting | Retesting | 2024-09-11 | 01:15:00 | 01:15:49 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-05 19:02:15 | 2024-09-05 19:02:15 | 1.25 | 1.26
734 | TT22830 | Saurabh Shelke | - | - | - | karagir nave TC review | Review. | 2024-10-01 | 00:45:00 | 00:27:53 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 16:16:17 | 2024-10-01 16:16:17 | 0.75 | 0.46
735 | TT21945 | Saurabh Shelke | - | - | - | P2P -QC Process Bug Review | Test Case Review | 2024-10-07 | 00:45:00 | 00:36:54 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 18:40:12 | 2024-10-07 18:40:12 | 0.75 | 0.62
736 | TT21899 | Saurabh Shelke | - | - | - | Set Tag Bug Discussion | Brainstorming with DEV Team \BA | 2024-09-03 | 00:45:00 | 00:49:32 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 17:02:33 | 2024-09-03 17:02:33 | 0.75 | 0.83
737 | TT22830 | Saurabh Shelke | - | - | - | Support Point to Kiran Karagir Nave | Support. | 2024-10-01 | 00:30:00 | 00:26:17 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:43 | 2024-10-01 19:02:43 | 0.5 | 0.44
738 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama (PO Check , LM & HM Centre) TC Review | Test Case Review | 2024-10-07 | 00:30:00 | 00:49:03 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 16:05:46 | 2024-10-07 16:05:46 | 0.5 | 0.82
739 | TT22830 | Saurabh Shelke | - | - | - | Support Point Karagir Nave/Jama | Support. | 2024-09-02 | 02:30:00 | 01:29:09 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:57:15 | 2024-09-06 19:57:15 | 2.5 | 1.49
740 | TT24776 | Saurabh Shelke | - | - | - | Support from Saurabh(Agent Master) | Query clarification | 2024-09-30 | 00:30:00 | 00:25:24 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:56:57 | 2024-09-30 19:56:57 | 0.5 | 0.42
741 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama (DC , QC & HM) test case review | Review Test cases | 2024-10-07 | 00:30:00 | 00:22:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:39:17 | 2024-10-07 13:39:17 | 0.5 | 0.37
742 | TT21945 | Saurabh Shelke | - | - | - | QC Process (Positive Flow PR , DC ,QC) scripting Using DTO | Test Script Preparation | 2024-09-02 | 19:17:00 | 18:44:18 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-10 15:48:01 | 2024-09-10 15:48:01 | 19.28 | 18.74
743 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:31:00 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 11:33:31 |  | 2 | 0.52
744 | TT21899 | Saurabh Shelke | - | - | - | Support from gokul - Set tag module | Query clarification | 2024-09-30 | 01:00:00 | 00:39:16 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:05 | 2024-10-01 19:34:05 | 1 | 0.65
745 | TT22830 | Saurabh Shelke | - | - | - | Support Point karagir Jama to Kiran | Query clarification | 2024-10-07 | 00:30:00 | 00:00:11 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 18:52:21 |  | 0.5 | 0
746 | TT18255 | Saurabh Shelke | - | - | - | Automation Support URD | Technical guidance/Process Input | 2024-09-02 | 01:30:00 | 01:16:18 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:41:38 | 2024-09-05 19:41:38 | 1.5 | 1.27
747 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:50:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 1.84
748 | TT23782 | Saurabh Shelke | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
749 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling for Next Week | Task Scheduling | 2024-09-26 | 01:00:00 | 02:11:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:21:29 | 2024-09-27 17:21:29 | 1 | 2.18
750 | TT24680 | Saurabh Shelke | - | - | - | subsmith master - test script review | Test script review | 2024-09-30 | 00:30:00 | 00:21:07 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:41:52 | 2024-09-30 19:41:52 | 0.5 | 0.35
751 | TT22830 | Saurabh Shelke | - | - | - | Karagir nave jama TCS review | Test Case Review | 2024-09-02 | 02:00:00 | 01:42:17 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 19:25:50 | 2024-09-03 19:25:50 | 2 | 1.7
752 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:08:40 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.14
753 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 01:00:00 | 00:23:43 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 19:18:04 |  | 1 | 0.4
754 | TT24680 | Saurabh Shelke | - | - | - | Support from gokul for Subsmith master script | Technical guidance/Process Input | 2024-09-30 | 00:30:00 | 00:20:55 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:17:23 | 2024-09-30 19:17:23 | 0.5 | 0.35
755 | TT23782 | Saurabh Shelke | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
756 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 02:00:00 | 01:41:54 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 2 | 1.7
757 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
758 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama positive flow (BR process Old process Scripting) | Automate test script | 2024-09-28 | 03:30:00 | 03:20:53 | 2024-09-28 |  | COMPLETED | DELAY | 2024-09-29 12:34:05 | 2024-09-29 12:34:05 | 3.5 | 3.35
759 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling for Next Week | Task Scheduling | 2024-09-19 | 01:00:00 | 00:36:54 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:40:27 | 2024-09-20 19:40:27 | 1 | 0.62
760 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
761 | TT22830 | Saurabh Shelke | - | - | - | karagir jama (Po raise old process) Positive flow | Automate test script | 2024-09-28 | 03:30:00 | 03:47:52 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 16:01:40 | 2024-09-28 16:01:40 | 3.5 | 3.8
762 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:27:58 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.47
763 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:36:59 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.62
764 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama - Provisional Parcel ,All vendors & Job work metal rate TC Writting | Test Case Writing | 2024-10-03 | 05:45:00 | 06:37:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:01:10 | 2024-10-04 19:01:10 | 5.75 | 6.63
765 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling for next Week | Task Scheduling | 2024-09-12 | 01:00:00 | 01:00:44 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 13:10:47 | 2024-09-13 13:10:47 | 1 | 1.01
766 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:38 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
767 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama Brainstorming | Brainstorming with DEV Team/BA | 2024-10-03 | 00:45:00 | 00:39:24 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:47:04 | 2024-10-03 18:47:04 | 0.75 | 0.66
768 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:22:27 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 2.37
769 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 01:45:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 1.75
770 | TT22830 | Saurabh Shelke | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
771 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling for next Week | Task Scheduling | 2024-09-05 | 01:00:00 | 01:10:50 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:56:45 | 2024-09-06 19:56:45 | 1 | 1.18
772 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:52:46 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.88
773 | TT22830 | Saurabh Shelke | - | - | - | Karagir Nave BrainStroming | Brainstorming with DEV Team/BA | 2024-09-30 | 00:15:00 | 00:13:50 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 15:35:06 | 2024-09-30 15:35:06 | 0.25 | 0.23
774 | TT24672 | Saurabh Shelke | Dev to Handover Config master | 2024-10-09 | 2024-10-22 | Configuration Master bugsheet review | Reporting Review | 2024-09-30 | 00:30:00 | 00:16:40 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 16:14:05 | 2024-09-30 16:14:05 | 0.5 | 0.28
775 | TT23932 | Saurabh Shelke | Sprint 1 | 2024-07-30 | 2024-08-31 | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:18 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
776 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:30:23 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.51
777 | TT22830 | Saurabh Shelke | - | - | - | Karagir nave Jama Scripting Support By Gokul | Technical guidance/Process Input | 2024-09-24 | 02:00:00 | 01:53:07 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 16:04:23 | 2024-09-27 16:04:23 | 2 | 1.89
778 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
779 | TT22830 | Saurabh Shelke | - | - | - | Karagir nave Positive Flow Scripting | Automate test script | 2024-09-24 | 09:44:00 | 10:26:25 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-03 17:19:17 | 2024-10-03 17:19:17 | 9.73 | 10.44
780 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
781 | TT24760 | Saurabh Shelke | - | - | - | Bank Master Test Case Review | Review Test cases | 2024-09-23 | 00:30:00 | 00:22:56 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 16:52:37 | 2024-09-24 16:52:37 | 0.5 | 0.38
782 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 01:13:42 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 1.23
783 | TT23985 | Saurabh Shelke | - | - | - | Support From Gokul | Technical guidance/Process Input | 2024-10-03 | 01:00:00 | 00:00:40 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:58 | 2024-10-04 19:41:58 | 1 | 0.01
784 | TT21945 | Saurabh Shelke | - | - | - | Automation support from gokul | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:24:18 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-25 14:04:22 | 2024-09-25 14:04:22 | 0.5 | 0.41
785 | TT21945 | Saurabh Shelke | - | - | - | QC Process (PR , DC , QC) TC Scripting | Automate test script | 2024-09-23 | 03:30:00 | 06:13:36 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-26 13:40:57 | 2024-09-26 13:40:57 | 3.5 | 6.23
786 | TT22200 | Saurabh Shelke | - | - | - | Job Work Charges Master Retesting | Retesting | 2024-09-24 | 03:30:00 | 02:53:11 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:45:06 | 2024-09-24 19:45:06 | 3.5 | 2.89
787 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair Positive flow Scripting | Automate test script | 2024-09-30 | 11:45:00 | 11:31:54 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:02:42 | 2024-10-04 19:02:42 | 11.75 | 11.53
788 | TT24206 | Saurabh Shelke | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
789 | TT24206 | Saurabh Shelke | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
790 | TT24774 | Saurabh Shelke | - | - | - | KT New development-HM pcs adjustment field in RNG Process | KT Session | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 12:26:03 | 2024-09-26 12:26:03 | 0 | 0
791 | TT24683 | Saurabh Shelke | - | - | - | PCS Adjustment KT by snehal | KT Session | 2024-09-23 | 01:00:00 | 00:50:48 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 13:58:07 | 2024-09-23 13:58:07 | 1 | 0.85
792 | TT24920 | Saurabh Shelke | - | - | - | Iteration 3 Set Tag Retesting | Retesting | 2024-09-25 | 04:30:00 | 05:15:47 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:21:00 | 2024-09-27 17:21:00 | 4.5 | 5.26
793 | TT21945 | Saurabh Shelke | - | - | - | Support for QC Multiple Lines to Vaishnavi | Query clarification | 2024-09-23 | 02:30:00 | 02:16:53 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 11:53:13 | 2024-09-27 11:53:13 | 2.5 | 2.28
794 | TT14931 | Saurabh Shelke | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:14 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
795 | TT24771 | Saurabh Shelke | - | - | - | Size Master TC Review | Test Case Review | 2024-09-23 | 01:15:00 | 00:44:00 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 12:27:18 | 2024-09-24 12:27:18 | 1.25 | 0.73
796 | TT23939 | Sayali Vyawahare | - | - | - | Task Scheduling for 06 Next Week | Task Scheduling | 2024-09-06 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:23:33 | 2024-09-06 19:23:33 | 1 | 0
797 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | D to TPOS scripting integration and modification (DTO) | Script Execution/ Modification | 2024-09-02 | 02:45:00 | 02:31:19 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:56:09 | 2024-09-03 23:56:09 | 2.75 | 2.52
798 | TT24670 | Sayali Vyawahare | - | - | - | support to prathamesh | Query clarification | 2024-10-03 | 02:00:00 | 01:40:38 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:19:19 | 2024-10-04 20:19:19 | 2 | 1.68
799 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:30:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0.5
800 | TT25148 | Sayali Vyawahare | Sales Return Advance & Utilization Demo | 2024-10-08 | 2024-10-09 | Sales return Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-10-09 | 01:00:00 | 00:35:22 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 20:43:41 | 2024-10-09 20:43:41 | 1 | 0.59
801 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Automation test case discussion meeting with team | Test Script Preparation | 2024-09-02 | 01:00:00 | 00:40:48 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:58 | 2024-09-02 19:54:58 | 1 | 0.68
802 | TT22455 | Sayali Vyawahare | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Modified Test cases review(Gift Voucher) | Review Test cases | 2024-10-04 | 00:15:00 | 00:18:16 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 17:10:37 | 2024-10-04 17:10:37 | 0.25 | 0.3
803 | TT22442 | Sayali Vyawahare | - | - | - | Fresh sale bill scripting (gold, silver, diamond jewellery) | Test Script Preparation | 2024-09-25 | 14:00:00 | 13:34:14 | 2024-09-30 |  | COMPLETED | DELAY | 2024-10-01 22:44:23 | 2024-10-01 22:44:23 | 14 | 13.57
804 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | meeting with gaurav sir regarding duplicate code | Meeting with PH | 2024-09-23 | 01:00:00 | 01:00:00 | 2024-09-23 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-24 18:06:25 | 2024-09-24 13:49:11 | 1 | 1
805 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to Prathamesh from sayali | Support. | 2024-09-03 | 03:00:00 | 03:05:28 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:32:49 | 2024-09-06 17:32:49 | 3 | 3.09
806 | TT22455 | Sayali Vyawahare | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Test Case Review-Gift Card | Review Test cases | 2024-10-03 | 01:30:00 | 01:35:35 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 23:44:25 | 2024-10-03 23:44:25 | 1.5 | 1.59
807 | TT22402 | Sayali Vyawahare | - | - | - | SWGP Scheme New CR KT | KT Session | 2024-09-27 | 00:33:00 | 00:38:57 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:17:47 | 2024-09-27 15:17:47 | 0.55 | 0.65
808 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:22:34 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 2.38
809 | TT22455 | Sayali Vyawahare | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Gift Voucher Sale Brainstorming | Brainstorming - Internal (Within Team member) | 2024-10-01 | 00:45:00 | 00:34:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:25:36 | 2024-10-01 15:25:36 | 0.75 | 0.58
810 | TT25629 | Sayali Vyawahare | - | - | - | Lumsam and mrp, Sterling rate | Demo | 2024-09-26 | 00:30:00 | 00:21:59 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 17:01:38 | 2024-09-26 17:01:38 | 0.5 | 0.37
811 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 01:00:00 | 00:16:29 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 13:31:36 |  | 1 | 0.27
812 | TT22455 | Sayali Vyawahare | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Gift Voucher-Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-24 16:22:06 | 2024-09-24 16:22:06 | 0 | 0
813 | TT22453 | Sayali Vyawahare | - | - | - | Customer order code review | Script review | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-24 16:23:10 | 2024-09-24 16:23:10 | 0 | 0
814 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (23rd - 27th Sep) | Sync call with Team | 2024-09-23 | 01:15:00 | 00:49:04 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:04:20 | 2024-09-27 20:04:20 | 1.25 | 0.82
815 | TT22455 | Sayali Vyawahare | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Gift card sales bill KT | KT Session | 2024-10-01 | 00:30:00 | 00:33:43 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 13:14:33 | 2024-10-01 13:14:33 | 0.5 | 0.56
816 | TT22453 | Sayali Vyawahare | - | - | - | support to prathamesh | Technical guidance/Process Input | 2024-09-25 | 03:00:00 | 01:12:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:57:16 | 2024-09-27 19:57:16 | 3 | 1.21
817 | TT24208 | Sayali Vyawahare | Testing_DPOS_Practice_Oct24_WK1 | 2024-09-30 | 2024-10-06 | CRM and Karagir repair practice review | Review | 2024-09-03 | 01:00:00 | 00:38:06 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 19:37:49 | 2024-09-03 19:37:49 | 1 | 0.64
818 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:41:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.7
819 | TT22402 | Sayali Vyawahare | - | - | - | Scheme sale bill bugs review | Reporting Review | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-24 16:21:20 | 2024-09-24 16:21:20 | 0 | 0
820 | TT24208 | Sayali Vyawahare | Testing_DPOS_Practice_Oct24_WK1 | 2024-09-30 | 2024-10-06 | Vastu jama and vastu jama Practice review | Review | 2024-09-03 | 01:15:00 | 01:06:52 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:39:08 | 2024-09-03 18:39:08 | 1.25 | 1.11
821 | TT22455 | Sayali Vyawahare | Gift card sales 1 | 2024-10-07 | 2024-10-22 | TT22455-Bug review(Gift card) | Reporting Review | 2024-10-07 | 02:00:00 | 02:30:39 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 23:42:32 | 2024-10-07 23:42:32 | 2 | 2.51
822 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 01:08:10 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 1.14
823 | TT22455 | Sayali Vyawahare | Gift card sales 1 | 2024-10-07 | 2024-10-22 | Gift voucher creation scripting | Test Script Preparation | 2024-09-04 | 08:00:00 | 08:30:21 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-10 11:41:48 | 2024-09-10 11:41:48 | 8 | 8.51
824 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (18th - 20th Sep) | Sync call with Team | 2024-09-18 | 01:30:00 | 00:14:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:26:13 | 2024-09-20 22:26:13 | 1.5 | 0.24
825 | TT21914 | Sayali Vyawahare | - | - | - | KRA -KPI relevant action plan with Gokul & Sayali | Explore Team capability/Improvement plan | 2024-09-23 | 02:00:00 | 01:02:26 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 20:31:38 | 2024-09-24 20:31:38 | 2 | 1.04
826 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Script report demo to Gaurav Sir | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:14 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:39:57 | 2024-09-20 19:39:57 | 1 | 0.27
827 | TT21914 | Sayali Vyawahare | - | - | - | Support to Sayali | Query clarification | 2024-09-23 | 02:30:00 | 00:21:15 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:39 | 2024-09-27 19:54:39 | 2.5 | 0.35
828 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 01:08:45 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 1.15
829 | TT24598 | Sayali Vyawahare | - | - | - | Customer Creation Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-23 | 01:00:00 | 00:47:19 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 01:40:00 | 2024-09-24 01:40:00 | 1 | 0.79
830 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Weekly meeting with gaurav sir 20th Sep | Weekly sync call | 2024-09-20 | 01:00:00 | 01:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:50:01 | 2024-09-20 20:50:01 | 1 | 1
831 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call | Daily Sync Call | 2024-10-07 | 02:00:00 | 01:14:12 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 2 | 1.24
832 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | support to prathamesh | Technical guidance/Process Input | 2024-09-11 | 02:00:00 | 00:42:20 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:02 | 2024-09-13 19:33:02 | 2 | 0.71
833 | TT24598 | Sayali Vyawahare | - | - | - | Customer Creation Test Case Review | Review Test cases | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 14:42:34 | 2024-09-24 14:42:34 | 0 | 0
834 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 02:27:18 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 2.46
835 | TT23819 | Sayali Vyawahare | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD Support from Sayali Script | Query clarification | 2024-10-07 | 00:30:00 | 00:15:55 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 21:33:39 | 2024-10-07 21:33:39 | 0.5 | 0.27
836 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 2 | 0
837 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:00:00 | 00:57:22 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1 | 0.96
838 | TT21914 | Sayali Vyawahare | - | - | - | Sayali - Support task | Query clarification | 2024-09-19 | 01:00:00 | 00:02:03 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:40:40 | 2024-09-20 20:40:40 | 1 | 0.03
839 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance bugs review | Reporting Review | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 16:19:08 | 2024-09-24 16:19:08 | 0 | 0
840 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (2th Sep - 6th Sep) | Sync call with Team | 2024-09-02 | 01:15:00 | 01:08:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:00:01 | 2024-09-06 13:00:01 | 1.25 | 1.14
841 | TT23819 | Sayali Vyawahare | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | TT23819 - URD exchange and purchase brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:00:00 | 01:11:21 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 16:20:37 | 2024-09-11 16:20:37 | 1 | 1.19
842 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (9th Sep - 13th Sep) | Sync call with Team | 2024-09-09 | 01:00:00 | 01:56:31 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:23 | 2024-09-13 19:33:23 | 1 | 1.94
843 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation and Installment TPOS bug review | Reporting Review | 2024-09-19 | 02:00:00 | 02:15:56 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 12:50:18 | 2024-09-20 12:50:18 | 2 | 2.27
844 | TT23350 | Sayali Vyawahare | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:25:07 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.42
845 | TT23819 | Sayali Vyawahare | URD PURCHASE AND EXCHANGE | 2024-10-08 | 2024-10-22 | URD estimation review | Estimation Review | 2024-09-05 | 00:15:00 | 00:22:00 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 18:55:39 | 2024-09-05 18:55:39 | 0.25 | 0.37
846 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 02:22:18 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 2.37
847 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
848 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation test case review after modification | Review updated Test cases | 2024-09-19 | 00:30:00 | 00:34:40 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 20:07:16 | 2024-09-19 20:07:16 | 0.5 | 0.58
849 | TT24598 | Sayali Vyawahare | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:49:04 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0.82
850 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS sync call | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:11:55 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 2 | 1.2
851 | TT22402 | Sayali Vyawahare | - | - | - | support to prathamesh | Mentoring | 2024-09-18 | 00:30:00 | 00:16:45 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 22:00:49 | 2024-09-18 22:00:49 | 0.5 | 0.28
852 | TT24670 | Sayali Vyawahare | - | - | - | support to prathamesh | Support. | 2024-09-20 | 00:45:00 | 00:25:12 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:26:33 | 2024-09-20 19:26:33 | 0.75 | 0.42
853 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 2309 to 2709 | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:17:08 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:30 | 2024-09-27 19:54:30 | 2.5 | 3.29
854 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:03:24 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.06
855 | TT22442 | Sayali Vyawahare | - | - | - | Payment mode validations scripting (UPI, card, cash) | Test Script Preparation | 2024-09-18 | 03:15:00 | 03:10:19 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 22:26:23 | 2024-09-20 22:26:23 | 3.25 | 3.17
856 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance on TPOS test case review | Review Test cases | 2024-09-20 | 01:30:00 | 01:26:02 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:57:06 | 2024-09-20 23:57:06 | 1.5 | 1.43
857 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for next week | Task Scheduling | 2024-09-27 | 01:00:00 | 01:52:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:58:39 | 2024-09-27 19:58:39 | 1 | 1.88
858 | TT22402 | Sayali Vyawahare | - | - | - | Scheme pos entry and instalment test case review | Review Test cases | 2024-09-13 | 01:30:00 | 01:26:39 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-15 20:58:40 | 2024-09-15 20:58:40 | 1.5 | 1.44
859 | TT24670 | Sayali Vyawahare | - | - | - | customer advance brainstorming | Brainstorming | 2024-09-19 | 00:30:00 | 00:44:25 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:04 | 2024-09-19 17:01:04 | 0.5 | 0.74
860 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for next week | Task Scheduling | 2024-09-20 | 01:00:00 | 00:58:41 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 19:57:00 | 2024-09-21 19:57:00 | 1 | 0.98
861 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 1809 to 2009 | Daily Sync Call | 2024-09-18 | 01:30:00 | 00:54:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:25:59 | 2024-09-20 22:25:59 | 1.5 | 0.91
862 | TT22402 | Sayali Vyawahare | - | - | - | Scheme estimation positive flow scripting | Test Script Preparation | 2024-09-10 | 04:30:00 | 04:30:49 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 16:20:51 | 2024-09-24 16:20:51 | 4.5 | 4.51
863 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | Task Scheduling for Next Week | Task Scheduling | 2024-09-13 | 01:00:00 | 00:02:02 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 18:43:15 | 2024-09-16 18:43:15 | 1 | 0.03
864 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation and Installment TPOS Brainstorming and scenario listing | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:30:00 | 00:25:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:59:50 | 2024-09-11 17:59:50 | 1.5 | 0.43
865 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | 2024-10-07 | 2024-10-11 | POS Sync Call 0909 to 1309 | Daily Sync Call | 2024-09-09 | 02:00:00 | 01:27:32 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:52 | 2024-09-13 18:56:52 | 2 | 1.46
866 | TT22442 | Sayali Vyawahare | - | - | - | POS Payment mode scripting (positive scenario) | Test Script Preparation | 2024-09-09 | 08:00:00 | 08:35:57 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-13 13:01:03 | 2024-09-13 13:01:03 | 8 | 8.6
867 | TT21914 | Sayali Vyawahare | - | - | - | support to sayali | Query clarification | 2024-09-09 | 02:00:00 | 00:51:02 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:43 | 2024-09-13 19:33:43 | 2 | 0.85
868 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Testing team sync call | Testing Team Meeting | 2024-10-08 | 01:30:00 | 01:26:50 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 17:07:38 |  | 1.5 | 1.45
869 | TT14931 | Sayali Vyawahare | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:01 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
870 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
871 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Self development Discussion- sayali | Testing Team Meeting | 2024-10-08 | 00:15:00 | 00:23:09 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:44:36 | 2024-10-08 16:44:36 | 0.25 | 0.39
872 | TT23782 | Sayali Vyawahare | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:05:00 | 00:03:51 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.08 | 0.06
873 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
874 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | daily sync call POS testers | Sync call with Team | 2024-10-07 | 01:00:00 | 00:41:27 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 16:19:46 |  | 1 | 0.69
875 | TT21914 | Sayali Vyawahare | - | - | - | support to sayali | Query clarification | 2024-09-02 | 02:30:00 | 01:01:25 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:04:13 | 2024-09-06 18:04:13 | 2.5 | 1.02
876 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Karagir repair KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:23:42 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:39 | 2024-09-02 19:54:39 | 1 | 0.4
877 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
878 | TT22442 | Sayali Vyawahare | - | - | - | Cancel Estimation scripting | Test Script Preparation | 2024-09-05 | 04:00:00 | 04:11:48 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:03:53 | 2024-09-06 18:03:53 | 4 | 4.2
879 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Sayali | Query clarification | 2024-10-07 | 01:00:00 | 03:08:11 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 3.14
880 | TT22442 | Sayali Vyawahare | - | - | - | Estimation module code review | Script review | 2024-09-04 | 03:00:00 | 01:18:26 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-13 09:59:39 | 2024-09-13 09:59:39 | 3 | 1.31
881 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance bugs review | Reporting Review | 2024-10-10 | 01:00:00 | 00:16:30 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 0.28
882 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | CRM KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:11:05 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:40:58 | 2024-09-02 23:40:58 | 1 | 0.18
883 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 0
884 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation and Installment TPOS Estimation | Estimate the requirement | 2024-09-02 | 00:45:00 | 00:23:23 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:54:09 | 2024-09-02 23:54:09 | 0.75 | 0.39
885 | TT25961 | Sayali Vyawahare | Gift card Redeem 1 | 2024-10-07 | 2024-10-31 | gift voucher redemption test case review | Test Case Review | 2024-10-09 | 02:00:00 | 02:01:18 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 15:24:12 | 2024-10-09 15:24:12 | 2 | 2.02
886 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to gokul (for padm scripting) | Query clarification | 2024-10-04 | 01:00:00 | 01:00:00 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-08 11:30:17 | 2024-10-07 18:03:30 | 1 | 1
887 | TT22442 | Sayali Vyawahare | - | - | - | Fresh sale bill scripting modification (10 TC) | Script Execution/ Modification | 2024-10-10 | 01:00:00 | 00:00:00 | 2024-10-13 |  | TO_DO | TO_DO |  |  | 1 | 0
888 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:45 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
889 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance on TPOS Estimation | Estimate the requirement | 2024-09-03 | 00:30:00 | 00:17:20 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-04 15:49:04 | 2024-09-04 15:49:04 | 0.5 | 0.29
890 | TT25961 | Sayali Vyawahare | Gift card Redeem 1 | 2024-10-07 | 2024-10-31 | gift voucher redemption estimation review | Estimate calculation | 2024-10-07 | 00:30:00 | 00:15:13 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 23:49:23 | 2024-10-07 23:49:23 | 0.5 | 0.25
891 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support from sayali | Query clarification | 2024-10-01 | 00:15:00 | 00:08:45 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:01 | 2024-10-01 19:02:01 | 0.25 | 0.15
892 | TT22442 | Sayali Vyawahare | - | - | - | Fresh sale bill payment mode card, cash, UPI scripting modifications | Script Execution/ Modification | 2024-10-08 | 09:00:00 | 05:08:35 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS |  |  | 9 | 5.14
893 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
894 | TT22402 | Sayali Vyawahare | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
895 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Automation Support By SV | Query clarification | 2024-09-26 | 04:00:00 | 07:38:43 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-28 23:01:07 | 2024-09-28 23:01:07 | 4 | 7.65
896 | TT24670 | Sayali Vyawahare | - | - | - | customer advance support to prathamesh | Query clarification | 2024-10-07 | 03:00:00 | 02:58:17 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-08 17:45:24 |  | 3 | 2.97
897 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:58:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 1 | 0.98
898 | TT24670 | Sayali Vyawahare | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 0.43
899 | TT25976 | Sayali Vyawahare | Rate Display on POS Document Creation | 2024-10-07 | 2024-10-08 | Rate Display on TPOS KT to Testers | KT Session | 2024-10-09 | 00:12:00 | 00:06:46 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 17:19:37 | 2024-10-09 17:19:37 | 0.2 | 0.11
900 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Support to dev team for duplicate code | Technical guidance/Process Input | 2024-09-24 | 04:00:00 | 03:33:23 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:04:42 | 2024-09-24 19:04:42 | 4 | 3.56
901 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance order code review | Code Review | 2024-10-03 | 01:30:00 | 01:03:15 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 00:02:19 | 2024-10-04 00:02:19 | 1.5 | 1.05
902 | TT22394 | Sayali Vyawahare | - | - | - | URD Purchase Exchange KT | KT Session | 2024-09-03 | 00:45:00 | 00:31:22 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:41:20 | 2024-09-03 18:41:20 | 0.75 | 0.52
903 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Duplicate code (xpath) on TPOS for all modules | Test Script Preparation | 2024-09-23 | 03:30:00 | 03:09:18 | 2024-09-23 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-24 12:10:21 | 2024-09-24 12:10:21 | 3.5 | 3.16
904 | TT24598 | Sayali Vyawahare | - | - | - | Customer creation test case review | Test Case Review | 2024-10-04 | 01:30:00 | 01:50:43 | 2024-10-07 |  | COMPLETED | DELAY | 2024-10-08 23:59:17 | 2024-10-08 23:59:17 | 1.5 | 1.85
905 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:22:33 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0.38
906 | TT23939 | Sayali Vyawahare | - | - | - | POS Sync Call 0209 to 0609 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:46:15 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:13:52 | 2024-09-06 18:13:52 | 2.5 | 2.77
907 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | List duplicate elements on TPOS | Test Script Preparation | 2024-09-05 | 01:30:00 | 01:20:55 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:59:48 | 2024-09-05 19:59:48 | 1.5 | 1.35
908 | TT24670 | Sayali Vyawahare | - | - | - | customer advance and blanket advance test case execution | E2E Testing | 2024-10-01 | 04:00:00 | 03:47:19 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 22:56:32 | 2024-10-01 22:56:32 | 4 | 3.79
909 | TT25975 | Sayali Vyawahare | Scheme Discount Bifurcation | 2024-10-07 | 2024-10-08 | Scheme Discount Bifurcation KT to Dev & Testers | KT Session | 2024-10-09 | 00:30:00 | 00:43:37 | 2024-10-09 |  | COMPLETED | IN_TIME | 2024-10-09 16:46:27 | 2024-10-09 16:46:27 | 0.5 | 0.73
910 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Sprint KT to team | KT from BA | 2024-09-24 | 00:34:00 | 00:17:34 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:24:50 | 2024-09-24 18:24:50 | 0.57 | 0.29
911 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Retesting Documentation Module | Bug Retesting | 2024-10-03 | 03:00:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY |  |  | 3 | 0
912 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore & practice the connect us 2.0( Customer Mapping , Create Ticket) | Explore the existing system. | 2024-09-25 | 04:00:00 | 01:56:18 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:55:44 | 2024-09-25 22:55:44 | 4 | 1.94
913 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 12:00:00 | 05:45:26 | 2024-10-04 |  | IN_PROGRESS | DELAY | 2024-09-27 20:27:44 |  | 12 | 5.76
914 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil (Customer Mapping , Create Ticket) | Internal KT/cross KT | 2024-09-25 | 01:30:00 | 01:27:01 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:54:56 | 2024-09-25 22:54:56 | 1.5 | 1.45
915 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | RAD for Documentation Module | RAD Testing | 2024-09-16 | 03:00:00 | 04:14:42 | 2024-09-16 |  | COMPLETED | DELAY | 2024-09-27 17:15:40 | 2024-09-27 17:15:40 | 3 | 4.25
916 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore & practice the connect us 2.0( Tenant Master, Dynamic Dropdown, Dynamic Form and Query Type Master) | Explore the existing system. | 2024-09-24 | 01:00:00 | 01:14:09 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 22:57:56 | 2024-09-24 22:57:56 | 1 | 1.24
917 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module Retesting | Retesting | 2024-09-10 | 02:30:00 | 03:28:18 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-27 10:00:55 | 2024-09-13 07:41:09 | 2.5 | 3.47
918 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil( Tenant Master, Dynamic form, Dropdown master, Query Type Master) | Internal KT/cross KT | 2024-09-24 | 02:00:00 | 00:27:31 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:03:39 | 2024-09-24 19:03:39 | 2 | 0.46
919 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:26:29 | 2024-09-06 18:26:29 | 0.75 | 0
920 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore & practice the connect us 2.0( User master, customer master, Role master and designation Master) | Explore the existing system. | 2024-09-23 | 01:00:00 | 01:05:27 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:06:43 | 2024-09-23 23:06:43 | 1 | 1.09
921 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Document module Test case modification | Test case updation\modification | 2024-09-03 | 02:00:00 | 02:39:17 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-06 15:13:08 | 2024-09-06 15:13:08 | 2 | 2.65
922 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil (User Master, Customer Master, Role Master, Designation Master) | Internal KT/cross KT | 2024-09-23 | 02:00:00 | 00:41:06 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 12:18:43 | 2024-09-23 12:18:43 | 2 | 0.69
923 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-02 | 00:44:00 | 00:37:07 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-03 19:29:26 | 2024-09-03 19:29:26 | 0.73 | 0.62
924 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Estimation KT to Swapnil | Internal KT/cross KT | 2024-09-06 | 00:45:00 | 00:42:10 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:53:10 | 2024-09-06 18:53:10 | 0.75 | 0.7
925 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Support to Swapnil for Consolidated report | Query clarification | 2024-09-02 | 01:30:00 | 00:24:07 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:31 | 2024-09-06 17:05:31 | 1.5 | 0.4
926 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
927 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Documentation Module Testing | Testing | 2024-09-02 | 02:30:00 | 04:00:10 | 2024-09-02 |  | COMPLETED | DELAY | 2024-09-03 11:53:14 | 2024-09-03 11:53:14 | 2.5 | 4
928 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Cross KT - Customer view | Internal KT/cross KT | 2024-09-02 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-08-30 20:15:30 | 2024-08-30 20:15:30 | 0 | 0
929 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 00:00:00 | 00:07:50 | 2024-09-16 |  | COMPLETED | IN_TIME | 2024-09-13 16:08:19 | 2024-09-13 16:08:19 | 0 | 0.13
930 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Country Master , State Master , City Master Add + Reflection on Grid | Test Script Preparation | 2024-09-19 | 07:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-24 16:22:16 | 2024-09-24 16:22:16 | 7 | 0
931 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Country Master , State Master , City Master test case Writing | Test Case Writing | 2024-09-12 | 01:30:00 | 00:00:00 | 2024-09-12 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-23 23:03:41 | 2024-09-23 23:03:41 | 1.5 | 0
932 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Customer mapping - Add + edit + reflection on Grid | Test Script Preparation | 2024-09-10 | 00:00:00 | 00:00:00 | 2024-09-12 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-16 11:15:59 | 2024-09-16 11:15:59 | 0 | 0
933 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Customer mapping test case writing | Test Case Writing | 2024-09-09 | 01:00:00 | 10:46:38 | 2024-09-09 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-10 10:53:46 | 2024-09-10 10:53:46 | 1 | 10.78
934 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | test | Application Support | 2024-10-03 | 00:40:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-04 20:50:51 | 2024-10-04 20:50:51 | 0.67 | 0
935 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Automation Script for reading Tool tip text | Test Script Preparation | 2024-09-06 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-12 15:42:11 | 2024-09-12 15:42:11 | 2 | 0
936 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA KPI - go through recording | Internal KT/cross KT | 2024-09-30 | 01:00:00 | 00:00:00 | 2024-09-30 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-04 20:49:11 | 2024-10-04 20:49:11 | 1 | 0
937 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | Customer Master Add Data preparation Add, Edit, View | Test case writing- | 2024-09-06 | 01:30:00 | 02:05:55 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:25:11 | 2024-09-06 20:25:11 | 1.5 | 2.1
938 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Task scheduling | Task Scheduling | 2024-09-06 | 00:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:26:17 | 2024-09-06 20:26:17 | 0.5 | 0
939 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | 2024-10-01 | 2024-10-06 | User Master Add edit negative Scripting | Test Script Preparation | 2024-09-02 | 06:00:00 | 03:42:45 | 2024-09-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-20 19:24:50 | 2024-09-20 19:24:50 | 6 | 3.71
940 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:12:47 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40 | 0.17 | 0.21
941 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CSM + Website Validation writing | Validation writing | 2024-09-27 | 03:00:00 | 03:00:00 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-01 15:05:56 | 2024-09-29 23:02:40 | 3 | 3
942 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
943 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | DSC - CMS | Daily Sync Call | 2024-09-02 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:16:17 | 2024-09-06 17:16:17 | 2 | 0
944 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Menu master, page master, section type master, page section master, page content master, Setting master, - Test case writing | Test Case Writing | 2024-09-30 | 03:30:00 | 01:33:54 | 2024-09-30 |  | IN_PROGRESS | DELAY | 2024-09-27 20:33:10 |  | 3.5 | 1.57
945 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
946 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS - Document Go through | Documentation Reading | 2024-09-23 | 01:00:00 | 00:46:26 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:07:54 | 2024-09-23 23:07:54 | 1 | 0.77
947 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-08 15:07:54 | 2024-10-08 15:07:54 | 0 | 0
948 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CMS KT Session | KT Session | 2024-09-26 | 01:30:00 | 01:30:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:12:46 | 2024-09-27 15:12:46 | 1.5 | 1.5
949 | TT15425 | Swapnil Ramdasi | Sprint 1 | 2023-08-30 | 2024-12-31 | Bill checking transaction - filter testing | Unit Testing | 2024-09-25 | 01:30:00 | 05:01:52 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:55:59 | 2024-09-25 22:55:59 | 1.5 | 5.03
950 | TT23294 | Swapnil Ramdasi | - | - | - | End to End testing for Time Regularization | E2E Testing. | 2024-09-09 | 04:00:00 | 03:58:31 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-10 04:53:21 | 2024-09-10 04:53:21 | 4 | 3.98
951 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Query clarification | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-09 18:59:53 | 2024-09-09 18:59:53 | 0 | 0
952 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01 | 0 | 0
953 | TT15425 | Swapnil Ramdasi | Sprint 1 | 2023-08-30 | 2024-12-31 | Vendor master, Approval setting page, Payment template master -Testing | Unit Testing | 2024-09-23 | 08:00:00 | 11:25:51 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 22:58:14 | 2024-09-24 22:58:14 | 8 | 11.43
954 | TT21914 | Swapnil Ramdasi | - | - | - | Task Scheduling for 9 to 13 Sept | Task Scheduling | 2024-09-06 | 00:30:00 | 00:14:11 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-10 04:53:43 | 2024-09-10 04:53:43 | 0.5 | 0.24
955 | TT23495 | Swapnil Ramdasi | CMS - Menu, Header | 2024-10-09 | 2024-10-24 | CS website - Support to swapnil | Mentoring | 2024-09-03 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:37:15 | 2024-09-06 16:37:15 | 1 | 0
956 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | 2024-09-30 | 2024-10-11 | Document reading | Document Reading | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-08 17:57:30 | 2024-10-08 17:57:30 | 0 | 0
957 | TT24437 | Swapnil Ramdasi | - | - | - | Regularization - Estimation | Estimate the requirement | 2024-09-03 | 00:00:00 | 00:00:00 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-06 17:27:39 | 2024-09-06 17:27:39 | 0 | 0
958 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore and Practice connect us 2.0(Reports-user task, resource planning, Variance) | Explore the existing system. | 2024-10-01 | 00:00:00 | 00:00:09 | 2024-10-13 |  | COMPLETED | IN_TIME | 2024-10-08 19:48:15 | 2024-10-08 19:48:15 | 0 | 0
959 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil(Reports- user task , variance, Resource planning) | Internal KT/cross KT | 2024-09-27 | 02:00:00 | 00:50:24 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-29 23:01:25 | 2024-09-29 23:01:25 | 2 | 0.84
960 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Doc Module Sync call | Daily Sync Call | 2024-10-01 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:26:18 | 2024-10-04 18:26:18 | 1 | 0
961 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Explore and Practice (My Ticket) | Explore the existing system. | 2024-09-26 | 04:00:00 | 04:53:32 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 23:22:18 | 2024-09-26 23:22:18 | 4 | 4.89
962 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | test | Application Support | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-09-27 17:54:38 | 2024-09-27 17:54:38 | 0 | 0
963 | TT24427 | Swapnil Ramdasi | E2E Testing | 2024-09-30 | 2024-10-12 | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-09 16:55:48 | 2024-10-09 16:55:48 | 0 | 0
964 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Swapnil(My Ticket) | Internal KT/cross KT | 2024-09-26 | 01:30:00 | 00:47:13 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 14:12:21 | 2024-09-26 14:12:21 | 1.5 | 0.79
965 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:54:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.91
966 | TT21945 | Vaishnavi Khandwe | - | - | - | DJ- Item P2P process Testing | E2E Testing | 2024-10-04 | 03:00:00 | 04:26:36 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:58:46 | 2024-10-04 19:58:46 | 3 | 4.44
967 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting Gold Purchase (Us-Other) Exchange (Us - Other) | Test Script Preparation | 2024-10-03 | 06:00:00 | 03:03:03 | 2024-10-15 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 16:47:42 |  | 6 | 3.05
968 | TT21945 | Vaishnavi Khandwe | - | - | - | Forming- Item P2P process Testing | E2E Testing | 2024-10-03 | 03:00:00 | 05:10:16 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 19:40:25 | 2024-10-03 19:40:25 | 3 | 5.17
969 | TT24777 | Vaishnavi Khandwe | - | - | - | Qc setup Master Support from gokul | Query clarification | 2024-09-27 | 00:30:00 | 00:56:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:04:11 | 2024-09-27 17:04:11 | 0.5 | 0.93
970 | TT25654 | Vaishnavi Khandwe | - | - | - | Support From Gokul (Pending vendor Invoices) | Technical guidance/Process Input | 2024-09-25 | 00:30:00 | 00:21:55 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:18:12 | 2024-09-25 19:18:12 | 0.5 | 0.37
971 | TT25654 | Vaishnavi Khandwe | - | - | - | Pending vendor Invoices Automation Scripting | Test Script Preparation | 2024-09-25 | 04:00:00 | 03:17:54 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:58:28 | 2024-09-25 19:58:28 | 4 | 3.3
972 | TT25655 | Vaishnavi Khandwe | - | - | - | Support from gokul (Post product receipt ) | Technical guidance/Process Input | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 11:14:00 | 2024-09-25 11:14:00 | 0.5 | 0
973 | TT25655 | Vaishnavi Khandwe | - | - | - | Post Product Receipt Scripting | Test Script Preparation | 2024-09-24 | 04:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 10:52:28 | 2024-09-25 10:52:28 | 4 | 0
974 | TT24777 | Vaishnavi Khandwe | - | - | - | QC Setup master Script positive Flow | Automate test script | 2024-09-27 | 01:45:00 | 01:40:49 | 2024-09-27 |  | COMPLETED | DELAY | 2024-09-30 12:48:28 | 2024-09-30 12:48:28 | 1.75 | 1.68
975 | TT18255 | Vaishnavi Khandwe | - | - | - | Support From Gokul URD | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:54:40 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 19:21:47 | 2024-09-23 19:21:47 | 0.5 | 0.91
976 | TT18255 | Vaishnavi Khandwe | - | - | - | Automation Support URD | Technical guidance/Process Input | 2024-09-02 | 01:30:00 | 00:54:21 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:41:38 | 2024-09-05 19:41:38 | 1.5 | 0.91
977 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting 50 Percent coverage | Script Execution/ Modification | 2024-09-23 | 04:00:00 | 03:45:02 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-25 16:29:54 | 2024-09-25 16:29:54 | 4 | 3.75
978 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Automation Scripting by using DTO | Test Script Preparation | 2024-09-02 | 18:00:00 | 16:19:28 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 20:07:23 | 2024-09-18 20:07:23 | 18 | 16.32
979 | TT24771 | Vaishnavi Khandwe | - | - | - | Automation scripting Size Master Test data Prepare | Test Script Preparation | 2024-09-26 | 01:00:00 | 00:22:42 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-30 12:16:26 | 2024-09-30 12:16:26 | 1 | 0.38
980 | TT23782 | Vaishnavi Khandwe | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
981 | TT24760 | Vaishnavi Khandwe | - | - | - | Automation Support From Gokul Bank Master | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 01:32:31 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 18:48:38 | 2024-09-26 18:48:38 | 0.5 | 1.54
982 | TT23782 | Vaishnavi Khandwe | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
983 | TT24760 | Vaishnavi Khandwe | - | - | - | Bank Master Automation Scripting | Test Script Preparation | 2024-09-26 | 03:00:00 | 03:28:59 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 19:27:16 | 2024-09-26 19:27:16 | 3 | 3.48
984 | TT21945 | Vaishnavi Khandwe | - | - | - | Support for QC Multiple Lines to Vaishnavi | Query clarification | 2024-09-23 | 02:30:00 | 02:50:58 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 11:53:13 | 2024-09-27 11:53:13 | 2.5 | 2.85
985 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 02:00:00 | 00:31:14 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 11:33:31 |  | 2 | 0.52
986 | TT21945 | Vaishnavi Khandwe | - | - | - | Support from Saurabh QC process | Technical guidance/Process Input | 2024-09-23 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-23 10:42:35 | 2024-09-23 10:42:35 | 0 | 0
987 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 00:44:23 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 0.74
988 | TT21945 | Vaishnavi Khandwe | - | - | - | QC Process Multiple Line Retesting | Bug Retesting | 2024-09-23 | 07:00:00 | 08:04:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:03:18 | 2024-09-27 17:03:18 | 7 | 8.08
989 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling next week | Task Scheduling | 2024-10-03 | 01:00:00 | 00:40:01 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 11:04:44 | 2024-10-04 11:04:44 | 1 | 0.67
990 | TT24771 | Vaishnavi Khandwe | - | - | - | Support from Saurabh(Size master) | Query clarification | 2024-09-19 | 00:30:00 | 00:25:24 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 18:28:15 | 2024-09-19 18:28:15 | 0.5 | 0.42
991 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:15:01 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.25
992 | TT24206 | Vaishnavi Khandwe | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
993 | TT18255 | Vaishnavi Khandwe | - | - | - | Support for automation URD from Gokul | Technical guidance/Process Input | 2024-09-19 | 01:00:00 | 02:33:12 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:24 | 2024-09-20 19:48:24 | 1 | 2.55
994 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling | Task Scheduling | 2024-09-26 | 01:00:00 | 01:20:19 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:02:52 | 2024-09-27 17:02:52 | 1 | 1.34
995 | TT24206 | Vaishnavi Khandwe | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
996 | TT24760 | Vaishnavi Khandwe | - | - | - | Support from saurabh | Query clarification | 2024-09-20 | 00:15:00 | 00:20:14 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 18:11:21 | 2024-09-20 18:11:21 | 0.25 | 0.34
997 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling | Task Scheduling | 2024-09-19 | 01:00:00 | 01:15:58 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:48:22 | 2024-09-20 16:48:22 | 1 | 1.27
998 | TT24760 | Vaishnavi Khandwe | - | - | - | Bank Master Test case writing | Test Case Writing | 2024-09-20 | 01:00:00 | 01:02:27 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:08 | 2024-09-20 19:48:08 | 1 | 1.04
999 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 02:00:00 | 01:29:58 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 2 | 1.5
1000 | TT24760 | Vaishnavi Khandwe | - | - | - | Bank Master Estimation | Estimate calculation | 2024-09-19 | 00:15:00 | 00:13:24 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:59:09 | 2024-09-19 17:59:09 | 0.25 | 0.22
1001 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | Task scheduling 13 feb | Task Scheduling | 2024-09-13 | 00:30:00 | 01:45:50 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:09:15 | 2024-09-13 20:09:15 | 0.5 | 1.76
1002 | TT24771 | Vaishnavi Khandwe | - | - | - | Test case writing of size master | Test case writing- | 2024-09-19 | 01:00:00 | 01:16:58 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:59:21 | 2024-09-19 17:59:21 | 1 | 1.28
1003 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 00:30:00 | 00:21:06 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 0.5 | 0.35
1004 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting through test cases | Test Script Preparation | 2024-09-18 | 11:15:00 | 08:24:35 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:19 | 2024-09-20 19:48:19 | 11.25 | 8.41
1005 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | Task Scheduling | Task Scheduling | 2024-09-05 | 00:00:00 | 00:00:00 | 2024-09-05 |  | COMPLETED | HIGHLY_DELAY | 2024-09-06 16:58:42 | 2024-09-06 16:58:42 | 0 | 0
1006 | TT14931 | Vaishnavi Khandwe | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:00:00 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0
1007 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 01:15:18 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 1.26
1008 | TT18255 | Vaishnavi Khandwe | - | - | - | Support Point To vaishnavi | Technical guidance/Process Input | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:16:14 | 2024-09-09 19:16:14 | 0 | 0
1009 | TT23932 | Vaishnavi Khandwe | Sprint 1 | 2024-07-30 | 2024-08-31 | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:18 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
1010 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 01:00:00 | 00:21:43 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 19:18:04 |  | 1 | 0.36
1011 | TT22830 | Vaishnavi Khandwe | - | - | - | Support Point Karagir Nave/Jama | Support. | 2024-09-02 | 02:30:00 | 00:18:45 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:57:15 | 2024-09-06 19:57:15 | 2.5 | 0.31
1012 | TT26038 | Vaishnavi Khandwe | - | - | - | LST- Item P2P process Testing | E2E Testing | 2024-10-08 | 01:45:00 | 01:30:33 | 2024-10-14 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1.75 | 1.51
1013 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34 | 1 | 1.04
1014 | TT22830 | Vaishnavi Khandwe | - | - | - | Silver TCW Karagir Nave Jama (Batch Registration ) | Test Case Writing | 2024-09-02 | 02:45:00 | 02:46:42 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 17:36:27 | 2024-09-06 17:36:27 | 2.75 | 2.78
1015 | TT18255 | Vaishnavi Khandwe | - | - | - | Support from Gokul URD Silver | Support. | 2024-10-05 | 01:00:00 | 01:00:05 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:22:37 | 2024-10-05 23:22:37 | 1 | 1
1016 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
1017 | TT22830 | Vaishnavi Khandwe | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 0
1018 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 00:15:00 | 00:25:32 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 0.25 | 0.43
1019 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting Silver purchase us and other | Test Script Preparation | 2024-10-05 | 06:00:00 | 07:30:42 | 2024-10-05 |  | COMPLETED | DELAY | 2024-10-08 15:03:05 | 2024-10-08 15:03:05 | 6 | 7.51
1020 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Walk in interview support | Interview | 2024-09-30 | 12:00:00 | 04:28:38 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 12 | 4.48
1021 | TT21945 | Vaishnavi Khandwe | - | - | - | P2P Process - Support from Saurabh | Support. | 2024-10-07 | 00:30:00 | 00:34:08 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:07:51 | 2024-10-07 19:07:51 | 0.5 | 0.57
1022 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
1023 | TT21945 | Vaishnavi Khandwe | - | - | - | P2P Process - Support from Gokul | Support. | 2024-10-08 | 00:30:00 | 00:00:00 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:49:54 | 2024-10-08 16:49:54 | 0.5 | 0
1024 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:20:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.34
1025 | TT21945 | Vaishnavi Khandwe | - | - | - | P2P Process Support from Gokul | Query clarification | 2024-10-03 | 01:00:00 | 00:09:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:47 | 2024-10-04 19:08:47 | 1 | 0.16
1026 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:00:00 | 00:34:59 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1 | 0.58
1027 | TT18255 | Vaishnavi Khandwe | - | - | - | Support from Gokul URD Automation | Query clarification | 2024-10-03 | 01:00:00 | 00:43:55 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:23 | 2024-10-04 19:08:23 | 1 | 0.73
1028 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:38 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
1029 | TT21945 | Vaishnavi Khandwe | - | - | - | LST- Item P2P process Testing | E2E Testing | 2024-10-08 | 00:00:00 | 00:00:00 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 10:28:38 | 2024-10-08 10:28:38 | 0 | 0
1030 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 01:57:33 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 1.96
1031 | TT21945 | Vaishnavi Khandwe | - | - | - | GB - Item P2P process Testing | E2E Testing | 2024-10-07 | 04:00:00 | 03:09:11 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:19:28 | 2024-10-08 16:19:28 | 4 | 3.15
1032 | TT18255 | Vaishnavi Khandwe | - | - | - | Support From Gokul URD | Test Script Preparation | 2024-10-07 | 01:00:00 | 01:00:36 | 2024-10-08 |  | COMPLETED | IN_TIME | 2024-10-08 16:19:07 | 2024-10-08 16:19:07 | 1 | 1.01