## data
sr | ticket_id | task_owner | sprint_name | sprint_start_date | sprint_end_date | task_name | type_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | scheduled hrs | Actual hrs
1 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Support to swapnil for automation | Query clarification | 2024-10-04 | 01:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 19:58:44 |  | 1.5 | 0
2 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | - | - | Document reading | Document Reading | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 20:31:31 |  | 0 | 0
3 | TT23495 | Amreen Shaikh | - | - | - | CS website test case review | Review Test cases | 2024-10-04 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 2 | 0
4 | TT23495 | Amreen Shaikh | - | - | - | Review estimation | Estimation Review | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 1 | 0
5 | TT23495 | Amreen Shaikh | - | - | - | Scheduling for upcoming week | Task Scheduling | 2024-10-04 | 00:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 0.5 | 0
6 | TT23495 | Amreen Shaikh | - | - | - | CS Website - Validation review | Test Case Review | 2024-10-03 | 00:45:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 19:16:57 |  | 0.75 | 0
7 | TT23495 | Amreen Shaikh | - | - | - | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 01:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 1.5 | 0
8 | TT23495 | Amreen Shaikh | - | - | - | Menu master, Default setting page & tenant master page - Testing | Unit Testing | 2024-10-02 | 00:00:00 | 00:00:00 | 2024-10-02 |  | COMPLETED | IN_TIME | 2024-09-27 19:26:44 | 2024-09-27 19:26:44 | 0 | 0
9 | TT23495 | Amreen Shaikh | - | - | - | Menu master, Default setting page & tenant master page - Test case writing | Test case writing- | 2024-08-27 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-01 15:05:57 | 2024-09-27 19:06:50 | 0 | 0
10 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Tester interview | Interview | 2024-09-30 | 07:00:00 | 06:35:42 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:20 | 2024-10-01 19:34:20 | 7 | 6.6
11 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 01:30:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 1.5 | 0
12 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Amreen - Support from Preeti Ma'am. | Query clarification | 2024-09-30 | 01:30:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:56 | 2024-10-04 20:47:56 | 1.5 | 0
13 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | Testing - Report preparation | Daily Summary report | 2024-10-03 | 00:15:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 20:30:39 |  | 0.25 | 0
14 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | MyCS Scheme Testing | Unit Testing | 2024-09-25 | 03:30:00 | 00:00:00 | 2024-10-03 |  | IN_PROGRESS | DELAY | 2024-09-27 20:29:37 |  | 3.5 | 0
15 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:30:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 17:53:31 |  | 0.5 | 0
16 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Support to swapnil - report preparation | Daily Summary report | 2024-10-03 | 00:30:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY |  |  | 0.5 | 0
17 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | - | - | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01 | 0 | 0
18 | TT23932 | Amruta Kore | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
19 | TT23932 | Amruta Kore | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 01:30:00 | 01:24:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 1.5 | 1.41
20 | TT23932 | Amruta Kore | Sprint 1 | - | - | Scheduling | Task Scheduling | 2024-10-03 | 01:00:00 | 00:11:57 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-07 09:26:42 | 2024-10-07 09:26:42 | 1 | 0.2
21 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
22 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
23 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:28:21 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 0.75 | 0.47
24 | TT21899 | Amruta Kore | - | - | - | Set Tag Module Scripting - 100 percent | Automate test script | 2024-09-30 | 05:45:00 | 13:56:31 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 10:52:25 | 2024-10-04 10:52:25 | 5.75 | 13.94
25 | TT22830 | Amruta Kore | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
26 | TT22163 | Amruta Kore | - | - | - | Support from gokul - Code Merged P2P process | Query clarification | 2024-10-05 | 01:00:00 | 01:40:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:24:33 | 2024-10-05 23:24:33 | 1 | 1.68
27 | TT21945 | Amruta Kore | - | - | - | Support from Gokul -P2P process(SS, SB) | Query clarification | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-08 |  | TO_DO | TO_DO | 2024-10-07 16:04:54 |  | 0.5 | 0
28 | TT23053 | Amruta Kore | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 01:19:06 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 1.32
29 | TT21945 | Amruta Kore | - | - | - | Support from Gokul - P2P process (Gold, Silver, Platinum) | Query clarification | 2024-10-01 | 01:00:00 | 00:52:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:33:21 | 2024-10-04 22:33:21 | 1 | 0.88
30 | TT22785 | Amruta Kore | - | - | - | Lot Tag Testcase Modification | Test case updation\modification | 2024-10-01 | 01:00:00 | 00:39:32 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 23:33:30 | 2024-10-01 23:33:30 | 1 | 0.66
31 | TT21945 | Amruta Kore | - | - | - | Sterling Silver - P2P process testing | E2E Testing | 2024-10-04 | 03:00:00 | 04:04:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:24:34 | 2024-10-04 23:24:34 | 3 | 4.07
32 | TT24774 | Amruta Kore | - | - | - | HallMarking Master Scripting - 100% | Automate test script | 2024-10-04 | 02:45:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 2.75 | 0
33 | TT21945 | Amruta Kore | - | - | - | Silver - P2P process testing | E2E Testing | 2024-10-03 | 03:00:00 | 05:39:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 23:20:25 | 2024-10-03 23:20:25 | 3 | 5.67
34 | TT21899 | Amruta Kore | - | - | - | Support from gokul - Set tag module | Query clarification | 2024-09-30 | 00:30:00 | 00:39:13 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:05 | 2024-10-01 19:34:05 | 0.5 | 0.65
35 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
36 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:10 | 2024-10-06 23:45:10 | 0 | 0
37 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:20 | 2024-10-06 23:45:20 | 0 | 0
38 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-06 23:48:07 |  | 0.25 | 0
39 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:47 | 2024-10-06 23:46:47 | 0 | 0
40 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:59 | 2024-10-06 23:46:59 | 0 | 0
41 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:43:31 | 2024-10-06 23:43:31 | 0.25 | 0
42 | TT22810 | Gokul Bhoi | - | - | - | Automation Support From gokul(RNG) | Query clarification | 2024-10-03 | 02:00:00 | 02:00:14 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 22:29:35 |  | 2 | 2
43 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
44 | TT24774 | Gokul Bhoi | - | - | - | HallMarking Script Review | Script review | 2024-10-04 | 00:15:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-29 12:05:11 |  | 0.25 | 0
45 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:49 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
46 | TT18255 | Gokul Bhoi | - | - | - | Support From Gokul URD | Test Script Preparation | 2024-10-07 | 00:30:00 | 01:00:34 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:40:39 |  | 0.5 | 1.01
47 | TT22163 | Gokul Bhoi | - | - | - | Support from gokul - Code Merged P2P process | Query clarification | 2024-10-05 | 01:00:00 | 01:40:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:24:33 | 2024-10-05 23:24:33 | 1 | 1.68
48 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
49 | TT22830 | Gokul Bhoi | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 0
50 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | P2P Process automation scripting demo | Demo | 2024-10-07 | 00:30:00 | 01:28:46 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 15:26:06 | 2024-10-07 15:26:06 | 0.5 | 1.48
51 | TT18255 | Gokul Bhoi | - | - | - | Support from Gokul URD Silver | Support. | 2024-10-05 | 01:00:00 | 00:59:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:22:37 | 2024-10-05 23:22:37 | 1 | 1
52 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Walk in interview support | Interview | 2024-09-30 | 06:00:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 6 | 0
53 | TT21945 | Gokul Bhoi | - | - | - | Support from Gokul - P2P process (Gold, Silver, Platinum) | Query clarification | 2024-10-01 | 01:00:00 | 00:52:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:33:21 | 2024-10-04 22:33:21 | 1 | 0.88
54 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
55 | TT23053 | Gokul Bhoi | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 03:08:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 3.15
56 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 01:30:00 | 00:22:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 1.5 | 0.38
57 | TT21945 | Gokul Bhoi | - | - | - | P2P Process Support from Gokul | Query clarification | 2024-10-03 | 01:00:00 | 00:09:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:47 | 2024-10-04 19:08:47 | 1 | 0.16
58 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 01:30:00 | 00:44:23 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 1.5 | 0.74
59 | TT18255 | Gokul Bhoi | - | - | - | Support from Gokul URD Automation | Query clarification | 2024-10-03 | 01:00:00 | 00:23:06 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:23 | 2024-10-04 19:08:23 | 1 | 0.39
60 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:20:27 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 0.75 | 0.34
61 | TT23985 | Gokul Bhoi | - | - | - | TT23985 -Review- Stock Repair Positive flow Scripting (50% TC Cover) | Test script review | 2024-10-07 | 00:24:00 | 00:00:00 | 2024-10-11 |  | TO_DO | DELAY | 2024-10-04 16:20:00 |  | 0.4 | 0
62 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 00:15:00 | 00:16:27 | 2024-10-10 |  | IN_PROGRESS | DELAY | 2024-10-07 13:31:36 |  | 0.25 | 0.27
63 | TT23985 | Gokul Bhoi | - | - | - | Support From Gokul | Technical guidance/Process Input | 2024-10-03 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:58 | 2024-10-04 19:41:58 | 1 | 0
64 | TT24206 | Gokul Bhoi | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
65 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | p2p scripting modification | Modify test script | 2024-10-07 | 01:00:00 | 01:13:27 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 1.22
66 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Code modification PADM customer order status | Automate test script | 2024-10-05 | 03:00:00 | 00:00:00 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:32:22 | 2024-10-05 23:32:22 | 3 | 0
67 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Padm Labour charges Automation scripting | Automate test script | 2024-10-03 | 08:00:00 | 07:20:10 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-03 13:21:32 | 2024-10-03 13:21:32 | 8 | 7.34
68 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Generic Methods for Framework Automation Scripting | Automate test script | 2024-10-03 | 08:00:00 | 04:54:44 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:32:18 | 2024-10-04 23:32:18 | 8 | 4.91
69 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
70 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
71 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 01:30:00 | 01:24:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 1.5 | 1.41
72 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | Scheduling 4 Oct | Task Scheduling | 2024-10-03 | 01:00:00 | 00:50:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:32:22 | 2024-10-04 23:32:22 | 1 | 0.84
73 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
74 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
75 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
76 | TT24206 | Kiran Dhanepkar | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
77 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:28:39 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 0.75 | 0.48
78 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point karagir Jama to Kiran | Query clarification | 2024-10-07 | 00:00:00 | 01:22:19 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0 | 1.37
79 | TT22810 | Kiran Dhanepkar | - | - | - | Automation Support From gokul(RNG) | Query clarification | 2024-10-03 | 02:00:00 | 02:00:14 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 22:29:35 |  | 2 | 2
80 | TT22810 | Kiran Dhanepkar | - | - | - | RNG process Scripting(100%) | Automate test script | 2024-10-03 | 12:00:00 | 10:20:50 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 22:24:37 |  | 12 | 10.35
81 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point to Kiran Karagir jama | Query clarification | 2024-10-03 | 01:00:00 | 00:26:51 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:36 | 2024-10-04 19:41:36 | 1 | 0.45
82 | TT22830 | Kiran Dhanepkar | - | - | - | karagir jama (QC Process - HM Centre,LM & PO check) TC Writing | Test Case Writing | 2024-10-04 | 03:00:00 | 02:34:47 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:31:42 | 2024-10-04 23:31:42 | 3 | 2.58
83 | TT22830 | Kiran Dhanepkar | - | - | - | karagir jama (QC Process - DC,QC,HM) TC Writing | Test Case Writing | 2024-10-03 | 02:30:00 | 02:25:48 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:28:06 | 2024-10-03 18:28:06 | 2.5 | 2.43
84 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point to Kiran Karagir Nave | Support. | 2024-10-01 | 00:30:00 | 00:27:02 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:43 | 2024-10-01 19:02:43 | 0.5 | 0.45
85 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Nave TC Writting and updation | Test Case Writing | 2024-10-01 | 04:30:00 | 04:00:41 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:53 | 2024-10-01 19:02:53 | 4.5 | 4.01
86 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Jama Brainstorming | Brainstorming with DEV Team/BA | 2024-10-03 | 00:45:00 | 00:39:24 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:47:04 | 2024-10-03 18:47:04 | 0.75 | 0.66
87 | TT22830 | Kiran Dhanepkar | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
88 | TT23819 | Maruti Hakke | - | - | - | URD Support from Sayali Script | Query clarification | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.5 | 0
89 | TT23819 | Maruti Hakke | - | - | - | URD purchase Test script E2E | Test Automation Script Preparation | 2024-10-07 | 06:00:00 | 02:04:47 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS |  |  | 6 | 2.08
90 | TT23819 | Maruti Hakke | - | - | - | URD Purchase Test case 1 to 5 Execute Script | Automation Script Execution/modification | 2024-10-04 | 06:15:00 | 04:32:21 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:59:07 | 2024-10-04 22:59:07 | 6.25 | 4.54
91 | TT23819 | Maruti Hakke | - | - | - | URD Report Modification | Automation Script Execution/modification | 2024-10-03 | 01:15:00 | 01:18:47 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 20:06:02 | 2024-10-03 20:06:02 | 1.25 | 1.31
92 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Test case writing | Test case writing- | 2024-10-03 | 04:00:00 | 04:36:15 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 19:56:02 | 2024-10-04 19:56:02 | 4 | 4.6
93 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
94 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
95 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:50:08 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.84
96 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
97 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:51:08 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 0.75 | 0.85
98 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Walk in interview support | Interview | 2024-09-30 | 06:00:00 | 15:07:42 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 6 | 15.13
99 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
100 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
101 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 0
102 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 1 | 0
103 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
104 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
105 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
106 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:51:08 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 0.75 | 0.85
107 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance support to prathamesh | Mentoring | 2024-10-07 | 01:00:00 | 00:49:21 | 2024-10-09 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 0.82
108 | TT25961 | Prathamesh Kulkarni | - | - | - | gift voucher redemption estimation | Estimate calculation | 2024-10-07 | 00:45:00 | 00:02:39 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.75 | 0.04
109 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance scripting | Test Script Preparation | 2024-09-30 | 16:00:00 | 07:48:56 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-07 10:34:28 |  | 16 | 7.82
110 | TT24670 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Query clarification | 2024-10-03 | 02:00:00 | 01:40:38 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:19:19 | 2024-10-04 20:19:19 | 2 | 1.68
111 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
112 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
113 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
114 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 01:48:09 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 1.8
115 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 01:30:00 | 00:25:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 1.5 | 0.43
116 | TT23495 | Preeti Bokade | - | - | - | Footer / Setting Discussion KT | KT Session | 2024-10-07 | 00:30:00 | 00:58:55 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:21:38 | 2024-10-07 13:21:38 | 0.5 | 0.98
117 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Resource planning Report analysis | Performance analysis and improvement plan | 2024-10-07 | 02:00:00 | 00:00:00 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 2 | 0
118 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Support from Gaurav sir | Query clarification | 2024-10-07 | 00:24:00 | 00:00:00 | 2024-10-31 |  | TO_DO | TO_DO |  |  | 0.4 | 0
119 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Resource planning report analysis | Performance analysis and improvement plan | 2024-10-03 | 01:00:00 | 01:13:23 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-06 00:19:32 | 2024-10-06 00:19:32 | 1 | 1.22
120 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | KT to Digvijay about connect us 2.0 (Masters , except customer mapping ) | Internal KT/cross KT | 2024-10-07 | 02:00:00 | 01:29:41 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 14:11:10 |  | 2 | 1.49
121 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:59 | 2024-10-06 23:46:59 | 0 | 0
122 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
123 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:43:31 | 2024-10-06 23:43:31 | 0.25 | 0
124 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-06 23:48:07 |  | 0.25 | 0
125 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Sayali | Query clarification | 2024-10-07 | 00:15:00 | 00:21:16 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.25 | 0.35
126 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:47 | 2024-10-06 23:46:47 | 0 | 0
127 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 03:19:24 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 3.32
128 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:20 | 2024-10-06 23:45:20 | 0 | 0
129 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:45 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
130 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:10 | 2024-10-06 23:45:10 | 0 | 0
131 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
132 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Walk in Drive - Interview ( Automation Tester) | Interview | 2024-09-30 | 11:12:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:21:45 | 2024-10-04 20:21:45 | 11.2 | 0
133 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 01:30:00 | 00:22:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 1.5 | 0.38
134 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Amreen - Support from Preeti Ma'am. | Query clarification | 2024-09-30 | 01:30:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:56 | 2024-10-04 20:47:56 | 1.5 | 0
135 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 00:15:00 | 00:16:27 | 2024-10-10 |  | IN_PROGRESS | DELAY | 2024-10-07 13:31:36 |  | 0.25 | 0.27
136 | TT22830 | Saurabh Shelke | - | - | - | Support Point to Kiran Karagir Nave | Support. | 2024-10-01 | 00:30:00 | 00:26:17 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:43 | 2024-10-01 19:02:43 | 0.5 | 0.44
137 | TT21899 | Saurabh Shelke | - | - | - | Support from gokul - Set tag module | Query clarification | 2024-09-30 | 00:30:00 | 00:39:13 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:05 | 2024-10-01 19:34:05 | 0.5 | 0.65
138 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama - Provisional Parcel ,All vendors & Job work metal rate TC Writting | Test Case Writing | 2024-10-03 | 05:45:00 | 06:37:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:01:10 | 2024-10-04 19:01:10 | 5.75 | 6.63
139 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama Brainstorming | Brainstorming with DEV Team/BA | 2024-10-03 | 00:45:00 | 00:39:24 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:47:04 | 2024-10-03 18:47:04 | 0.75 | 0.66
140 | TT22830 | Saurabh Shelke | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
141 | TT23985 | Saurabh Shelke | - | - | - | Support From Gokul | Technical guidance/Process Input | 2024-10-03 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:58 | 2024-10-04 19:41:58 | 1 | 0
142 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair Positive flow Scripting | Automate test script | 2024-09-30 | 08:15:00 | 06:27:38 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:02:42 | 2024-10-04 19:02:42 | 8.25 | 6.46
143 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
144 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 01:30:00 | 01:24:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 1.5 | 1.41
145 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
146 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
147 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
148 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:28:10 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 0.75 | 0.47
149 | TT24206 | Saurabh Shelke | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
150 | TT23053 | Saurabh Shelke | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 01:45:56 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 1.77
151 | TT21945 | Saurabh Shelke | - | - | - | P2P Process - Support from Saurabh | Support. | 2024-10-07 | 00:30:00 | 00:34:08 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:50:51 |  | 0.5 | 0.57
152 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair TC Scripting (60 %) | Automate test script | 2024-10-07 | 02:15:00 | 00:43:37 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-03 19:11:32 |  | 2.25 | 0.73
153 | TT21945 | Saurabh Shelke | - | - | - | P2P -QC Process Bug Review | Test Case Review | 2024-10-07 | 00:45:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 15:52:06 |  | 0.75 | 0
154 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama (PO Check , LM & HM Centre) TC Review | Test Case Review | 2024-10-07 | 00:30:00 | 00:49:03 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 16:05:46 | 2024-10-07 16:05:46 | 0.5 | 0.82
155 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama (DC , QC & HM) test case review | Review Test cases | 2024-10-07 | 00:30:00 | 00:22:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:39:17 | 2024-10-07 13:39:17 | 0.5 | 0.37
156 | TT22830 | Saurabh Shelke | - | - | - | Support Point karagir Jama to Kiran | Query clarification | 2024-10-07 | 00:00:00 | 00:00:11 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0 | 0
157 | TT22785 | Saurabh Shelke | - | - | - | Lot tag testcase review | Review Test cases | 2024-10-01 | 00:45:00 | 00:32:39 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:47:43 | 2024-10-01 15:47:43 | 0.75 | 0.54
158 | TT22830 | Saurabh Shelke | - | - | - | Support Point to Kiran Karagir jama | Query clarification | 2024-10-03 | 01:00:00 | 00:24:40 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:36 | 2024-10-04 19:41:36 | 1 | 0.41
159 | TT22830 | Saurabh Shelke | - | - | - | karagir nave TC review | Review. | 2024-10-01 | 00:45:00 | 00:27:53 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 16:16:17 | 2024-10-01 16:16:17 | 0.75 | 0.46
160 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | TT22455-Bug review(Gift card) | Reporting Review | 2024-10-07 | 02:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-04 20:53:03 |  | 2 | 0
161 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | TT22455-Modified Test cases review(Gift Voucher) | Review Test cases | 2024-10-04 | 00:15:00 | 00:18:16 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 17:10:37 | 2024-10-04 17:10:37 | 0.25 | 0.3
162 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | TT22455-Test Case Review-Gift Card | Review Test cases | 2024-10-03 | 01:30:00 | 01:35:35 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 23:44:25 | 2024-10-03 23:44:25 | 1.5 | 1.59
163 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | Gift Voucher Sale Brainstorming | Brainstorming - Internal (Within Team member) | 2024-10-01 | 00:45:00 | 00:34:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:25:36 | 2024-10-01 15:25:36 | 0.75 | 0.58
164 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | Gift card sales bill KT | KT Session | 2024-10-01 | 00:30:00 | 00:33:43 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 13:14:33 | 2024-10-01 13:14:33 | 0.5 | 0.56
165 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
166 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
167 | TT23819 | Sayali Vyawahare | - | - | - | URD Support from Sayali Script | Query clarification | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.5 | 0
168 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 01:30:00 | 00:22:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 1.5 | 0.38
169 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Support to Sayali | Query clarification | 2024-10-07 | 00:15:00 | 00:21:16 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.25 | 0.35
170 | TT24670 | Sayali Vyawahare | - | - | - | customer advance support to prathamesh | Mentoring | 2024-10-07 | 01:00:00 | 00:49:29 | 2024-10-09 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 0.82
171 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 00:15:00 | 00:16:29 | 2024-10-10 |  | IN_PROGRESS | DELAY | 2024-10-07 13:31:36 |  | 0.25 | 0.27
172 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 0
173 | TT25961 | Sayali Vyawahare | - | - | - | gift voucher redemption estimation review | Estimate calculation | 2024-10-07 | 00:30:00 | 00:15:13 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.5 | 0.25
174 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:45 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
175 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance order code review | Code Review | 2024-10-03 | 01:30:00 | 01:03:15 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 00:02:19 | 2024-10-04 00:02:19 | 1.5 | 1.05
176 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
177 | TT24598 | Sayali Vyawahare | - | - | - | Customer creation test case review | Test Case Review | 2024-10-04 | 01:30:00 | 01:27:59 | 2024-10-07 |  | IN_PROGRESS | DELAY | 2024-10-07 11:55:45 |  | 1.5 | 1.47
178 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:58:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 0.75 | 0.98
179 | TT24670 | Sayali Vyawahare | - | - | - | customer advance and blanket advance test case execution | E2E Testing | 2024-10-01 | 04:00:00 | 03:47:19 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 22:56:32 | 2024-10-01 22:56:32 | 4 | 3.79
180 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
181 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
182 | TT24670 | Sayali Vyawahare | - | - | - | support to prathamesh | Query clarification | 2024-10-03 | 02:00:00 | 01:40:38 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:19:19 | 2024-10-04 20:19:19 | 2 | 1.68
183 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
184 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 02:22:18 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 2.37
185 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 01:30:00 | 00:51:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 1.5 | 0.85
186 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | Support from sayali | Query clarification | 2024-10-01 | 00:15:00 | 00:08:45 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:01 | 2024-10-01 19:02:01 | 0.25 | 0.15
187 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | test | Application Support | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-09-27 17:54:38 | 2024-09-27 17:54:38 | 0 | 0
188 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | - | - | test | Application Support | 2024-10-03 | 00:40:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-04 20:50:51 | 2024-10-04 20:50:51 | 0.67 | 0
189 | TT23495 | Swapnil Ramdasi | - | - | - | Scheduling for upcoming week | Task Scheduling | 2024-10-04 | 00:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 0.5 | 0
190 | TT23495 | Swapnil Ramdasi | - | - | - | CS Website - Estimation | Estimate the requirement | 2024-10-04 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 19:28:51 |  | 2 | 0
191 | TT23495 | Swapnil Ramdasi | - | - | - | Menu master, page master, section type master, page section master, page content master, Setting master, - Test case Updation | Test case updation\modification | 2024-10-07 | 01:30:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-09-27 20:47:29 |  | 1.5 | 0
192 | TT23495 | Swapnil Ramdasi | - | - | - | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 01:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 1.5 | 0
193 | TT23495 | Swapnil Ramdasi | - | - | - | CSM + Website Validation updation | Validation updation | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | TO_DO | DELAY | 2024-09-24 19:22:10 |  | 1.5 | 0
194 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Explore and Practice connect us 2.0(Reports-user task, resource planning, Variance) | Explore the existing system. | 2024-10-01 | 00:00:00 | 00:00:00 | 2024-10-13 |  | IN_PROGRESS | DELAY | 2024-10-03 15:26:04 |  | 0 | 0
195 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:30:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 17:53:31 |  | 0.5 | 0
196 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Retesting Documentation Module | Bug Retesting | 2024-10-03 | 03:00:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY |  |  | 3 | 0
197 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | - | - | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01 | 0 | 0
198 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 03:00:00 | 00:00:00 | 2024-10-04 |  | IN_PROGRESS | DELAY | 2024-09-27 20:27:44 |  | 3 | 0
199 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | - | - | Document reading | Document Reading | 2024-10-03 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 20:31:31 |  | 2 | 0
200 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Doc Module Sync call | Daily Sync Call | 2024-10-01 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:26:18 | 2024-10-04 18:26:18 | 1 | 0
201 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Voucher Sale Bill Estimation | Estimate the requirement | 2024-10-01 | 00:20:00 | 00:18:38 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:01:40 | 2024-10-01 19:01:40 | 0.33 | 0.31
202 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Prepare automation script for Gift Voucher creation-POS | Test Script Preparation | 2024-10-01 | 03:00:00 | 02:44:56 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:01:33 | 2024-10-01 19:01:33 | 3 | 2.75
203 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
204 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift voucher Sale Test case writing | Test Case Writing | 2024-10-01 | 03:00:00 | 02:14:44 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:01:27 | 2024-10-01 19:01:27 | 3 | 2.25
205 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
206 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift Voucher Sale Brainstorming | Brainstorming - Internal (Within Team member) | 2024-10-01 | 00:45:00 | 00:34:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:25:36 | 2024-10-01 15:25:36 | 0.75 | 0.58
207 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
208 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift card sales bill KT | KT Session | 2024-10-01 | 00:30:00 | 00:33:44 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 13:14:33 | 2024-10-01 13:14:33 | 0.5 | 0.56
209 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:48:34 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 0.75 | 0.81
210 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
211 | TT24206 | Uttareshwar Bhusari | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
212 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
213 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 01:30:26 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 1.51
214 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 01:00:00 | 00:25:14 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 1 | 0.42
215 | TT24390 | Uttareshwar Bhusari | Testing_AutomationPractice_OCT24_WK1 | - | - | Support from sayali | Query clarification | 2024-10-01 | 00:15:00 | 00:08:45 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:01 | 2024-10-01 19:02:01 | 0.25 | 0.15
216 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift Voucher Sale Prepare automation script | Test Automation Script Preparation | 2024-10-07 | 03:00:00 | 00:00:00 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS |  |  | 3 | 0
217 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Card Test Case execution | E2E Testing | 2024-10-07 | 04:15:00 | 01:19:31 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 19:42:53 |  | 4.25 | 1.33
218 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Voucher Test Case Modification | Test case updation\modification | 2024-10-04 | 01:00:00 | 02:33:35 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:33:43 | 2024-10-04 19:33:43 | 1 | 2.56
219 | TT18255 | Vaishnavi Khandwe | - | - | - | Support From Gokul URD | Test Script Preparation | 2024-10-07 | 00:30:00 | 01:00:36 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:40:39 |  | 0.5 | 1.01
220 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting Gold | Test Script Preparation | 2024-10-03 | 06:00:00 | 00:59:34 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 10:31:37 |  | 6 | 0.99
221 | TT22830 | Vaishnavi Khandwe | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 0
222 | TT21945 | Vaishnavi Khandwe | - | - | - | P2P Process - Support from Saurabh | Support. | 2024-10-07 | 00:30:00 | 00:34:08 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:50:51 |  | 0.5 | 0.57
223 | TT21945 | Vaishnavi Khandwe | - | - | - | P2P Process Support from Gokul | Query clarification | 2024-10-03 | 01:00:00 | 00:09:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:47 | 2024-10-04 19:08:47 | 1 | 0.16
224 | TT21945 | Vaishnavi Khandwe | - | - | - | GB - Item P2P process Testing | E2E Testing | 2024-10-07 | 02:00:00 | 00:09:14 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 13:20:35 |  | 2 | 0.15
225 | TT21945 | Vaishnavi Khandwe | - | - | - | DJ- Item P2P process Testing | E2E Testing | 2024-10-04 | 03:00:00 | 04:26:36 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:58:46 | 2024-10-04 19:58:46 | 3 | 4.44
226 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
227 | TT21945 | Vaishnavi Khandwe | - | - | - | Forming- Item P2P process Testing | E2E Testing | 2024-10-03 | 03:00:00 | 05:10:16 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 19:40:25 | 2024-10-03 19:40:25 | 3 | 5.17
228 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 01:30:00 | 00:44:23 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 1.5 | 0.74
229 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | Task Scheduling next week | Task Scheduling | 2024-10-03 | 01:00:00 | 00:40:01 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 11:04:44 | 2024-10-04 11:04:44 | 1 | 0.67
230 | TT24206 | Vaishnavi Khandwe | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
231 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
232 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
233 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
234 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Walk in interview support | Interview | 2024-09-30 | 06:00:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 6 | 0
235 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:20:26 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 0.75 | 0.34
236 | TT18255 | Vaishnavi Khandwe | - | - | - | Support from Gokul URD Silver | Support. | 2024-10-05 | 01:00:00 | 01:00:05 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:22:37 | 2024-10-05 23:22:37 | 1 | 1
237 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting Silver purchase us and other | Test Script Preparation | 2024-10-05 | 06:00:00 | 07:30:42 | 2024-10-05 |  | IN_PROGRESS | DELAY | 2024-10-07 12:38:11 |  | 6 | 7.51
238 | TT18255 | Vaishnavi Khandwe | - | - | - | Support from Gokul URD Automation | Query clarification | 2024-10-03 | 01:00:00 | 00:43:55 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:23 | 2024-10-04 19:08:23 | 1 | 0.73