## Sheet1
task_delivery_scheduled | (Multiple Items) |  |  |  | task_delivery_scheduled | (Multiple Items)
sprint_name | (ALL) |  |  |  | sprint_name | (ALL)
Count of task_name | task_status |  |  |  | Count of task_name | task_actual_status
task_owner | COMPLETED | IN_PROGRESS | TO_DO | Grand Total | task_owner | IN_TIME | SLIGHTLY_DELAY | DELAY | HIGHLY_DELAY | Grand Total
Amreen Shaikh | 83 | 3 | 11 | 97 | Amreen Shaikh | 72 | 1 | 24 |  | 97
Amruta Kore | 96 | 1 | 1 | 98 | Amruta Kore | 88 |  | 10 |  | 98
Gokul Bhoi | 141 |  | 1 | 142 | Gokul Bhoi | 117 | 1 | 22 | 2 | 142
Kiran Dhanepkar | 64 |  |  | 64 | Kiran Dhanepkar | 56 |  | 7 | 1 | 64
Maruti Hakke | 69 |  |  | 69 | Maruti Hakke | 50 | 3 | 16 |  | 69
Prathamesh Kulkarni | 57 |  |  | 57 | Prathamesh Kulkarni | 49 | 1 | 7 |  | 57
Preeti Bokade | 65 | 1 |  | 66 | Preeti Bokade | 58 | 2 | 6 |  | 66
Saurabh Shelke | 69 |  |  | 69 | Saurabh Shelke | 59 |  | 10 |  | 69
Sayali Vyawahare | 93 |  |  | 93 | Sayali Vyawahare | 78 | 3 | 12 |  | 93
Swapnil Ramdasi | 47 | 2 | 7 | 56 | Swapnil Ramdasi | 30 | 9 | 17 |  | 56
Uttareshwar Bhusari | 67 |  |  | 67 | Uttareshwar Bhusari | 57 |  | 10 |  | 67
Vaishnavi Khandwe | 56 | 1 |  | 57 | Vaishnavi Khandwe | 47 | 1 | 8 | 1 | 57
Grand Total | 907 | 8 | 20 | 935 | Grand Total | 761 | 21 | 149 | 4 | 935

## data
sr | ticket_id | task_owner | sprint_name | sprint_start_date | sprint_end_date | task_name | type_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Scheduled hrs | Actual hrs
1 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Task scheduling 30 Sept - 4 oct | Task Scheduling | 2024-09-27 | 00:30:00 | 01:45:14 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:50:31 | 2024-09-27 20:50:31 | 0.5 | 1.75
2 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-18 | 01:30:00 | 01:18:49 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:59:00 | 2024-09-20 20:59:00 | 1.5 | 1.31
3 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Support to D team for Automation | Technical guidance/Process Input | 2024-09-19 | 01:00:00 | 00:53:41 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 21:52:24 | 2024-09-20 21:52:24 | 1 | 0.89
4 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 01:12:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 1.2
5 | TT23495 | Amreen Shaikh | - | - | - | CS website - Support to swapnil | Query clarification | 2024-09-18 | 01:30:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:04:45 | 2024-09-20 22:04:45 | 1.5 | 0
6 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
7 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Task scheduling 23 Sept - 27 sept | Task Scheduling | 2024-09-20 | 00:30:00 | 00:44:13 | 2024-09-20 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-23 16:42:05 | 2024-09-23 16:42:05 | 0.5 | 0.74
8 | TT19645 | Amreen Shaikh | - | - | - | AS BC retesting. | Bug Retesting | 2024-09-18 | 03:30:00 | 04:34:29 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-23 16:39:51 | 2024-09-23 16:39:51 | 3.5 | 4.57
9 | TT24206 | Amreen Shaikh | Testing_KT_Oct24_Wk1 | - | - | Cross KT - Customer view | Internal KT/cross KT | 2024-09-02 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-08-30 20:15:30 | 2024-08-30 20:15:30 | 0 | 0
10 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Review and provide remark/suggestion on Swapnils automation code | Script review | 2024-09-18 | 02:00:00 | 00:48:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:00 | 2024-09-20 20:38:00 | 2 | 0.8
11 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:15:00 | 00:40:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1.25 | 0.67
12 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-09 | 02:30:00 | 00:29:56 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:19 | 2024-09-13 20:11:19 | 2.5 | 0.5
13 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Logic building guidence | Technical guidance/Process Input | 2024-09-18 | 02:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:05 | 2024-09-20 20:38:05 | 2 | 0
14 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Task scheduling 16 Sept - 20 sept | Task Scheduling | 2024-09-13 | 00:30:00 | 00:25:49 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:32 | 2024-09-13 20:08:32 | 0.5 | 0.43
15 | TT23294 | Amreen Shaikh | - | - | - | Regularization - Report Preparation | Daily Summary report | 2024-09-09 | 00:15:00 | 00:00:00 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 21:42:56 | 2024-09-09 21:42:56 | 0.25 | 0
16 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Review and provide remark/suggestion on Swapnils automation code | Query clarification | 2024-09-09 | 03:45:00 | 02:53:19 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:22 | 2024-09-13 20:10:22 | 3.75 | 2.89
17 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:14:50 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40 | 0.17 | 0.25
18 | TT19645 | Amreen Shaikh | - | - | - | AS report preparation | Daily Summary report | 2024-09-02 | 00:15:00 | 00:00:05 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:03:01 | 2024-09-06 19:03:01 | 0.25 | 0
19 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:30:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 17:53:31 |  | 0.5 | 0
20 | TT23294 | Amreen Shaikh | - | - | - | Support for Regularization | Query clarification | 2024-09-09 | 00:30:00 | 00:47:01 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 17:55:43 | 2024-09-09 17:55:43 | 0.5 | 0.78
21 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Logic building guidence | Technical guidance/Process Input | 2024-09-09 | 03:45:00 | 02:42:35 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:15 | 2024-09-13 20:10:15 | 3.75 | 2.71
22 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
23 | TT24437 | Amreen Shaikh | - | - | - | Regularization - validation review | Review. | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:26 | 2024-09-06 17:23:26 | 0 | 0
24 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Support to swapnil - report preparation | Daily Summary report | 2024-10-03 | 00:30:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY |  |  | 0.5 | 0
25 | TT23495 | Amreen Shaikh | - | - | - | CS Website - Document reading | Document Reading | 2024-09-26 | 01:00:00 | 02:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 13:41:43 | 2024-09-26 13:41:43 | 1 | 2
26 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Support to D team for Automation | Technical guidance/Process Input | 2024-09-09 | 05:00:00 | 03:54:18 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:03 | 2024-09-13 20:10:03 | 5 | 3.91
27 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Support to swapnil for automation | Query clarification | 2024-10-04 | 01:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 19:58:44 |  | 1.5 | 0
28 | TT23495 | Amreen Shaikh | - | - | - | CS website - Support to swapnil | Query clarification | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-09 18:59:53 | 2024-09-09 18:59:53 | 0 | 0
29 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Support to D team for Automation | Technical guidance/Process Input | 2024-09-04 | 03:00:00 | 02:58:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:20:39 | 2024-09-06 18:20:39 | 3 | 2.98
30 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
31 | TT24437 | Amreen Shaikh | - | - | - | Support to swapnil - regularization | Query clarification | 2024-09-06 | 00:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:40 | 2024-09-06 17:23:40 | 0.5 | 0
32 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Document module - Report preparation. | Daily Summary report | 2024-09-13 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:00 | 2024-09-13 20:11:00 | 0 | 0
33 | TT21914 | Amreen Shaikh | - | - | - | Automation code test round - nirgun | Interview | 2024-09-06 | 01:30:00 | 01:22:16 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:09:40 | 2024-09-06 19:09:40 | 1.5 | 1.37
34 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Support to D team for Automation | Technical guidance/Process Input | 2024-09-03 | 01:00:00 | 00:48:00 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-06 17:35:09 | 2024-09-03 22:03:33 | 1 | 0.8
35 | TT23932 | Amreen Shaikh | Sprint 1 | - | - | AS BC DIS GS PS | General meeting | 2024-09-12 | 00:30:00 | 00:27:33 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 19:58:04 | 2024-09-12 19:58:04 | 0.5 | 0.46
36 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Automation Scheduling - support to Swapnil | Support. | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:12:44 | 2024-09-06 20:12:44 | 0 | 0
37 | TT24437 | Amreen Shaikh | - | - | - | Regularization - validation writing | Validation writing | 2024-09-06 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:23:51 | 2024-09-06 17:23:51 | 0 | 0
38 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Document module - Report preparation | Daily Summary report | 2024-09-12 | 00:15:00 | 00:17:26 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 19:37:16 | 2024-09-12 19:37:16 | 0.25 | 0.29
39 | TT20736 | Amreen Shaikh | - | - | - | Issue explanation to dev | Requirement gathering | 2024-09-03 | 00:30:00 | 00:34:21 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 17:09:31 | 2024-09-03 17:09:31 | 0.5 | 0.57
40 | TT24216 | Amreen Shaikh | Testing_Skill Upgrade_Oct24_Wk1 | - | - | Automation Planning - support to Swapnil | Planning | 2024-09-13 | 00:30:00 | 00:23:28 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:17:42 | 2024-09-13 20:17:42 | 0.5 | 0.39
41 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Logic building guidence | Technical guidance/Process Input | 2024-09-02 | 02:15:00 | 02:28:04 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:18:48 | 2024-09-06 20:18:48 | 2.25 | 2.47
42 | TT23932 | Amreen Shaikh | Sprint 1 | - | - | AS BC Discussions | General meeting | 2024-09-06 | 00:30:00 | 00:29:19 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 14:16:41 | 2024-09-06 14:16:41 | 0.5 | 0.49
43 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 04:02:53 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 4.05
44 | TT19645 | Amreen Shaikh | - | - | - | As BC Retesting | Testing. | 2024-09-02 | 04:00:00 | 02:10:25 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:09:15 | 2024-09-06 19:09:15 | 4 | 2.17
45 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Document module - Support to Swapnil | Query clarification | 2024-09-10 | 01:00:00 | 01:09:55 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:10:38 | 2024-09-13 20:10:38 | 1 | 1.17
46 | TT23495 | Amreen Shaikh | - | - | - | CS website - Support to swapnil | Mentoring | 2024-09-03 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:37:15 | 2024-09-06 16:37:15 | 1 | 0
47 | TT24216 | Amreen Shaikh | Testing_Skill Upgrade_Oct24_Wk1 | - | - | Automation Planning - support to Swapnil | Planning | 2024-09-06 | 00:30:00 | 00:27:35 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:39:52 | 2024-09-06 20:39:52 | 0.5 | 0.46
48 | TT24390 | Amreen Shaikh | Testing_AutomationPractice_OCT24_WK1 | - | - | Review and provide remark/suggestion on Swapnils automation code | Script review | 2024-09-02 | 02:15:00 | 02:46:39 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:18:42 | 2024-09-06 20:18:42 | 2.25 | 2.78
49 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Task scheduling 9 Sept - 13 sept | Task Scheduling | 2024-09-06 | 00:30:00 | 00:29:14 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:12:26 | 2024-09-06 20:12:26 | 0.5 | 0.49
50 | TT23495 | Amreen Shaikh | - | - | - | DSC - CMS | Daily Sync Call | 2024-09-02 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:16:17 | 2024-09-06 17:16:17 | 2 | 0
51 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:26:29 | 2024-09-06 18:26:29 | 0.75 | 0
52 | TT21914 | Amreen Shaikh | - | - | - | Support from Preeti Ma'am. | Query clarification | 2024-09-02 | 02:30:00 | 03:43:21 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-08 23:15:06 | 2024-09-06 19:27:58 | 2.5 | 3.72
53 | TT15425 | Amreen Shaikh | Sprint 1 | - | - | Bill checking test on Live server | E2E Testing. | 2024-09-29 | 02:30:00 | 02:36:52 | 2024-09-29 |  | IN_PROGRESS | DELAY |  |  | 2.5 | 2.61
54 | TT19645 | Amreen Shaikh | - | - | - | AS Bill Checking RAD | RAD Testing | 2024-08-28 | 04:00:00 | 00:00:00 | 2024-09-02 |  | COMPLETED | DELAY | 2024-09-23 16:42:43 | 2024-09-23 16:42:43 | 4 | 0
55 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Document module - Review and update test cases on TS | Test Case Review | 2024-09-03 | 00:45:00 | 01:00:54 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-04 20:09:41 | 2024-09-04 20:09:41 | 0.75 | 1.02
56 | TT15425 | Amreen Shaikh | Sprint 1 | - | - | Support to swapnil | Query clarification | 2024-09-23 | 02:30:00 | 00:00:00 | 2024-09-27 |  | TO_DO | DELAY |  |  | 2.5 | 0
57 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | - | - | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01 | 0 | 0
58 | TT23495 | Amreen Shaikh | - | - | - | Menu master, Default setting page & tenant master page - Testing | Unit Testing | 2024-10-02 | 00:00:00 | 00:00:00 | 2024-10-02 |  | COMPLETED | IN_TIME | 2024-09-27 19:26:44 | 2024-09-27 19:26:44 | 0 | 0
59 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-02 | 00:44:00 | 00:34:46 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-03 19:29:26 | 2024-09-03 19:29:26 | 0.73 | 0.58
60 | TT15425 | Amreen Shaikh | Sprint 1 | - | - | Issue explanation to developer | Brainstorming with DEV Team \BA | 2024-09-26 | 00:30:00 | 01:26:40 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 19:48:57 | 2024-09-26 19:48:57 | 0.5 | 1.44
61 | TT22602 | Amreen Shaikh | QR Code - HRMS Sprint 1 | - | - | Document reading | Document Reading | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 20:31:31 |  | 0 | 0
62 | TT23495 | Amreen Shaikh | - | - | - | Menu master, Default setting page & tenant master page - Test case writing | Test case writing- | 2024-08-27 | 00:00:00 | 00:12:32 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-01 15:05:57 | 2024-09-27 19:06:50 | 0 | 0.21
63 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Document module - report review | Reporting Review | 2024-09-02 | 00:15:00 | 00:53:10 | 2024-09-02 |  | COMPLETED | DELAY | 2024-09-03 20:42:38 | 2024-09-03 20:42:38 | 0.25 | 0.89
64 | TT15425 | Amreen Shaikh | Sprint 1 | - | - | E2E retesting - Bill transaction | E2E Testing. | 2024-09-26 | 12:00:00 | 11:39:15 | 2024-09-27 |  | IN_PROGRESS | DELAY |  |  | 12 | 11.65
65 | TT23495 | Amreen Shaikh | - | - | - | CS website document reading | Documentation Reading | 2024-08-21 | 00:00:00 | 00:00:00 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 16:57:18 | 2024-09-06 16:57:18 | 0 | 0
66 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Document module - report preparation | Daily Summary report | 2024-09-04 | 00:20:00 | 00:24:54 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 17:07:04 | 2024-09-06 17:07:04 | 0.33 | 0.42
67 | TT15425 | Amreen Shaikh | Sprint 1 | - | - | E2E testing - Bill transaction | E2E Testing. | 2024-09-23 | 18:00:00 | 16:11:19 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 11:35:41 | 2024-09-26 11:35:41 | 18 | 16.19
68 | TT24427 | Amreen Shaikh | E2E Testing | - | - | Support to Swapnil for Consolidated report | Query clarification | 2024-09-02 | 01:30:00 | 01:59:48 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:31 | 2024-09-06 17:05:31 | 1.5 | 2
69 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | My CS APP Daily Sync call 23-27 | Daily Sync Call | 2024-09-23 | 00:50:00 | 00:18:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:07:41 | 2024-09-27 17:07:41 | 0.83 | 0.31
70 | TT15425 | Amreen Shaikh | Sprint 1 | - | - | E2E testing - Bill transaction - add, edit, view, grid view, approval & rejection cycle. + Payment details page. | E2E Testing. | 2024-09-21 | 00:00:00 | 00:00:00 | 2024-09-21 |  | COMPLETED | DELAY | 2024-09-25 13:57:11 | 2024-09-25 13:57:11 | 0 | 0
71 | TT15425 | Amreen Shaikh | Sprint 1 | - | - | Issue explaination | Requirement gathering | 2024-09-02 | 00:30:00 | 00:33:52 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 15:25:44 | 2024-09-02 15:25:44 | 0.5 | 0.56
72 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | MyCS Validation updation | Validation updation | 2024-09-09 | 00:20:00 | 00:20:10 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:03:18 | 2024-09-09 19:03:18 | 0.33 | 0.34
73 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | MyCS Test case modification | Test case updation\modification | 2024-09-13 | 01:00:00 | 02:02:29 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-20 19:54:36 | 2024-09-20 19:54:36 | 1 | 2.04
74 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | MyCS Testcase writing | Test case writing- | 2024-09-09 | 03:30:00 | 02:33:13 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-13 16:29:19 | 2024-09-13 16:29:19 | 3.5 | 2.55
75 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | MyCS Scheme - Daily sync call | Sync call with BA | 2024-09-09 | 00:50:00 | 17:19:08 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:15:56 | 2024-09-13 19:15:56 | 0.83 | 17.32
76 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | Testing - Report preparation | Daily Summary report | 2024-10-03 | 00:15:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 20:30:39 |  | 0.25 | 0
77 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | MyCS Scheme Testing | Unit Testing | 2024-09-25 | 05:30:00 | 02:36:34 | 2024-10-03 |  | IN_PROGRESS | DELAY | 2024-09-27 20:29:37 |  | 5.5 | 2.61
78 | TT23495 | Amreen Shaikh | - | - | - | CS website test case review | Review Test cases | 2024-10-04 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 2 | 0
79 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | Validation writing | Validation writing | 2024-09-05 | 00:30:00 | 00:42:50 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 20:14:18 | 2024-09-05 20:14:18 | 0.5 | 0.71
80 | TT23495 | Amreen Shaikh | - | - | - | Review estimation | Estimation Review | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 1 | 0
81 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | Scheme Enrollment - Daily sync call | Daily Sync Call | 2024-09-06 | 01:15:00 | 00:41:15 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-06 19:34:56 | 2024-09-06 19:34:56 | 1.25 | 0.69
82 | TT23495 | Amreen Shaikh | - | - | - | Scheduling for upcoming week | Task Scheduling | 2024-10-04 | 00:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 0.5 | 0
83 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | New scheme Enrollment Brain storming | Brainstorming | 2024-09-05 | 00:30:00 | 00:50:05 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 17:48:00 | 2024-09-05 17:48:00 | 0.5 | 0.83
84 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Tester interview | Interview | 2024-09-30 | 12:00:00 | 13:07:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:20 | 2024-10-01 19:34:20 | 12 | 13.13
85 | TT23495 | Amreen Shaikh | - | - | - | CS Website - Validation review | Test Case Review | 2024-10-03 | 00:45:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 19:16:57 |  | 0.75 | 0
86 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | Prepare estimation | Estimate the requirement | 2024-09-05 | 00:30:00 | 00:45:14 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 20:14:24 | 2024-09-05 20:14:24 | 0.5 | 0.75
87 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0
88 | TT23495 | Amreen Shaikh | - | - | - | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 2 | 0
89 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | Go through the recording | Explore the existing system. | 2024-09-04 | 00:40:00 | 00:50:25 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:47 | 2024-09-04 19:41:47 | 0.67 | 0.84
90 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Amreen - Support from Preeti Ma'am. | Query clarification | 2024-09-30 | 02:00:00 | 00:40:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:56 | 2024-10-04 20:47:56 | 2 | 0.68
91 | TT24961 | Amreen Shaikh | New Scheme Enrollment on mobile App | - | - | Go through the document | Document Reading | 2024-09-04 | 00:40:00 | 00:45:42 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:52 | 2024-09-04 19:41:52 | 0.67 | 0.76
92 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0
93 | TT23495 | Amreen Shaikh | - | - | - | CMS KT Session | KT Session | 2024-09-26 | 01:30:00 | 01:29:36 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:12:46 | 2024-09-27 15:12:46 | 1.5 | 1.49
94 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:54:27 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 2.91
95 | TT23495 | Amreen Shaikh | - | - | - | CMS - KT Session | KT Session | 2024-09-26 | 01:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:16 | 2024-09-20 20:38:16 | 1 | 0
96 | TT24303 | Amreen Shaikh | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:44:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.74
97 | TT21914 | Amreen Shaikh | - | - | - | Amreen - Support from Preeti ma'am | Query clarification | 2024-09-23 | 02:30:00 | 03:48:53 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:51:17 | 2024-09-27 20:51:17 | 2.5 | 3.81
98 | TT24774 | Amruta Kore | - | - | - | Testcase writing Hallmarking master | Test case writing- | 2024-09-19 | 01:00:00 | 00:37:42 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 22:27:00 | 2024-09-19 22:27:00 | 1 | 0.63
99 | TT22455 | Amruta Kore | Gift card sales 1 | - | - | Support from Gokul - For Gift Voucher Script | Technical guidance/Process Input | 2024-09-11 | 01:30:00 | 00:50:43 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 21:22:32 | 2024-09-13 21:22:32 | 1.5 | 0.85
100 | TT24680 | Amruta Kore | - | - | - | Test cases writing of sub smith master | Test case writing- | 2024-09-20 | 01:00:00 | 00:33:59 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 13:50:11 | 2024-09-20 13:50:11 | 1 | 0.57
101 | TT22455 | Amruta Kore | Gift card sales 1 | - | - | Gift Voucher Automation script for 10 Testcase | Automate test script | 2024-09-11 | 12:00:00 | 12:58:42 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 00:04:32 | 2024-09-21 00:04:32 | 12 | 12.98
102 | TT24774 | Amruta Kore | - | - | - | Automation Script of HallMarking Master | Automate test script | 2024-09-18 | 04:00:00 | 03:26:06 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 22:35:11 | 2024-09-19 22:35:11 | 4 | 3.44
103 | TT22163 | Amruta Kore | - | - | - | Support from gokul - Code Merged P2P process | Query clarification | 2024-10-05 | 01:00:00 | 01:40:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:24:33 | 2024-10-05 23:24:33 | 1 | 1.68
104 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - BDD Scheme Script | Technical guidance/Process Input | 2024-09-09 | 01:00:00 | 02:18:47 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:38:14 | 2024-09-10 19:38:14 | 1 | 2.31
105 | TT23053 | Amruta Kore | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 01:19:06 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 1.32
106 | TT24773 | Amruta Kore | - | - | - | QC setting master - Testcase writing | Test case writing- | 2024-09-13 | 01:30:00 | 00:59:52 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 09:54:24 | 2024-09-13 09:54:24 | 1.5 | 1
107 | TT22785 | Amruta Kore | - | - | - | Lot Tag Testcase Modification | Test case updation\modification | 2024-10-01 | 01:00:00 | 00:39:32 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 23:33:30 | 2024-10-01 23:33:30 | 1 | 0.66
108 | TT24776 | Amruta Kore | - | - | - | Agent master - Testcase writing | Test case writing- | 2024-09-12 | 01:00:00 | 00:46:54 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 12:50:15 | 2024-09-12 12:50:15 | 1 | 0.78
109 | TT24774 | Amruta Kore | - | - | - | HallMarking Master Scripting - 100% | Automate test script | 2024-10-04 | 02:45:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 2.75 | 0
110 | TT24777 | Amruta Kore | - | - | - | QC ssetup master - Testcase writing | Test case writing- | 2024-09-13 | 01:00:00 | 00:51:20 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 09:54:37 | 2024-09-13 09:54:37 | 1 | 0.86
111 | TT21899 | Amruta Kore | - | - | - | Support from gokul - Set tag module | Query clarification | 2024-09-30 | 01:00:00 | 00:39:13 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:05 | 2024-10-01 19:34:05 | 1 | 0.65
112 | TT24778 | Amruta Kore | - | - | - | Item type master - Testcase writing | Test case writing- | 2024-09-12 | 01:00:00 | 00:59:57 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 22:08:56 | 2024-09-12 22:08:56 | 1 | 1
113 | TT21899 | Amruta Kore | - | - | - | Set Tag Module Scripting - 100 percent | Automate test script | 2024-09-30 | 08:00:00 | 13:56:31 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 10:52:25 | 2024-10-04 10:52:25 | 8 | 13.94
114 | TT22830 | Amruta Kore | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
115 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
116 | TT24681 | Amruta Kore | - | - | - | Ornament Number Sequence Master | Test case writing- | 2024-09-11 | 01:30:00 | 01:29:26 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 19:09:42 | 2024-09-11 19:09:42 | 1.5 | 1.49
117 | TT21945 | Amruta Kore | - | - | - | Support from Gokul -P2P process(SS, SB) | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-08 |  | TO_DO | TO_DO | 2024-10-07 15:40:09 |  | 0 | 0
118 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
119 | TT24772 | Amruta Kore | - | - | - | Designer Master Testcase writing | Test case writing- | 2024-09-11 | 01:00:00 | 01:28:33 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 13:15:51 | 2024-09-11 13:15:51 | 1 | 1.48
120 | TT21945 | Amruta Kore | - | - | - | Support from Gokul - P2P process (Gold, Silver, Platinum) | Query clarification | 2024-10-01 | 01:00:00 | 00:52:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:33:21 | 2024-10-04 22:33:21 | 1 | 0.88
121 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:37:10 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.62
122 | TT23423 | Amruta Kore | - | - | - | SSRS report Estimation - 5 reports | Estimate calculation | 2024-09-10 | 01:15:00 | 00:25:54 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 22:50:01 | 2024-09-10 22:50:01 | 1.25 | 0.43
123 | TT21945 | Amruta Kore | - | - | - | Sterling Silver - P2P process testing | E2E Testing | 2024-10-04 | 03:00:00 | 04:04:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:24:34 | 2024-10-04 23:24:34 | 3 | 4.07
124 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:44:19 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.74
125 | TT22163 | Amruta Kore | - | - | - | offline tagging Estimation merge with gr wt adjustment | Estimate calculation | 2024-09-10 | 00:15:00 | 00:40:24 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 22:49:32 | 2024-09-10 22:49:32 | 0.25 | 0.67
126 | TT21945 | Amruta Kore | - | - | - | Silver - P2P process testing | E2E Testing | 2024-10-03 | 03:00:00 | 05:39:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 23:20:25 | 2024-10-03 23:20:25 | 3 | 5.67
127 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 02:04:01 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 2.07
128 | TT22823 | Amruta Kore | - | - | - | Karagir Nave jama new CR estimation | Estimate calculation | 2024-09-09 | 00:30:00 | 00:38:08 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 12:46:20 | 2024-09-09 12:46:20 | 0.5 | 0.64
129 | TT22785 | Amruta Kore | - | - | - | Lot Tag BrainStroming - | Brainstorming - Internal ( Within Team member) | 2024-09-27 | 00:30:00 | 00:54:12 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:45:04 | 2024-09-27 19:45:04 | 0.5 | 0.9
130 | TT24778 | Amruta Kore | - | - | - | Item Type Master Estimation - | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:14:12 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 12:07:54 | 2024-09-04 12:07:54 | 0.25 | 0.24
131 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:49 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 0.28
132 | TT14931 | Amruta Kore | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:21 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
133 | TT24776 | Amruta Kore | - | - | - | Agent Master - Estimation | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:10:37 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 12:18:47 | 2024-09-04 12:18:47 | 0.25 | 0.18
134 | TT24206 | Amruta Kore | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
135 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:54:15 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.9
136 | TT22830 | Amruta Kore | - | - | - | Kariger requirement discussion | Requirement gathering | 2024-09-04 | 02:00:00 | 01:54:04 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 18:00:50 | 2024-09-04 18:00:50 | 2 | 1.9
137 | TT24683 | Amruta Kore | - | - | - | Pcs adjustment in offline tagging - document reading | Document Reading | 2024-09-26 | 00:45:00 | 00:34:13 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 20:25:59 | 2024-09-26 20:25:59 | 0.75 | 0.57
138 | TT24777 | Amruta Kore | - | - | - | QC Setup Master - Estimation | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:13:08 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 11:53:56 | 2024-09-04 11:53:56 | 0.25 | 0.22
139 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:30:54 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.52
140 | TT23932 | Amruta Kore | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
141 | TT24678 | Amruta Kore | - | - | - | Testcase writing - Making charges Master | Test case writing- | 2024-09-05 | 01:30:00 | 01:32:45 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 18:51:12 | 2024-09-09 18:51:12 | 1.5 | 1.55
142 | TT24672 | Amruta Kore | Dev to Handover Config master | - | - | Configuration Master Testing | E2E Testing | 2024-09-30 | 01:00:00 | 01:04:49 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 12:28:28 | 2024-09-30 12:28:28 | 1 | 1.08
143 | TT24680 | Amruta Kore | - | - | - | Support from gokul for Subsmith master script | Technical guidance/Process Input | 2024-09-30 | 00:30:00 | 00:20:55 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:17:23 | 2024-09-30 19:17:23 | 0.5 | 0.35
144 | TT24647 | Amruta Kore | - | - | - | BDD estimation | Estimate the requirement | 2024-09-04 | 00:30:00 | 00:37:55 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 21:55:59 | 2024-09-04 21:55:59 | 0.5 | 0.63
145 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
146 | TT23932 | Amruta Kore | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:50:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 1.84
147 | TT24772 | Amruta Kore | - | - | - | Estimation of Designer master | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:07:44 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 11:04:55 | 2024-09-04 11:04:55 | 0.25 | 0.13
148 | TT24672 | Amruta Kore | Dev to Handover Config master | - | - | Support from gokul - Configuration master script | Technical guidance/Process Input | 2024-09-27 | 00:30:00 | 00:20:32 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:12:38 | 2024-09-27 20:12:38 | 0.5 | 0.34
149 | TT24680 | Amruta Kore | - | - | - | Sub smith master - Automation script(Positive Flow) | Automate test script | 2024-09-30 | 01:30:00 | 04:26:20 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:41:12 | 2024-09-30 19:41:12 | 1.5 | 4.44
150 | TT24647 | Amruta Kore | - | - | - | BDD Cross KT | KT Session | 2024-09-03 | 00:45:00 | 00:33:21 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:40 | 2024-09-03 22:23:40 | 0.75 | 0.56
151 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
152 | TT23932 | Amruta Kore | Sprint 1 | - | - | Scheduling | Task Scheduling | 2024-10-03 | 01:00:00 | 00:11:57 | 2024-10-04 |  | COMPLETED | DELAY | 2024-10-07 09:26:42 | 2024-10-07 09:26:42 | 1 | 0.2
153 | TT24769 | Amruta Kore | - | - | - | Wastage code master - Estimation | Estimate the requirement | 2024-09-05 | 00:15:00 | 00:23:10 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 11:20:29 | 2024-09-05 11:20:29 | 0.25 | 0.39
154 | TT24672 | Amruta Kore | Dev to Handover Config master | - | - | configuration master - Automation script | Automate test script | 2024-09-27 | 03:00:00 | 02:38:42 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:39:27 | 2024-09-27 23:39:27 | 3 | 2.65
155 | TT24674 | Amruta Kore | - | - | - | Support from gokul | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 00:29:21 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:59:58 | 2024-09-27 16:59:58 | 0.5 | 0.49
156 | TT23932 | Amruta Kore | Sprint 1 | - | - | Task scheduling | Task Scheduling | 2024-09-12 | 00:30:00 | 00:42:07 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:57:02 | 2024-09-13 18:57:02 | 0.5 | 0.7
157 | TT24303 | Amruta Kore | Testing_GM_Oct_2024_Wk1 | - | - | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 01:26:08 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 1.44
158 | TT23932 | Amruta Kore | Sprint 1 | - | - | Task scheduling 26 to 27 Sept | Task Scheduling | 2024-09-26 | 01:00:00 | 01:14:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:56:23 | 2024-09-27 23:56:23 | 1 | 1.24
159 | TT24770 | Amruta Kore | - | - | - | Sub category Master - Estimation | Estimate the requirement | 2024-09-04 | 00:15:00 | 00:10:31 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 11:42:53 | 2024-09-04 11:42:53 | 0.25 | 0.18
160 | TT24672 | Amruta Kore | Dev to Handover Config master | - | - | Configuration master - Document reading | Documentation Reading | 2024-09-10 | 00:15:00 | 00:18:59 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 12:45:07 | 2024-09-10 12:45:07 | 0.25 | 0.32
161 | TT24674 | Amruta Kore | - | - | - | Weight range master scripting | Automate test script | 2024-09-26 | 03:00:00 | 02:36:37 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 23:56:55 | 2024-09-27 23:56:55 | 3 | 2.61
162 | TT23932 | Amruta Kore | Sprint 1 | - | - | Scheduling | Task Scheduling | 2024-09-05 | 00:30:00 | 00:31:35 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 21:02:32 | 2024-09-06 21:02:32 | 0.5 | 0.53
163 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 6 Sept | Technical guidance/Process Input | 2024-09-06 | 00:30:00 | 00:46:52 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:17 | 2024-09-06 20:14:17 | 0.5 | 0.78
164 | TT23932 | Amruta Kore | Sprint 1 | - | - | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:38:21 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.64
165 | TT24774 | Amruta Kore | - | - | - | KT New development-HM pcs adjustment field in RNG Process | KT Session | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 12:26:03 | 2024-09-26 12:26:03 | 0 | 0
166 | TT24672 | Amruta Kore | Dev to Handover Config master | - | - | Modification testcase of configuration master | Test case updation\modification | 2024-09-10 | 00:30:00 | 00:32:01 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 13:17:46 | 2024-09-10 13:17:46 | 0.5 | 0.53
167 | TT22785 | Amruta Kore | - | - | - | Lot tag testcase writing | Test case writing- | 2024-09-27 | 02:00:00 | 01:22:11 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 23:04:00 | 2024-09-30 23:04:00 | 2 | 1.37
168 | TT23932 | Amruta Kore | Sprint 1 | - | - | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:00:00 | 01:45:36 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2 | 1.76
169 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 5 Sept | Technical guidance/Process Input | 2024-09-05 | 00:30:00 | 00:10:34 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 22:54:47 | 2024-09-05 22:54:47 | 0.5 | 0.18
170 | TT23932 | Amruta Kore | Sprint 1 | - | - | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 01:30:00 | 01:27:19 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 1.5 | 1.46
171 | TT24683 | Amruta Kore | - | - | - | PCS Adjustment in offline tagging estimation | Estimate calculation | 2024-09-20 | 00:15:00 | 00:12:25 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:45:59 | 2024-09-20 23:45:59 | 0.25 | 0.21
172 | TT24390 | Amruta Kore | Testing_AutomationPractice_OCT24_WK1 | - | - | Supprot from Gokul | Support. | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:06:31 | 2024-09-18 17:06:31 | 0 | 0
173 | TT24683 | Amruta Kore | - | - | - | Pcs adjustment in offline tagging - Testcase writing | Test case writing- | 2024-09-26 | 02:00:00 | 01:47:54 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:54:29 | 2024-09-27 23:54:29 | 2 | 1.8
174 | TT23932 | Amruta Kore | Sprint 1 | - | - | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:37 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
175 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 4 Sept | Technical guidance/Process Input | 2024-09-04 | 00:30:00 | 00:16:25 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 21:42:25 | 2024-09-04 21:42:25 | 0.5 | 0.27
176 | TT23932 | Amruta Kore | Sprint 1 | - | - | Task scheduling 19 to 20 Sept | Task Scheduling | 2024-09-19 | 01:00:00 | 01:19:22 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:57:59 | 2024-09-20 23:57:59 | 1 | 1.32
177 | TT24683 | Amruta Kore | - | - | - | PCS Adjustment KT by snehal | KT Session | 2024-09-23 | 01:00:00 | 00:49:34 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 13:58:07 | 2024-09-23 13:58:07 | 1 | 0.83
178 | TT24390 | Amruta Kore | Testing_AutomationPractice_OCT24_WK1 | - | - | Set Tag Module - Script(As per testcase) | Automate test script | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:05:58 | 2024-09-18 17:05:58 | 0 | 0
179 | TT24683 | Amruta Kore | - | - | - | PCS adjustment in offline tagging - Brainstroming | Brainstorming - Internal ( Within Team member) | 2024-09-26 | 00:30:00 | 00:20:36 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:51:21 | 2024-09-27 16:51:21 | 0.5 | 0.34
180 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 3 Sept | Technical guidance/Process Input | 2024-09-03 | 00:30:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:09 | 2024-09-03 22:23:09 | 0.5 | 0.43
181 | TT23932 | Amruta Kore | Sprint 1 | - | - | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:39:51 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.66
182 | TT24674 | Amruta Kore | - | - | - | Weight Range master - Testcase writing | Test case writing- | 2024-09-24 | 01:00:00 | 01:18:06 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 16:52:05 | 2024-09-24 16:52:05 | 1 | 1.3
183 | TT22785 | Amruta Kore | - | - | - | Lot tag document reading | Document Reading | 2024-09-24 | 00:30:00 | 00:35:52 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 17:06:09 | 2024-09-24 17:06:09 | 0.5 | 0.6
184 | TT24647 | Amruta Kore | - | - | - | Support From Gokul - 2 Sept | Technical guidance/Process Input | 2024-09-02 | 00:30:00 | 00:12:30 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:44:17 | 2024-09-02 19:44:17 | 0.5 | 0.21
185 | TT24674 | Amruta Kore | - | - | - | Weight range master - Document reading | Document Reading | 2024-09-23 | 00:15:00 | 00:16:41 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 15:07:26 | 2024-09-23 15:07:26 | 0.25 | 0.28
186 | TT22163 | Amruta Kore | - | - | - | Support from gokul - Gr wt adjustment in offline tagging | Technical guidance/Process Input | 2024-09-23 | 01:30:00 | 00:29:32 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:10:16 | 2024-09-25 23:10:16 | 1.5 | 0.49
187 | TT24647 | Amruta Kore | - | - | - | BDD Module - Automation Script(Positive Testing) | Automate test script | 2024-09-02 | 28:00:00 | 25:34:17 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 22:49:49 | 2024-09-10 22:49:49 | 4 | 1.57
188 | TT22163 | Amruta Kore | - | - | - | Gross wt Adjustment in offline tagging- Automation script | Automate test script | 2024-09-23 | 12:00:00 | 10:51:07 | 2024-09-30 |  | IN_PROGRESS | DELAY | 2024-09-30 16:18:45 |  | 12 | 10.85
189 | TT23782 | Amruta Kore | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
190 | TT24678 | Amruta Kore | - | - | - | Making Charges Master - Testing | Testing | 2024-09-24 | 02:30:00 | 04:27:53 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 12:46:10 | 2024-09-26 12:46:10 | 2.5 | 4.46
191 | TT23782 | Amruta Kore | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
192 | TT24678 | Amruta Kore | - | - | - | Making charges Master Testcase Modification | Test case updation\modification | 2024-09-23 | 00:30:00 | 00:42:46 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:16:56 | 2024-09-23 23:16:56 | 0.5 | 0.71
193 | TT22785 | Amruta Kore | - | - | - | Lot Tag KT | KT Session | 2024-09-19 | 00:30:00 | 00:40:14 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 20:31:42 | 2024-09-19 20:31:42 | 0.5 | 0.67
194 | TT22163 | Amruta Kore | - | - | - | Gross wt Adjustment - Retesting | Retesting | 2024-09-19 | 04:00:00 | 04:32:43 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-25 10:50:41 | 2024-09-22 18:29:17 | 4 | 4.55
195 | TT24920 | Amruta Kore | - | - | - | Support from Gokul - Set tag Module | Technical guidance/Process Input | 2024-09-20 | 00:30:00 | 00:38:21 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:58:11 | 2024-09-20 23:58:11 | 0.5 | 0.64
196 | TT24920 | Amruta Kore | - | - | - | Set tag - Automation script as per Testcases | Script Execution/ Modification | 2024-09-20 | 04:00:00 | 03:30:13 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:19:43 | 2024-09-23 23:19:43 | 4 | 3.5
197 | TT21899 | Amruta Kore | - | - | - | Set Tag Module - Script(As per testcase) | Script Execution/ Modification | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-18 17:10:34 | 2024-09-18 17:10:34 | 0 | 0
198 | TT24769 | Amruta Kore | - | - | - | Testcase writing - Wastage code master | Test case writing- | 2024-09-20 | 01:00:00 | 00:54:35 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 13:14:15 | 2024-09-20 13:14:15 | 1 | 0.91
199 | TT17156 | Gokul Bhoi | - | - | - | Review code-Transfer order -Document scan/Old metal copy scan | Test script review | 2024-09-19 | 00:30:00 | 00:51:08 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-23 16:39:33 | 2024-09-23 16:39:33 | 0.5 | 0.85
200 | TT22830 | Gokul Bhoi | - | - | - | Karagir nave Jama Scripting Support By Gokul | Technical guidance/Process Input | 2024-09-24 | 02:00:00 | 01:56:36 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 16:04:23 | 2024-09-27 16:04:23 | 2 | 1.94
201 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:59 | 2024-10-06 23:46:59 | 0 | 0
202 | TT24647 | Gokul Bhoi | - | - | - | BDD Cross KT | KT Session | 2024-09-03 | 00:45:00 | 00:33:15 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:40 | 2024-09-03 22:23:40 | 0.75 | 0.55
203 | TT17156 | Gokul Bhoi | - | - | - | Automation Support(Transfer Order-Document scan and old metal copy ) | Technical guidance/Process Input | 2024-09-19 | 00:30:00 | 01:12:04 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-21 11:59:37 | 2024-09-21 11:59:37 | 0.5 | 1.2
204 | TT25654 | Gokul Bhoi | - | - | - | TT25654 Review Script (Pending vendor Invoices) | Script review | 2024-09-25 | 00:30:00 | 00:35:19 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:17:51 | 2024-09-25 23:17:51 | 0.5 | 0.59
205 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:43:31 | 2024-10-06 23:43:31 | 0.25 | 0
206 | TT17156 | Gokul Bhoi | - | - | - | Automation support | Technical guidance/Process Input | 2024-09-02 | 02:30:00 | 02:40:02 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:51 | 2024-09-06 20:14:51 | 2.5 | 2.67
207 | TT24678 | Gokul Bhoi | - | - | - | Making charge master Automation scripting | Automate test script | 2024-09-13 | 05:00:00 | 05:40:13 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-14 14:58:14 | 2024-09-14 14:58:14 | 5 | 5.67
208 | TT25654 | Gokul Bhoi | - | - | - | Support From Gokul (Pending vendor Invoices) | Technical guidance/Process Input | 2024-09-25 | 00:30:00 | 00:21:55 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:18:12 | 2024-09-25 19:18:12 | 0.5 | 0.37
209 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
210 | TT22455 | Gokul Bhoi | Gift card sales 1 | - | - | Review Gift voucher Automation script | Test script review | 2024-09-11 | 03:00:00 | 01:30:07 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 23:49:50 | 2024-09-13 23:49:50 | 3 | 1.5
211 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 6 Sept | Technical guidance/Process Input | 2024-09-06 | 00:30:00 | 00:46:52 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:17 | 2024-09-06 20:14:17 | 0.5 | 0.78
212 | TT23782 | Gokul Bhoi | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:01 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
213 | TT25655 | Gokul Bhoi | - | - | - | TT25655 Script Review Post Product Receipt | Script review | 2024-09-24 | 00:30:00 | 00:31:42 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 16:18:17 | 2024-09-25 16:18:17 | 0.5 | 0.53
214 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:49 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
215 | TT22455 | Gokul Bhoi | Gift card sales 1 | - | - | Support from Gokul - For Gift Voucher Script | Technical guidance/Process Input | 2024-09-11 | 01:30:00 | 00:47:30 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 21:22:32 | 2024-09-13 21:22:32 | 1.5 | 0.79
216 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 5 Sept | Technical guidance/Process Input | 2024-09-05 | 00:30:00 | 00:10:34 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 22:54:47 | 2024-09-05 22:54:47 | 0.5 | 0.18
217 | TT21914 | Gokul Bhoi | - | - | - | support to gokul | Query clarification | 2024-09-09 | 02:30:00 | 02:27:38 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:36:02 | 2024-09-13 22:36:02 | 2.5 | 2.46
218 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:28:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 2.47
219 | TT25655 | Gokul Bhoi | - | - | - | Support from gokul (Post product receipt ) | Technical guidance/Process Input | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 11:14:00 | 2024-09-25 11:14:00 | 0.5 | 0
220 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
221 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 4 Sept | Technical guidance/Process Input | 2024-09-04 | 00:30:00 | 00:16:25 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 21:42:25 | 2024-09-04 21:42:25 | 0.5 | 0.27
222 | TT22454 | Gokul Bhoi | - | - | - | Customer order repair Test case SCRIPTING | Automate test script | 2024-09-09 | 07:00:00 | 07:05:36 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:35:28 | 2024-09-13 22:35:28 | 7 | 7.09
223 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 00:15:00 | 00:16:27 | 2024-10-10 |  | IN_PROGRESS | DELAY | 2024-10-07 13:31:36 |  | 0.25 | 0.27
224 | TT24760 | Gokul Bhoi | - | - | - | TT24760 -Review Bank Master Automation Scripting | Script review | 2024-09-26 | 00:30:00 | 00:43:54 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 19:19:05 | 2024-09-26 19:19:05 | 0.5 | 0.73
225 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Walk in interview support | Interview | 2024-09-30 | 12:00:00 | 05:22:43 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 12 | 5.38
226 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 3 Sept | Technical guidance/Process Input | 2024-09-03 | 00:30:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 22:23:09 | 2024-09-03 22:23:09 | 0.5 | 0.43
227 | TT21945 | Gokul Bhoi | - | - | - | Review -HM Centre & PO check Positive Flow Scripting | Test script review | 2024-09-11 | 01:30:00 | 02:24:35 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:07:22 | 2024-09-13 22:07:22 | 1.5 | 2.41
228 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
229 | TT18255 | Gokul Bhoi | - | - | - | TT18255 -Review URD Scripting 50 Percent coverage | Script review | 2024-09-23 | 00:30:00 | 00:30:49 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:15:07 | 2024-09-23 23:15:07 | 0.5 | 0.51
230 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:22:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0.38
231 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - 2 Sept | Technical guidance/Process Input | 2024-09-02 | 00:30:00 | 00:12:13 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:44:17 | 2024-09-02 19:44:17 | 0.5 | 0.2
232 | TT21945 | Gokul Bhoi | - | - | - | Review -HM , LM Stage (QC process) Positive flow Scripting | Test script review | 2024-09-09 | 01:00:00 | 01:09:25 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-11 11:30:42 | 2024-09-11 11:30:42 | 1 | 1.16
233 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 02:00:01 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 2
234 | TT21914 | Gokul Bhoi | - | - | - | KRA -KPI relevant action plan with Gokul & Sayali | Explore Team capability/Improvement plan | 2024-09-23 | 02:00:00 | 00:56:14 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 20:31:38 | 2024-09-24 20:31:38 | 2 | 0.94
235 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:20:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.34
236 | TT23782 | Gokul Bhoi | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
237 | TT17156 | Gokul Bhoi | - | - | - | Review Transfer Order Automation Scripting | Test script review | 2024-09-09 | 03:45:00 | 01:24:21 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 23:50:31 | 2024-09-13 23:50:31 | 3.75 | 1.41
238 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 01:08:10 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 1.14
239 | TT21914 | Gokul Bhoi | - | - | - | Support to Gokul | Query clarification | 2024-09-23 | 02:30:00 | 00:43:06 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:53:43 | 2024-09-27 19:53:43 | 2.5 | 0.72
240 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:30:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0.5
241 | TT22454 | Gokul Bhoi | - | - | - | Customer Order Repair bug sheet review | Review | 2024-09-02 | 01:15:00 | 01:12:49 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 21:10:29 | 2024-09-02 21:10:29 | 1.25 | 1.21
242 | TT24647 | Gokul Bhoi | - | - | - | Review BDD Automation scripting | Test script review | 2024-09-09 | 01:30:00 | 01:02:57 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-11 11:37:36 | 2024-09-11 11:37:36 | 1.5 | 1.05
243 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:52:24 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.87
244 | TT14931 | Gokul Bhoi | - | - | - | Estimate Review - Customer Order | Review | 2024-09-06 | 00:15:00 | 00:16:57 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:15:40 | 2024-09-06 20:15:40 | 0.25 | 0.28
245 | TT24647 | Gokul Bhoi | - | - | - | Support From Gokul - BDD Scheme Script | Technical guidance/Process Input | 2024-09-09 | 01:00:00 | 01:00:57 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:38:14 | 2024-09-10 19:38:14 | 1 | 1.02
246 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 01:02:44 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 1.05
247 | TT24678 | Gokul Bhoi | - | - | - | Review - Making charges Master Testcase After Modification | Review updated Test cases | 2024-09-23 | 00:15:00 | 00:14:42 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 23:57:33 | 2024-09-24 23:57:33 | 0.25 | 0.25
248 | TT24678 | Gokul Bhoi | - | - | - | Making charges master - Testcase Review | Test Case Review | 2024-09-09 | 00:30:00 | 00:40:42 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-10 10:54:12 | 2024-09-10 10:54:12 | 0.5 | 0.68
249 | TT23423 | Gokul Bhoi | - | - | - | SSRS report Estimation - 5 reports - Review | Review | 2024-09-10 | 00:30:00 | 00:13:14 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 23:43:34 | 2024-09-10 23:43:34 | 0.5 | 0.22
250 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:15:00 | 01:09:45 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1.25 | 1.16
251 | TT22163 | Gokul Bhoi | - | - | - | TT22163 -Review -Gross wt Adjustment in offline tagging- Automation script | Test script review | 2024-09-23 | 01:30:00 | 01:05:59 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:10:05 | 2024-09-25 23:10:05 | 1.5 | 1.1
252 | TT14931 | Gokul Bhoi | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:21 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
253 | TT22163 | Gokul Bhoi | - | - | - | Review - offline tagging Estimation merge with gr wt adjustment | Review | 2024-09-10 | 00:15:00 | 00:19:26 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 23:26:26 | 2024-09-10 23:26:26 | 0.25 | 0.32
254 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:27:43 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.46
255 | TT23985 | Gokul Bhoi | - | - | - | TT23985 -Review- Stock Repair Positive flow Scripting (50% TC Cover) | Test script review | 2024-10-07 | 00:24:00 | 00:00:00 | 2024-10-11 |  | TO_DO | DELAY | 2024-10-04 16:20:00 |  | 0.4 | 0
256 | TT22810 | Gokul Bhoi | - | - | - | Review test case of RNG | Test Case Review | 2024-09-09 | 00:30:00 | 00:44:08 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-13 17:41:36 | 2024-09-13 17:41:36 | 0.5 | 0.74
257 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:48 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
258 | TT21945 | Gokul Bhoi | - | - | - | TT21945 -Review- QC Process (PR , DC , QC) TC Scripting | Test script review | 2024-09-23 | 00:30:00 | 00:15:17 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 20:04:02 | 2024-09-23 20:04:02 | 0.5 | 0.25
259 | TT17156 | Gokul Bhoi | - | - | - | Automation Support | Technical guidance/Process Input | 2024-09-09 | 02:30:00 | 02:56:48 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:25:13 | 2024-09-13 18:25:13 | 2.5 | 2.95
260 | TT14931 | Gokul Bhoi | - | - | - | Review customer order testing | Review | 2024-09-12 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:10 | 2024-09-13 12:08:10 | 0 | 0
261 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support By Preeti ma'am | Mentoring | 2024-09-02 | 02:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-02 14:41:34 | 2024-09-02 14:41:34 | 2.5 | 0
262 | TT24674 | Gokul Bhoi | - | - | - | Support from gokul | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 00:29:15 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:59:58 | 2024-09-27 16:59:58 | 0.5 | 0.49
263 | TT24683 | Gokul Bhoi | - | - | - | KT - PCS Adjustment Sub Module to developer and tester | KT Session | 2024-09-06 | 01:13:00 | 01:06:13 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:16:03 | 2024-09-06 19:16:03 | 1.22 | 1.1
264 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | P2P Process automation scripting demo | Demo | 2024-10-07 | 00:30:00 | 01:28:46 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 15:26:06 | 2024-10-07 15:26:06 | 0.5 | 1.48
265 | TT14931 | Gokul Bhoi | - | - | - | Review customer order update test case | Test Case Review | 2024-09-11 | 00:15:00 | 00:20:00 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 19:03:28 | 2024-09-11 19:03:28 | 0.25 | 0.33
266 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:07:59 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.13
267 | TT24674 | Gokul Bhoi | - | - | - | Weight range master script review | Test script review | 2024-09-26 | 00:30:00 | 00:21:09 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 23:56:47 | 2024-09-27 23:56:47 | 0.5 | 0.35
268 | TT14931 | Gokul Bhoi | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:01 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
269 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
270 | TT23985 | Gokul Bhoi | - | - | - | Support From Gokul | Technical guidance/Process Input | 2024-10-03 | 01:00:00 | 00:49:16 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:58 | 2024-10-04 19:41:58 | 1 | 0.82
271 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Weekly meeting with gaurav sir 20th Sep | Weekly sync call | 2024-09-20 | 01:00:00 | 00:59:39 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:50:01 | 2024-09-20 20:50:01 | 1 | 0.99
272 | TT24674 | Gokul Bhoi | - | - | - | Weight range master - testcase review | Test Case Review | 2024-09-24 | 00:30:00 | 00:17:05 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 17:27:15 | 2024-09-25 17:27:15 | 0.5 | 0.28
273 | TT21914 | Gokul Bhoi | - | - | - | support to Gokul | Query clarification | 2024-09-02 | 02:30:00 | 00:36:59 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:29:04 | 2024-09-06 19:29:04 | 2.5 | 0.62
274 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 00:44:23 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 0.74
275 | TT21945 | Gokul Bhoi | - | - | - | Automation support from gokul | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:24:53 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-25 14:04:22 | 2024-09-25 14:04:22 | 0.5 | 0.41
276 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 01:27:33 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 1.46
277 | TT24683 | Gokul Bhoi | - | - | - | PCS adjustment in offline tagging - Brainstroming | Brainstorming - Internal ( Within Team member) | 2024-09-26 | 00:30:00 | 00:20:36 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-27 16:51:21 | 2024-09-27 16:51:21 | 0.5 | 0.34
278 | TT14931 | Gokul Bhoi | - | - | - | Customer order Automation Scripting (Positive flow) | Automate test script | 2024-09-04 | 02:30:00 | 03:34:35 | 2024-09-05 |  | COMPLETED | DELAY | 2024-09-06 17:20:06 | 2024-09-06 17:20:06 | 2.5 | 3.58
279 | TT24760 | Gokul Bhoi | - | - | - | Automation Support From Gokul Bank Master | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 01:32:31 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 18:48:38 | 2024-09-26 18:48:38 | 0.5 | 1.54
280 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 02:27:19 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 2.46
281 | TT22454 | Gokul Bhoi | - | - | - | Review customer order repair testing | Reporting Review | 2024-09-24 | 00:45:00 | 00:34:56 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 16:55:20 | 2024-09-26 16:55:20 | 0.75 | 0.58
282 | TT23436 | Gokul Bhoi | - | - | - | PadmStockBalance API Testing | Api Testing | 2024-09-06 | 01:30:00 | 01:34:27 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-09 16:36:46 | 2024-09-09 16:36:46 | 1.5 | 1.57
283 | TT22454 | Gokul Bhoi | - | - | - | Support From Gokul(Customer order repair) | Query clarification | 2024-09-24 | 00:45:00 | 03:12:15 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:30:23 | 2024-09-25 19:30:23 | 0.75 | 3.2
284 | TT14931 | Gokul Bhoi | - | - | - | Review Customer order testing 23 sep | Reporting Review | 2024-09-23 | 01:00:00 | 00:37:42 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 23:45:01 | 2024-09-24 23:45:01 | 1 | 0.63
285 | TT23436 | Gokul Bhoi | - | - | - | PadmStockBalance API Test case writing | Test Case Writing | 2024-09-03 | 01:25:00 | 01:21:04 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:09:37 | 2024-09-03 23:09:37 | 1.42 | 1.35
286 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | Task rescheduling | Task Scheduling | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 23:51:57 | 2024-09-24 23:51:57 | 0.5 | 0
287 | TT22163 | Gokul Bhoi | - | - | - | Support from gokul - Gr wt adjustment in offline tagging | Technical guidance/Process Input | 2024-09-23 | 01:30:00 | 00:29:29 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:10:16 | 2024-09-25 23:10:16 | 1.5 | 0.49
288 | TT24647 | Gokul Bhoi | - | - | - | Review Stock transfer Automation Scripting | Review | 2024-09-02 | 02:30:00 | 01:44:15 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:13:45 | 2024-09-06 20:13:45 | 2.5 | 1.74
289 | TT14931 | Gokul Bhoi | - | - | - | Support from Gokul(customer order) | Query clarification | 2024-09-23 | 00:30:00 | 00:27:36 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:42:41 | 2024-09-24 19:42:41 | 0.5 | 0.46
290 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | Modification and Update of Generic Method in Framework | Modify test script | 2024-09-25 | 04:00:00 | 14:07:49 | 2024-09-27 |  | COMPLETED | HIGHLY_DELAY | 2024-09-29 23:25:05 | 2024-09-29 23:25:05 | 4 | 14.13
291 | TT18255 | Gokul Bhoi | - | - | - | Support From Gokul URD | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:40:43 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 19:21:47 | 2024-09-23 19:21:47 | 0.5 | 0.68
292 | TT24672 | Gokul Bhoi | Dev to Handover Config master | - | - | Configuration Master - Script review | Script review | 2024-09-27 | 00:30:00 | 00:28:54 | 2024-09-27 |  | COMPLETED | DELAY | 2024-09-29 23:54:45 | 2024-09-29 23:54:45 | 0.5 | 0.48
293 | TT24647 | Gokul Bhoi | - | - | - | Review BDD module Automation Scripting | Review | 2024-09-02 | 02:30:00 | 01:47:46 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 23:44:27 | 2024-09-06 23:44:27 | 2.5 | 1.8
294 | TT24683 | Gokul Bhoi | - | - | - | PCS Adjustment in offline tagging estimation | Estimate calculation | 2024-09-20 | 00:15:00 | 00:12:33 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:45:59 | 2024-09-20 23:45:59 | 0.25 | 0.21
295 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | Task Scheduling | Task Scheduling | 2024-09-26 | 01:00:00 | 00:42:40 | 2024-09-27 |  | COMPLETED | HIGHLY_DELAY | 2024-09-29 23:25:36 | 2024-09-29 23:25:36 | 1 | 0.71
296 | TT24774 | Gokul Bhoi | - | - | - | HallMarking Script Review | Script review | 2024-10-04 | 00:15:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-29 12:05:11 |  | 0.25 | 0
297 | TT24672 | Gokul Bhoi | Dev to Handover Config master | - | - | Support from gokul - Configuration master script | Technical guidance/Process Input | 2024-09-27 | 00:30:00 | 00:20:32 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:12:38 | 2024-09-27 20:12:38 | 0.5 | 0.34
298 | TT14720 | Gokul Bhoi | - | - | - | review estimation of RNG | Review | 2024-09-02 | 00:15:00 | 00:10:13 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:56:33 | 2024-09-02 19:56:33 | 0.25 | 0.17
299 | TT24206 | Gokul Bhoi | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
300 | TT24774 | Gokul Bhoi | - | - | - | KT New development-HM pcs adjustment field in RNG Process | KT Session | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 12:26:03 | 2024-09-26 12:26:03 | 0 | 0
301 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | p2p scripting modification | Modify test script | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 0
302 | TT14931 | Gokul Bhoi | - | - | - | Cutomer order and customer order repair bugs explain by gokul sir | General meeting | 2024-09-28 | 00:30:00 | 00:45:15 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 18:23:11 | 2024-09-28 18:23:11 | 0.5 | 0.75
303 | TT24772 | Gokul Bhoi | - | - | - | Designer master - Estimation Review | Review | 2024-09-04 | 00:15:00 | 00:07:26 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:59:58 | 2024-09-04 19:59:58 | 0.25 | 0.12
304 | TT24206 | Gokul Bhoi | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
305 | TT22163 | Gokul Bhoi | - | - | - | Support from gokul - Code Merged P2P process | Query clarification | 2024-10-05 | 01:00:00 | 01:40:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:24:33 | 2024-10-05 23:24:33 | 1 | 1.68
306 | TT24683 | Gokul Bhoi | - | - | - | PCS Adjustment KT by snehal | KT Session | 2024-09-23 | 00:00:00 | 00:00:00 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 13:58:07 | 2024-09-23 13:58:07 | 0 | 0
307 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 26:36:28 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.61
308 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Code modification PADM customer order status | Automate test script | 2024-10-05 | 03:00:00 | 00:00:00 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:32:22 | 2024-10-05 23:32:22 | 3 | 0
309 | TT24678 | Gokul Bhoi | - | - | - | Making charges Master bugsheet Review | Reporting Review | 2024-09-28 | 00:30:00 | 00:27:04 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 18:22:51 | 2024-09-28 18:22:51 | 0.5 | 0.45
310 | TT24769 | Gokul Bhoi | - | - | - | Wastage code master Estimation - Review | Review | 2024-09-05 | 00:15:00 | 00:06:57 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 11:41:05 | 2024-09-05 11:41:05 | 0.25 | 0.12
311 | TT18255 | Gokul Bhoi | - | - | - | Support from Gokul URD Silver | Support. | 2024-10-05 | 01:00:00 | 00:59:51 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:22:37 | 2024-10-05 23:22:37 | 1 | 1
312 | TT24920 | Gokul Bhoi | - | - | - | Set Tag Automation Script Review | Test script review | 2024-09-23 | 00:30:00 | 00:00:00 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:15:37 | 2024-09-23 23:15:37 | 0.5 | 0
313 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | Task Scheduling | Task Scheduling | 2024-09-19 | 01:00:00 | 01:18:17 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:47:16 | 2024-09-20 23:47:16 | 1 | 1.3
314 | TT18255 | Gokul Bhoi | - | - | - | Support From Gokul URD | Test Script Preparation | 2024-10-07 | 00:30:00 | 01:00:34 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:40:39 |  | 0.5 | 1.01
315 | TT14931 | Gokul Bhoi | - | - | - | Support(Customer order ) | Query clarification | 2024-09-11 | 00:30:00 | 00:23:21 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:06:31 | 2024-09-13 12:06:31 | 0.5 | 0.39
316 | TT23053 | Gokul Bhoi | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 03:08:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 3.15
317 | TT18255 | Gokul Bhoi | - | - | - | Support for automation URD from Gokul | Technical guidance/Process Input | 2024-09-19 | 01:00:00 | 02:10:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:24 | 2024-09-20 19:48:24 | 1 | 2.18
318 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 01:30:00 | 01:35:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 1.5 | 1.59
319 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Padm Labour charges Automation scripting | Automate test script | 2024-10-03 | 08:00:00 | 07:20:10 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-03 13:21:32 | 2024-10-03 13:21:32 | 8 | 7.34
320 | TT24770 | Gokul Bhoi | - | - | - | Sub category Master - Estimation review | Review | 2024-09-04 | 00:15:00 | 00:07:05 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:54:07 | 2024-09-04 19:54:07 | 0.25 | 0.12
321 | TT18255 | Gokul Bhoi | - | - | - | Support from Gokul URD Automation | Query clarification | 2024-10-03 | 01:00:00 | 00:23:06 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:23 | 2024-10-04 19:08:23 | 1 | 0.39
322 | TT24920 | Gokul Bhoi | - | - | - | Support from Gokul - Set tag Module | Technical guidance/Process Input | 2024-09-20 | 00:30:00 | 00:38:21 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:58:11 | 2024-09-20 23:58:11 | 0.5 | 0.64
323 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:39:51 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.66
324 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Generic Methods for Framework Automation Scripting | Automate test script | 2024-10-03 | 08:00:00 | 04:54:44 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:32:18 | 2024-10-04 23:32:18 | 8 | 4.91
325 | TT22830 | Gokul Bhoi | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 0
326 | TT24778 | Gokul Bhoi | - | - | - | Item Type Master Estimation - Review | Review | 2024-09-04 | 00:15:00 | 00:08:12 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:41:10 | 2024-09-04 19:41:10 | 0.25 | 0.14
327 | TT22810 | Gokul Bhoi | - | - | - | Automation Support From gokul(RNG) | Query clarification | 2024-10-03 | 02:00:00 | 02:00:14 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 22:29:35 |  | 2 | 2
328 | TT14931 | Gokul Bhoi | - | - | - | Customer order Scripting as Per test cases(40%) | Automate test script | 2024-09-20 | 03:30:00 | 03:02:30 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-30 01:50:15 | 2024-09-30 01:50:15 | 3.5 | 3.04
329 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | Task Scheduling 6-9-2024 | Task Scheduling | 2024-09-05 | 01:00:00 | 01:00:14 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 23:58:01 | 2024-09-06 23:58:01 | 1 | 1
330 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | P2P process code merge | Automate test script | 2024-09-28 | 05:00:00 | 04:53:49 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 23:17:09 | 2024-09-28 23:17:09 | 5 | 4.9
331 | TT21945 | Gokul Bhoi | - | - | - | Support from Gokul - P2P process (Gold, Silver, Platinum) | Query clarification | 2024-10-01 | 01:00:00 | 00:52:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:33:21 | 2024-10-04 22:33:21 | 1 | 0.88
332 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
333 | TT24777 | Gokul Bhoi | - | - | - | QC Setup Master - Estimation Review | Review | 2024-09-04 | 00:15:00 | 00:13:07 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:50:52 | 2024-09-04 19:50:52 | 0.25 | 0.22
334 | TT22200 | Gokul Bhoi | - | - | - | Items Category code modification | Automate test script | 2024-09-18 | 06:00:00 | 05:26:23 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 21:21:12 | 2024-09-19 21:21:12 | 6 | 5.44
335 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:18:57 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 2.32
336 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Supprot from Gokul | Support. | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:06:31 | 2024-09-18 17:06:31 | 0 | 0
337 | TT21945 | Gokul Bhoi | - | - | - | P2P Process Support from Gokul | Query clarification | 2024-10-03 | 01:00:00 | 00:09:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:47 | 2024-10-04 19:08:47 | 1 | 0.16
338 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
339 | TT22810 | Gokul Bhoi | - | - | - | Support form gokul(RNG) | Technical guidance/Process Input | 2024-09-18 | 00:15:00 | 00:35:46 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 19:18:21 | 2024-09-18 19:18:21 | 0.25 | 0.6
340 | TT23932 | Gokul Bhoi | Sprint 1 | - | - | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:18 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
341 | TT24390 | Gokul Bhoi | Testing_AutomationPractice_OCT24_WK1 | - | - | Review code - Set Tag Module Atomation Script | Test script review | 2024-09-19 | 00:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-18 17:05:27 | 2024-09-18 17:05:27 | 0 | 0
342 | TT22785 | Gokul Bhoi | - | - | - | Lot Tag BrainStroming - | Brainstorming - Internal ( Within Team member) | 2024-09-27 | 00:30:00 | 00:54:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:45:04 | 2024-09-27 19:45:04 | 0.5 | 0.9
343 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:10 | 2024-10-06 23:45:10 | 0 | 0
344 | TT24776 | Gokul Bhoi | - | - | - | Agent Master Review | Review | 2024-09-04 | 00:15:00 | 00:13:03 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 19:33:44 | 2024-09-04 19:33:44 | 0.25 | 0.22
345 | TT14931 | Gokul Bhoi | - | - | - | Review customer order testing | Reporting Review | 2024-09-19 | 01:00:00 | 00:40:14 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-23 19:41:03 | 2024-09-23 19:41:03 | 1 | 0.67
346 | TT24777 | Gokul Bhoi | - | - | - | QC Setup Master script Review | Script review | 2024-09-27 | 00:30:00 | 00:21:32 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:51:58 | 2024-09-27 19:51:58 | 0.5 | 0.36
347 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:20 | 2024-10-06 23:45:20 | 0 | 0
348 | TT24771 | Gokul Bhoi | - | - | - | Review of Size master | Review | 2024-09-03 | 00:10:00 | 00:06:03 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:08:16 | 2024-09-03 23:08:16 | 0.17 | 0.1
349 | TT14931 | Gokul Bhoi | - | - | - | Support from gokul(Customer order) | Query clarification | 2024-09-19 | 00:30:00 | 01:03:37 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:56:13 | 2024-09-20 22:56:13 | 0.5 | 1.06
350 | TT24777 | Gokul Bhoi | - | - | - | Qc setup Master Support from gokul | Query clarification | 2024-09-27 | 00:30:00 | 00:56:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:04:11 | 2024-09-27 17:04:11 | 0.5 | 0.93
351 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-06 23:48:07 |  | 0.25 | 0
352 | TT24680 | Gokul Bhoi | - | - | - | Review estimation of sub-smith master | Review | 2024-09-03 | 00:10:00 | 00:08:39 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:08:49 | 2024-09-03 23:08:49 | 0.17 | 0.14
353 | TT24774 | Gokul Bhoi | - | - | - | Code Review - HallMarking automation script | Test script review | 2024-09-19 | 00:30:00 | 00:23:32 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 23:44:38 | 2024-09-19 23:44:38 | 0.5 | 0.39
354 | TT24678 | Gokul Bhoi | - | - | - | Making charges master - bugsheet Review | Reporting Review | 2024-09-25 | 00:30:00 | 00:14:16 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 23:59:36 | 2024-09-25 23:59:36 | 0.5 | 0.24
355 | TT24303 | Gokul Bhoi | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:47 | 2024-10-06 23:46:47 | 0 | 0
356 | TT24647 | Gokul Bhoi | - | - | - | BDD Estimation Review | Review. | 2024-09-04 | 00:30:00 | 00:24:10 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 23:12:47 | 2024-09-04 23:12:47 | 0.5 | 0.4
357 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:37 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
358 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point to Kiran Karagir Nave | Support. | 2024-10-01 | 00:30:00 | 00:27:02 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:43 | 2024-10-01 19:02:43 | 0.5 | 0.45
359 | TT14931 | Kiran Dhanepkar | - | - | - | Customer Order retesting(Gold and silver) | E2E Testing | 2024-09-12 | 01:30:00 | 01:04:41 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:00:02 | 2024-09-13 12:00:02 | 1.5 | 1.08
360 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Nave TC Writting and updation | Test Case Writing | 2024-10-01 | 04:30:00 | 04:00:41 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:53 | 2024-10-01 19:02:53 | 4.5 | 4.01
361 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Nave BrainStroming | Brainstorming with DEV Team/BA | 2024-09-30 | 00:15:00 | 00:13:17 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 15:35:06 | 2024-09-30 15:35:06 | 0.25 | 0.22
362 | TT24776 | Kiran Dhanepkar | - | - | - | Support from Saurabh(Agent Master) | Query clarification | 2024-09-30 | 00:30:00 | 00:22:31 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:56:57 | 2024-09-30 19:56:57 | 0.5 | 0.38
363 | TT24776 | Kiran Dhanepkar | - | - | - | Agent Master Automation Scripting-Positive flow | Automate test script | 2024-09-30 | 03:45:00 | 03:40:38 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 20:08:35 | 2024-09-30 20:08:35 | 3.75 | 3.68
364 | TT22830 | Kiran Dhanepkar | - | - | - | Karagir Jama Brainstorming | Brainstorming with DEV Team/BA | 2024-10-03 | 00:45:00 | 00:39:24 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:47:04 | 2024-10-03 18:47:04 | 0.75 | 0.66
365 | TT22830 | Kiran Dhanepkar | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
366 | TT22810 | Kiran Dhanepkar | - | - | - | Automation script RNG As per test cases | Test Script Preparation | 2024-09-18 | 03:00:00 | 03:08:24 | 2024-09-18 |  | COMPLETED | DELAY | 2024-09-19 17:10:04 | 2024-09-19 17:10:04 | 3 | 3.14
367 | TT22454 | Kiran Dhanepkar | - | - | - | Customer order repair retesting(All type) | E2E Testing. | 2024-09-24 | 07:00:00 | 07:02:46 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:28:50 | 2024-09-25 19:28:50 | 7 | 7.05
368 | TT14931 | Kiran Dhanepkar | - | - | - | Support from gokul(Customer order) | Query clarification | 2024-09-19 | 00:30:00 | 00:47:33 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:56:13 | 2024-09-20 22:56:13 | 0.5 | 0.79
369 | TT22454 | Kiran Dhanepkar | - | - | - | Support From Gokul(Customer order repair) | Query clarification | 2024-09-24 | 00:45:00 | 00:40:30 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:30:23 | 2024-09-25 19:30:23 | 0.75 | 0.68
370 | TT14931 | Kiran Dhanepkar | - | - | - | Customer order retesting according to new CR(Gold, Silver, platinum and diamond jewellery) | E2E Testing. | 2024-09-19 | 07:30:00 | 07:32:38 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 13:22:27 | 2024-09-21 13:22:27 | 7.5 | 7.54
371 | TT14931 | Kiran Dhanepkar | - | - | - | Customer order retesting according to new CR(MRP,Forming ,Gold Bullion and Silver Bullion) | E2E Testing. | 2024-09-23 | 06:30:00 | 06:42:20 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:42:49 | 2024-09-24 19:42:49 | 6.5 | 6.71
372 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Support(Transfer Order-Document scan and old metal copy ) | Technical guidance/Process Input | 2024-09-19 | 00:30:00 | 01:12:04 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-21 11:59:37 | 2024-09-21 11:59:37 | 0.5 | 1.2
373 | TT14931 | Kiran Dhanepkar | - | - | - | Customer order bugs discussion | Testing | 2024-09-23 | 00:30:00 | 00:20:36 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 19:20:21 | 2024-09-23 19:20:21 | 0.5 | 0.34
374 | TT14931 | Kiran Dhanepkar | - | - | - | Support from Gokul(customer order) | Query clarification | 2024-09-23 | 00:30:00 | 00:35:51 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:42:41 | 2024-09-24 19:42:41 | 0.5 | 0.6
375 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Scripting by DTO(Transfer Order-Document scan and Old Metal copy ) | Test Script Preparation | 2024-09-19 | 04:00:00 | 05:02:12 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-21 13:24:46 | 2024-09-21 13:24:46 | 4 | 5.04
376 | TT22810 | Kiran Dhanepkar | - | - | - | Support form gokul(RNG) | Technical guidance/Process Input | 2024-09-18 | 00:15:00 | 00:35:56 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 19:18:21 | 2024-09-18 19:18:21 | 0.25 | 0.6
377 | TT14931 | Kiran Dhanepkar | - | - | - | Update customer order test cases according to new changes | Test case updation\modification | 2024-09-11 | 01:00:00 | 01:10:01 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-12 15:54:45 | 2024-09-12 15:54:45 | 1 | 1.17
378 | TT14931 | Kiran Dhanepkar | - | - | - | Estimation of Customer order | Estimate calculation | 2024-09-06 | 00:30:00 | 00:30:34 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:30 | 2024-09-06 17:05:30 | 0.5 | 0.51
379 | TT14931 | Kiran Dhanepkar | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:21 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
380 | TT24206 | Kiran Dhanepkar | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
381 | TT24683 | Kiran Dhanepkar | - | - | - | KT - PCS Adjustment Sub Module to developer and tester | KT Session | 2024-09-06 | 01:13:00 | 01:06:13 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:16:03 | 2024-09-06 19:16:03 | 1.22 | 1.1
382 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
383 | TT24206 | Kiran Dhanepkar | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
384 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Support | Technical guidance/Process Input | 2024-09-09 | 02:30:00 | 03:30:07 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:25:13 | 2024-09-13 18:25:13 | 2.5 | 3.5
385 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:37:28 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.62
386 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Scripting by DTO(Tag/Bulk tag-transfer order-Branch to branch and State to state) | Test Script Preparation | 2024-09-09 | 21:00:00 | 22:15:06 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 16:57:55 | 2024-09-18 16:57:55 | 21 | 22.25
387 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:37 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
388 | TT14931 | Kiran Dhanepkar | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
389 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 00:45:00 | 01:21:23 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 0.75 | 1.36
390 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
391 | TT17156 | Kiran Dhanepkar | - | - | - | Estimation of E-way bill added in E-Invoice | Estimate calculation | 2024-09-03 | 00:15:00 | 00:15:34 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:53:41 | 2024-09-03 14:53:41 | 0.25 | 0.26
392 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:31 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 0.28
393 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
394 | TT14931 | Kiran Dhanepkar | - | - | - | Support(Customer order ) | Query clarification | 2024-09-11 | 00:30:00 | 00:23:33 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:06:31 | 2024-09-13 12:06:31 | 0.5 | 0.39
395 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:54:24 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.91
396 | TT24771 | Kiran Dhanepkar | - | - | - | Estimation of Size master | Estimate calculation | 2024-09-03 | 00:15:00 | 00:16:45 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:53:04 | 2024-09-03 14:53:04 | 0.25 | 0.28
397 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:30:36 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.51
398 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
399 | TT24680 | Kiran Dhanepkar | - | - | - | Estimation of sub-smith master | Estimate calculation | 2024-09-03 | 00:15:00 | 00:12:29 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:53:16 | 2024-09-03 14:53:16 | 0.25 | 0.21
400 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
401 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:50:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 1.84
402 | TT24774 | Kiran Dhanepkar | - | - | - | Estimation of hallmarking master | Estimate calculation | 2024-09-03 | 00:30:00 | 00:26:33 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:52:52 | 2024-09-03 14:52:52 | 0.5 | 0.44
403 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
404 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | Scheduling 4 Oct | Task Scheduling | 2024-10-03 | 01:00:00 | 00:50:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:32:22 | 2024-10-04 23:32:22 | 1 | 0.84
405 | TT24674 | Kiran Dhanepkar | - | - | - | Estimation of weight range master | Estimate calculation | 2024-09-02 | 00:15:00 | 00:13:53 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 18:23:37 | 2024-09-02 18:23:37 | 0.25 | 0.23
406 | TT24303 | Kiran Dhanepkar | Testing_GM_Oct_2024_Wk1 | - | - | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 03:28:08 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 3.47
407 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | Scheduling | Task Scheduling | 2024-09-25 | 01:00:00 | 00:50:52 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 16:02:00 | 2024-09-30 16:02:00 | 1 | 0.85
408 | TT14720 | Kiran Dhanepkar | - | - | - | Estimation of RNG | Estimate calculation | 2024-09-02 | 00:15:00 | 00:31:32 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 18:23:24 | 2024-09-02 18:23:24 | 0.25 | 0.53
409 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 01:30:00 | 01:49:26 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 1.5 | 1.82
410 | TT17156 | Kiran Dhanepkar | - | - | - | Automation support | Technical guidance/Process Input | 2024-09-02 | 02:30:00 | 02:39:45 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:14:51 | 2024-09-06 20:14:51 | 2.5 | 2.66
411 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 01:30:00 | 01:35:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 1.5 | 1.59
412 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point karagir Jama to Kiran | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0 | 0
413 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | Scheduling 20 sep | Task Scheduling | 2024-09-19 | 01:00:00 | 00:54:50 | 2024-09-20 |  | COMPLETED | HIGHLY_DELAY | 2024-09-21 10:44:39 | 2024-09-21 10:44:39 | 1 | 0.91
414 | TT22810 | Kiran Dhanepkar | - | - | - | Automation Support From gokul(RNG) | Query clarification | 2024-10-03 | 02:24:00 | 02:00:14 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 22:29:35 |  | 2.4 | 2
415 | TT17156 | Kiran Dhanepkar | - | - | - | Automation Scripting by DTO(Stock Transfer counter to counter positive flow) | Test Script Preparation | 2024-09-02 | 23:15:00 | 25:23:09 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-10 17:02:31 | 2024-09-10 17:02:31 | 23.25 | 1.39
416 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:39:51 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.66
417 | TT22810 | Kiran Dhanepkar | - | - | - | RNG process Scripting(100%) | Automate test script | 2024-10-03 | 12:00:00 | 10:20:50 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 22:24:37 |  | 12 | 10.35
418 | TT23782 | Kiran Dhanepkar | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
419 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | Scheduling 12 sep | Task Scheduling | 2024-09-12 | 01:00:00 | 00:57:35 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:24:41 | 2024-09-13 18:24:41 | 1 | 0.96
420 | TT22830 | Kiran Dhanepkar | - | - | - | Support Point to Kiran Karagir jama | Query clarification | 2024-10-03 | 01:00:00 | 00:26:51 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:36 | 2024-10-04 19:41:36 | 1 | 0.45
421 | TT22810 | Kiran Dhanepkar | - | - | - | Test case writing RNG Process(gold,silver, platinum and diamond jewellery) | Test Case Writing | 2024-09-09 | 02:30:00 | 02:32:38 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:56:45 | 2024-09-10 19:56:45 | 2.5 | 2.54
422 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | Scheduling 6 September | Task Scheduling | 2024-09-05 | 01:00:00 | 00:50:32 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:12:09 | 2024-09-06 18:12:09 | 1 | 0.84
423 | TT22830 | Kiran Dhanepkar | - | - | - | karagir jama (QC Process - HM Centre,LM & PO check) TC Writing | Test Case Writing | 2024-10-04 | 03:00:00 | 02:34:47 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 23:31:42 | 2024-10-04 23:31:42 | 3 | 2.58
424 | TT22810 | Kiran Dhanepkar | - | - | - | Estimation of Hall marking RNG | Estimate calculation | 2024-09-03 | 00:00:00 | 00:00:00 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 11:47:31 | 2024-09-03 11:47:31 | 0 | 0
425 | TT23932 | Kiran Dhanepkar | Sprint 1 | - | - | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:16:28 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 2.27
426 | TT22830 | Kiran Dhanepkar | - | - | - | karagir jama (QC Process - DC,QC,HM) TC Writing | Test Case Writing | 2024-10-03 | 02:30:00 | 02:25:48 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:28:06 | 2024-10-03 18:28:06 | 2.5 | 2.43
427 | TT23782 | Kiran Dhanepkar | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
428 | TT18735 | Maruti Hakke | - | - | - | Bil to Bil adjustment receipt scripts | Test Script Preparation | 2024-09-27 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-24 14:45:37 | 2024-09-24 14:45:37 | 0 | 0
429 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | - | - | CRM KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:11:05 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:40:58 | 2024-09-02 23:40:58 | 1 | 0.18
430 | TT18735 | Maruti Hakke | - | - | - | Receipt Module Scripts | Script Execution/ Modification | 2024-09-23 | 00:00:00 | 00:49:52 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-23 23:50:07 | 2024-09-23 23:50:07 | 0 | 0.83
431 | TT22442 | Maruti Hakke | - | - | - | TT22442 - Invoice Script Code Review | Script review | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-24 14:47:57 | 2024-09-24 14:47:57 | 0 | 0
432 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Test case Execution | Testing. | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-24 14:41:57 | 2024-09-24 14:41:57 | 0 | 0
433 | TT24598 | Maruti Hakke | - | - | - | Customer Creation test case modification | Test case updation\modification | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 14:42:05 | 2024-09-24 14:42:05 | 0 | 0
434 | TT24390 | Maruti Hakke | Testing_AutomationPractice_OCT24_WK1 | - | - | Automation Support By SV | Query clarification | 2024-09-26 | 04:00:00 | 09:11:46 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-28 23:01:07 | 2024-09-28 23:01:07 | 4 | 9.2
435 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-23 | 01:00:00 | 00:47:19 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 01:40:00 | 2024-09-24 01:40:00 | 1 | 0.79
436 | TT24390 | Maruti Hakke | Testing_AutomationPractice_OCT24_WK1 | - | - | Automation test case discussion meeting with team | Test Script Preparation | 2024-09-02 | 01:00:00 | 00:40:48 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:58 | 2024-09-02 19:54:58 | 1 | 0.68
437 | TT23819 | Maruti Hakke | - | - | - | Test case Modification Review | Review updated Test cases | 2024-09-23 | 00:00:00 | 00:00:00 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 11:36:44 | 2024-09-24 11:36:44 | 0 | 0
438 | TT24208 | Maruti Hakke | Testing_DPOS_Practice_Oct24_WK1 | - | - | CRM AND KARAGIR REPAIR PRACTICE | D Practice | 2024-09-02 | 01:15:00 | 00:56:40 | 2024-09-02 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-03 10:58:12 | 2024-09-03 10:58:12 | 1.25 | 0.94
439 | TT18735 | Maruti Hakke | - | - | - | Cash receipt module script updation | Script Execution/ Modification | 2024-09-20 | 02:30:00 | 05:11:36 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 00:05:41 | 2024-09-21 00:05:41 | 2.5 | 5.19
440 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Test case writing | Test case writing- | 2024-10-03 | 04:00:00 | 06:38:38 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 19:56:02 | 2024-10-04 19:56:02 | 4 | 6.64
441 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Document Reading | Document Reading | 2024-09-19 | 01:00:00 | 00:27:05 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 17:33:27 | 2024-09-20 17:33:27 | 1 | 0.45
442 | TT24598 | Maruti Hakke | - | - | - | Customer Creation Estimate | Estimate the requirement | 2024-09-19 | 01:00:00 | 01:00:28 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:38:49 | 2024-09-20 17:38:49 | 1 | 1.01
443 | TT22442 | Maruti Hakke | - | - | - | Tax Page Scripting (all module ) | Test Script Preparation | 2024-09-10 | 11:00:00 | 14:54:27 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-14 16:22:44 | 2024-09-14 16:22:44 | 11 | 14.91
444 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
445 | TT23350 | Maruti Hakke | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:25:07 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.42
446 | TT22455 | Maruti Hakke | Gift card sales 1 | - | - | TT22455-Gift Voucher Test case modification review | Review updated Test cases | 2024-09-27 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-01 19:30:00 | 2024-10-01 19:30:00 | 0 | 0
447 | TT23819 | Maruti Hakke | - | - | - | Urd purchase test case modification review | Review updated Test cases | 2024-09-19 | 00:30:00 | 00:25:43 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 18:59:29 | 2024-09-19 18:59:29 | 0.5 | 0.43
448 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
449 | TT24598 | Maruti Hakke | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:41:29 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0.69
450 | TT22455 | Maruti Hakke | Gift card sales 1 | - | - | TT22455-Gift Voucher Test case review | Review Test cases | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-24 14:48:48 | 2024-09-24 14:48:48 | 0 | 0
451 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 0
452 | TT24670 | Maruti Hakke | - | - | - | customer advance brainstorming | Brainstorming | 2024-09-19 | 00:30:00 | 00:44:25 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:04 | 2024-09-19 17:01:04 | 0.5 | 0.74
453 | TT22455 | Maruti Hakke | Gift card sales 1 | - | - | TT22455-Gift Card document reading | Document Reading | 2024-09-24 | 01:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 09:24:44 | 2024-09-25 09:24:44 | 1 | 0
454 | TT23819 | Maruti Hakke | - | - | - | URD purchase test case review | Test Case Review | 2024-09-19 | 02:00:00 | 02:13:40 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 09:42:47 | 2024-09-19 09:42:47 | 2 | 2.23
455 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 01:30:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 1.5 | 0
456 | TT22442 | Maruti Hakke | - | - | - | Tax Page Test Script Modification | Script Execution/ Modification | 2024-09-18 | 03:00:00 | 03:39:21 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 22:32:02 | 2024-09-18 22:32:02 | 3 | 3.66
457 | TT22455 | Maruti Hakke | Gift card sales 1 | - | - | TT22455-Gift Voucher-Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-24 16:22:06 | 2024-09-24 16:22:06 | 0 | 0
458 | TT23819 | Maruti Hakke | - | - | - | TT23819 - URD exchange and purchase brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:00:00 | 01:11:21 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 16:20:37 | 2024-09-11 16:20:37 | 1 | 1.19
459 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 2309 to 2709 | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:16:12 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:30 | 2024-09-27 19:54:30 | 2.5 | 3.27
460 | TT18735 | Maruti Hakke | - | - | - | TT18735 - Receipt Module Test Script Execution | Script Execution/ Modification | 2024-09-13 | 03:45:00 | 02:38:02 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 22:44:53 | 2024-09-18 22:44:53 | 3.75 | 2.63
461 | TT22402 | Maruti Hakke | - | - | - | Scheme creation and Installment TPOS Brainstorming and scenario listing | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:30:00 | 00:25:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:59:50 | 2024-09-11 17:59:50 | 1.5 | 0.43
462 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-27 | 01:00:00 | 01:52:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:58:39 | 2024-09-27 19:58:39 | 1 | 1.88
463 | TT18735 | Maruti Hakke | - | - | - | TT18735 - Receipt module Test Script Preparation | Test Script Preparation | 2024-09-12 | 07:15:00 | 23:15:11 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 14:33:14 | 2024-09-18 14:33:14 | 7.25 | 23.25
464 | TT14931 | Maruti Hakke | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
465 | TT22456 | Maruti Hakke | - | - | - | Karagir repair sale bill test script execution | Script Execution/ Modification | 2024-09-05 | 12:00:00 | 13:48:45 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-12 11:43:36 | 2024-09-12 11:43:36 | 12 | 13.81
466 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-20 | 01:00:00 | 01:29:35 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 19:57:00 | 2024-09-21 19:57:00 | 1 | 1.49
467 | TT25148 | Maruti Hakke | Sales Return Advance & Utilization Demo | - | - | Sales Return Figma KT to Developers & Testers | KT Session | 2024-09-12 | 00:10:00 | 00:07:36 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 15:10:15 | 2024-09-12 15:10:15 | 0.17 | 0.13
468 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
469 | TT22456 | Maruti Hakke | - | - | - | Karagir repair sale bill test script preparation | Test Script Preparation | 2024-09-02 | 09:15:00 | 08:08:58 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 19:19:10 | 2024-09-06 19:19:10 | 9.25 | 8.15
470 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 1809 to 2009 | Daily Sync Call | 2024-09-18 | 01:30:00 | 00:54:24 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:25:59 | 2024-09-20 22:25:59 | 1.5 | 0.91
471 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
472 | TT22402 | Maruti Hakke | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
473 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for Next Week | Task Scheduling | 2024-09-13 | 01:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 18:43:15 | 2024-09-16 18:43:15 | 1 | 0
474 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
475 | TT24670 | Maruti Hakke | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 0.43
476 | TT25176 | Maruti Hakke | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 0909 to 1309 | Daily Sync Call | 2024-09-09 | 02:30:00 | 01:39:24 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:52 | 2024-09-13 18:56:52 | 2.5 | 1.66
477 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:51:08 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 1 | 0.85
478 | TT22394 | Maruti Hakke | - | - | - | URD Purchase Exchange KT | KT Session | 2024-09-03 | 00:45:00 | 00:31:22 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:41:20 | 2024-09-03 18:41:20 | 0.75 | 0.52
479 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Walk in interview support | Interview | 2024-09-30 | 12:00:00 | 22:10:55 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 12 | 22.18
480 | TT23939 | Maruti Hakke | - | - | - | POS Sync Call 0209 to 0609 | Daily Sync Call | 2024-09-02 | 02:00:00 | 02:20:07 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:13:52 | 2024-09-06 18:13:52 | 2 | 2.34
481 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Sprint KT to team | KT from BA | 2024-09-24 | 00:34:00 | 00:17:34 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:24:50 | 2024-09-24 18:24:50 | 0.57 | 0.29
482 | TT23939 | Maruti Hakke | - | - | - | Task Scheduling for 06 Next Week | Task Scheduling | 2024-09-06 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:23:33 | 2024-09-06 19:23:33 | 1 | 0
483 | TT23819 | Maruti Hakke | - | - | - | URD purchase Test script E2E | Test Automation Script Preparation | 2024-10-07 | 06:00:00 | 01:53:28 | 2024-10-12 |  | IN_PROGRESS | IN_PROGRESS |  |  | 6 | 1.89
484 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
485 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (23rd - 27th Sep) | Sync call with Team | 2024-09-23 | 01:15:00 | 00:50:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:04:20 | 2024-09-27 20:04:20 | 1.25 | 0.84
486 | TT23819 | Maruti Hakke | - | - | - | URD Purchase Test case 1 to 5 Execute Script | Automation Script Execution/modification | 2024-10-04 | 06:15:00 | 04:32:21 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:59:07 | 2024-10-04 22:59:07 | 6.25 | 4.54
487 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
488 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:41:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.7
489 | TT23819 | Maruti Hakke | - | - | - | URD Report Modification | Automation Script Execution/modification | 2024-10-03 | 01:15:00 | 01:18:47 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 20:06:02 | 2024-10-03 20:06:02 | 1.25 | 1.31
490 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (2th Sep - 6th Sep) | Sync call with Team | 2024-09-02 | 01:15:00 | 00:49:37 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:00:01 | 2024-09-06 13:00:01 | 1.25 | 0.83
491 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (18th - 20th Sep) | Sync call with Team | 2024-09-18 | 01:30:00 | 00:14:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:26:13 | 2024-09-20 22:26:13 | 1.5 | 0.24
492 | TT23819 | Maruti Hakke | - | - | - | URD purchase test script | Script Execution/ Modification | 2024-09-28 | 07:00:00 | 07:11:35 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 22:58:42 | 2024-09-28 22:58:42 | 7 | 7.19
493 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Script report demo to Gaurav Sir | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:14 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:39:57 | 2024-09-20 19:39:57 | 1 | 0.27
494 | TT23819 | Maruti Hakke | - | - | - | URD Purchase Test Script | Script Execution/ Modification | 2024-09-25 | 19:00:00 | 09:43:52 | 2024-09-27 |  | COMPLETED | DELAY | 2024-09-28 23:00:09 | 2024-09-28 23:00:09 | 19 | 9.73
495 | TT24303 | Maruti Hakke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (9th Sep - 13th Sep) | Sync call with Team | 2024-09-09 | 01:15:00 | 01:57:49 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:23 | 2024-09-13 19:33:23 | 1.25 | 1.96
496 | TT22402 | Maruti Hakke | - | - | - | SWGP Scheme New CR KT | KT Session | 2024-09-27 | 00:33:00 | 00:38:57 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:17:47 | 2024-09-27 15:17:47 | 0.55 | 0.65
497 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:50:08 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.84
498 | TT23819 | Maruti Hakke | - | - | - | URD IMPS Flow Support By MK | Query clarification | 2024-09-25 | 01:00:00 | 00:21:48 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 17:38:46 | 2024-09-25 17:38:46 | 1 | 0.36
499 | TT23819 | Maruti Hakke | - | - | - | URD Purchase Data creation Scripting | Test Script Preparation | 2024-09-24 | 05:45:00 | 06:57:44 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 10:30:39 | 2024-09-25 10:30:39 | 5.75 | 6.96
500 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
501 | TT25629 | Maruti Hakke | - | - | - | Lumsam and mrp, Sterling rate | Demo | 2024-09-26 | 00:30:00 | 00:21:58 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 17:01:38 | 2024-09-26 17:01:38 | 0.5 | 0.37
502 | TT24206 | Maruti Hakke | Testing_KT_Oct24_Wk1 | - | - | Karagir repair KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:23:42 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:39 | 2024-09-02 19:54:39 | 1 | 0.4
503 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 0909 to 1309 | Daily Sync Call | 2024-09-09 | 02:30:00 | 01:20:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:52 | 2024-09-13 18:56:52 | 2.5 | 1.33
504 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Sprint KT to team | KT from BA | 2024-09-24 | 00:34:00 | 00:17:34 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:24:50 | 2024-09-24 18:24:50 | 0.57 | 0.29
505 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 02:00:00 | 00:25:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 2 | 0.43
506 | TT23939 | Prathamesh Kulkarni | - | - | - | POS Sync Call 0209 to 0609 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:10:12 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:13:52 | 2024-09-06 18:13:52 | 2.5 | 2.17
507 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (23rd - 27th Sep) | Sync call with Team | 2024-09-23 | 01:15:00 | 00:50:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:04:20 | 2024-09-27 20:04:20 | 1.25 | 0.84
508 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 2309 to 2709 | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:17:08 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:30 | 2024-09-27 19:54:30 | 2.5 | 3.29
509 | TT23939 | Prathamesh Kulkarni | - | - | - | Task Scheduling for 06 Next Week | Task Scheduling | 2024-09-06 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:23:33 | 2024-09-06 19:23:33 | 1 | 0
510 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:41:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.7
511 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-27 | 01:00:00 | 01:52:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:58:39 | 2024-09-27 19:58:39 | 1 | 1.88
512 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (18th - 20th Sep) | Sync call with Team | 2024-09-18 | 01:30:00 | 00:14:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:26:13 | 2024-09-20 22:26:13 | 1.5 | 0.24
513 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-20 | 01:00:00 | 01:31:09 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 19:57:00 | 2024-09-21 19:57:00 | 1 | 1.52
514 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | support to prathamesh | Technical guidance/Process Input | 2024-09-11 | 02:00:00 | 00:25:11 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:02 | 2024-09-13 19:33:02 | 2 | 0.42
515 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 1809 to 2009 | Daily Sync Call | 2024-09-18 | 01:30:00 | 01:01:13 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:25:59 | 2024-09-20 22:25:59 | 1.5 | 1.02
516 | TT24208 | Prathamesh Kulkarni | Testing_DPOS_Practice_Oct24_WK1 | - | - | CRM and karargir repair practice | D Practice | 2024-09-02 | 01:15:00 | 00:35:43 | 2024-09-02 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-04 09:48:31 | 2024-09-04 09:48:31 | 1.25 | 0.6
517 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (9th Sep - 13th Sep) | Sync call with Team | 2024-09-09 | 01:15:00 | 00:48:09 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:23 | 2024-09-13 19:33:23 | 1.25 | 0.8
518 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance support to prathamesh | Mentoring | 2024-10-07 | 01:00:00 | 00:04:10 | 2024-10-09 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 0.07
519 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
520 | TT25961 | Prathamesh Kulkarni | - | - | - | gift voucher redemption estimation | Estimate calculation | 2024-10-07 | 00:45:00 | 00:02:39 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.75 | 0.04
521 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (2th Sep - 6th Sep) | Sync call with Team | 2024-09-02 | 01:15:00 | 01:08:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:00:01 | 2024-09-06 13:00:01 | 1.25 | 1.14
522 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance scripting | Test Script Preparation | 2024-09-30 | 16:00:00 | 07:48:56 | 2024-10-09 |  | IN_PROGRESS | DELAY | 2024-10-07 10:34:28 |  | 16 | 7.82
523 | TT24670 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Query clarification | 2024-10-03 | 02:00:00 | 01:40:38 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:19:19 | 2024-10-04 20:19:19 | 2 | 1.68
524 | TT22402 | Prathamesh Kulkarni | - | - | - | SWGP Scheme New CR KT | KT Session | 2024-09-27 | 00:33:00 | 00:38:57 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:17:47 | 2024-09-27 15:17:47 | 0.55 | 0.65
525 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
526 | TT25629 | Prathamesh Kulkarni | - | - | - | Lumsam and mrp, Sterling rate | Demo | 2024-09-26 | 00:30:00 | 00:21:58 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 17:01:38 | 2024-09-26 17:01:38 | 0.5 | 0.37
527 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
528 | TT22453 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Technical guidance/Process Input | 2024-09-25 | 03:00:00 | 01:12:36 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:57:16 | 2024-09-27 19:57:16 | 3 | 1.21
529 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | - | - | Karagir repair KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:23:42 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:39 | 2024-09-02 19:54:39 | 1 | 0.4
530 | TT22453 | Prathamesh Kulkarni | - | - | - | customer order automation | Test Script Preparation | 2024-09-23 | 27:30:00 | 26:03:53 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-03 11:29:00 | 2024-10-03 11:29:00 | 3.5 | 2.06
531 | TT24206 | Prathamesh Kulkarni | Testing_KT_Oct24_Wk1 | - | - | CRM KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:11:05 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:40:58 | 2024-09-02 23:40:58 | 1 | 0.18
532 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme sale bill retesting | Testing | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-25 19:35:12 | 2024-09-25 19:35:12 | 0 | 0
533 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme estimate retesting | Testing. | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:36:03 | 2024-09-25 19:36:03 | 0 | 0
534 | TT24670 | Prathamesh Kulkarni | - | - | - | Customer advance test case modification | Test Case Writing | 2024-09-23 | 01:30:00 | 01:43:59 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 12:55:49 | 2024-09-23 12:55:49 | 1.5 | 1.73
535 | TT24670 | Prathamesh Kulkarni | - | - | - | Customer advance test case execution | Testing. | 2024-09-24 | 04:30:00 | 00:22:11 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 11:38:03 | 2024-09-24 11:38:03 | 4.5 | 0.37
536 | TT25148 | Prathamesh Kulkarni | Sales Return Advance & Utilization Demo | - | - | Sales Return Figma KT to Developers & Testers | KT Session | 2024-09-12 | 00:10:00 | 00:07:36 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 15:10:15 | 2024-09-12 15:10:15 | 0.17 | 0.13
537 | TT23350 | Prathamesh Kulkarni | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:25:07 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.42
538 | TT24390 | Prathamesh Kulkarni | Testing_AutomationPractice_OCT24_WK1 | - | - | Automation test case discussion meeting with team | Test Script Preparation | 2024-09-02 | 01:00:00 | 00:40:48 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:58 | 2024-09-02 19:54:58 | 1 | 0.68
539 | TT24598 | Prathamesh Kulkarni | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:49:04 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0.82
540 | TT24390 | Prathamesh Kulkarni | Testing_AutomationPractice_OCT24_WK1 | - | - | Support to Prathamesh from sayali | Support. | 2024-09-03 | 04:00:00 | 02:56:21 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:32:49 | 2024-09-06 17:32:49 | 4 | 2.94
541 | TT24670 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Support. | 2024-09-20 | 00:45:00 | 00:21:27 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:26:33 | 2024-09-20 19:26:33 | 0.75 | 0.36
542 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance positive flow scripting | Test script execution | 2024-09-20 | 03:00:00 | 03:08:17 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 09:16:46 | 2024-09-24 09:16:46 | 3 | 3.14
543 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance testcase writing | Test Case Writing | 2024-09-19 | 03:00:00 | 02:37:36 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 18:44:04 | 2024-09-20 18:44:04 | 3 | 2.63
544 | TT24670 | Prathamesh Kulkarni | - | - | - | customer advance brainstorming | Brainstorming | 2024-09-19 | 00:30:00 | 00:44:25 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:04 | 2024-09-19 17:01:04 | 0.5 | 0.74
545 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme creation and installment execution | Testing | 2024-09-19 | 04:30:00 | 04:27:06 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 20:07:50 | 2024-09-19 20:07:50 | 4.5 | 4.45
546 | TT23819 | Prathamesh Kulkarni | - | - | - | TT23819 - URD exchange and purchase brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:00:00 | 01:00:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 16:20:37 | 2024-09-11 16:20:37 | 1 | 1.01
547 | TT22402 | Prathamesh Kulkarni | - | - | - | support to prathamesh | Mentoring | 2024-09-18 | 00:30:00 | 00:10:48 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 22:00:49 | 2024-09-18 22:00:49 | 0.5 | 0.18
548 | TT22402 | Prathamesh Kulkarni | - | - | - | Scheme creation and Installment TPOS Brainstorming and scenario listing | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:30:00 | 00:25:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:59:50 | 2024-09-11 17:59:50 | 1.5 | 0.43
549 | TT22442 | Prathamesh Kulkarni | - | - | - | TT22442-Estimate Module Data Preparation | Data Preparation | 2024-09-18 | 01:00:00 | 01:00:29 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 18:03:26 | 2024-09-18 18:03:26 | 1 | 1.01
550 | TT14931 | Prathamesh Kulkarni | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
551 | TT22402 | Prathamesh Kulkarni | - | - | - | Scheme creation and installment test case modification | Test Case Writing | 2024-09-18 | 02:00:00 | 02:15:55 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 23:15:56 | 2024-09-18 23:15:56 | 2 | 2.27
552 | TT22442 | Prathamesh Kulkarni | - | - | - | Estimate module automation using DTO | Automation. | 2024-09-02 | 22:45:00 | 21:52:17 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-17 10:12:38 | 2024-09-17 10:12:38 | 22.75 | 21.87
553 | TT22442 | Prathamesh Kulkarni | - | - | - | TT22442-Data Preparation For Estimate Module For Different Product groups | Data Preparation | 2024-09-13 | 00:45:00 | 00:34:32 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 14:52:15 | 2024-09-16 14:52:15 | 0.75 | 0.58
554 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
555 | TT22402 | Prathamesh Kulkarni | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
556 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme creation and installment test case writing | Test Case Writing | 2024-09-12 | 04:00:00 | 03:55:54 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:15 | 2024-09-13 18:56:15 | 4 | 3.93
557 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
558 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
559 | TT22402 | Prathamesh Kulkarni | - | - | - | scheme creation and installment go through KT session recording | KT Session | 2024-09-12 | 00:30:00 | 00:26:06 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-13 09:12:32 | 2024-09-13 09:12:32 | 0.5 | 0.44
560 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
561 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
562 | TT24670 | Prathamesh Kulkarni | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 0.43
563 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for Next Week | Task Scheduling | 2024-09-13 | 01:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 18:43:15 | 2024-09-16 18:43:15 | 1 | 0
564 | TT24303 | Prathamesh Kulkarni | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 00:45:00 | 00:51:08 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 0.75 | 0.85
565 | TT25176 | Prathamesh Kulkarni | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 01:48:09 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 1.8
566 | TT22455 | Prathamesh Kulkarni | Gift card sales 1 | - | - | TT22455-Gift Voucher-Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-24 16:22:06 | 2024-09-24 16:22:06 | 0 | 0
567 | TT22394 | Prathamesh Kulkarni | - | - | - | URD Purchase Exchange KT | KT Session | 2024-09-03 | 00:45:00 | 00:31:22 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:41:20 | 2024-09-03 18:41:20 | 0.75 | 0.52
568 | TT21914 | Preeti Bokade | - | - | - | KRA -KPI relevant action plan with Gokul & Sayali | Explore Team capability/Improvement plan | 2024-09-23 | 02:00:00 | 00:56:14 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 20:31:38 | 2024-09-24 20:31:38 | 2 | 0.94
569 | TT21914 | Preeti Bokade | - | - | - | Automation Tester Interview | Interview | 2024-09-23 | 05:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 23:00:18 | 2024-09-27 23:00:18 | 5 | 0
570 | TT21914 | Preeti Bokade | - | - | - | Support to Gokul | Query clarification | 2024-09-23 | 02:30:00 | 00:43:06 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:53:43 | 2024-09-27 19:53:43 | 2.5 | 0.72
571 | TT24207 | Preeti Bokade | Testing_D365_Practice_Oct24_Wk1 | - | - | Going through Masters KT- recording listening | Explore the existing system. | 2024-09-06 | 00:40:00 | 01:13:56 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:31:58 | 2024-09-06 16:31:58 | 0.67 | 1.23
572 | TT21914 | Preeti Bokade | - | - | - | Support to Sayali | Query clarification | 2024-09-23 | 02:30:00 | 00:21:15 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:39 | 2024-09-27 19:54:39 | 2.5 | 0.35
573 | TT24427 | Preeti Bokade | E2E Testing | - | - | Doc Module Sync call | Daily Sync Call | 2024-09-26 | 00:30:00 | 01:37:11 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:48:06 | 2024-09-27 18:48:06 | 0.5 | 1.62
574 | TT21914 | Preeti Bokade | - | - | - | Amreen - Support from Preeti ma'am | Query clarification | 2024-09-23 | 02:30:00 | 03:45:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:51:17 | 2024-09-27 20:51:17 | 2.5 | 3.75
575 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
576 | TT24598 | Preeti Bokade | - | - | - | estimation review | Estimation Review | 2024-09-19 | 00:30:00 | 00:43:03 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 20:41:40 | 2024-09-20 20:41:40 | 0.5 | 0.72
577 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-06 23:48:07 |  | 0.25 | 0
578 | TT21914 | Preeti Bokade | - | - | - | Automation Tester Interview | Interview | 2024-09-19 | 00:45:00 | 01:07:23 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:45:16 | 2024-09-19 17:45:16 | 0.75 | 1.12
579 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:47 | 2024-10-06 23:46:47 | 0 | 0
580 | TT23350 | Preeti Bokade | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:21:23 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.36
581 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:20 | 2024-10-06 23:45:20 | 0 | 0
582 | TT24216 | Preeti Bokade | Testing_Skill Upgrade_Oct24_Wk1 | - | - | Explore BDD concept through Youtube | Explore New things\other | 2024-09-10 | 02:00:00 | 01:20:12 | 2024-09-11 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-16 07:32:05 | 2024-09-16 07:32:05 | 2 | 1.34
583 | TT24598 | Preeti Bokade | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:00:00 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0
584 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:10 | 2024-10-06 23:45:10 | 0 | 0
585 | TT21914 | Preeti Bokade | - | - | - | Sayali - Support task | Query clarification | 2024-09-19 | 01:00:00 | 00:02:03 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:40:40 | 2024-09-20 20:40:40 | 1 | 0.03
586 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:59 | 2024-10-06 23:46:59 | 0 | 0
587 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Walk in Drive - Interview ( Automation Tester) | Interview | 2024-09-30 | 14:00:00 | 10:07:17 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:21:45 | 2024-10-04 20:21:45 | 14 | 10.12
588 | TT21914 | Preeti Bokade | - | - | - | Automation interview - 16sept | Interview | 2024-09-16 | 01:30:00 | 01:37:37 | 2024-09-16 |  | COMPLETED | DELAY | 2024-09-18 15:32:49 | 2024-09-18 15:32:49 | 1.5 | 1.63
589 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:43:31 | 2024-10-06 23:43:31 | 0.25 | 0
590 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:22:31 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0.38
591 | TT21914 | Preeti Bokade | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-18 | 01:30:00 | 00:50:22 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:59:00 | 2024-09-20 20:59:00 | 1.5 | 0.84
592 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support to Sayali | Query clarification | 2024-10-07 | 00:15:00 | 00:21:16 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.25 | 0.35
593 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | - | - | Query clarification with BA | Brainstorming with DEV Team \BA | 2024-09-19 | 00:15:00 | 00:13:36 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 15:36:18 | 2024-09-19 15:36:18 | 0.25 | 0.23
594 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Amreen - Support from Preeti Ma'am. | Query clarification | 2024-09-30 | 02:00:00 | 00:03:46 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:56 | 2024-10-04 20:47:56 | 2 | 0.06
595 | TT21914 | Preeti Bokade | - | - | - | support to gokul | Query clarification | 2024-09-09 | 02:30:00 | 02:50:18 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 22:36:02 | 2024-09-13 22:36:02 | 2.5 | 2.84
596 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 03:19:24 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 3.32
597 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | - | - | My CS Test case review | Review Test cases | 2024-09-13 | 01:00:00 | 05:40:46 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 14:07:25 | 2024-09-16 14:07:25 | 1 | 5.68
598 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | General discussion on Dashboard(Power BI Report) | Explore the existing system | 2024-09-26 | 00:27:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 18:52:44 | 2024-09-26 18:52:44 | 0.45 | 0
599 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | KT to Digvijay about connect us 2.0 (Masters , except customer mapping ) | Internal KT/cross KT | 2024-10-07 | 02:00:00 | 01:29:41 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 14:11:10 |  | 2 | 1.49
600 | TT21914 | Preeti Bokade | - | - | - | support to sayali | Query clarification | 2024-09-09 | 02:00:00 | 01:52:46 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:43 | 2024-09-13 19:33:43 | 2 | 1.88
601 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:45 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
602 | TT23932 | Preeti Bokade | Sprint 1 | - | - | AS BC Discussions | General meeting | 2024-09-06 | 00:30:00 | 00:29:19 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 14:16:41 | 2024-09-06 14:16:41 | 0.5 | 0.49
603 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | - | - | Review estimation | Estimation Review | 2024-09-05 | 00:30:00 | 00:31:44 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:50:07 | 2024-09-05 19:50:07 | 0.5 | 0.53
604 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0
605 | TT21914 | Preeti Bokade | - | - | - | Amreen - Support from Preeti ma'am. | Query clarification | 2024-09-09 | 02:30:00 | 23:11:49 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:11:19 | 2024-09-13 20:11:19 | 2.5 | 23.2
606 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
607 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | - | - | New scheme Enrollment Brain storming | Brainstorming | 2024-09-05 | 00:30:00 | 00:50:05 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 17:48:00 | 2024-09-05 17:48:00 | 0.5 | 0.83
608 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:04:06 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 3.07
609 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil(Reports- user task , variance, Resource planning) | Internal KT/cross KT | 2024-09-27 | 02:00:00 | 00:44:03 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-29 23:01:25 | 2024-09-29 23:01:25 | 2 | 0.73
610 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | - | - | Go through the document | Document Reading | 2024-09-03 | 00:40:00 | 01:12:51 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 20:34:42 | 2024-09-03 20:34:42 | 0.67 | 1.21
611 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 00:15:00 | 00:16:27 | 2024-10-10 |  | IN_PROGRESS | DELAY | 2024-10-07 13:31:36 |  | 0.25 | 0.27
612 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil(My Ticket) | Internal KT/cross KT | 2024-09-26 | 01:30:00 | 00:46:54 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 14:12:21 | 2024-09-26 14:12:21 | 1.5 | 0.78
613 | TT21914 | Preeti Bokade | - | - | - | support to Gokul | Query clarification | 2024-09-02 | 02:30:00 | 01:00:09 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:29:04 | 2024-09-06 19:29:04 | 2.5 | 1
614 | TT24961 | Preeti Bokade | New Scheme Enrollment on mobile App | - | - | New scheme Enrollment KT | KT Session | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:26:28 | 2024-09-04 13:26:28 | 0.75 | 0
615 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:38 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
616 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil (Customer Mapping , Create Ticket) | Internal KT/cross KT | 2024-09-25 | 01:30:00 | 01:26:26 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:54:56 | 2024-09-25 22:54:56 | 1.5 | 1.44
617 | TT21914 | Preeti Bokade | - | - | - | support to sayali | Query clarification | 2024-09-02 | 02:30:00 | 01:32:12 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:04:13 | 2024-09-06 18:04:13 | 2.5 | 1.54
618 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 01:08:10 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 1.14
619 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil( Tenant Master, Dynamic form, Dropdown master, Query Type Master) | Internal KT/cross KT | 2024-09-24 | 02:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:03:39 | 2024-09-24 19:03:39 | 2 | 0
620 | TT22402 | Preeti Bokade | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
621 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 02:19:28 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 2.32
622 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil (User Master, Customer Master, Role Master, Designation Master) | Internal KT/cross KT | 2024-09-23 | 02:00:00 | 00:41:06 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 12:18:43 | 2024-09-23 12:18:43 | 2 | 0.69
623 | TT24670 | Preeti Bokade | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 02:56:46 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 2.95
624 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Resource planning report analysis | Performance analysis and improvement plan | 2024-10-03 | 01:00:00 | 01:13:23 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-06 00:19:32 | 2024-10-06 00:19:32 | 1 | 1.22
625 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:15:00 | 00:56:30 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1.25 | 0.94
626 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | Estimation KT to Swapnil | Internal KT/cross KT | 2024-09-06 | 00:45:00 | 00:50:56 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:53:10 | 2024-09-06 18:53:10 | 0.75 | 0.85
627 | TT21914 | Preeti Bokade | - | - | - | Support from Preeti Ma'am. | Query clarification | 2024-09-02 | 02:30:00 | 04:45:39 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-08 23:15:06 | 2024-09-06 19:27:58 | 2.5 | 4.76
628 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Weekly sync call with Gaurav sir | Weekly sync call | 2024-09-25 | 01:00:00 | 01:24:13 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-27 19:32:25 | 2024-09-27 19:32:25 | 1 | 1.4
629 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:13:01 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40 | 0.17 | 0.22
630 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
631 | TT21914 | Preeti Bokade | - | - | - | Support from Gaurav sir | Query clarification | 2024-08-30 | 09:30:00 | 17:06:26 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 23:03:49 | 2024-09-30 23:03:49 | 9.5 | 17.11
632 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:37:53 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.63
633 | TT23782 | Preeti Bokade | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 01:17:59 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 1.3
634 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Weekly sync call with Gaurav sir | Meeting with PH | 2024-09-18 | 01:00:00 | 00:44:26 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 17:32:12 | 2024-09-18 17:32:12 | 1 | 0.74
635 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Support By Preeti ma'am | Mentoring | 2024-09-02 | 02:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-02 14:41:34 | 2024-09-02 14:41:34 | 2.5 | 0
636 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Weekly sync call with Gaurav sir | Meeting with PH | 2024-09-11 | 01:00:00 | 00:04:03 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 23:29:13 | 2024-09-11 23:29:13 | 1 | 0.07
637 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
638 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Resource planning Report analysis | Performance analysis and improvement plan | 2024-10-07 | 02:00:00 | 00:00:00 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS |  |  | 2 | 0
639 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Weekly sync Report preparation | Weekly sync call report | 2024-09-11 | 01:00:00 | 02:59:46 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 23:29:56 | 2024-09-11 23:29:56 | 1 | 3
640 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Weekly meeting with gaurav sir 20th Sep | Weekly sync call | 2024-09-20 | 01:00:00 | 00:00:36 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:50:01 | 2024-09-20 20:50:01 | 1 | 0.01
641 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Support from Gaurav sir | Query clarification | 2024-10-07 | 00:24:00 | 00:00:00 | 2024-10-31 |  | TO_DO | TO_DO |  |  | 0.4 | 0
642 | TT24180 | Preeti Bokade | Oct-2024 | - | - | Resource planning task analysis | Explore Team capability/Improvement plan | 2024-09-09 | 01:00:00 | 02:13:52 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 15:41:29 | 2024-09-09 15:41:29 | 1 | 2.23
643 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 03:23:12 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 3.39
644 | TT23495 | Preeti Bokade | - | - | - | Footer / Setting Discussion KT | KT Session | 2024-10-07 | 00:30:00 | 00:58:55 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:21:38 | 2024-10-07 13:21:38 | 0.5 | 0.98
645 | TT24148 | Preeti Bokade | - | - | - | Regularization issue testing task | Application Support | 2024-09-25 | 01:00:00 | 00:33:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 18:07:35 | 2024-09-25 18:07:35 | 1 | 0.55
646 | TT21914 | Preeti Bokade | - | - | - | Prepare the Function point on Ticketing system ( Reusable purpose) | Estimate the requirement | 2024-09-26 | 04:00:00 | 00:00:14 | 2024-09-30 |  | IN_PROGRESS | DELAY |  |  | 4 | 0
647 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:08:40 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.14
648 | TT21945 | Saurabh Shelke | - | - | - | Automation support from gokul | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:24:18 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-25 14:04:22 | 2024-09-25 14:04:22 | 0.5 | 0.41
649 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 02:00:00 | 01:41:54 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 2 | 1.7
650 | TT21945 | Saurabh Shelke | - | - | - | QC Process (PR , DC , QC) TC Scripting | Automate test script | 2024-09-23 | 03:30:00 | 06:13:36 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-26 13:40:57 | 2024-09-26 13:40:57 | 3.5 | 6.23
651 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | Task Scheduling for Next Week | Task Scheduling | 2024-09-19 | 01:00:00 | 00:36:54 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:40:27 | 2024-09-20 19:40:27 | 1 | 0.62
652 | TT22200 | Saurabh Shelke | - | - | - | Job Work Charges Master Retesting | Retesting | 2024-09-24 | 03:30:00 | 02:53:11 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:45:06 | 2024-09-24 19:45:06 | 3.5 | 2.89
653 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:27:58 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 2.5 | 2.47
654 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair Positive flow Scripting | Automate test script | 2024-09-30 | 11:45:00 | 11:31:54 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:02:42 | 2024-10-04 19:02:42 | 11.75 | 11.53
655 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | Task Scheduling for next Week | Task Scheduling | 2024-09-12 | 01:00:00 | 01:00:44 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 13:10:47 | 2024-09-13 13:10:47 | 1 | 1.01
656 | TT24774 | Saurabh Shelke | - | - | - | KT New development-HM pcs adjustment field in RNG Process | KT Session | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 12:26:03 | 2024-09-26 12:26:03 | 0 | 0
657 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:22:27 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 2.37
658 | TT24683 | Saurabh Shelke | - | - | - | PCS Adjustment KT by snehal | KT Session | 2024-09-23 | 01:00:00 | 00:50:48 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 13:58:07 | 2024-09-23 13:58:07 | 1 | 0.85
659 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | Task Scheduling for next Week | Task Scheduling | 2024-09-05 | 01:00:00 | 01:10:50 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:56:45 | 2024-09-06 19:56:45 | 1 | 1.18
660 | TT24920 | Saurabh Shelke | - | - | - | Iteration 3 Set Tag Retesting | Retesting | 2024-09-25 | 04:30:00 | 05:15:47 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:21:00 | 2024-09-27 17:21:00 | 4.5 | 5.26
661 | TT21945 | Saurabh Shelke | - | - | - | Support for QC Multiple Lines to Vaishnavi | Query clarification | 2024-09-23 | 02:30:00 | 02:16:53 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 11:53:13 | 2024-09-27 11:53:13 | 2.5 | 2.28
662 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
663 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:18 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
664 | TT24771 | Saurabh Shelke | - | - | - | Size Master TC Review | Test Case Review | 2024-09-23 | 01:15:00 | 00:44:00 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 12:27:18 | 2024-09-24 12:27:18 | 1.25 | 0.73
665 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
666 | TT24771 | Saurabh Shelke | - | - | - | Support from Saurabh(Size master) | Query clarification | 2024-09-19 | 00:30:00 | 00:25:09 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 18:28:15 | 2024-09-19 18:28:15 | 0.5 | 0.42
667 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
668 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:36:59 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.62
669 | TT24760 | Saurabh Shelke | - | - | - | Support from saurabh | Query clarification | 2024-09-20 | 00:15:00 | 00:20:35 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 18:11:21 | 2024-09-20 18:11:21 | 0.25 | 0.34
670 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:38 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
671 | TT23985 | Saurabh Shelke | - | - | - | Iteration 2 Stock Repair Retesting | Retesting | 2024-09-20 | 03:30:00 | 02:39:09 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:41:17 | 2024-09-20 19:41:17 | 3.5 | 2.65
672 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 01:45:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 1.75
673 | TT21945 | Saurabh Shelke | - | - | - | Support from Gokul -P2P process(SS, SB) | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-08 |  | TO_DO | TO_DO | 2024-10-07 15:40:09 |  | 0 | 0
674 | TT22911 | Saurabh Shelke | - | - | - | Batch Registration Positive Flow Scripting | Automate test script | 2024-09-18 | 11:15:00 | 11:28:46 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:39:36 | 2024-09-20 19:39:36 | 11.25 | 11.48
675 | TT23053 | Saurabh Shelke | - | - | - | Sprint Demo | Demo | 2024-10-04 | 00:30:00 | 01:45:56 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 22:32:56 | 2024-10-04 22:32:56 | 0.5 | 1.77
676 | TT22823 | Saurabh Shelke | - | - | - | Karagir nave jama new CR estimation - Review | Review | 2024-09-09 | 00:30:00 | 00:42:42 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:45:00 | 2024-09-09 19:45:00 | 0.5 | 0.71
677 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:52:46 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.88
678 | TT21945 | Saurabh Shelke | - | - | - | P2P Process - Support from Saurabh | Support. | 2024-10-07 | 00:30:00 | 00:34:08 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:50:51 |  | 0.5 | 0.57
679 | TT14931 | Saurabh Shelke | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:40:14 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0.67
680 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 01:15:00 | 01:30:23 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 1.25 | 1.51
681 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair TC Scripting (60 %) | Automate test script | 2024-10-07 | 02:15:00 | 00:43:37 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-03 19:11:32 |  | 2.25 | 0.73
682 | TT18255 | Saurabh Shelke | - | - | - | Support Point To vaishnavi | Technical guidance/Process Input | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:16:14 | 2024-09-09 19:16:14 | 0 | 0
683 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
684 | TT21899 | Saurabh Shelke | - | - | - | (Iteration 2) Set Tag Retesting | Retesting | 2024-09-11 | 04:30:00 | 04:05:47 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:14:12 | 2024-09-13 19:14:12 | 4.5 | 4.1
685 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
686 | TT21945 | Saurabh Shelke | - | - | - | QC Process Bug Review | Test Case Review | 2024-10-07 | 00:45:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO |  |  | 0.75 | 0
687 | TT22830 | Saurabh Shelke | - | - | - | Support Point Karagir Nave/Jama | Support. | 2024-09-02 | 02:30:00 | 01:29:09 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:57:15 | 2024-09-06 19:57:15 | 2.5 | 1.49
688 | TT21945 | Saurabh Shelke | - | - | - | LM PO check Positive Flow Scripting | Automate test script | 2024-09-11 | 12:40:00 | 14:22:22 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 11:05:41 | 2024-09-16 11:05:41 | 12.67 | 14.37
689 | TT24303 | Saurabh Shelke | Testing_GM_Oct_2024_Wk1 | - | - | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:15:00 | 01:13:42 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1.25 | 1.23
690 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama (PO Check , LM & HM Centre) TC Review | Test Case Review | 2024-10-07 | 00:30:00 | 00:49:03 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 11:07:47 |  | 0.5 | 0.82
691 | TT21945 | Saurabh Shelke | - | - | - | QC Process (Positive Flow PR , DC ,QC) scripting Using DTO | Test Script Preparation | 2024-09-02 | 19:17:00 | 18:44:18 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-10 15:48:01 | 2024-09-10 15:48:01 | 19.28 | 18.74
692 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair retesting | Retesting | 2024-09-10 | 03:00:00 | 02:37:03 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-12 12:07:21 | 2024-09-12 12:07:21 | 3 | 2.62
693 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama (DC , QC & HM) test case review | Review Test cases | 2024-10-07 | 00:30:00 | 00:22:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:39:17 | 2024-10-07 13:39:17 | 0.5 | 0.37
694 | TT18255 | Saurabh Shelke | - | - | - | Automation Support URD | Technical guidance/Process Input | 2024-09-02 | 01:30:00 | 01:16:18 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:41:38 | 2024-09-05 19:41:38 | 1.5 | 1.27
695 | TT21945 | Saurabh Shelke | - | - | - | HM , LM Stage (QC process) Positive flow Scripting | Automate test script | 2024-09-09 | 08:30:00 | 07:55:26 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-11 15:39:48 | 2024-09-11 15:39:48 | 8.5 | 7.92
696 | TT22830 | Saurabh Shelke | - | - | - | Support Point karagir Jama to Kiran | Query clarification | 2024-10-07 | 00:00:00 | 00:00:11 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0 | 0
697 | TT22830 | Saurabh Shelke | - | - | - | Kariger requirement discussion | Requirement gathering | 2024-09-04 | 02:00:00 | 01:51:02 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 18:00:50 | 2024-09-04 18:00:50 | 2 | 1.85
698 | TT22785 | Saurabh Shelke | - | - | - | Lot tag testcase review | Review Test cases | 2024-10-01 | 00:45:00 | 00:32:39 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:47:43 | 2024-10-01 15:47:43 | 0.75 | 0.54
699 | TT23782 | Saurabh Shelke | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
700 | TT23985 | Saurabh Shelke | - | - | - | Stock Repair Retesting | Retesting | 2024-09-11 | 01:15:00 | 01:15:49 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-05 19:02:15 | 2024-09-05 19:02:15 | 1.25 | 1.26
701 | TT22830 | Saurabh Shelke | - | - | - | Support Point to Kiran Karagir jama | Query clarification | 2024-10-03 | 01:00:00 | 00:24:40 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:36 | 2024-10-04 19:41:36 | 1 | 0.41
702 | TT22830 | Saurabh Shelke | - | - | - | Karagir nave jama TCS review | Test Case Review | 2024-09-02 | 02:00:00 | 01:42:17 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 19:25:50 | 2024-09-03 19:25:50 | 2 | 1.7
703 | TT21899 | Saurabh Shelke | - | - | - | Set Tag Bug Discussion | Brainstorming with DEV Team \BA | 2024-09-03 | 00:45:00 | 00:49:32 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 17:02:33 | 2024-09-03 17:02:33 | 0.75 | 0.83
704 | TT24672 | Saurabh Shelke | Dev to Handover Config master | - | - | Configuration Master bugsheet review | Reporting Review | 2024-09-30 | 00:30:00 | 00:16:40 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 16:14:05 | 2024-09-30 16:14:05 | 0.5 | 0.28
705 | TT22830 | Saurabh Shelke | - | - | - | karagir nave TC review | Review. | 2024-10-01 | 00:45:00 | 00:27:53 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 16:16:17 | 2024-10-01 16:16:17 | 0.75 | 0.46
706 | TT23782 | Saurabh Shelke | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
707 | TT22830 | Saurabh Shelke | - | - | - | karagir jama (Po raise old process) Positive flow | Automate test script | 2024-09-28 | 03:30:00 | 03:47:52 | 2024-09-28 |  | COMPLETED | IN_TIME | 2024-09-28 16:01:40 | 2024-09-28 16:01:40 | 3.5 | 3.8
708 | TT22830 | Saurabh Shelke | - | - | - | Support Point to Kiran Karagir Nave | Support. | 2024-10-01 | 00:30:00 | 00:26:17 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:43 | 2024-10-01 19:02:43 | 0.5 | 0.44
709 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama - Provisional Parcel ,All vendors & Job work metal rate TC Writting | Test Case Writing | 2024-10-03 | 05:45:00 | 06:37:30 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:01:10 | 2024-10-04 19:01:10 | 5.75 | 6.63
710 | TT24776 | Saurabh Shelke | - | - | - | Support from Saurabh(Agent Master) | Query clarification | 2024-09-30 | 00:30:00 | 00:25:24 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:56:57 | 2024-09-30 19:56:57 | 0.5 | 0.42
711 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama Brainstorming | Brainstorming with DEV Team/BA | 2024-10-03 | 00:45:00 | 00:39:24 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 18:47:04 | 2024-10-03 18:47:04 | 0.75 | 0.66
712 | TT21899 | Saurabh Shelke | - | - | - | Support from gokul - Set tag module | Query clarification | 2024-09-30 | 01:00:00 | 00:39:16 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:34:05 | 2024-10-01 19:34:05 | 1 | 0.65
713 | TT24680 | Saurabh Shelke | - | - | - | subsmith master - test script review | Test script review | 2024-09-30 | 00:30:00 | 00:21:07 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:41:52 | 2024-09-30 19:41:52 | 0.5 | 0.35
714 | TT22830 | Saurabh Shelke | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 01:46:24 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 1.77
715 | TT24206 | Saurabh Shelke | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
716 | TT24680 | Saurabh Shelke | - | - | - | Support from gokul for Subsmith master script | Technical guidance/Process Input | 2024-09-30 | 00:30:00 | 00:20:55 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 19:17:23 | 2024-09-30 19:17:23 | 0.5 | 0.35
717 | TT22830 | Saurabh Shelke | - | - | - | Karagir Nave BrainStroming | Brainstorming with DEV Team/BA | 2024-09-30 | 00:15:00 | 00:13:50 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 15:35:06 | 2024-09-30 15:35:06 | 0.25 | 0.23
718 | TT24206 | Saurabh Shelke | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
719 | TT22830 | Saurabh Shelke | - | - | - | Karagir Jama positive flow (BR process Old process Scripting) | Automate test script | 2024-09-28 | 03:30:00 | 03:20:53 | 2024-09-28 |  | COMPLETED | DELAY | 2024-09-29 12:34:05 | 2024-09-29 12:34:05 | 3.5 | 3.35
720 | TT22830 | Saurabh Shelke | - | - | - | Karagir nave Jama Scripting Support By Gokul | Technical guidance/Process Input | 2024-09-24 | 02:00:00 | 01:53:07 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 16:04:23 | 2024-09-27 16:04:23 | 2 | 1.89
721 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
722 | TT22830 | Saurabh Shelke | - | - | - | Karagir nave Positive Flow Scripting | Automate test script | 2024-09-24 | 09:44:00 | 10:26:25 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-03 17:19:17 | 2024-10-03 17:19:17 | 9.73 | 10.44
723 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:50:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 1.84
724 | TT24760 | Saurabh Shelke | - | - | - | Bank Master Test Case Review | Review Test cases | 2024-09-23 | 00:30:00 | 00:22:56 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 16:52:37 | 2024-09-24 16:52:37 | 0.5 | 0.38
725 | TT23932 | Saurabh Shelke | Sprint 1 | - | - | Task Scheduling for Next Week | Task Scheduling | 2024-09-26 | 01:00:00 | 02:11:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:21:29 | 2024-09-27 17:21:29 | 1 | 2.18
726 | TT23985 | Saurabh Shelke | - | - | - | Support From Gokul | Technical guidance/Process Input | 2024-10-03 | 01:00:00 | 00:00:40 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:41:58 | 2024-10-04 19:41:58 | 1 | 0.01
727 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:41:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.7
728 | TT22402 | Sayali Vyawahare | - | - | - | Scheme estimation positive flow scripting | Test Script Preparation | 2024-09-10 | 04:30:00 | 04:30:49 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 16:20:51 | 2024-09-24 16:20:51 | 4.5 | 4.51
729 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | Duplicate code (xpath) on TPOS for all modules | Test Script Preparation | 2024-09-23 | 03:30:00 | 03:09:18 | 2024-09-23 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-24 12:10:21 | 2024-09-24 12:10:21 | 3.5 | 3.16
730 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-09 | 01:00:00 | 00:57:22 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:08:39 | 2024-09-13 20:08:39 | 1 | 0.96
731 | TT14931 | Sayali Vyawahare | - | - | - | Customer Order New Development KT Session | KT Session | 2024-09-04 | 01:00:00 | 01:05:01 | 2024-09-04 |  | COMPLETED | IN_TIME | 2024-09-04 13:11:48 | 2024-09-04 13:11:48 | 1 | 1.08
732 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir regarding script | Meeting with PH | 2024-09-18 | 01:00:00 | 01:08:10 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 20:38:07 | 2024-09-18 20:38:07 | 1 | 1.14
733 | TT23819 | Sayali Vyawahare | - | - | - | TT23819 - URD exchange and purchase brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:00:00 | 01:11:21 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 16:20:37 | 2024-09-11 16:20:37 | 1 | 1.19
734 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | List duplicate elements on TPOS | Test Script Preparation | 2024-09-05 | 01:30:00 | 01:20:55 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:59:48 | 2024-09-05 19:59:48 | 1.5 | 1.35
735 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (9th Sep - 13th Sep) | Sync call with Team | 2024-09-09 | 01:00:00 | 01:56:31 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:23 | 2024-09-13 19:33:23 | 1 | 1.94
736 | TT23782 | Sayali Vyawahare | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:05:00 | 00:03:51 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.08 | 0.06
737 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
738 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (18th - 20th Sep) | Sync call with Team | 2024-09-18 | 01:30:00 | 00:14:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:26:13 | 2024-09-20 22:26:13 | 1.5 | 0.24
739 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation and Installment TPOS Brainstorming and scenario listing | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:30:00 | 00:25:53 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:59:50 | 2024-09-11 17:59:50 | 1.5 | 0.43
740 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | D to TPOS scripting integration and modification (DTO) | Script Execution/ Modification | 2024-09-02 | 02:45:00 | 02:31:19 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 23:56:09 | 2024-09-03 23:56:09 | 2.75 | 2.52
741 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
742 | TT21914 | Sayali Vyawahare | - | - | - | support to sayali | Query clarification | 2024-09-02 | 02:30:00 | 01:01:25 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:04:13 | 2024-09-06 18:04:13 | 2.5 | 1.02
743 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
744 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | Automation test case discussion meeting with team | Test Script Preparation | 2024-09-02 | 01:00:00 | 00:40:48 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:58 | 2024-09-02 19:54:58 | 1 | 0.68
745 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:03:24 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.06
746 | TT22442 | Sayali Vyawahare | - | - | - | Cancel Estimation scripting | Test Script Preparation | 2024-09-05 | 04:00:00 | 04:11:48 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:03:53 | 2024-09-06 18:03:53 | 4 | 4.2
747 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 02:22:18 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 2.37
748 | TT24670 | Sayali Vyawahare | - | - | - | customer advance support to prathamesh | Mentoring | 2024-10-07 | 01:00:00 | 00:04:10 | 2024-10-09 |  | IN_PROGRESS | IN_PROGRESS |  |  | 1 | 0.07
749 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | Support to Prathamesh from sayali | Support. | 2024-09-03 | 03:00:00 | 03:05:28 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:32:49 | 2024-09-06 17:32:49 | 3 | 3.09
750 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | TT22455-Bug review(Gift card) | Reporting Review | 2024-10-07 | 02:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-04 20:53:03 |  | 2 | 0
751 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Weekly meeting with gaurav sir 20th Sep | Weekly sync call | 2024-09-20 | 01:00:00 | 01:00:00 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:50:01 | 2024-09-20 20:50:01 | 1 | 1
752 | TT22442 | Sayali Vyawahare | - | - | - | Estimation module code review | Script review | 2024-09-04 | 03:00:00 | 01:18:26 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-13 09:59:39 | 2024-09-13 09:59:39 | 3 | 1.31
753 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 02:00:00 | 01:11:55 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 2 | 1.2
754 | TT25961 | Sayali Vyawahare | - | - | - | gift voucher redemption estimation review | Estimate calculation | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO |  |  | 0.5 | 0
755 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | TT22455-Modified Test cases review(Gift Voucher) | Review Test cases | 2024-10-04 | 00:15:00 | 00:18:16 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 17:10:37 | 2024-10-04 17:10:37 | 0.25 | 0.3
756 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-02 | 01:15:00 | 02:27:18 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:42:31 | 2024-09-06 17:42:31 | 1.25 | 2.46
757 | TT24208 | Sayali Vyawahare | Testing_DPOS_Practice_Oct24_WK1 | - | - | CRM and Karagir repair practice review | Review | 2024-09-03 | 01:00:00 | 00:38:06 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 19:37:49 | 2024-09-03 19:37:49 | 1 | 0.64
758 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation and Installment TPOS Estimation | Estimate the requirement | 2024-09-02 | 00:45:00 | 00:23:23 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:54:09 | 2024-09-02 23:54:09 | 0.75 | 0.39
759 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 2309 to 2709 | Daily Sync Call | 2024-09-23 | 02:30:00 | 03:17:08 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:30 | 2024-09-27 19:54:30 | 2.5 | 3.29
760 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | TT22455-Test Case Review-Gift Card | Review Test cases | 2024-10-03 | 01:30:00 | 01:35:35 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 23:44:25 | 2024-10-03 23:44:25 | 1.5 | 1.59
761 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (2th Sep - 6th Sep) | Sync call with Team | 2024-09-02 | 01:15:00 | 01:08:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:00:01 | 2024-09-06 13:00:01 | 1.25 | 1.14
762 | TT24208 | Sayali Vyawahare | Testing_DPOS_Practice_Oct24_WK1 | - | - | Vastu jama and vastu jama Practice review | Review | 2024-09-03 | 01:15:00 | 01:06:52 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:39:08 | 2024-09-03 18:39:08 | 1.25 | 1.11
763 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance on TPOS Estimation | Estimate the requirement | 2024-09-03 | 00:30:00 | 00:17:20 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-04 15:49:04 | 2024-09-04 15:49:04 | 0.5 | 0.29
764 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-27 | 01:00:00 | 01:52:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:58:39 | 2024-09-27 19:58:39 | 1 | 1.88
765 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance order code review | Code Review | 2024-10-03 | 01:30:00 | 01:03:15 | 2024-10-03 |  | COMPLETED | DELAY | 2024-10-04 00:02:19 | 2024-10-04 00:02:19 | 1.5 | 1.05
766 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | Gift Voucher Sale Brainstorming | Brainstorming - Internal (Within Team member) | 2024-10-01 | 00:45:00 | 00:34:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:25:36 | 2024-10-01 15:25:36 | 0.75 | 0.58
767 | TT22402 | Sayali Vyawahare | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:12:56 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.22
768 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-20 | 01:00:00 | 00:58:41 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 19:57:00 | 2024-09-21 19:57:00 | 1 | 0.98
769 | TT24598 | Sayali Vyawahare | - | - | - | Customer creation test case review | Test Case Review | 2024-10-04 | 01:30:00 | 01:27:59 | 2024-10-07 |  | IN_PROGRESS | DELAY | 2024-10-07 11:55:45 |  | 1.5 | 1.47
770 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | TT22455-Gift Voucher-Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-24 16:22:06 | 2024-09-24 16:22:06 | 0 | 0
771 | TT24670 | Sayali Vyawahare | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 0.43
772 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 1809 to 2009 | Daily Sync Call | 2024-09-18 | 01:30:00 | 00:54:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:25:59 | 2024-09-20 22:25:59 | 1.5 | 0.91
773 | TT24670 | Sayali Vyawahare | - | - | - | customer advance and blanket advance test case execution | E2E Testing | 2024-10-01 | 04:00:00 | 03:47:19 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 22:56:32 | 2024-10-01 22:56:32 | 4 | 3.79
774 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | Gift card sales bill KT | KT Session | 2024-10-01 | 00:30:00 | 00:33:43 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 13:14:33 | 2024-10-01 13:14:33 | 0.5 | 0.56
775 | TT22394 | Sayali Vyawahare | - | - | - | URD Purchase Exchange KT | KT Session | 2024-09-03 | 00:45:00 | 00:31:22 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:41:20 | 2024-09-03 18:41:20 | 0.75 | 0.52
776 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for Next Week | Task Scheduling | 2024-09-13 | 01:00:00 | 00:02:02 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 18:43:15 | 2024-09-16 18:43:15 | 1 | 0.03
777 | TT24670 | Sayali Vyawahare | - | - | - | support to prathamesh | Query clarification | 2024-10-03 | 02:00:00 | 01:40:38 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:19:19 | 2024-10-04 20:19:19 | 2 | 1.68
778 | TT22455 | Sayali Vyawahare | Gift card sales 1 | - | - | Gift voucher creation scripting | Test Script Preparation | 2024-09-04 | 08:00:00 | 08:30:21 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-10 11:41:48 | 2024-09-10 11:41:48 | 8 | 8.51
779 | TT23939 | Sayali Vyawahare | - | - | - | POS Sync Call 0209 to 0609 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:46:15 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:13:52 | 2024-09-06 18:13:52 | 2.5 | 2.77
780 | TT25176 | Sayali Vyawahare | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 0909 to 1309 | Daily Sync Call | 2024-09-09 | 02:00:00 | 01:27:32 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:52 | 2024-09-13 18:56:52 | 2 | 1.46
781 | TT22442 | Sayali Vyawahare | - | - | - | Fresh sale bill scripting (gold, silver, diamond jewellery) | Test Script Preparation | 2024-09-25 | 14:00:00 | 13:34:14 | 2024-09-30 |  | COMPLETED | DELAY | 2024-10-01 22:44:23 | 2024-10-01 22:44:23 | 14 | 13.57
782 | TT23939 | Sayali Vyawahare | - | - | - | Task Scheduling for 06 Next Week | Task Scheduling | 2024-09-06 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:23:33 | 2024-09-06 19:23:33 | 1 | 0
783 | TT22402 | Sayali Vyawahare | - | - | - | SWGP Scheme New CR KT | KT Session | 2024-09-27 | 00:33:00 | 00:38:57 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:17:47 | 2024-09-27 15:17:47 | 0.55 | 0.65
784 | TT25629 | Sayali Vyawahare | - | - | - | Lumsam and mrp, Sterling rate | Demo | 2024-09-26 | 00:30:00 | 00:21:59 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 17:01:38 | 2024-09-26 17:01:38 | 0.5 | 0.37
785 | TT22453 | Sayali Vyawahare | - | - | - | Customer order code review | Script review | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-24 16:23:10 | 2024-09-24 16:23:10 | 0 | 0
786 | TT22453 | Sayali Vyawahare | - | - | - | support to prathamesh | Technical guidance/Process Input | 2024-09-25 | 03:00:00 | 01:12:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:57:16 | 2024-09-27 19:57:16 | 3 | 1.21
787 | TT22402 | Sayali Vyawahare | - | - | - | Scheme sale bill bugs review | Reporting Review | 2024-09-26 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-24 16:21:20 | 2024-09-24 16:21:20 | 0 | 0
788 | TT21914 | Sayali Vyawahare | - | - | - | KRA -KPI relevant action plan with Gokul & Sayali | Explore Team capability/Improvement plan | 2024-09-23 | 02:00:00 | 01:02:26 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 20:31:38 | 2024-09-24 20:31:38 | 2 | 1.04
789 | TT21914 | Sayali Vyawahare | - | - | - | Support to Sayali | Query clarification | 2024-09-23 | 02:30:00 | 00:21:15 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:39 | 2024-09-27 19:54:39 | 2.5 | 0.35
790 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
791 | TT24598 | Sayali Vyawahare | - | - | - | Customer Creation Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-23 | 01:00:00 | 00:47:19 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-24 01:40:00 | 2024-09-24 01:40:00 | 1 | 0.79
792 | TT24598 | Sayali Vyawahare | - | - | - | Customer Creation Test Case Review | Review Test cases | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 14:42:34 | 2024-09-24 14:42:34 | 0 | 0
793 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
794 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance bugs review | Reporting Review | 2024-09-24 | 00:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 16:19:08 | 2024-09-24 16:19:08 | 0 | 0
795 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Support to Sayali | Query clarification | 2024-10-07 | 00:15:00 | 00:21:16 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS |  |  | 0.25 | 0.35
796 | TT23350 | Sayali Vyawahare | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:25:07 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.42
797 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 0
798 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Roaster preaparation Meeting | Testing Team Meeting | 2024-10-03 | 01:00:00 | 00:50:45 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 21:30:36 | 2024-10-03 21:30:36 | 1 | 0.85
799 | TT24598 | Sayali Vyawahare | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:49:04 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0.82
800 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
801 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Lambda test meeting | Meeting with PH | 2024-10-03 | 00:45:00 | 00:53:58 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 17:25:04 | 2024-10-03 17:25:04 | 0.75 | 0.9
802 | TT24670 | Sayali Vyawahare | - | - | - | support to prathamesh | Support. | 2024-09-20 | 00:45:00 | 00:25:12 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:26:33 | 2024-09-20 19:26:33 | 0.75 | 0.42
803 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
804 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:58:42 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 1 | 0.98
805 | TT24670 | Sayali Vyawahare | - | - | - | Customer advance on TPOS test case review | Review Test cases | 2024-09-20 | 01:30:00 | 01:26:02 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:57:06 | 2024-09-20 23:57:06 | 1.5 | 1.43
806 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | - | - | Karagir repair KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:23:42 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:39 | 2024-09-02 19:54:39 | 1 | 0.4
807 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Testing Team Meeting | 2024-09-30 | 02:00:00 | 00:22:33 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:47:48 | 2024-10-04 20:47:48 | 2 | 0.38
808 | TT24670 | Sayali Vyawahare | - | - | - | customer advance brainstorming | Brainstorming | 2024-09-19 | 00:30:00 | 00:44:25 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:04 | 2024-09-19 17:01:04 | 0.5 | 0.74
809 | TT24206 | Sayali Vyawahare | Testing_KT_Oct24_Wk1 | - | - | CRM KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:11:05 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:40:58 | 2024-09-02 23:40:58 | 1 | 0.18
810 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Sprint KT to team | KT from BA | 2024-09-24 | 00:34:00 | 00:17:34 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:24:50 | 2024-09-24 18:24:50 | 0.57 | 0.29
811 | TT21914 | Sayali Vyawahare | - | - | - | Sayali - Support task | Query clarification | 2024-09-19 | 01:00:00 | 00:02:03 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:40:40 | 2024-09-20 20:40:40 | 1 | 0.03
812 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Meeting with Gaurav Sir | Meeting with PH | 2024-09-24 | 00:30:00 | 00:30:00 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 18:25:05 | 2024-09-24 18:25:05 | 0.5 | 0.5
813 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation and Installment TPOS bug review | Reporting Review | 2024-09-19 | 02:00:00 | 02:15:56 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 12:50:18 | 2024-09-20 12:50:18 | 2 | 2.27
814 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | meeting with gaurav sir regarding duplicate code | Meeting with PH | 2024-09-23 | 01:00:00 | 01:00:00 | 2024-09-23 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-24 18:06:25 | 2024-09-24 13:49:11 | 1 | 1
815 | TT22402 | Sayali Vyawahare | - | - | - | Scheme creation test case review after modification | Review updated Test cases | 2024-09-19 | 00:30:00 | 00:34:40 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 20:07:16 | 2024-09-19 20:07:16 | 0.5 | 0.58
816 | TT22442 | Sayali Vyawahare | - | - | - | POS Payment mode scripting (positive scenario) | Test Script Preparation | 2024-09-09 | 08:00:00 | 08:35:57 | 2024-09-11 |  | COMPLETED | DELAY | 2024-09-13 13:01:03 | 2024-09-13 13:01:03 | 8 | 8.6
817 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call By TL | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:22:34 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:41:09 | 2024-09-27 17:41:09 | 2.5 | 2.38
818 | TT22402 | Sayali Vyawahare | - | - | - | support to prathamesh | Mentoring | 2024-09-18 | 00:30:00 | 00:16:45 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 22:00:49 | 2024-09-18 22:00:49 | 0.5 | 0.28
819 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | Support from sayali | Query clarification | 2024-10-01 | 00:15:00 | 00:08:45 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:01 | 2024-10-01 19:02:01 | 0.25 | 0.15
820 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Script report demo to Gaurav Sir | Meeting with PH | 2024-09-18 | 01:00:00 | 00:16:14 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:39:57 | 2024-09-20 19:39:57 | 1 | 0.27
821 | TT21914 | Sayali Vyawahare | - | - | - | support to sayali | Query clarification | 2024-09-09 | 02:00:00 | 00:51:02 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:43 | 2024-09-13 19:33:43 | 2 | 0.85
822 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 00:15:00 | 00:16:29 | 2024-10-10 |  | IN_PROGRESS | DELAY | 2024-10-07 13:31:36 |  | 0.25 | 0.27
823 | TT22442 | Sayali Vyawahare | - | - | - | Payment mode validations scripting (UPI, card, cash) | Test Script Preparation | 2024-09-18 | 03:15:00 | 03:10:19 | 2024-09-19 |  | COMPLETED | DELAY | 2024-09-20 22:26:23 | 2024-09-20 22:26:23 | 3.25 | 3.17
824 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | Automation Support By SV | Query clarification | 2024-09-26 | 04:00:00 | 07:38:43 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-28 23:01:07 | 2024-09-28 23:01:07 | 4 | 7.65
825 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call testing team. | Sync call with Team | 2024-09-18 | 00:45:00 | 01:08:45 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 20:38:40 | 2024-09-20 20:38:40 | 0.75 | 1.15
826 | TT23819 | Sayali Vyawahare | - | - | - | URD estimation review | Estimation Review | 2024-09-05 | 00:15:00 | 00:22:00 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 18:55:39 | 2024-09-05 18:55:39 | 0.25 | 0.37
827 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (23rd - 27th Sep) | Sync call with Team | 2024-09-23 | 01:15:00 | 00:49:04 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:04:20 | 2024-09-27 20:04:20 | 1.25 | 0.82
828 | TT22402 | Sayali Vyawahare | - | - | - | Scheme pos entry and instalment test case review | Review Test cases | 2024-09-13 | 01:30:00 | 01:26:39 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-15 20:58:40 | 2024-09-15 20:58:40 | 1.5 | 1.44
829 | TT24390 | Sayali Vyawahare | Testing_AutomationPractice_OCT24_WK1 | - | - | Support to dev team for duplicate code | Technical guidance/Process Input | 2024-09-24 | 04:00:00 | 03:33:23 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:04:42 | 2024-09-24 19:04:42 | 4 | 3.56
830 | TT24303 | Sayali Vyawahare | Testing_GM_Oct_2024_Wk1 | - | - | support to prathamesh | Technical guidance/Process Input | 2024-09-11 | 02:00:00 | 00:42:20 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:02 | 2024-09-13 19:33:02 | 2 | 0.71
831 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Support to swapnil for document module | Query clarification | 2024-10-03 | 00:30:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY | 2024-09-27 17:53:31 |  | 0.5 | 0
832 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil( Tenant Master, Dynamic form, Dropdown master, Query Type Master) | Internal KT/cross KT | 2024-09-24 | 02:00:00 | 00:27:31 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 19:03:39 | 2024-09-24 19:03:39 | 2 | 0.46
833 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Document module Test case modification | Test case updation\modification | 2024-09-03 | 02:00:00 | 02:39:17 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-06 15:13:08 | 2024-09-06 15:13:08 | 2 | 2.65
834 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Explore & practice the connect us 2.0( User master, customer master, Role master and designation Master) | Explore the existing system. | 2024-09-23 | 01:00:00 | 01:05:27 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:06:43 | 2024-09-23 23:06:43 | 1 | 1.09
835 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-02 | 00:44:00 | 00:37:07 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-03 19:29:26 | 2024-09-03 19:29:26 | 0.73 | 0.62
836 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil (User Master, Customer Master, Role Master, Designation Master) | Internal KT/cross KT | 2024-09-23 | 02:00:00 | 00:41:06 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 12:18:43 | 2024-09-23 12:18:43 | 2 | 0.69
837 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Support to Swapnil for Consolidated report | Query clarification | 2024-09-02 | 01:30:00 | 00:24:07 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:05:31 | 2024-09-06 17:05:31 | 1.5 | 0.4
838 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Estimation KT to Swapnil | Internal KT/cross KT | 2024-09-06 | 00:45:00 | 00:42:10 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:53:10 | 2024-09-06 18:53:10 | 0.75 | 0.7
839 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Documentation Module Testing | Testing | 2024-09-02 | 02:30:00 | 04:00:10 | 2024-09-02 |  | COMPLETED | DELAY | 2024-09-03 11:53:14 | 2024-09-03 11:53:14 | 2.5 | 4
840 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
841 | TT23495 | Swapnil Ramdasi | - | - | - | Menu master, page master, section type master, page section master, page content master, Setting master, - Test case writing | Test Case Writing | 2024-09-30 | 03:30:00 | 01:33:54 | 2024-09-30 |  | IN_PROGRESS | DELAY | 2024-09-27 20:33:10 |  | 3.5 | 1.57
842 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Cross KT - Customer view | Internal KT/cross KT | 2024-09-02 | 00:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-08-30 20:15:30 | 2024-08-30 20:15:30 | 0 | 0
843 | TT23495 | Swapnil Ramdasi | - | - | - | Support to Swapnil - for cs website | Query clarification | 2024-09-30 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 2 | 0
844 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | Country Master , State Master , City Master test case Writing | Test Case Writing | 2024-09-12 | 01:30:00 | 00:00:00 | 2024-09-12 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-23 23:03:41 | 2024-09-23 23:03:41 | 1.5 | 0
845 | TT23495 | Swapnil Ramdasi | - | - | - | CMS KT Session | KT Session | 2024-09-26 | 01:30:00 | 01:30:16 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 15:12:46 | 2024-09-27 15:12:46 | 1.5 | 1.5
846 | TT23294 | Swapnil Ramdasi | - | - | - | End to End testing for Time Regularization | E2E Testing. | 2024-09-09 | 04:00:00 | 03:58:31 | 2024-09-09 |  | COMPLETED | DELAY | 2024-09-10 04:53:21 | 2024-09-10 04:53:21 | 4 | 3.98
847 | TT23495 | Swapnil Ramdasi | - | - | - | Scheduling for upcoming week | Task Scheduling | 2024-10-04 | 00:30:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY |  |  | 0.5 | 0
848 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | Customer mapping - Add + edit + reflection on Grid | Test Script Preparation | 2024-09-10 | 00:00:00 | 00:00:00 | 2024-09-12 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-16 11:15:59 | 2024-09-16 11:15:59 | 0 | 0
849 | TT21914 | Swapnil Ramdasi | - | - | - | Task Scheduling for 9 to 13 Sept | Task Scheduling | 2024-09-06 | 00:30:00 | 00:14:11 | 2024-09-06 |  | COMPLETED | DELAY | 2024-09-10 04:53:43 | 2024-09-10 04:53:43 | 0.5 | 0.24
850 | TT23495 | Swapnil Ramdasi | - | - | - | CS Website - Estimation | Estimate the requirement | 2024-10-04 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 19:28:51 |  | 2 | 0
851 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | Customer mapping test case writing | Test Case Writing | 2024-09-09 | 01:00:00 | 10:46:38 | 2024-09-09 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-10 10:53:46 | 2024-09-10 10:53:46 | 1 | 10.78
852 | TT23495 | Swapnil Ramdasi | - | - | - | Menu master, page master, section type master, page section master, page content master, Setting master, - Test case Updation | Test case updation\modification | 2024-10-07 | 01:30:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-09-27 20:47:29 |  | 1.5 | 0
853 | TT15425 | Swapnil Ramdasi | Sprint 1 | - | - | Bill checking transaction - filter testing | Unit Testing | 2024-09-25 | 01:30:00 | 05:01:52 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:55:59 | 2024-09-25 22:55:59 | 1.5 | 5.03
854 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | Automation Script for reading Tool tip text | Test Script Preparation | 2024-09-06 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-12 15:42:11 | 2024-09-12 15:42:11 | 2 | 0
855 | TT23495 | Swapnil Ramdasi | - | - | - | CS website - Support to swapnil | Query clarification | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-09 18:59:53 | 2024-09-09 18:59:53 | 0 | 0
856 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 00:00:00 | 00:07:50 | 2024-09-16 |  | COMPLETED | IN_TIME | 2024-09-13 16:08:19 | 2024-09-13 16:08:19 | 0 | 0.13
857 | TT15425 | Swapnil Ramdasi | Sprint 1 | - | - | Vendor master, Approval setting page, Payment template master -Testing | Unit Testing | 2024-09-23 | 08:00:00 | 11:25:51 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 22:58:14 | 2024-09-24 22:58:14 | 8 | 11.43
858 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | - | - | QR Code - KT session | KT from BA | 2024-10-04 | 00:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 10:23:01 | 2024-10-04 10:23:01 | 0 | 0
859 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | Customer Master Add Data preparation Add, Edit, View | Test case writing- | 2024-09-06 | 01:30:00 | 02:05:55 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:25:11 | 2024-09-06 20:25:11 | 1.5 | 2.1
860 | TT23495 | Swapnil Ramdasi | - | - | - | CS website - Support to swapnil | Mentoring | 2024-09-03 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:37:15 | 2024-09-06 16:37:15 | 1 | 0
861 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | Country Master , State Master , City Master Add + Reflection on Grid | Test Script Preparation | 2024-09-19 | 07:00:00 | 00:00:00 | 2024-09-20 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-24 16:22:16 | 2024-09-24 16:22:16 | 7 | 0
862 | TT22602 | Swapnil Ramdasi | QR Code - HRMS Sprint 1 | - | - | Document reading | Document Reading | 2024-10-03 | 02:00:00 | 00:00:00 | 2024-10-04 |  | TO_DO | DELAY | 2024-09-27 20:31:31 |  | 2 | 0
863 | TT24390 | Swapnil Ramdasi | Testing_AutomationPractice_OCT24_WK1 | - | - | User Master Add edit negative Scripting | Test Script Preparation | 2024-09-02 | 06:00:00 | 03:42:45 | 2024-09-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-20 19:24:50 | 2024-09-20 19:24:50 | 6 | 3.71
864 | TT24437 | Swapnil Ramdasi | - | - | - | Regularization - Estimation | Estimate the requirement | 2024-09-03 | 00:00:00 | 00:00:00 | 2024-09-03 |  | COMPLETED | DELAY | 2024-09-06 17:27:39 | 2024-09-06 17:27:39 | 0 | 0
865 | TT23495 | Swapnil Ramdasi | - | - | - | CSM + Website Validation updation | Validation updation | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | TO_DO | DELAY | 2024-09-24 19:22:10 |  | 1.5 | 0
866 | TT23495 | Swapnil Ramdasi | - | - | - | CSM + Website Validation writing | Validation writing | 2024-09-27 | 03:00:00 | 03:00:00 | 2024-09-27 |  | COMPLETED | DELAY | 2024-10-01 15:05:56 | 2024-09-29 23:02:40 | 3 | 3
867 | TT23495 | Swapnil Ramdasi | - | - | - | DSC - CMS | Daily Sync Call | 2024-09-02 | 02:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 17:16:17 | 2024-09-06 17:16:17 | 2 | 0
868 | TT23495 | Swapnil Ramdasi | - | - | - | CMS - Document Go through | Documentation Reading | 2024-09-23 | 01:00:00 | 00:46:26 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 23:07:54 | 2024-09-23 23:07:54 | 1 | 0.77
869 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | - | - | test | Application Support | 2024-10-03 | 00:40:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-04 20:50:51 | 2024-10-04 20:50:51 | 0.67 | 0
870 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | - | - | KRA KPI - go through recording | Internal KT/cross KT | 2024-09-30 | 01:00:00 | 00:00:00 | 2024-09-30 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-04 20:49:11 | 2024-10-04 20:49:11 | 1 | 0
871 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | - | - | Task scheduling | Task Scheduling | 2024-09-06 | 00:30:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 20:26:17 | 2024-09-06 20:26:17 | 0.5 | 0
872 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | - | - | Conflict resolution meeting with Swapnil | Conflict resolution meeting | 2024-09-06 | 00:10:00 | 00:12:47 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 15:01:40 | 2024-09-06 15:01:40 | 0.17 | 0.21
873 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
874 | TT24303 | Swapnil Ramdasi | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
875 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Explore and Practice connect us 2.0(Reports-user task, resource planning, Variance) | Explore the existing system. | 2024-10-01 | 00:00:00 | 00:00:09 | 2024-10-13 |  | IN_PROGRESS | DELAY | 2024-10-03 15:26:04 |  | 0 | 0
876 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil(Reports- user task , variance, Resource planning) | Internal KT/cross KT | 2024-09-27 | 02:00:00 | 00:50:24 | 2024-09-27 |  | COMPLETED | SLIGHTLY_DELAY | 2024-09-29 23:01:25 | 2024-09-29 23:01:25 | 2 | 0.84
877 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Retesting Documentation Module | Bug Retesting | 2024-10-03 | 03:00:00 | 00:00:00 | 2024-10-03 |  | TO_DO | DELAY |  |  | 3 | 0
878 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Explore and Practice (My Ticket) | Explore the existing system. | 2024-09-26 | 04:00:00 | 04:53:32 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 23:22:18 | 2024-09-26 23:22:18 | 4 | 4.89
879 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil(My Ticket) | Internal KT/cross KT | 2024-09-26 | 01:30:00 | 00:47:13 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 14:12:21 | 2024-09-26 14:12:21 | 1.5 | 0.79
880 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Document Module Automation Scripting | Test Script Preparation | 2024-09-13 | 12:00:00 | 05:45:26 | 2024-10-04 |  | IN_PROGRESS | DELAY | 2024-09-27 20:27:44 |  | 12 | 5.76
881 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Explore & practice the connect us 2.0( Customer Mapping , Create Ticket) | Explore the existing system. | 2024-09-25 | 04:00:00 | 01:56:18 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:55:44 | 2024-09-25 22:55:44 | 4 | 1.94
882 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | RAD for Documentation Module | RAD Testing | 2024-09-16 | 03:00:00 | 04:14:42 | 2024-09-16 |  | COMPLETED | DELAY | 2024-09-27 17:15:40 | 2024-09-27 17:15:40 | 3 | 4.25
883 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Doc Module Sync call | Daily Sync Call | 2024-10-01 | 01:00:00 | 00:00:00 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:26:18 | 2024-10-04 18:26:18 | 1 | 0
884 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | KT to Swapnil (Customer Mapping , Create Ticket) | Internal KT/cross KT | 2024-09-25 | 01:30:00 | 01:27:01 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 22:54:56 | 2024-09-25 22:54:56 | 1.5 | 1.45
885 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Documentation Module Retesting | Retesting | 2024-09-10 | 02:30:00 | 03:28:18 | 2024-09-10 |  | COMPLETED | DELAY | 2024-09-27 10:00:55 | 2024-09-13 07:41:09 | 2.5 | 3.47
886 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | test | Application Support | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-09-27 17:54:38 | 2024-09-27 17:54:38 | 0 | 0
887 | TT24206 | Swapnil Ramdasi | Testing_KT_Oct24_Wk1 | - | - | Explore & practice the connect us 2.0( Tenant Master, Dynamic Dropdown, Dynamic Form and Query Type Master) | Explore the existing system. | 2024-09-24 | 01:00:00 | 01:14:09 | 2024-09-24 |  | COMPLETED | IN_TIME | 2024-09-24 22:57:56 | 2024-09-24 22:57:56 | 1 | 1.24
888 | TT24427 | Swapnil Ramdasi | E2E Testing | - | - | Daily Sync Call -Documentation module | Daily Sync Call | 2024-09-04 | 00:45:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:26:29 | 2024-09-06 18:26:29 | 0.75 | 0
889 | TT23819 | Uttareshwar Bhusari | - | - | - | TT23819-Create Estimation for URD Exchange and Purchase | Estimate the requirement | 2024-09-05 | 00:30:00 | 00:29:48 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 16:19:56 | 2024-09-05 16:19:56 | 0.5 | 0.5
890 | TT23819 | Uttareshwar Bhusari | - | - | - | URD purchas Test case execution | Functional Testing | 2024-09-24 | 03:15:00 | 00:51:15 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 09:26:02 | 2024-09-25 09:26:02 | 3.25 | 0.85
891 | TT22402 | Uttareshwar Bhusari | - | - | - | TPOS Scheme KT to developer and Tester | KT Session | 2024-09-02 | 01:00:00 | 01:09:22 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-03 10:41:55 | 2024-09-02 16:43:53 | 1 | 1.16
892 | TT23819 | Uttareshwar Bhusari | - | - | - | URD purchase and exchange test case modification | Test case updation\modification | 2024-09-19 | 01:00:00 | 00:58:39 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:25:19 | 2024-09-19 17:25:19 | 1 | 0.98
893 | TT24670 | Uttareshwar Bhusari | - | - | - | Customer Order Advance KT | KT Session | 2024-09-03 | 01:00:00 | 00:25:31 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:16:32 | 2024-09-03 18:16:32 | 1 | 0.43
894 | TT23819 | Uttareshwar Bhusari | - | - | - | URD Exchange and Purchase Test case writing | Test case writing- | 2024-09-12 | 04:30:00 | 05:00:43 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-13 18:08:01 | 2024-09-13 18:08:01 | 4.5 | 5.01
895 | TT22394 | Uttareshwar Bhusari | - | - | - | URD Purchase Exchange KT | KT Session | 2024-09-03 | 00:45:00 | 00:31:19 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 18:41:20 | 2024-09-03 18:41:20 | 0.75 | 0.52
896 | TT23819 | Uttareshwar Bhusari | - | - | - | TT23819 - URD exchange and purchase brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-11 | 01:00:00 | 01:00:08 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 16:20:37 | 2024-09-11 16:20:37 | 1 | 1
897 | TT23819 | Uttareshwar Bhusari | - | - | - | TT23819-Urd purchase and exchange Document reading | Documentation Reading | 2024-09-11 | 00:30:00 | 00:22:22 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:48:00 | 2024-09-11 17:48:00 | 0.5 | 0.37
898 | TT23939 | Uttareshwar Bhusari | - | - | - | POS Sync Call 0209 to 0609 | Daily Sync Call | 2024-09-02 | 02:30:00 | 02:10:12 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:13:52 | 2024-09-06 18:13:52 | 2.5 | 2.17
899 | TT23939 | Uttareshwar Bhusari | - | - | - | Task Scheduling for 06 Next Week | Task Scheduling | 2024-09-06 | 01:00:00 | 00:00:00 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:23:33 | 2024-09-06 19:23:33 | 1 | 0
900 | TT24206 | Uttareshwar Bhusari | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:56:06 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.94
901 | TT24206 | Uttareshwar Bhusari | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
902 | TT24206 | Uttareshwar Bhusari | Testing_KT_Oct24_Wk1 | - | - | Karagir repair KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:00:00 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:39 | 2024-09-02 19:54:39 | 1 | 0
903 | TT24206 | Uttareshwar Bhusari | Testing_KT_Oct24_Wk1 | - | - | CRM KT to POS testers | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 00:07:41 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 23:40:58 | 2024-09-02 23:40:58 | 1 | 0.13
904 | TT24390 | Uttareshwar Bhusari | Testing_AutomationPractice_OCT24_WK1 | - | - | Support from sayali | Query clarification | 2024-10-01 | 00:15:00 | 00:08:45 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:02:01 | 2024-10-01 19:02:01 | 0.25 | 0.15
905 | TT24390 | Uttareshwar Bhusari | Testing_AutomationPractice_OCT24_WK1 | - | - | Automation test case discussion meeting with team | Test Script Preparation | 2024-09-02 | 01:00:00 | 00:00:00 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:54:58 | 2024-09-02 19:54:58 | 1 | 0
906 | TT24390 | Uttareshwar Bhusari | Testing_AutomationPractice_OCT24_WK1 | - | - | TT24390-Test script execution (Test suit creation) | Test script execution | 2024-09-06 | 01:30:00 | 01:21:56 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:55:38 | 2024-09-06 16:55:38 | 1.5 | 1.37
907 | TT25148 | Uttareshwar Bhusari | Sales Return Advance & Utilization Demo | - | - | Sales Return Figma KT to Developers & Testers | KT Session | 2024-09-12 | 00:10:00 | 00:07:36 | 2024-09-12 |  | COMPLETED | IN_TIME | 2024-09-12 15:10:15 | 2024-09-12 15:10:15 | 0.17 | 0.13
908 | TT24390 | Uttareshwar Bhusari | Testing_AutomationPractice_OCT24_WK1 | - | - | TT24390- Core Logic creation(Vastu Jama) | Automate test script | 2024-09-03 | 23:00:00 | 21:22:07 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 16:56:07 | 2024-09-06 16:56:07 | 23 | 21.37
909 | TT24390 | Uttareshwar Bhusari | Testing_AutomationPractice_OCT24_WK1 | - | - | TT24390-POM creation for vastu Jama | Automate test script | 2024-09-02 | 04:00:00 | 03:57:34 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 14:42:52 | 2024-09-03 14:42:52 | 4 | 3.96
910 | TT17470 | Uttareshwar Bhusari | - | - | - | Meeting with Gaurav Sir Regarding Automation points | General meeting | 2024-09-30 | 00:15:00 | 00:06:53 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 15:22:53 | 2024-09-30 15:22:53 | 0.25 | 0.11
911 | TT22402 | Uttareshwar Bhusari | - | - | - | TT22402-Scheme GDP Create Automation script | Automate test script | 2024-09-26 | 12:00:00 | 08:56:24 | 2024-09-27 |  | COMPLETED | DELAY | 2024-09-30 11:30:43 | 2024-09-30 11:30:43 | 12 | 8.94
912 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
913 | TT22402 | Uttareshwar Bhusari | - | - | - | TT22402-Scheme GDP Create Automation script | Automate test script | 2024-09-25 | 06:00:00 | 07:18:28 | 2024-09-25 |  | COMPLETED | DELAY | 2024-09-26 10:28:24 | 2024-09-26 10:28:24 | 6 | 7.31
914 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-04 20:53:28 | 2024-10-04 20:53:28 | 0.5 | 0
915 | TT25629 | Uttareshwar Bhusari | - | - | - | Lumsam and mrp, Sterling rate | Demo | 2024-09-26 | 00:30:00 | 00:21:58 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 17:01:38 | 2024-09-26 17:01:38 | 0.5 | 0.37
916 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (23rd - 27th Sep) | Sync call with Team | 2024-09-23 | 01:15:00 | 00:33:15 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 20:04:20 | 2024-09-27 20:04:20 | 1.25 | 0.55
917 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | task scheduling | Task Scheduling | 2024-10-04 | 01:00:00 | 01:30:26 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:58:06 | 2024-10-04 21:58:06 | 1 | 1.51
918 | TT22442 | Uttareshwar Bhusari | - | - | - | TT22442-Prepare automation script for Invoice | Automate test script | 2024-09-23 | 19:15:00 | 06:16:04 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-25 09:26:18 | 2024-09-25 09:26:18 | 19.25 | 6.27
919 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift Voucher Sale Prepare automation script | Test Automation Script Preparation | 2024-10-07 | 03:00:00 | 00:00:00 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS |  |  | 3 | 0
920 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS sync call | Daily Sync Call | 2024-09-30 | 01:30:00 | 00:54:40 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 21:57:48 | 2024-10-04 21:57:48 | 1.5 | 0.91
921 | TT23819 | Uttareshwar Bhusari | - | - | - | TT23819-Test case modification | Test case updation\modification | 2024-09-23 | 00:30:00 | 00:00:00 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-25 09:25:39 | 2024-09-25 09:25:39 | 0.5 | 0
922 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Card Test Case execution | E2E Testing | 2024-10-07 | 04:15:00 | 01:19:31 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 19:42:53 |  | 4.25 | 1.33
923 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:41:51 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.7
924 | TT23350 | Uttareshwar Bhusari | - | - | - | Add and remove Payment mode And Document series KT To Tester | KT Session | 2024-09-19 | 00:30:00 | 00:25:07 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:59 | 2024-09-19 17:01:59 | 0.5 | 0.42
925 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | daily sync call POS testers | Testing Team Meeting | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.25 | 0
926 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Voucher Test Case Modification | Test case updation\modification | 2024-10-04 | 01:00:00 | 02:33:35 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:33:43 | 2024-10-04 19:33:43 | 1 | 2.56
927 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (18th - 20th Sep) | Sync call with Team | 2024-09-18 | 01:30:00 | 00:14:10 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:26:13 | 2024-09-20 22:26:13 | 1.5 | 0.24
928 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 2309 to 2709 | Daily Sync Call | 2024-09-23 | 02:30:00 | 01:45:13 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:54:30 | 2024-09-27 19:54:30 | 2.5 | 1.75
929 | TT24598 | Uttareshwar Bhusari | - | - | - | Customer Master KT to tester | KT Session | 2024-09-19 | 01:00:00 | 00:49:04 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:11 | 2024-09-19 17:01:11 | 1 | 0.82
930 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
931 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Voucher Sale Bill Estimation | Estimate the requirement | 2024-10-01 | 00:20:00 | 00:18:38 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:01:40 | 2024-10-01 19:01:40 | 0.33 | 0.31
932 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (9th Sep - 13th Sep) | Sync call with Team | 2024-09-09 | 01:15:00 | 02:36:39 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 19:33:23 | 2024-09-13 19:33:23 | 1.25 | 2.61
933 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-27 | 01:00:00 | 01:52:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 19:58:39 | 2024-09-27 19:58:39 | 1 | 1.88
934 | TT22442 | Uttareshwar Bhusari | - | - | - | TT22442-Automation Test Case Selection for Invoice | Planning | 2024-09-18 | 00:30:00 | 00:36:22 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 19:41:09 | 2024-09-18 19:41:09 | 0.5 | 0.61
935 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift card Test Case Modification | Test case updation\modification | 2024-09-26 | 00:30:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-25 09:25:03 | 2024-09-25 09:25:03 | 0.5 | 0
936 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
937 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Prepare automation script for Gift Voucher creation-POS | Test Script Preparation | 2024-10-01 | 03:00:00 | 02:44:56 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:01:33 | 2024-10-01 19:01:33 | 3 | 2.75
938 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Meeting With HR (Leave policy) | HR meeting | 2024-09-06 | 00:30:00 | 00:33:44 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 12:58:25 | 2024-09-06 12:58:25 | 0.5 | 0.56
939 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for next week | Task Scheduling | 2024-09-20 | 01:00:00 | 00:39:46 | 2024-09-20 |  | COMPLETED | DELAY | 2024-09-21 19:57:00 | 2024-09-21 19:57:00 | 1 | 0.66
940 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Voucher Test case Writing | Test case writing- | 2024-09-25 | 02:30:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 09:24:55 | 2024-09-25 09:24:55 | 2.5 | 0
941 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (30th sep - 4th Oct) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:48:34 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 20:42:59 | 2024-10-04 20:42:59 | 1 | 0.81
942 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Card add sale bill Script Preparation | Automate test script | 2024-09-30 | 06:00:00 | 05:50:44 | 2024-09-30 |  | COMPLETED | IN_TIME | 2024-09-30 21:43:39 | 2024-09-30 21:43:39 | 6 | 5.85
943 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
944 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 1809 to 2009 | Daily Sync Call | 2024-09-18 | 01:30:00 | 00:54:24 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 22:25:59 | 2024-09-20 22:25:59 | 1.5 | 0.91
945 | TT22442 | Uttareshwar Bhusari | - | - | - | TT22442-Invoice Automation script For(Grid View validation, both Estimate + Tag scan scenerio + Cancel functionality ) | Automate test script | 2024-09-20 | 06:00:00 | 05:30:54 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:03 | 2024-09-20 17:06:03 | 6 | 5.52
946 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift voucher Sale Test case writing | Test Case Writing | 2024-10-01 | 03:00:00 | 02:14:44 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 19:01:27 | 2024-10-01 19:01:27 | 3 | 2.25
947 | TT24303 | Uttareshwar Bhusari | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call POS Testers (2th Sep - 6th Sep) | Sync call with Team | 2024-09-02 | 01:15:00 | 01:08:38 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:00:01 | 2024-09-06 13:00:01 | 1.25 | 1.14
948 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | Task Scheduling for Next Week | Task Scheduling | 2024-09-13 | 01:00:00 | 00:00:00 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-16 18:43:15 | 2024-09-16 18:43:15 | 1 | 0
949 | TT22442 | Uttareshwar Bhusari | - | - | - | TT22442-Invoice-Create script for all mandatory feilds | Automate test script | 2024-09-19 | 01:00:00 | 00:59:52 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:26:55 | 2024-09-19 17:26:55 | 1 | 1
950 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Card document reading | Document Reading | 2024-09-24 | 01:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 09:24:44 | 2024-09-25 09:24:44 | 1 | 0
951 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift Voucher Sale Document Reading | Document Reading | 2024-09-30 | 00:45:00 | 00:43:29 | 2024-09-30 |  | COMPLETED | DELAY | 2024-10-01 11:13:19 | 2024-10-01 11:13:19 | 0.75 | 0.72
952 | TT25176 | Uttareshwar Bhusari | POS SYNC CALL & SCHEDULING | - | - | POS Sync Call 0909 to 1309 | Daily Sync Call | 2024-09-09 | 02:30:00 | 02:05:44 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:56:52 | 2024-09-13 18:56:52 | 2.5 | 2.1
953 | TT24670 | Uttareshwar Bhusari | - | - | - | customer advance brainstorming | Brainstorming | 2024-09-19 | 00:30:00 | 00:44:25 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:01:04 | 2024-09-19 17:01:04 | 0.5 | 0.74
954 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Voucher-Brainstorming | Brainstorming - Internal ( Within Team member) | 2024-09-25 | 00:00:00 | 00:00:00 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-24 16:22:06 | 2024-09-24 16:22:06 | 0 | 0
955 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift Voucher Sale Brainstorming | Brainstorming - Internal (Within Team member) | 2024-10-01 | 00:45:00 | 00:34:36 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:25:36 | 2024-10-01 15:25:36 | 0.75 | 0.58
956 | TT22442 | Uttareshwar Bhusari | - | - | - | TT22442-Test Script Modification & Execution Invoice Positive Flow | Modify test script | 2024-09-18 | 03:00:00 | 02:51:16 | 2024-09-18 |  | COMPLETED | IN_TIME | 2024-09-18 19:40:56 | 2024-09-18 19:40:56 | 3 | 2.85
957 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | Gift card sales bill KT | KT Session | 2024-10-01 | 00:30:00 | 00:33:44 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 13:14:33 | 2024-10-01 13:14:33 | 0.5 | 0.56
958 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Card Test Case Execution | Testing | 2024-09-26 | 03:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-25 09:25:10 | 2024-09-25 09:25:10 | 3 | 0
959 | TT22442 | Uttareshwar Bhusari | - | - | - | TT22442-Test script preparation Positive flow of invoice | Automate test script | 2024-09-13 | 05:15:00 | 04:58:26 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:07:25 | 2024-09-13 18:07:25 | 5.25 | 4.97
960 | TT22455 | Uttareshwar Bhusari | Gift card sales 1 | - | - | TT22455-Gift Voucher Sale Bill Estimation | Estimate the requirement | 2024-09-20 | 00:30:00 | 00:34:49 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:39 | 2024-09-20 17:06:39 | 0.5 | 0.58
961 | TT22457 | Uttareshwar Bhusari | - | - | - | TT22457-Create automation script (POM+Core)for Vastu Jama handover | Automate test script | 2024-09-09 | 20:45:00 | 19:34:58 | 2024-09-11 |  | COMPLETED | IN_TIME | 2024-09-11 17:48:21 | 2024-09-11 17:48:21 | 20.75 | 19.58
962 | TT22457 | Uttareshwar Bhusari | - | - | - | Vastu Jama Test method Modification and create final report | Automate test script | 2024-09-12 | 01:45:00 | 01:35:13 | 2024-09-12 |  | COMPLETED | DELAY | 2024-09-13 15:52:32 | 2024-09-13 15:52:32 | 1.75 | 1.59
963 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Automation Scripting by using DTO | Test Script Preparation | 2024-09-02 | 18:00:00 | 16:19:28 | 2024-09-13 |  | COMPLETED | DELAY | 2024-09-18 20:07:23 | 2024-09-18 20:07:23 | 18 | 16.32
964 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-18 | 00:45:00 | 00:54:34 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 17:06:10 | 2024-09-20 17:06:10 | 0.75 | 0.91
965 | TT21945 | Vaishnavi Khandwe | - | - | - | P2P Process - Support from Saurabh | Support. | 2024-10-07 | 00:30:00 | 00:34:08 | 2024-10-07 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:50:51 |  | 0.5 | 0.57
966 | TT18255 | Vaishnavi Khandwe | - | - | - | Support from Gokul URD Silver | Support. | 2024-10-05 | 01:00:00 | 01:00:05 | 2024-10-05 |  | COMPLETED | IN_TIME | 2024-10-05 23:22:37 | 2024-10-05 23:22:37 | 1 | 1
967 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call- D Team (Internal) 9-13 sep | Daily Sync Call | 2024-09-09 | 00:15:00 | 00:25:32 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 12:08:41 | 2024-09-13 12:08:41 | 0.25 | 0.43
968 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D sync call 7-11 | Daily Sync Call | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO |  |  | 0.5 | 0
969 | TT21945 | Vaishnavi Khandwe | - | - | - | P2P Process Support from Gokul | Query clarification | 2024-10-03 | 01:00:00 | 00:09:25 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:47 | 2024-10-04 19:08:47 | 1 | 0.16
970 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting Silver purchase us and other | Test Script Preparation | 2024-10-05 | 06:00:00 | 07:30:42 | 2024-10-05 |  | IN_PROGRESS | DELAY | 2024-10-07 12:38:11 |  | 6 | 7.51
971 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Monthly Meeting with Gaurav Sir | Meeting with PH | 2024-09-13 | 00:55:00 | 01:05:05 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:02 | 2024-09-13 18:05:02 | 0.92 | 1.08
972 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D sync call 30-04 | Daily Sync Call | 2024-09-30 | 02:00:00 | 00:44:23 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:56:45 | 2024-10-04 19:56:45 | 2 | 0.74
973 | TT21945 | Vaishnavi Khandwe | - | - | - | GB - Item P2P process Testing | E2E Testing | 2024-10-07 | 02:00:00 | 00:09:14 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 13:20:35 |  | 2 | 0.15
974 | TT18255 | Vaishnavi Khandwe | - | - | - | Support from Gokul URD Automation | Query clarification | 2024-10-03 | 01:00:00 | 00:43:55 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:08:23 | 2024-10-04 19:08:23 | 1 | 0.73
975 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | D Testing Team Sync call 2 to 6 sep | Daily Sync Call | 2024-09-02 | 01:00:00 | 00:34:59 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 13:03:17 | 2024-09-06 13:03:17 | 1 | 0.58
976 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | Task Scheduling next week | Task Scheduling | 2024-10-03 | 01:00:00 | 00:40:01 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 11:04:44 | 2024-10-04 11:04:44 | 1 | 0.67
977 | TT21945 | Vaishnavi Khandwe | - | - | - | DJ- Item P2P process Testing | E2E Testing | 2024-10-04 | 03:00:00 | 04:26:36 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:58:46 | 2024-10-04 19:58:46 | 3 | 4.44
978 | TT18255 | Vaishnavi Khandwe | - | - | - | Support From Gokul URD | Test Script Preparation | 2024-10-07 | 00:30:00 | 01:00:36 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-04 10:40:39 |  | 0.5 | 1.01
979 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D Sync Call 23-27 | Daily Sync Call | 2024-09-23 | 02:30:00 | 02:15:01 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 18:45:12 | 2024-09-27 18:45:12 | 2.5 | 2.25
980 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting Gold | Test Script Preparation | 2024-10-03 | 06:00:00 | 00:59:34 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 10:31:37 |  | 6 | 0.99
981 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | Task Scheduling | Task Scheduling | 2024-09-26 | 01:00:00 | 01:20:19 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:02:52 | 2024-09-27 17:02:52 | 1 | 1.34
982 | TT21945 | Vaishnavi Khandwe | - | - | - | Forming- Item P2P process Testing | E2E Testing | 2024-10-03 | 03:00:00 | 05:10:16 | 2024-10-03 |  | COMPLETED | IN_TIME | 2024-10-03 19:40:25 | 2024-10-03 19:40:25 | 3 | 5.17
983 | TT22830 | Vaishnavi Khandwe | - | - | - | karagir Jama KT by Sanmati Sir | KT Session | 2024-10-01 | 01:30:00 | 00:00:00 | 2024-10-01 |  | COMPLETED | IN_TIME | 2024-10-01 15:48:16 | 2024-10-01 15:48:16 | 1.5 | 0
984 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | Task Scheduling | Task Scheduling | 2024-09-19 | 01:00:00 | 01:15:58 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:48:22 | 2024-09-20 16:48:22 | 1 | 1.27
985 | TT24777 | Vaishnavi Khandwe | - | - | - | Qc setup Master Support from gokul | Query clarification | 2024-09-27 | 00:30:00 | 00:56:05 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:04:11 | 2024-09-27 17:04:11 | 0.5 | 0.93
986 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D Sync call 16-20 | Daily Sync Call | 2024-09-16 | 02:00:00 | 01:29:58 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 23:17:07 | 2024-09-20 23:17:07 | 2 | 1.5
987 | TT25654 | Vaishnavi Khandwe | - | - | - | Support From Gokul (Pending vendor Invoices) | Technical guidance/Process Input | 2024-09-25 | 00:30:00 | 00:21:55 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:18:12 | 2024-09-25 19:18:12 | 0.5 | 0.37
988 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | Task scheduling 13 feb | Task Scheduling | 2024-09-13 | 00:30:00 | 01:45:50 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 20:09:15 | 2024-09-13 20:09:15 | 0.5 | 1.76
989 | TT25654 | Vaishnavi Khandwe | - | - | - | Pending vendor Invoices Automation Scripting | Test Script Preparation | 2024-09-25 | 04:00:00 | 03:17:54 | 2024-09-25 |  | COMPLETED | IN_TIME | 2024-09-25 19:58:28 | 2024-09-25 19:58:28 | 4 | 3.3
990 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D Sync call 9-13 | Daily Sync Call | 2024-09-09 | 00:30:00 | 00:21:06 | 2024-09-13 |  | COMPLETED | IN_TIME | 2024-09-13 18:05:07 | 2024-09-13 18:05:07 | 0.5 | 0.35
991 | TT25655 | Vaishnavi Khandwe | - | - | - | Support from gokul (Post product receipt ) | Technical guidance/Process Input | 2024-09-24 | 00:30:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 11:14:00 | 2024-09-25 11:14:00 | 0.5 | 0
992 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | Task Scheduling | Task Scheduling | 2024-09-05 | 00:00:00 | 00:00:00 | 2024-09-05 |  | COMPLETED | HIGHLY_DELAY | 2024-09-06 16:58:42 | 2024-09-06 16:58:42 | 0 | 0
993 | TT25655 | Vaishnavi Khandwe | - | - | - | Post Product Receipt Scripting | Test Script Preparation | 2024-09-24 | 04:00:00 | 00:00:00 | 2024-09-24 |  | COMPLETED | DELAY | 2024-09-25 10:52:28 | 2024-09-25 10:52:28 | 4 | 0
994 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | D sync call 02-06 | Daily Sync Call | 2024-09-02 | 02:30:00 | 01:15:18 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 18:48:57 | 2024-09-06 18:48:57 | 2.5 | 1.26
995 | TT24777 | Vaishnavi Khandwe | - | - | - | QC Setup master Script positive Flow | Automate test script | 2024-09-27 | 01:45:00 | 01:40:49 | 2024-09-27 |  | COMPLETED | DELAY | 2024-09-30 12:48:28 | 2024-09-30 12:48:28 | 1.75 | 1.68
996 | TT23932 | Vaishnavi Khandwe | Sprint 1 | - | - | SSRS KT Session (5 Reports) | KT Session | 2024-09-03 | 01:00:00 | 00:47:18 | 2024-09-03 |  | COMPLETED | IN_TIME | 2024-09-03 15:55:16 | 2024-09-03 15:55:16 | 1 | 0.79
997 | TT18255 | Vaishnavi Khandwe | - | - | - | Support From Gokul URD | Technical guidance/Process Input | 2024-09-23 | 00:30:00 | 00:54:40 | 2024-09-23 |  | COMPLETED | IN_TIME | 2024-09-23 19:21:47 | 2024-09-23 19:21:47 | 0.5 | 0.91
998 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting 50 Percent coverage | Script Execution/ Modification | 2024-09-23 | 04:00:00 | 03:45:02 | 2024-09-23 |  | COMPLETED | DELAY | 2024-09-25 16:29:54 | 2024-09-25 16:29:54 | 4 | 3.75
999 | TT24771 | Vaishnavi Khandwe | - | - | - | Automation scripting Size Master Test data Prepare | Test Script Preparation | 2024-09-26 | 01:00:00 | 00:22:42 | 2024-09-26 |  | COMPLETED | DELAY | 2024-09-30 12:16:26 | 2024-09-30 12:16:26 | 1 | 0.38
1000 | TT24760 | Vaishnavi Khandwe | - | - | - | Automation Support From Gokul Bank Master | Technical guidance/Process Input | 2024-09-26 | 00:30:00 | 01:32:31 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 18:48:38 | 2024-09-26 18:48:38 | 0.5 | 1.54
1001 | TT24760 | Vaishnavi Khandwe | - | - | - | Bank Master Automation Scripting | Test Script Preparation | 2024-09-26 | 03:00:00 | 03:28:59 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-26 19:27:16 | 2024-09-26 19:27:16 | 3 | 3.48
1002 | TT24206 | Vaishnavi Khandwe | Testing_KT_Oct24_Wk1 | - | - | handling windows GUI using Autoit KT to all testers | Internal KT/cross KT | 2024-10-07 | 01:00:00 | 00:35:20 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:53:14 | 2024-10-07 13:53:14 | 1 | 0.59
1003 | TT21945 | Vaishnavi Khandwe | - | - | - | Support for QC Multiple Lines to Vaishnavi | Query clarification | 2024-09-23 | 02:30:00 | 02:50:58 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 11:53:13 | 2024-09-27 11:53:13 | 2.5 | 2.85
1004 | TT24206 | Vaishnavi Khandwe | Testing_KT_Oct24_Wk1 | - | - | Test case module KT (ticketing system) | Internal KT/cross KT | 2024-09-02 | 01:00:00 | 01:56:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:24:01 | 2024-09-02 19:24:01 | 1 | 1.94
1005 | TT21945 | Vaishnavi Khandwe | - | - | - | Support from Saurabh QC process | Technical guidance/Process Input | 2024-09-23 | 00:00:00 | 00:00:00 | 2024-09-26 |  | COMPLETED | IN_TIME | 2024-09-23 10:42:35 | 2024-09-23 10:42:35 | 0 | 0
1006 | TT21945 | Vaishnavi Khandwe | - | - | - | QC Process Multiple Line Retesting | Bug Retesting | 2024-09-23 | 07:00:00 | 08:04:30 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:03:18 | 2024-09-27 17:03:18 | 7 | 8.08
1007 | TT24771 | Vaishnavi Khandwe | - | - | - | Support from Saurabh(Size master) | Query clarification | 2024-09-19 | 00:30:00 | 00:25:24 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 18:28:15 | 2024-09-19 18:28:15 | 0.5 | 0.42
1008 | TT18255 | Vaishnavi Khandwe | - | - | - | Support for automation URD from Gokul | Technical guidance/Process Input | 2024-09-19 | 01:00:00 | 02:33:12 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:24 | 2024-09-20 19:48:24 | 1 | 2.55
1009 | TT24760 | Vaishnavi Khandwe | - | - | - | Support from saurabh | Query clarification | 2024-09-20 | 00:15:00 | 00:20:14 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 18:11:21 | 2024-09-20 18:11:21 | 0.25 | 0.34
1010 | TT24760 | Vaishnavi Khandwe | - | - | - | Bank Master Test case writing | Test Case Writing | 2024-09-20 | 01:00:00 | 01:02:27 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:08 | 2024-09-20 19:48:08 | 1 | 1.04
1011 | TT24760 | Vaishnavi Khandwe | - | - | - | Bank Master Estimation | Estimate calculation | 2024-09-19 | 00:15:00 | 00:13:24 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:59:09 | 2024-09-19 17:59:09 | 0.25 | 0.22
1012 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | D testing Team sync call (Internal) | Daily Sync Call | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | TO_DO | TO_DO | 2024-10-07 15:03:08 |  | 0.25 | 0
1013 | TT24771 | Vaishnavi Khandwe | - | - | - | Test case writing of size master | Test case writing- | 2024-09-19 | 01:00:00 | 01:16:58 | 2024-09-19 |  | COMPLETED | IN_TIME | 2024-09-19 17:59:21 | 2024-09-19 17:59:21 | 1 | 1.28
1014 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 00:00:00 | 2024-10-07 |  | TO_DO | TO_DO | 2024-10-07 10:58:58 |  | 1 | 0
1015 | TT18255 | Vaishnavi Khandwe | - | - | - | URD Scripting through test cases | Test Script Preparation | 2024-09-18 | 11:15:00 | 08:24:35 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 19:48:19 | 2024-09-20 19:48:19 | 11.25 | 8.41
1016 | TT23782 | Vaishnavi Khandwe | - | - | - | E-way bill KT | KT Session | 2024-08-29 | 00:10:00 | 00:13:17 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:38:29 | 2024-09-02 19:38:29 | 0.17 | 0.22
1017 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Cspl training | HR meeting | 2024-10-04 | 01:00:00 | 01:34:02 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 18:17:23 | 2024-10-04 18:17:23 | 1 | 1.57
1018 | TT14931 | Vaishnavi Khandwe | - | - | - | Customer Order Demo | Demo | 2024-09-10 | 01:00:00 | 00:00:00 | 2024-09-10 |  | COMPLETED | IN_TIME | 2024-09-10 19:33:35 | 2024-09-10 19:33:35 | 1 | 0
1019 | TT23782 | Vaishnavi Khandwe | - | - | - | TDS and TCS KT by sanmati sir | KT Session | 2024-09-02 | 00:46:00 | 00:53:02 | 2024-09-02 |  | COMPLETED | IN_TIME | 2024-09-02 19:32:07 | 2024-09-02 19:32:07 | 0.77 | 0.88
1020 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Walk in interview support | Interview | 2024-09-30 | 12:00:00 | 04:28:38 | 2024-10-01 |  | COMPLETED | SLIGHTLY_DELAY | 2024-10-03 17:12:57 | 2024-10-03 17:12:57 | 12 | 4.48
1021 | TT18255 | Vaishnavi Khandwe | - | - | - | Support Point To vaishnavi | Technical guidance/Process Input | 2024-09-09 | 00:00:00 | 00:00:00 | 2024-09-09 |  | COMPLETED | IN_TIME | 2024-09-09 19:16:14 | 2024-09-09 19:16:14 | 0 | 0
1022 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Daily sync call with D testing (internal) | Testing Team Meeting | 2024-09-30 | 01:00:00 | 00:20:29 | 2024-10-04 |  | COMPLETED | IN_TIME | 2024-10-04 19:50:39 | 2024-10-04 19:50:39 | 1 | 0.34
1023 | TT22830 | Vaishnavi Khandwe | - | - | - | Support Point Karagir Nave/Jama | Support. | 2024-09-02 | 02:30:00 | 00:18:45 | 2024-09-06 |  | COMPLETED | IN_TIME | 2024-09-06 19:57:15 | 2024-09-06 19:57:15 | 2.5 | 0.31
1024 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | KRA/KPI discussion with Gaurav sir | Testing Team Meeting | 2024-09-20 | 00:30:00 | 00:42:38 | 2024-09-20 |  | COMPLETED | IN_TIME | 2024-09-20 16:09:31 | 2024-09-20 16:09:31 | 0.5 | 0.71
1025 | TT22830 | Vaishnavi Khandwe | - | - | - | Silver TCW Karagir Nave Jama (Batch Registration ) | Test Case Writing | 2024-09-02 | 02:45:00 | 02:46:42 | 2024-09-04 |  | COMPLETED | DELAY | 2024-09-06 17:36:27 | 2024-09-06 17:36:27 | 2.75 | 2.78
1026 | TT18255 | Vaishnavi Khandwe | - | - | - | Automation Support URD | Technical guidance/Process Input | 2024-09-02 | 01:30:00 | 00:54:21 | 2024-09-05 |  | COMPLETED | IN_TIME | 2024-09-05 19:41:38 | 2024-09-05 19:41:38 | 1.5 | 0.91
1027 | TT24303 | Vaishnavi Khandwe | Testing_GM_Oct_2024_Wk1 | - | - | Daily Sync Call with D Testing (Internal) | Daily Sync Call | 2024-09-23 | 01:15:00 | 01:57:33 | 2024-09-27 |  | COMPLETED | IN_TIME | 2024-09-27 17:25:09 | 2024-09-27 17:25:09 | 1.25 | 1.96