## Sheet1
task_delivery_scheduled | (Multiple Items) |  |  | task_delivery_scheduled | (Multiple Items)
Count of task_name | task_status |  |  | Count of task_name | task_actual_status
task_owner | COMPLETED | IN_PROGRESS | Grand Total | task_owner | HIGHLY_DELAY | IN_TIME | SLIGHTLY_DELAY | DELAY | Grand Total
Amreen Shaikh | 79 | 1 | 80 | Amreen Shaikh |  | 66 | 4 | 10 | 80
Amruta Kore | 84 |  | 84 | Amruta Kore |  | 77 |  | 7 | 84
Gokul Bhoi | 123 |  | 123 | Gokul Bhoi | 2 | 100 |  | 21 | 123
Kiran Dhanepkar | 53 |  | 53 | Kiran Dhanepkar | 1 | 45 |  | 7 | 53
Maruti Hakke | 61 |  | 61 | Maruti Hakke |  | 44 | 4 | 13 | 61
Prathmesh Shinde | 52 |  | 52 | Prathmesh Shinde |  | 41 |  | 11 | 52
Preeti Bokade | 58 | 1 | 59 | Preeti Bokade |  | 52 | 2 | 5 | 59
Saurabh Shelke | 55 |  | 55 | Saurabh Shelke |  | 45 |  | 10 | 55
Sayali Vyawahare | 78 |  | 78 | Sayali Vyawahare |  | 64 | 5 | 9 | 78
Uttareshwar Bhusari | 56 |  | 56 | Uttareshwar Bhusari |  | 46 | 2 | 8 | 56
Vaishnavi Khandwe | 45 |  | 45 | Vaishnavi Khandwe | 1 | 37 |  | 7 | 45
Grand Total | 744 | 2 | 746 | Grand Total | 4 | 617 | 17 | 108 | 746
|  |  |  | task_delivery_scheduled | (Multiple Items)
task_delivery_scheduled | (Multiple Items) |  |  | sprint_name | -
task_owner | type_name | Sum of Scheduled hr | Sum of Actual hr | task_owner | type_name | ticket_id | Distinct Count of ticket_id
Amreen Shaikh |  | 123.48 | 127.09 | Amruta Kore |  |  | 8
| Query clarification | 20.25 | 16.18 |  | Query clarification |  | 3
| Daily Summary report | 1.08 | 0.71 |  |  | TT22163 | 1
| Internal KT/cross KT | 1 | 1.94 |  |  | TT21899 | 1
| Technical guidance/Process Input | 18 | 13.76 |  |  | TT21945 | 1
| Planning | 1 | 0.85 |  | Task Scheduling |  | 1
| Validation writing | 0.5 | 0.71 |  |  | TT24678 | 1
| Daily Sync Call | 8.06 | 4.49 |  | KT Session |  | 1
| Meeting with PH | 1.42 | 1.08 |  |  | TT22830 | 1
| Testing. | 4 | 2.17 |  | Test case updation\modification |  | 1
| Test Case Review | 0.75 | 1.02 |  |  | TT24674 | 1
| Sync call with Team | 3.25 | 5.92 |  | E2E Testing |  | 1
| Testing Team Meeting | 0.5 | 0.74 |  |  | TT21945 | 1
| Interview | 1.5 | 1.37 |  | Automate test script |  | 3
| General meeting | 1 | 0.95 |  |  | TT24774 | 1
| Task Scheduling | 2 | 3.41 |  |  | TT22163 | 1
| Requirement gathering | 1 | 1.13 |  |  | TT21899 | 1
| Script review | 4.25 | 3.58 |  | Demo |  | 1
| RAD Testing | 4 | 0 |  |  | TT23053 | 1
| Reporting Review | 0.25 | 0.89 | Digvijay Tulse |  |  | 1
| HR meeting | 0.5 | 0.56 |  | Explore the existing system. |  | 1
| Review. | 0 | 0 |  |  | TT26085 | 1
| Sync call with BA | 0.83 | 17.32 | Gokul Bhoi |  |  | 12
| E2E Testing. | 32.5 | 30.45 |  | Query clarification |  | 5
| Brainstorming with DEV Team \BA | 0.5 | 1.44 |  |  | TT22163 | 1
| Conflict resolution meeting | 0.17 | 0.25 |  |  | TT21945 | 1
| KT Session | 2.5 | 1.49 |  |  | TT18255 | 1
| Document Reading | 1.67 | 2.76 |  |  | TT22810 | 1
| Support. | 0 | 0 |  |  | TT17156 | 1
| Mentoring | 1 | 0 |  | Technical guidance/Process Input |  | 1
| Validation updation | 0.33 | 0.34 |  |  | TT21901 | 1
| Test case updation\modification | 1 | 2.04 |  | Task Scheduling |  | 1
| Test case writing- | 3.5 | 2.55 |  |  | TT24678 | 1
| Estimate the requirement | 0.5 | 0.75 |  | Script review |  | 3
| Bug Retesting | 3.5 | 4.57 |  |  | TT24774 | 1
| Documentation Reading | 0 | 0 |  |  | TT24771 | 1
| Explore the existing system. | 0.67 | 0.84 |  |  | TT21901 | 1
| Brainstorming | 0.5 | 0.83 |  | KT Session |  | 1
Amruta Kore |  | 111.11 | 111.74 |  |  | TT22830 | 1
| Internal KT/cross KT | 1 | 1.94 |  | Support. |  | 2
| Technical guidance/Process Input | 8.5 | 7.34 |  |  | TT21945 | 1
| Daily Sync Call | 13 | 14.45 |  |  | TT18255 | 1
| Meeting with PH | 1.92 | 1.36 |  | Demo |  | 1
| Testing Team Meeting | 0.5 | 0.74 |  |  | TT23053 | 1
| Task Scheduling | 3 | 3.79 |  | Review updated Test cases |  | 1
| Requirement gathering | 2 | 1.9 |  |  | TT24674 | 1
| HR meeting | 0.5 | 0.56 |  | Test Script Preparation |  | 1
| KT Session | 4.19 | 3.95 |  |  | TT18255 | 1
| Document Reading | 1.5 | 1.45 | Kiran Dhanepkar |  |  | 3
| Support. | 0 | 0 |  | Query clarification |  | 3
| Test case updation\modification | 1 | 1.24 |  |  | TT22830 | 1
| Test case writing- | 16.5 | 14.74 |  |  | TT22810 | 1
| Estimate the requirement | 2 | 1.97 |  |  | TT17156 | 1
| Documentation Reading | 0.25 | 0.32 |  | Test Case Writing |  | 1
| E2E Testing | 1 | 1.08 |  |  | TT22830 | 1
| Automate test script | 39.5 | 38.54 |  | KT Session |  | 1
| Brainstorming - Internal ( Within Team member) | 1 | 1.24 |  |  | TT22830 | 1
| Script Execution/ Modification | 4 | 3.5 |  | Support. |  | 1
| Estimate calculation | 2.25 | 1.95 |  |  | TT22830 | 1
| Demo | 1 | 0.67 |  | Automate test script |  | 2
| Testing | 2.5 | 4.46 |  |  | TT22810 | 1
| Retesting | 4 | 4.55 |  |  | TT17156 | 1
Gokul Bhoi |  | 139.09 | 143.14 |  | Brainstorming with DEV Team/BA |  | 1
| Query clarification | 10.25 | 9.84 |  |  | TT22830 | 1
| Internal KT/cross KT | 1 | 1.94 | Maruti Hakke |  |  | 1
| Technical guidance/Process Input | 19.25 | 20.17 |  | Test case writing- |  | 1
| Daily Sync Call | 16 | 17.44 |  |  | TT24598 | 1
| Meeting with PH | 2.42 | 2.77 | Prathmesh Shinde |  |  | 6
| Test Case Review | 1.75 | 2.03 |  | General meeting |  | 1
| Sync call with Team | 3.25 | 4.67 |  |  | TT15138 | 1
| Testing Team Meeting | 0.5 | 0.71 |  | Requirement gathering |  | 1
| General meeting | 0.5 | 0.75 |  |  | TT23532 | 1
| Task Scheduling | 3.5 | 3.01 |  | Mentoring |  | 1
| Script review | 3 | 3.2 |  |  | TT20806 | 1
| Reporting Review | 3.75 | 2.57 |  | Data Preparation |  | 1
| HR meeting | 0.5 | 0.56 |  |  | TT20806 | 1
| Review. | 0.5 | 0.4 |  | Code Review |  | 1
| Test Case Writing | 1.42 | 1.35 |  |  | TT26106 | 1
| KT Session | 4.91 | 4.62 |  | Bug |  | 3
| Support. | 0 | 0 |  |  | TT20806 | 1
| Mentoring | 2.5 | 0 |  |  | TT23513 | 1
| Automate test script | 29 | 29.72 |  |  | TT20553 | 1
| Brainstorming - Internal ( Within Team member) | 1 | 1.24 |  | Development Planning and logic discussion |  | 1
| Estimate calculation | 0.25 | 0.21 |  |  | TT20806 | 1
| Demo | 1 | 0.67 |  | Bug solving |  | 1
| Review updated Test cases | 0.25 | 0.25 |  |  | TT20806 | 1
| Review | 9.34 | 6.92 |  | Development |  | 1
| Test script review | 14.75 | 10.47 |  |  | TT20806 | 1
| Api Testing | 1.5 | 1.57 | Preeti Bokade |  |  | 1
| Explore Team capability/Improvement plan | 2 | 0.94 |  | General meeting |  | 1
| Weekly sync call | 1 | 0.99 |  |  | TT23155 | 1
| Modify test script | 4 | 14.13 | Saurabh Shelke |  |  | 5
Kiran Dhanepkar |  | 117.58 | 103.87 |  | Query clarification |  | 3
| Query clarification | 2.75 | 2.84 |  |  | TT22830 | 1
| Internal KT/cross KT | 1 | 1.94 |  |  | TT21899 | 1
| Technical guidance/Process Input | 5.75 | 7.96 |  |  | TT17156 | 1
| Daily Sync Call | 12 | 15.59 |  | Test Case Review |  | 2
| Meeting with PH | 1.92 | 1.36 |  |  | TT22830 | 1
| Testing Team Meeting | 0.5 | 0.71 |  |  | TT21945 | 1
| Task Scheduling | 4 | 3.56 |  | Review. |  | 1
| HR meeting | 0.5 | 0.56 |  |  | TT22830 | 1
| E2E Testing. | 21 | 21.3 |  | Test Case Writing |  | 1
| Test Case Writing | 2.5 | 2.54 |  |  | TT22830 | 1
| KT Session | 4.16 | 4.07 |  | KT Session |  | 1
| Test case updation\modification | 1 | 1.17 |  |  | TT22830 | 1
| E2E Testing | 1.5 | 1.08 |  | Review Test cases |  | 1
| Automate test script | 3.75 | 3.68 |  |  | TT22830 | 1
| Estimate calculation | 2.25 | 2.46 |  | Support. |  | 2
| Demo | 1 | 0.67 |  |  | TT22830 | 1
| Testing | 0.5 | 0.34 |  |  | TT21945 | 1
| Test Script Preparation | 51.25 | 31.82 |  | Demo |  | 1
| Brainstorming with DEV Team/BA | 0.25 | 0.22 |  |  | TT23053 | 1
Maruti Hakke |  | 127.96 | 141.11 |  | Brainstorming with DEV Team/BA |  | 1
| Query clarification | 5 | 9.56 |  |  | TT22830 | 1
| Internal KT/cross KT | 3 | 2.52 | Sayali Vyawahare |  |  | 3
| Daily Sync Call | 8.5 | 8.18 |  | Query clarification |  | 1
| Meeting with PH | 1.92 | 1.35 |  |  | TT24670 | 1
| Testing. | 0 | 0 |  | Test Case Review |  | 1
| Test Case Review | 2 | 2.23 |  |  | TT24598 | 1
| Sync call with Team | 5.25 | 3.87 |  | Reporting Review |  | 1
| Testing Team Meeting | 0.5 | 0.7 |  |  | TT24670 | 1
| Task Scheduling | 4 | 3.37 |  | E2E Testing |  | 1
| Script review | 0 | 0 |  |  | TT24670 | 1
| HR meeting | 0.5 | 0.56 |  | Script Execution/ Modification |  | 1
| KT Session | 5.97 | 5.14 |  |  | TT22442 | 1
| Review Test cases | 0 | 0 |  | Code Review |  | 1
| Document Reading | 2 | 0.45 |  |  | TT24670 | 1
| Test case updation\modification | 0 | 0 | Vaishnavi Khandwe |  |  | 6
| KT from BA | 0.57 | 0.29 |  | Query clarification |  | 2
| Estimate the requirement | 1 | 1.01 |  |  | TT21945 | 1
| Brainstorming | 0.5 | 0.74 |  |  | TT18255 | 1
| Brainstorming - Internal ( Within Team member) | 3.5 | 2.41 |  | Technical guidance/Process Input |  | 1
| Script Execution/ Modification | 47.25 | 43.04 |  |  | TT21901 | 1
| Demo | 0.5 | 0.37 |  | KT Session |  | 1
| Review updated Test cases | 0.5 | 0.43 |  |  | TT22830 | 1
| Test Script Preparation | 34.25 | 53.95 |  | Support. |  | 2
| D Practice | 1.25 | 0.94 |  |  | TT21945 | 1
Prathmesh Shinde |  | 73 | 56.63 |  |  | TT18255 | 1
| Daily Sync Call | 2.5 | 3.34 |  | Test case updation\modification |  | 2
| Meeting with PH | 2 | 0.74 |  |  | TT24771 | 1
| Interview | 1 | 0.41 |  |  | TT24760 | 1
| General meeting | 1.17 | 0.94 |  | E2E Testing |  | 1
| HR meeting | 0.5 | 0.56 |  |  | TT21945 | 1
| Sync call with BA | 0.83 | 0 |  | Automate test script |  | 1
| KT Session | 2.03 | 2.32 |  |  | TT24771 | 1
| Mentoring | 22 | 26.07 |  | Test Script Preparation |  | 2
| Data Preparation | 0.67 | 1.34 |  |  | TT18255 | 1
| Brainstorming | 1.42 | 1.64 |  |  | TT21901 | 1
| Weekly sync call | 1 | 0 | Grand Total |  |  | 25
| Code Review | 6.5 | 8.71
| Application Support | 4.05 | 0
| Development Planning and logic discussion | 15.5 | 6.34
| Bug solving | 7 | 1.8
| Development | 2.5 | 2.09
| RND | 1 | 0
| Weekly sync call report | 1 | 0
| Live Deployment | 0.33 | 0.33
Preeti Bokade |  | 89.4 | 109.59
| Query clarification | 34 | 58.02
| Internal KT/cross KT | 10.75 | 6.43
| Daily Sync Call | 3 | 4.69
| Meeting with PH | 4.42 | 3.03
| Sync call with Team | 3.25 | 6.65
| Testing Team Meeting | 0.5 | 0.71
| Interview | 7.25 | 2.75
| General meeting | 0.5 | 0.49
| HR meeting | 0.5 | 0.63
| Brainstorming with DEV Team \BA | 0.25 | 0.23
| Conflict resolution meeting | 0.17 | 0.22
| KT Session | 5.02 | 5.83
| Review Test cases | 1 | 5.68
| Document Reading | 0.67 | 1.21
| Mentoring | 2.5 | 0
| Estimate the requirement | 4 | 0.24
| Explore the existing system. | 0.67 | 1.23
| Brainstorming | 0.5 | 0.83
| Explore Team capability/Improvement plan | 3 | 3.17
| Explore New things\other | 2 | 1.34
| Weekly sync call | 2 | 1.41
| Estimation Review | 1 | 1.25
| Explore the existing system | 0.45 | 0
| Application Support | 1 | 0.55
| Weekly sync call report | 1 | 3
Saurabh Shelke |  | 136.04 | 137.78
| Query clarification | 3.75 | 3.46
| Internal KT/cross KT | 1 | 1.94
| Technical guidance/Process Input | 4.5 | 3.92
| Daily Sync Call | 14 | 14.05
| Meeting with PH | 0.92 | 1.08
| Test Case Review | 3.25 | 2.43
| Testing Team Meeting | 0.5 | 0.71
| Task Scheduling | 4 | 4.99
| Requirement gathering | 2 | 1.85
| Reporting Review | 0.5 | 0.28
| HR meeting | 0.5 | 0.56
| Brainstorming with DEV Team \BA | 0.75 | 0.83
| KT Session | 2.94 | 2.74
| Review Test cases | 0.5 | 0.38
| Support. | 2.5 | 1.49
| Automate test script | 52.65 | 57.59
| Demo | 1 | 0.67
| Retesting | 20.25 | 18.78
| Review | 0.5 | 0.71
| Test Script Preparation | 19.28 | 18.74
| Test script review | 0.5 | 0.35
| Brainstorming with DEV Team/BA | 0.25 | 0.23
Sayali Vyawahare |  | 133.37 | 120.48
| Query clarification | 12 | 9.9
| Internal KT/cross KT | 3 | 2.52
| Technical guidance/Process Input | 9 | 5.48
| Daily Sync Call | 11 | 10.81
| Meeting with PH | 4.42 | 3.97
| Sync call with Team | 8 | 8.71
| Testing Team Meeting | 0.5 | 0.7
| Task Scheduling | 4 | 2.89
| Script review | 3 | 1.31
| Reporting Review | 2 | 2.27
| HR meeting | 0.5 | 0.56
| KT Session | 5.88 | 5.2
| Review Test cases | 3 | 2.87
| Support. | 3.75 | 3.51
| Mentoring | 0.5 | 0.28
| KT from BA | 0.57 | 0.29
| Estimate the requirement | 1.25 | 0.68
| Brainstorming | 0.5 | 0.74
| Brainstorming - Internal ( Within Team member) | 3.5 | 2.41
| Script Execution/ Modification | 2.75 | 2.52
| Demo | 0.5 | 0.37
| Review updated Test cases | 0.5 | 0.58
| Review | 2.25 | 1.75
| Test Script Preparation | 47.75 | 47.75
| Explore Team capability/Improvement plan | 2 | 1.04
| Weekly sync call | 1 | 1
| Estimation Review | 0.25 | 0.37
Uttareshwar Bhusari |  | 159.34 | 124.32
| Internal KT/cross KT | 3 | 2.07
| Planning | 0.5 | 0.61
| Daily Sync Call | 9 | 6.93
| Meeting with PH | 0.92 | 1.08
| Sync call with Team | 5.25 | 4.54
| Testing Team Meeting | 0.5 | 0.7
| General meeting | 0.25 | 0.11
| Task Scheduling | 4 | 2.54
| HR meeting | 0.5 | 0.56
| KT Session | 4.42 | 3.48
| Document Reading | 1.75 | 0.72
| Test case updation\modification | 2 | 0.98
| Test case writing- | 7 | 5.01
| Estimate the requirement | 1 | 1.08
| Documentation Reading | 0.5 | 0.37
| Brainstorming | 0.5 | 0.74
| Automate test script | 105 | 86.36
| Brainstorming - Internal ( Within Team member) | 1 | 1
| Demo | 0.5 | 0.37
| Testing | 3 | 0
| Test Script Preparation | 1 | 0
| Modify test script | 3 | 2.85
| Test script execution | 1.5 | 1.37
| Functional Testing | 3.25 | 0.85
Vaishnavi Khandwe |  | 88.36 | 81.08
| Query clarification | 3.75 | 4.54
| Internal KT/cross KT | 1 | 1.94
| Technical guidance/Process Input | 4.5 | 6.28
| Daily Sync Call | 10.75 | 9.24
| Meeting with PH | 0.92 | 1.08
| Testing Team Meeting | 0.5 | 0.71
| Task Scheduling | 2.5 | 4.37
| Test Case Writing | 3.75 | 3.82
| KT Session | 1.94 | 1.89
| Support. | 2.5 | 0.31
| Test case writing- | 1 | 1.28
| Bug Retesting | 7 | 8.08
| Automate test script | 1.75 | 1.68
| Script Execution/ Modification | 4 | 3.75
| Estimate calculation | 0.25 | 0.22
| Demo | 1 | 0
| Test Script Preparation | 41.25 | 31.89
Grand Total |  | 1298.73 | 1256.83