## Test Case Template Example
| Project Name: | Metal Booking Mobile App | Test Designed by: | Priyanka Dupargude
| Module Name: | Log in get metal details. | Test Designed date: | 23Feb 2022
| Sub ModuleName: |  | Test Executed by: | Priyanka Dupargude
| Release Version: |  | Test Execution date: | 2022-03-29
Ticket:
Pre-condition | Application related services must be active
Dependencies:
Test Priority
Description
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Testing Type | Excepted Result | Actual Result | Status | Developer remark | BA Remark | Tester remark | Remark | Tester remark
TC_1 | Login | To check, Login successfully done or not | 1.go to the metal booking apk. |  | Smoke Testing | It should be login sucessfully | Error message is showing that something went wrong' | Fail | Backend work |  | Pass
2.Enter :: Username
3.Enter ::Password
4.Click on :: Login
5.Observe
TC_2 | loginPage->Username | To check whether username accepts alphanumeric characters or not. | 1.Open the app. | click here | functional testing | username field should be accept alphanumeric characters. | As excepted | Pass
2.Enter :: Username
TC_3 | loginPage->Username | To check whether username field accepts . and @ or not. | 1.Open the app. | click here | functional testing | username field should be accept . and @ symbol. | As excepted | Pass
2.Enter :: Username
TC_4 | loginPage->Username | To check whether username field should not be accept blank data. | 1.Open the app. | click here | functional testing | username field should not be empty. | As excepted | Pass
2.keep username field blank.
TC_4 | loginPage->Username | after entering username To check whether it is displaying proper or not. | 1.Open the app. | click here | functional testing | username field shouldbe display proper. | username is not displaying proper. | Fail | Fixed |  | Fail |  | Pass
2.Enter Username
Done
TC_5 | loginPage->Password | To check whether password field accepts more than 8 characters or not. | 1.Open the app. | click here | functional testing | password field should not be accept less than 8 chracters. | it is not giving error when password is too small. | Fail | Fixed |  | Fail | Please check the credential of back end in back end 6 digits password also accepting
2.Enter :: Username
|  |  | 3.Enter ::Password | [9 empty] | Provide BA's Remark for that
4.Observe.
TC_6 | loginPage->Password | To check that password field should not empty. | 1.Open the app. | click here | functional testing | password field should not be empty. | Suggestion:there should be one eye button for show password. | Pass
2.Enter :: Username
3.Enter ::Password
4.Observe.
TC_7 | Forgot password | To check forgot password option is added or not. | 1.Open the app. |  | functional testing | forgot password option should be available. | No prevision for that | Pending |  |  | Pass
2.Enter :: Username
3.Enter ::Password
4.Observe.
TC_8 | Forgot password | TO verify that, on click of forgot password page should redirected to users mail. | 1.Open the app. |  | Integration testing. | page shoud be redirect to the users email id. | No prevision for that | Pending |  |  | Pass
2.Enter :: Username
3.Enter ::Password
4.Observe.
TC_8 | Forgot password | To check whether new generated password is system accepts or not. | 1.Open the app. |  | Integration testing. | whether new generated password should be system accepts | No prevision for that | Pending |  |  | Pass
2.Enter :: Username
3.Enter ::Password
4.Observe.
TC_9 | Forgot password | To check that after clicking on forgot password whether new password is sent on users register email id or not. | 1.Open the app. |  | Integration testing. | after clicking on forgot password, password should be sent on users register email id. | No prevision for that | Pending |  |  | Pass
2.Enter :: Username
3.Enter ::Password
4.Observe.
TC_10 | loginPage->Proceed | To check proceed button is working or not. | 1.Open the app. | click here | Integration testing. | page should redirect to the next page. | As excepted | Pass
2.Enter :: Username
3.Enter ::Password
4.Click on proceed.
TC_11 | loginPage->Proceed | without entering username proceed button displays error notification or not. | 1.Open the app. | click here | functional testing | It should display error notification. | As excepted | Pass
2.Enter :: Username
3.Enter ::Password
4.Click on proceed.
TC_12 | loginPage->Proceed | without entering password proceed button displays error notification or not. | 1.Open the app. | click here | functional testing | It should display error notification. | As excepted | Pass
2.Enter :: Username
3.Enter ::Password
4.Click on proceed.
TC_12 | Login Page | To check whether exit app confirmation window is showing or not. | 1.open the app. |  | functional testing | if we click on the back button it should be display exit app confirmation window. | killing the app directly. | Fail | Done |  | Pass
2.click on login page.
3.click on back.
4.Observe.
TC_13 | Todays Price | To check whether gold and silver metal name is displayed or not. |  | click here |  | both metal name should be display. | As excepted | Pass
TC_14 | Todays Price->Buy | To check gold and silver prices are display correct not. |  |  |  | both gold and silver rate should be display correct. | As excepted | Pass
TC_15 | Todays Price->Buy | To check whether buy and sell button is displayed or not. | 1.click on book tab. | click here |  | buy and sell button should be display properly. | As excepted | Pass
2.Observe.
TC_16 | Todays Price->Buy | to check whether buy button is working or not. | 1.click on book tab. | click here |  | It should redirected to the book metal page. | As excepted | Pass
2.Click on buy.
3.Observe.
TC_17 | Todays Price->Sell | To check whether sell button is working or not. | 1.click on book tab. | click here |  | whether sell button should be working | sell button is not working. | Fail | No |  | Fail | Ask BA | Fail.
2.Click on buy.
3.Observe.
TC_18 | Todays Price | when metal prices are increases to check whether arrow is upward or not. | 1.click on book tab. |  |  | arrow should be display in upward direction. | It Is Static While price is Increase or Decrease and Color Also not change | Fail | Done |  | Pass
2.Click on buy.
3.Observe.
TC_19 | Todays Price | when metal prices are increases to check whether arrow is displayed in green color or not. |  |  |  | arrow should be displayed in green color. | It Is Static While price is Increase or Decrease and Color Also not change | Fail | Done |  | Pass
TC_20 | Todays Price | when metal prices are decreases to check whether arrow is displayed in downwards or not. |  |  |  | arrow should be display downwards. | It Is Static While price is Increase or Decrease and Color Also not change | Fail | Done |  | Pass
TC_21 | Todays Price | when metal prices are decreases to check whether arrow is displayed in green color or not. |  |  |  | arrow should be display in red color. | It Is Static While price is Increase or Decrease and Color Also not change | Fail | Done |  | ??
TC_22 | Book metal | To check whether quantity, remark and buy now fields are displayed or not. | 1.click on book tab. | click here | functional testing | all fields should be display. | As excepted | Pass
2.click on buy .
3.Observe.
TC_23 | Book metal->Quantity | To check whether quantity field is mandatory or not. | 1.click on book tab. | click here | Smoke Testing | quantity field should be mandatory field. | without entering quantity displaying 'order placed successfully' message. | Fail | Done |  | Pass
2.click on buy .
3.Observe.
TC_24 | Book metal->Quantity | To check whether quantity field displays available limit or not. | 1.click on book tab. |  | functional testing | quantity field should be display available limit of particular user. | the Label is Static, it should be Dynimic | Fail | Done |  |  | Pass
2.click on buy .
3.Observe.
TC_25 | Book metal->Quantity | when we enter gram quantity more than available limit to check whether it is display error notification or not. | 1.click on book tab. |  | functional testing | it should be display error notification. | As excepted | Pending |  |  | Pass
2.click on buy .
3.Observe.
TC_25 | Book metal->Quantity | When order get successful to check view all orders option is visible or not. | 1.click on book tab. |  | functional testing | it should be display 'View all Orders.' | It is displaying 'View all Triggers' | Fail |  |  | Fail |  | Fail
2.click on buy .
3.Observe.
Need to check again
TC_26 | Book metal->Trigger Order->trigger On | on click of trigger on to check whether quantity field is visible or not. | 1.click on book tab. | click here | functional testing | on click of trigger on button quantity field should be display. | As excepted | Pass
2.click on buy .
3.Observe.
TC_27 | Book metal->Trigger Order->trigger Off | on click of trigger off to check whether quantity field is hidden or not. | 1.click on book tab. |  | functional testing | on click of trigger off button quantity field should be invisible. | As excepted | Pass
2.click on buy .
3.Observe.
TC_28 | Book metal->Trigger Order- | To verify that trigger order field should not accepts alphabet values. | 1.click on book tab. | click here |  | trigger order field should be accept only numeric values. | As excepted | Pass
2.click on buy .
3.click on trigger order field
4.enter quantity.
TC_29 | Book metal-> | Without entering remark To check whether order is getting placed or not. | 1.click on book tab. |  |  | without entering any remark order should be placed. |  | Pending | Done |  | Pass
2.click on buy .
3.Observe.
TC_30 | Book metal->Remark | To check whether remark field is available or not. | 1.click on book tab. | click here | click here | reamark field should be available. | As excepted | Pass
2.click on buy .
3.Observe.
TC_31 | Book metal->Remark | To check whether remark field should not be mandatory field. | 1.Open the app. | click here | click here | reamark field should be optional. | As excepted | Pass
2.Enter :: Username
3.Enter ::Password
4.Click on :: Login
5click on book and buy now button
6observe.
TC_32 | Book metal->Buy Now | To check that buy now button is working or not. | 1.click on book tab. |  |  | on click of buy now button order should be placed. and page should be redirected to order page. | As excepted | Pass
2.click on buy now button is working or not.
3.Observe.
TC_33 | Book metal->Buy Now | To check that 'Order placed successfully' message is received or not. | 1.click on book tab. |  |  | after booking the metal 'order placed successfully' message should be display. | order placed successfully message should be display instaed of 'order successful'. | Fail | Done |  | Pass
2.click on buy now button is working or not.
3.Observe.
TC_34 | Book Metal->View All Orders | after placing the order To check that order no, order rate and quantity is displaying or not. | 1click on orders. |  |  | Order no, Order rate and quantity should be display. | recent order is not displaying | Fail | Done |  | Fail..(Order amount is displaying wrong.) |  | Fail..(Order amount is displaying wrong.)
2.Observe.
TC_35 | Book Metal->View All Orders | after placing the order To check that order date and timing are displaying correct or not. | 1.click on book tab. |  |  | order date and timing should be display correct. | No provision for Time , And The alignment of status should be in middle | Fail | Done |  | Fail | Done | Fail
2.click on orders.
3.Observe.
TC_36 | View All Orders | To verify that 'View all orders' option is vailable or not. | 1.click on orders. |  |  | View all orders' option should be available. | As excepted | Pass
2.Observe.
TC_37 | View All Orders | To check whether View all order' button is working or not. | 1.click on orders. |  |  | on click of 'View All Orders' page should redirected to orders page.(all orders should be display.) | As excepted | Pass
2.click on view orders.
|  |  | 3.observe. | [9 empty] | Fail..on click of view all orders it is redirecting to the Trigger Orders page.
TC_38 | View All Orders | To check that recent orders with all fields (order Id,metal name, qty date,status and amount)are displayed or not. | 1.click on orders. |  |  | orders with all fields (order Id,metal name, qty date,status and amount) should be display | order fields are not display correct. | Fail | Done |  | Fail | will update it workig | Fail..status allignment should be display proper.
2.click on view orders.
3.observe.
TC_39 | Recent Orders | To verify that order id should not be display duplicate. | 1.Click on view all orders |  |  | duplicate order id should not be display duplicate. | As excepted | Pass
2.Observe.
TC_40 | View All Orders->Recent Orders->View All | To check whether view all button is working or not. | 1.click on orders. |  |  | on click of 'view all' page shpould redirect to tha orders page. | As excepted | Pass
2.click on view all.
3.Observe.
TC_41 | View all->All Orders | To check whether all order details are properly display or not. | 1.click on orders. |  |  | All order details should be display proper. | As excepted | Pass
2.click on view all.
3.check all orders.
4.Observe.
TC_42 | All Orders | To check that order ID should not be display duplicate. | 1.click on orders. |  |  | Orders should not be display duplicate. | As excepted | Pass
2.check Order Id.
TC_43 | All Orders | To verify that all details of orders display correct or not. | 1.click on orders. |  |  | Order details should be display correct. | As excepted | Pass
2.Observe.
TC_44 | Triggered Orders | To check that all recent triggered orders are displayed or not. | 1.click on Orders | click here |  | all triggered orders should be display correct. | recent trigger order is not displaying trigger orders. | Fail |  |  | Pass
2.click on trigger orders.
TC_45 | Triggered Orders | after placing the order To check that order is removed from triggered orders or not. | 1.click on Orders | click here |  | After getting triggered order placed it should be removed from trigger orders tab. |  | Pending |  |  | Need to discuss.
2.click on trigger orders.
Okay..
TC_46 | View All Triggers | To check that 'View All Triggers' button is working or not. | 1.click on Orders | click here |  | page should redirected to the trigger orders page. | As excepted | pass
2.click on trigger orders.
TC_47 | View All Triggers | To check that all triggered orders are displaying proper or not. | 1.click on trigger orders. | click here |  | all triggers orders should be diplay orders. | triggered order is not displaying in trigger orders. | Fail | Done |  | pass |  | Fail..view all triggers page is redirected to 'All Orders'
2.Observe.
TC_48 | View All Triggers | To verify that trigger order ID should not be display duplicate. | 1.click on trigger orders. | click here |  | trigger order ID should not be display duplicate. | As excepted | Pass |  |  | pass
2.Obersve.
TC_49` | Book metal | To check Quentity LAbel Should be Dynamic | 1.click on book tab. | click here |  | Quentity LAbel Should not be dynamic.it should not be editable. | quantity field is editable. | Fail |  |  | Fail | Done | pass
2.click on buy.
3.click on specific order
TC_48 | View All Triggers | To verify that if click on trigger order toggle button then it should be Current rate Displyed in Text Box | 1.click on book tab. |  |  | if click on trigger order toggle button then it should be Current rate Displayed in Text Box | Not Displayed | Fail |  |  | Fail.. |  | pass
2.click on buy.
|  |  | 3.click on quantity. | [5 empty] | Not Available IN UI
|  |  | 4observe trigger price. | [8 empty] | Done
TC_49 | View All Triggers->Trigger Orders->click on specific order. | To check whether trigger order should be clickable. | 1.click on trigger orders. | click here |  | page should be redireected to the edit trigger order. | As excepted | pass |  |  | pass
2.click on specific orders.
TC_49 | Orders | To check whether back button is present or not.. | 1.click on orders. |  |  | back butyon should be available.. | back button is not available on all page. | Fail |  |  | Fail |  | Fail | Added back buttons
2.Observe.
Done
TC_50 | View All Triggers->Trigger Orders->click on specific order. | To verify that trigger order (quantity field) is editable or not. | 1.click on trigger orders. |  |  | trigered order should be editable. | As excepted | pass |  |  | Fail-(quantity field accepting alphabet values.) | Done | pass
2.click on specific order.
3.Observe.
TC_51 | View All Triggers->Trigger Orders->click on specific order. | To verify that all trigger order details are displaying correct or not. | 1.click on trigger orders. | click here |  | all trigger order details should be correct. | As excepted | pass |  |  |  |  | Fail
2.click on specific order.
3.Observe.
TC_52 | View All Triggers->Trigger Orders->click on specific order.->update | To check update button is working or not. | 1.click on trigger orders. | click here |  | on click of update updated changes in trigger order should be reflected. | Trigger Order data not Updated | Fail | Done |  | pass
2.click on specific order.
3.Observe.
TC_53 | View All Triggers->Trigger Orders->click on specific order.->Close | To check close button is working or not. | 1.click on orders. |  |  | on click of close page should redirected to the trigger orders page. | As excepted | pass
2.click on specific order.
TC_54 | View All Orders->view all->click on specific order.-> | To verify that all feilds should be disable except refernce no,payment date and remark. | 1.click on orders. |  |  | refernce no,payment date and remark field should be editable. | Remark Field Is not editable, Payment Date Filed Should be In date picker | Fail |  |  | Fail | Done | Fail..payment date initially displays null.
2.click on specific order.
TC_55 | View All Triggers->Trigger Orders->click on specific order.->Close | To verify that all feilds should be disable except rate and remark. | 1.click on orders. |  |  | all fields should be disable except rate ,Quantity and remark. | As excepted | Pass |  |  |  |  | Fail..Remark field is not displaying proper.
2.click on specific order.
TC_56 | Profile | To check whether profile tab is opening or not. | 1.click on profile. | click here |  | profile tab should be open.profile should be display. | on click of profile it doesnt display the profile page. | Fail | Done |  | pass
2.Observe.
TC_56 | Profile | To verify that profile pic, email id ,contact no and country correctly displayed or not. | 1.click on profile. | click here |  | profile pic,email id ,contact no and country should be display correct. | once Email ID updated then It is not to be Updated in profile | Fail | Done |  | pass
2.Observe.
TC_57 | Profile | To verify that email id and contact no field should not be editable. | 1.click on profile. | click here |  | email id and contact no field should not be editable. | As excepted | Pass
2.Observe.
TC_58 | Profile->Account Settings | To check whether account setying button is clickable or not. | 1.click on profile. | click here |  | Account Settings' button should be clickable.it should be redirect to the profile settings page. | As excepted | Pass
2.Observe.
TC_59 | Profile->Account Settings | To verify that all details on profile is displayed correct or not. | 1.click on profile. | click here |  | All details on profile should be display correct. | Adhar Card No. is missing | Fail | Not Provided from back end |  | okay.Pass
2.Observe.
TC_60 | Profile->Account Settings | To verify that name and email id field should be disable. | 1.click on profile. | click here |  | name and email id field should not be ediatble. | It Is Editable Field in Profile Setting | Fail | Done |  | pass
2.Observe.
TC_60 | Profile->Account Settings | To verify that , if Profile Pic Updated then it update in backend too | 1.click on profile. | click here |  | if Profile Pic Updated then it should be update in backend too | Not Updated in Backend | Fail | Not Provided from back end |  | okay.
2.update profile
3.click on account settings.
TC_60 | Reports | To verify that reports option is clickable or not. | 1.click on reports. | click here |  | that reports option should be clickable | As excepted | Pass
2.Observe.
TC_61 | Reports->From date and To date | To verify that from and to date field is mandatory or not. | 1.click on reports. | click here |  | from and to date field should be mandatory or not. | By default Todays Date Selected | Pass
2.Observe.
TC_62 | Reports->From date | to check whether on click of from date calender is opening or not. | 1.click on reports. | click here | functional testing | from date calender should be open. | As excepted | Pass
2.Enter from date
3.Observe.
TC_63 | Reports->From date | To verify that from date should not be accept future date. | 1.click on reports. | click here | functional testing | from date should not be accept wrong(future) date. | It Accept Future Date | Fail | Done |  | pass
2.Enter from date
3.Observe.
TC_64 | Reports->From date. | To verify that from date field should not greater than to date. | 1.click on reports. | click here | functional testing | from date field should not greater than to date. | It accept greter than to date | Fail | Done |  | pass
2.Enter from date
3.Observe.
TC_65 | Reports->From date. | to check that on click of clancel it should close the date picker | 1.click on reports. | click here | functional testing | on click of cancel it should close the date picker | As excepted | Pass
2.Enter from date
3.Observe.
TC_66 | Reports->To date | on click of to date To check whether to date calender is opening or not. | 1.click on reports. | click here |  | To date calender should be open. | As excepted | Pass
2.Enter to date
3.Observe.
TC_67 | Reports->To date | To check whether to date field should not be accept future date. | 1.click on reports. |  |  | to date field should not be accept future date. | It accept future Date | Fail | Done |  | pass
2.Enter to date
3.Observe.
TC_68 | Reports->To date | To verify that to date field should be accept equal or equal to from date. | 1.click on reports. |  |  | To date should not be less than from date. | As excepted | Pass
2.Enter to date
3.Observe.
TC_69 | Reports->To date | To check whether clear functionalty is working or not. | 1.click on reports. |  | Suggestions:There should be one submit button to generate the report | to date should be remove on click on of clear. | No clear button | Pass
2.Enter to date
3.Observe.
TC_69 | Reports->Total amount/Pending amount | To check whether total amount is displaying correct or not. | 1.click on reports. | click here |  | The amount should be upto two decimal points. | As excepted | Pass
2.Click on export.
3.Observe.
TC_69 | Reports->Total amount/Pending amount | To check whether total amount is displaying in green color and pending amount is displayed in red color or not. | 1.click on reports. | click here |  | total amount should be display in green color and pending amount should be display in red color. | As excepted | Pass
2.Observe.
TC_70 | Reports->Export | To verify that export button is clickable or not. | 1.click on reports. | click here |  | export button should be clickable. | As excepted | Pass
2.Click on export.
3.Observe.
TC_71 | Reports->Export | To check functionality of export button. | 1.click on reports. | click here | Integration testing. | Account leadger report should be downloaded. | PAyment, Payment Ref no, And Payment Date Field sIs missing | Fail | Not Available IN UI |  | Okay.
2.Click on export.
3.Observe.
TC_72 | Reports->Export | To verify that downloaded report have correct name or not. | 1.click on reports. |  |  | Downloaded report should have display correct name. | As excepted | Fail |  |  | Fail | Done | pass
2.Click on export.
3.Observe.
TC_73 | Reports->Export | To verify that downloaded report is in .CSV format or not. | 1.click on reports. |  |  | report should be download in .CSV format. | As excepted | Fail |  |  | pass
2.Click on export.
3.Observe.
TC_73 | Reports->Export | To verify that export functionality | 1.click on reports. |  |  | if any metal order not displayed in report and we clicked on export it should be display something something error message. | it is displaying downloaded successfully. | Fail |  |  | Fail |  | Fail
2.Click on export.
|  |  | 3.Observe. | [8 empty] | Need to check again
TC_74 | Reports->Export | To verify that in downloaded report has all fields available or not. | 1.click on reports. |  |  | all data should be display in downloaded report. | As excepted | Pass
2.Click on export.
3.Observe.
TC_75 | Reports | To verify that account leager report display all fields correct or not. | 1.click on reports. |  |  | all fields should be display correct in account leadger. | As excepted | Pass
2.Click on export.
3.Observe.
TC_76 | Profile->Account Settings | To verify that all fileds(Whats app no,adress,pincodeGst, PAN,)should be editable except name and email id. | 1.click on profile. | click here |  | all fileds(Whats app no,adress,pincodeGst, PAN,)should be editable except name and email id.() | Give Place holder For that, Missing Adhar card No.pan no and gst field need validation. | Fail | Adhaar card not provided from backend |  | Fail | Ask BA | Fail..name field not displaying proper.
2.click on account settings.
3.Observe.
TC_77 | Profile->Account Settings->Update | To check whether update button is working or not. | 1.click on profile. | click here |  | after updating some profile info updated changes should be reflected in account. | Not Reflected In Account | Fail | Done |  |  |  | Fail..update button is not working
2.click on account settings.
3.Observe.
TC_78 | Profile->Account Settings->Close | To check whether close button is working or not. | 1.click on profile. | Suggestion:There should be option cancel instead of close. |  | it should be redirected to the home page. | As excepted | Pass
2.click on account settings.
3.Observe.
TC_79 | Profile->Account Settings->Update | to check whether user can change profile pic or not. | 1.click on profile. |  |  | profile pic should be editable. | No prevision for that | Fail | Not provided in backend |  | Need to discuss.
2.click on account settings.
3.update profile pic.
Okay..
TC_80 | Profile->Account Settings->Update | To check whether by deault selected profile is displaying or not. | 1.click on profile. |  |  | default (Previously selected) profile should be display. | As excepted | Pass
2.click on account settings.
3.Observe.
TC_81 | Backend Website | TO check, If in App Data Updated then It Update too in The Backend Website. | 1.Open dummy website. |  |  | If in App Data Updated then It Update too in The Backend Website. |  | Pending | Done |  | pass
2.update anything in app.
3.observe in front end.
TC_82 | All Orders | without internet connection To check whether correct error message is displayed or not. | 1.without internet connection book any order. |  |  | Correct error message should be displayed. | correct error message is not displying. | Fail |  |  | Fail | Done | pass
2.Observe.
TC_83 | Trigger Order | To verify that order should not be edit after placed. | 1.click on book tab. |  |  | order should not be edit after placed. | order is editable after placed. | Fail |  |  | Fail | Done | Fail
2.click on buy .
3.click on quantity.
4click on trigger price
5.click on trigger specific order.
TC_84 | Trigger Order | To check Whether scrollview is not proper.trigger order is not displaying proper.(view all and view all triggers buttons are overiding) | 1.click on orders. | click here |  | trigger orders should be display proper. | it is not displaying proper message. | Fail |  |  | Fail | it will look like same working scroll
Need to discuss
TC_85 | Book metal->Buy | To verify that when we order new then rate field and remark field is not cleared.(For all users) | 1.Click on book tab. | click here |  | remark and rate field should be cleared after booking new order. | remark and rate field should be cleared after booking one order. | Fail |  |  | Fail | Done | Fail..remark field is not cleared while confirming new order.
2.Click on buy.
3.confirm the order.
4.click on back.
5Observe.
TC_86 | Trigger orders. | To check whether trigger orders not displaying trigger orders or not. | 1.click on book tab. |  |  | trigger order should be display in trigger orders. | trigger orders are not displaying trigger orders tab. | Fail |  |  | pass
2.click on buy .
3.click on quantity.
4.enter quantity.
5.click on trigger price
6.click on buy now.
TC_87 | Book->buy | when we try to new order then trigger should be off. | 1.Click on book tab. | click here |  | trigger should be closed after placing one order. | previously data and trigger button remains same. | Fail |  |  | Fail | Done | Fail
2.Click on buy.
3.confirm the order.
4.click on back.
5Observe.
TC_88 | All orders | To verify that booked orders is displaying in orders.or not. |  |  |  | booked orders not displaying in orders tab. | (Something went wrong error is showing.) | Fail |  |  | pass
TC_89 | Book->buy | To verify that when we trigger the order there should be one dialogue box or not telling that available buying limit.(For both silver and gold.) | 1.click on book tab. | click here |  | available limit should be display correct. | available limit is not displaying correct. | Fail |  |  | Fail | Done | Fail..available limit should be remove below of the trigger rate.
2.click on buy .
3.click on quantity.
4.click on buy now
5Observe.
TC_90 | Book->buy->trigger order | while booking the metal there should be display bydefault current gold rate or not. | 1.click on book tab. | click here |  | not displaying current gold rate in field | not displaying current gold rate in trigger order field. | Fail |  |  | Fail | Done | pass
2.click on buy .
3.click on quantity.
4.click on buy now
5Observe.
TC_91 | Book->buy->trigger order | while booking the metal there should be display bydefault current silver rate or not. | 1.click on book tab. |  |  | not displaying current silver rate in field. | not displaying current silver rate. | Fail |  |  | Fail | Done | pass
2.click on buy .
3.click on quantity.
4.click on buy now
5Observe.
TC_92 | Book->Buy | if we click buy now without entering price there should be display correct message like 'Please enter the price' instead of 'invalid input'. | 1.click on book tab. |  |  | if we click buy now without entering price there should be display correct message like 'Please enter the price' instead of 'invalid input'. | not displaying exact message. | Fail |  |  | pass
2.click on buy .
3.click on quantity.
4.click on buy now
5Observe.
TC_93 | Book->buy-->(aarti.dalvi@techneai.com) | when we book metal with another user orders doesnt display. | 1.click on book tab. |  |  | Orders should be display in orders tab. | orders are not showing in orders tab. | Fail |  |  | pass
2.click on buy .
3.click on quantity.
4.click on buy now
5Observe.
TC_94 | Book->buy-->(aarti.dalvi@techneai.com) | trigger order is not displaying for another user. | 1.click on book tab. |  |  | trigger orders should be display in orders tab. | orders are not showing in trigger orders tab. | Fail |  |  | pass
2.click on buy .
3.click on quantity.
4.enter quantity.
5.click on trigger price
6.click on buy now.
TC_95 | Order Overview | To check whether In order overview displays proper or not. | 1.click on orders. |  |  | there should be display some gold or silver booked percentage. | order overview initially displays 405 and 60% . | Fail |  |  | Fail | NEED TO UPDATE | Fail
2.check order overview.
TC_96 | Account leadger Report | To check whether orders are displaying correct not. | 1.click on book tab. |  |  | Orders should be display in orders tab also. | Orders are not displaying in orders tab but it is displaying download successfully message.. | Fail |  |  | Fail | NEED TO UPDATE | Fail
2.click on orders.
3.Observe.
4.click on account leadger report.
5.Observe
TC_97 | Book->Buy | If we order metal then without entering triggering price order should be placed. | 1.click on quantity. |  |  | order should be placed with current rate. | Something went wrong' error message is displaying. | Fail |  |  | Fail | Done | pass
2.click on buy now
3.Observe.
TC_98 | Book->Sell | To check whether sell button is working or not. | 1.click on book tab. |  |  | Sell button should be redirect to another respective page. | sell button is not working. | Fail | Not Provided from back end |  | Fail | Not Provided from back end
2.click on sell.
3.Observe.
Need to discuss
TC_99 | Account leadger Report | To check export button is displayed properly or not. | 1.click on reports. | click here |  | export button should be above. | it is not displaying proper | Fail |  |  | Fail | Done | Fail
2click on export.
TC_100
TC_101
TC_102
TC_103
TC_104
TC_105