## data
sr | ticket_id | task_owner | task_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at | Actual Result | Reason
40 | TT7361 | Preeti Bokade | TT3032 Point Explanation | 2023-03-21 | 01:00 | 05:57:04 | 2023-03-21 |  | IN_PROGRESS | DELAYED
41 | TT10598 | Preeti Bokade | Test Execution -Project Master - Add/Edit ( 13 web element *2), Grid View, Search, Export | 2023-03-21 | 00:40 | 00:01:03 | 2023-03-21 |  | COMPLETED | COMPLETED | 2023-03-24 20:07:37 | 2023-03-24 20:07:37
42 | TT10598 | Preeti Bokade | Test Execution - Module Master - Add/Edit (9 web element *2), Grid View, Search, Export | 2023-03-21 | 00:35 | 15:40:22 | 2023-03-21 |  | COMPLETED | DELAYED | 2023-03-24 20:07:47 | 2023-03-24 20:07:48
43 | TT10598 | Preeti Bokade | Test Execution - Sub Module Master - Add/Edit(9 web element *2), Grid View, Search, Export | 2023-03-21 | 00:35 |  | 2023-03-21 |  | COMPLETED | COMPLETED | 2023-03-24 20:08:03 | 2023-03-24 20:08:03
44 | TT10598 | Preeti Bokade | Test Execution - Consolidated View - Project wise - Pending Tickets, Completed Tickets, Pending Task, Delayed Tickets | 2023-03-21 | 01:30 |  | 2023-03-21 |  | IN_PROGRESS | DELAYED | 2023-03-24 20:08:23
45 | TT10598 | Preeti Bokade | Test Execution - Consolidated View -Module wise - Pending Tickets, Completed Tickets, Pending Task, Delayed Tickets | 2023-03-21 | 01:30 |  | 2023-03-21 |  | TO_DO | DELAYED | 2023-03-21 16:07:58
46 | TT10598 | Preeti Bokade | Verifying Project owner has same authority same as Ticket owner | 2023-03-22 | 00:35 |  | 2023-03-22 |  | TO_DO | DELAYED | 2023-03-21 16:09:43
47 | TT10598 | Preeti Bokade | Task planning -Multiple Projects | 2023-03-21 | 00:40 |  | 2023-03-21 |  | COMPLETED | COMPLETED | 2023-03-24 20:08:44 | 2023-03-24 20:08:44
48 | TT10598 | Preeti Bokade | Verifying Project owner has same authority same as Basket owner | 2023-03-22 | 00:35 |  | 2023-03-22 |  | TO_DO | DELAYED
49 | TT10598 | Preeti Bokade | Verifying Project Owner has same authority same as Task Owner | 2023-03-22 | 00:35 |  | 2023-03-22 |  | TO_DO | DELAYED
50 | TT10598 | Preeti Bokade | Defect Reporting, explaining and logging | 2023-03-21 | 02:00 | 00:22:05 | 2023-03-22 |  | COMPLETED | COMPLETED | 2023-03-24 20:07:02 | 2023-03-24 20:07:03
51 | TT10599 | Preeti Bokade | Verifying Customer can create Customer mapping of Departmentwise Round Robin | 2023-03-21 | 00:10 | 01:36:26 | 2023-03-22 |  | COMPLETED | DELAYED | 2023-03-24 20:05:36 | 2023-03-24 20:05:36
52 | TT10599 | Preeti Bokade | Verifying newly created tickets assign by manual method to Round robin allocated person | 2023-03-22 | 00:35 | 01:45:11 | 2023-03-22 |  | COMPLETED | DELAYED | 2023-03-24 20:04:59 | 2023-03-24 20:05:00
53 | TT10599 | Preeti Bokade | Verifying newly created tickets assign by Bulk method to Round robin allocated person with live dynamic form | 2023-03-22 | 00:40 | 01:53:25 | 2023-03-22 |  | COMPLETED | DELAYED | 2023-03-24 20:04:44 | 2023-03-24 20:04:44
54 | TT10599 | Preeti Bokade | Verifying with Department wise round robin query Ticket owner can assign to new ticket owner | 2023-03-22 | 00:10 |  | 2023-03-22 |  | COMPLETED | COMPLETED | 2023-03-24 20:03:39 | 2023-03-24 20:03:39
55 | TT10599 | Preeti Bokade | Verifying create ticket , create basket, edit basket, Crete Task , edit task , report validation with respect to Department wise round robin | 2023-03-22 | 02:00 | 01:14:36 | 2023-03-22 |  | IN_PROGRESS | DELAYED | 2023-03-24 20:03:05
56 | TT10599 | Preeti Bokade | Task planning - Round Robin | 2023-03-21 | 00:10 | 00:08:42 | 2023-03-21 |  | COMPLETED | COMPLETED | 2023-03-24 20:05:19 | 2023-03-24 20:05:20
57 | TT3032 | Preeti Bokade | Task Planning - TT3032 | 2023-03-21 | 00:10 |  | 2023-03-21 |  | TO_DO | DELAYED
58 | TT3032 | Preeti Bokade | Go through Design Document | 2023-03-21 | 00:40 |  | 2023-03-21 |  | IN_PROGRESS | DELAYED
59 | TT3032 | Preeti Bokade | Test Case Writing | 2023-03-22 | 01:00 | 03:04:18 | 2023-03-22 |  | IN_PROGRESS | DELAYED
60 | TT3032 | Preeti Bokade | Test Data Preparation | 2023-03-22 | 00:30 | 00:09:23 | 2023-03-22 |  | IN_PROGRESS | DELAYED
61 | TT3032 | Preeti Bokade | Test Execution | 2023-03-23 | 01:00 |  | 2023-03-23 |  | TO_DO | DELAYED | 2023-03-21 17:04:59
62 | TT3032 | Preeti Bokade | Defect Reporting | 2023-03-23 | 01:00 |  | 2023-03-23 |  | TO_DO | DELAYED | 2023-03-21 17:07:12
63 | TT2803 | Preeti Bokade | Go through Design Document | 2023-03-23 | 00:35 |  | 2023-03-23 |  | TO_DO | DELAYED
64 | TT2803 | Preeti Bokade | Test Case Writing | 2023-03-23 | 00:45 |  | 2023-03-23 |  | TO_DO | DELAYED
65 | TT2803 | Preeti Bokade | Test Data Preparation | 2023-03-23 | 00:40 |  | 2023-03-23 |  | TO_DO | DELAYED
66 | TT2803 | Preeti Bokade | Test Execution | 2023-03-23 | 00:40 |  | 2023-03-23 |  | TO_DO | DELAYED
67 | TT2803 | Preeti Bokade | Defect Reporting | 2023-03-23 | 01:00 |  | 2023-03-23 |  | TO_DO | DELAYED
68 | TT2803 | Preeti Bokade | Task planning - TT2803 | 2023-03-21 | 00:10 |  | 2023-03-21 |  | TO_DO | DELAYED
69 | TT4338 | Preeti Bokade | Understand the bugs | 2023-03-23 | 00:40 |  | 2023-03-23 |  | IN_PROGRESS | DELAYED | 2023-03-24 20:10:02
70 | TT4338 | Preeti Bokade | Retest the defect | 2023-03-23 | 02:00 |  | 2023-03-23 |  | TO_DO | DELAYED
71 | TT4338 | Preeti Bokade | Report the conclusion | 2023-03-23 | 00:30 |  | 2023-03-23 |  | TO_DO | DELAYED
72 | TT4337 | Preeti Bokade | Understand the bugs - | 2023-03-24 | 00:40 |  | 2023-03-24 |  | IN_PROGRESS | IN_PROGRESS | 2023-03-24 20:10:58
73 | TT4337 | Preeti Bokade | Retest the defect | 2023-03-24 | 00:40 |  | 2023-03-24 |  | TO_DO | TO_DO
74 | TT4337 | Preeti Bokade | Report the bugs , explain to them | 2023-03-24 | 00:40 |  | 2023-03-24 |  | TO_DO | TO_DO
75 | TT10598 | Preeti Bokade | Ticketing System KT | 2023-03-24 | 02:00 |  | 2023-03-24 |  | TO_DO | TO_DO
76 | TT2803 | Preeti Bokade | Query clarification | 2023-03-23 | 00:30 |  | 2023-03-23 |  | TO_DO | DELAYED | 2023-03-21 17:13:07
77 | TT9346 | Preeti Bokade | Test cases group discussion | 2023-03-23 | 07:30 | 15:16:34 | 2023-03-23 |  | COMPLETED | DELAYED | 2023-03-24 17:03:18 | 2023-03-24 17:03:20
78 | TT6027 | Preeti Bokade | Testing Team Meeting. Meeting Agenda : Test case writing in ticketing system. | 2023-03-23 | 07:00 | 01:51:50 | 2023-03-23 |  | COMPLETED | COMPLETED | 2023-03-23 18:53:24 | 2023-03-23 18:53:25