## Summary
Project:- CSPL
TPM Document Revision History
Author | Sprint | Ticket ID | Start Date | End Date | Version | Description | Scope Document | No. of Test Cases | Passed Test Cases | Failed Test Cases | Review By | Date

## TPM_Sheet
Ticket ID | TT2610 | Released Version
Project Name | Ticketing System | Project live Date
Module Name | Bulk Upload | Testing Owner | Sayali
Ticket Owner | Mounika A | Email / User Name | ParthP
Testing URL | http://10.2.9.199:3000/TechTicket/ | Password | abcd123
Description | User should be logged in
Case ID | Module--> SubModule | Test Description | Testing Type | Screenshot Path | Expected Result | Actual Result | Tester Status | Tester Remark | Priority | Severity | Script | BA Status | BA Remark | Developer Status | Developer Remark | Tester Name | Reviewed By | Final BA Remark | Remark
TC_01 | Bulk Upload | Verify that "Ticket" option is visible in My-Task side panel or not | UI/UX |  | "Ticket" option should be visible in My-Task side panel | As Expected | Pass
TC_02 | Bulk Upload | Verify that "Ticket" dropdown is clickable in My-Task side panel or not | Sanity |  | "Ticket" dropdown should be clickable in My-Task side panel | As Expected | Pass
TC_03 | Bulk Upload | Verify that after clicking on "Ticket" dropdown "My Tickets" and "Create ticket" option is visible and clickable or not | Sanity |  | After clicking on "Ticket" dropdown "My Tickets" and "Create ticket" option should be visible and clickable | As Expected | Pass
TC_04 | Bulk Upload | Verify that after clicking on "Create ticket" option is it redirecting to create ticket page or not | Functionality |  | After clicking on "Create ticket" option it should redirect to create ticket page | As Expected | Pass
TC_05 | Bulk Upload | Verify that "Your department" dropdown, "Query type" dropdown, and Ticket uploading radio buttons with options "Regular" and "Bulk Uploading" are visible or not | UI/UX |  | "Your department" dropdown, "Query type" dropdown, and Ticket uploading radio buttons with options "Regular" and "Bulk Uploading" should be visible | upload file, submit and cancel button is also visible | Fail
TC_06 | Bulk Upload | Verify that "Your department" dropdown is active or not | Sanity |  | "Your department" dropdown should be active | As Expected | Pass
TC_07 | Bulk Upload | Verify that after clicking on "Your department" dropdown all options are visible and clickable or not | Sanity |  | After clicking on "Your department" dropdown all options should be visible and clickable | As Expected | Pass
TC_08 | Bulk Upload | Verify that only one option is selecting from "Your department" dropdown or not | Functionality |  | Only one option should be selected from "Your department" dropdown | As Expected | Pass
TC_09 | Bulk Upload | Verify that "Query Type" dropdown is active or not | Sanity |  | "Query Type" dropdown should be active | As Expected | Pass
TC_10 | Bulk Upload | Verify that after clicking on "Query Type" dropdown all options are visible and clickable or not | Sanity |  | After clicking on "Query Type" dropdown all options should be visible and clickable | As Expected | Pass
TC_11 | Bulk Upload | Verify that only one option is selecting from "Query Type" dropdown or not | Functionality |  | Only one option should be selected from "Query Type" dropdown | As Expected | Pass
TC_12 | Bulk Upload | Verify that by default "Regular" option is checked in "Ticket uploading" field or not | Validation |  | By default "Regular" option should be checked in "Ticket uploading" field | As Expected | Pass
TC_13 | Bulk Upload | Verify that only one option is checked from "Ticket Uploading" radio buttons or not | Validation |  | Only one option should be checked from "Ticket Uploading" radio buttons | As Expected | Pass
TC_14 | Bulk Upload | Verify that after checking "Bulk Uploading" option "Get Format" button is visible or not | UI/UX |  | After checking "Bulk Uploading" option "Get Format" button should be visible | not getting "Get format" button | Fail
TC_15 | Bulk Upload | Verify that "Get Format" button is disable or not if user didn't select "Your Department" and "Query Type" fields | Functionality |  | "Get Format" button should be disable if user didn't select "Your Department" and "Query Type" fields | "Get Format" button is active | Fail
TC_16 | Bulk Upload | Verify that after selecting "Your department" and "Query type" fields and by checking "Bulk Uploading" radio button check that Get format button is active or not | Functionality |  | After selecting "Your department" and "Query type" fields and by checking "Bulk Uploading" radio button check that Get format button should be active | Select department and query type pop-up is appearing and get format button is not visible | Fail
TC_17 | Bulk Upload | Verify that after clicking on "Get format" button "Download File" button is visible or not | Sanity |  | After clicking on "Get format" button "Download File" button should be visible | "Get format" button not added | Fail
TC_18 | Bulk Upload | Verify that after clicking on "Download File" button format file is downloading or not | Functionality |  | After clicking on "Download File" button format file should be download | "download file" button not visible | Fail
TC_19 | Bulk Upload | Verify that format file is according to selected query type or not | Functionality |  | Format file should be according to selected query type | "Get format" button not added | Fail
TC_20 | Bulk Upload | Verify that "Submit" and "Cancel" button is visible or not | UI/UX |  | "Submit" and "Cancel" button should be visible | "Submit" and "cancel" buttons duplicated | Fail
TC_21 | Bulk Upload | Verify that "Submit" and "Cancel" button is clickable or not | Sanity |  | "Submit" and "Cancel" button should be clickable | As Expected | Pass
TC_22 | Bulk Upload | Verify that after selecting "Your department", "Query type" fields and by checking "Bulk Uploading" radio button and clicking on Submit button check that is it showing error message or not | Functionality |  | After selecting "Your department", "Query type" fields and by checking "Bulk Uploading" radio button and clicking on Submit button it should show error warning to upload file. | After clicking on submit it is creating ticket without uploading any file | Fail
TC_23 | Bulk Upload | Verify that "Bulk upload" button is visible or not | UI/UX |  | "Bulk upload" button should be visible | "Bulk upload" button is not added | Fail
TC_24 | Bulk Upload | Verify that "Bulk upload" button is clickable or not | Sanity |  | "Bulk upload" button should be clickable | not added | Fail
TC_25 | Bulk Upload | Verify that after clicking on "Bulk Upload" button pop-up window to upload file is appearing or not | Functionality |  | After clicking on "Bulk Upload" button pop-up window to upload file should appear | not added | Fail
TC_26 | Bulk Upload | verify that "choose file" button in pop-up window is clickable or not | Sanity |  | "choose file" button in pop-up window should be clickable | not added | Fail
TC_27 | Bulk Upload | Verify that after clicking on choose file button is it browsing device to upload a file or not | Functionality |  | After clicking on choose file button it should browse device to upload a file | not added | Fail
TC_28 | Bulk Upload | Verify that choose file option is accepting only "CSV" file or not | Functionality |  | Choose file option should accept only "CSV" file | not added | Fail
TC_29 | Bulk Upload | Verify that "Submit" and "Cancel" button in pop-up window is visible and clickable or not | Sanity |  | "Submit" and "Cancel" button in pop-up window should be visible and clickable | not added | Fail
TC_30 | Bulk Upload | Verify that after selecting CSV file and by clicking on submit button success message is displaying or not | Functionality |  | After selecting CSV file and by clicking on submit button success message should be display | not added | Fail
TC_31 | Bulk Upload | Verify that after selecting CSV file and clicking on Cancel button check that file uploading or not | Functionality |  | After selecting CSV file and clicking on Cancel button file should not be uploaded | not added | Fail
TC_32 | Bulk Upload | Verify that if user added empty file then after submitting the file is it showing error message or not | Functionality |  | If user added empty file then after submitting the file it should show error message "file is empty" | not added | Fail
TC_33 | Bulk Upload | Verify that data is inserted as per the format or not | Validation |  | Data should be inserted as per the format | not added | Fail
TC_34 | Bulk Upload | Verify that in file format mandatory fields are marked as mandatory or not | Validation |  | In file format mandatory fields should be marked as mandatory | not done | Fail
TC_35 | Bulk Upload | Verify that if mandatory fields are empty then after submitting is it showing error message or not | Functionality |  | If mandatory fields are empty then after submitting it should show error message | not added | Fail
TC_36 | Bulk Upload | Verify that if mandatorty field data is invalid then check that is it showing error message or not | Functionality |  | If mandatorty field data is invalid then it should show error message | not added | Fail
TC_37 | Bulk Upload | Verify that after getting error message "download error file" button is visible or not | UI/UX |  | After getting error message "download error file" button should be visible | not added | Fail
TC_38 | Bulk Upload | Verify that after getting error message "download error file" button is clickable or not | Sanity |  | After getting error message "download error file" button should be clickable | not added | Fail
TC_39 | Bulk Upload | Verify that after clicking on "download error file" button error file is downloading or not | Functionality |  | After clicking on "download error file" button error file should be downloaded | not added | Fail
TC_40 | Bulk Upload | Verify that if user choose any duplicate file to upload then check that is it showing "duplicate" file error or not | Functionality |  | If user choose any duplicate file to upload then it should show "duplicate" file error | not added | Fail
TC_41 | Bulk Upload | Verify that if user choose file that have duplicate entries and clicked on submit button then is it showing error message or not | Functionality |  | If user choose file that have duplicate entries and clicked on submit button then it should show error message | not added | Fail
TC_42 | Bulk Upload | Verify that after uploading file is it creating tickets in "My Tickets" "Your Task" tab or not | Functionality |  | After uploading file is it creating tickets in "My Tickets" "Your Task" tab or not | not added | Fail
TC_43 | Bulk Upload | Verify that if user added single row in CSV file is it creating ticket for single entry or not | Functionality |  | If user added single row in CSV file it should create ticket for single entry | not added | Fail
TC_44 | Bulk Upload | Verify that at the time of ticket creation if confirmation required field is yes then after uploading file and after solved those tickets is it asking for confirmation from ticket creator or passing authority person of selected or not | Functionality |  | At the time of ticket creation if confirmation required field is yes then after uploading file and after solved those tickets it should ask for confirmation from ticket creator or passing authority person of selected department
TC_45 | Bulk Upload | Verify that at the time of ticket creation if confirmation required field is no then after uploading file and after solving those tickets is it asking for confirmation from ticket creator or passing authority person of selected or not | Functionality |  | At the time of ticket creation if confirmation required field is no then after uploading file and after solving those tickets it should not ask for confirmation from ticket creator or passing authority person of selected department

## TPM_MISC
Testing Type | Status | Priority | Severity | Final BA remark | Developer remark | BA Remark | Tester Name | Reviewd By | Script
Smoke | Pass | High | Critical | Closed | Resolved | Closed | Amreen | Harshali R | Possible
Sanity | Fail | Medium | Major | Pending | Not a bug | Re-open | Priyanka | Bharat D | Not Possible
Regression |  | Low | Minor | Re-open | Deffered | Deffered | Monika | Mounika A
Functionality |  |  | Low | Blocker |  | Not a bug | Abhijeet | Sandeep A
Intergration |  |  |  | Re-Test |  | Suggestion | Sayali
Validation | [6 empty] | Saurabh
UI/UX | [6 empty] | Shradhdabharti