## Detail3
Details for Count of Defect ID - Defect State: backend issue 2/21/2023
SR No. | Identifier | Defect ID | Defect Raised Date | Severity | Priority | Module | Sub-Module | Defect State | Defect category | Defect Description | Tester | Assigned To | Remark | Remark by Dev | Defect Close Date | screenshots
128 | MT | TT_MT_128 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Manage task | backend issue 2/21/2023 | Functional | when user have multiple baskets at a time different "group activities" are playing from "differnet baskets" of same user. | Priyanka | Rushikesh |  |  |  | Sheet3!A71
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17
97 | CT | TT_CT_97 | 2023-02-07 | 1 High | 1 High | Ticket | Bulk - Upload | backend issue | Functional | For bulk upload Ticket creation, Assign to Field is not populated , Test data , Query Type - Program Management, User id - Preetib | Preeti | Punam | 2/23/2023: Unable to retest as with correct input as well system throwing error | Solved 23-02-2023
98 | CT | TT_CT_98 | 2023-02-07 | 1 High | 1 High | Ticket | Bulk - Upload | backend issue | Functional | While creating the ticket through Bulk Upload it has been observed that under department wise tab tickets created by bulk uploading are not reflecting . username - Preetib, Ticket no - same as created by me tab ( for yesterday's day ) display | Preeti | Punam | 2/23/2023: Unable to retest as with correct input as well system throwing error | Solved 23-02-2023
115 | MT | TT_MT_115 | 2023-02-07 | 2 Medium | 2 Medium | Ticket | Manage task | backend issue | Functional | All task total timing are displaying wrong. | Preeti |  |  | Bug not found
85 | MT | TT_MT_85 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | backend issue | Functional | When task status is “In_Progress” it doesn’t reflect in basket owner’s login. It displays “not started”. | Priyanka |  |  | Bug not found
80 | MTBU | TT_MTBU_80 | 2023-02-06 | 1 High | 1 High | Ticket | My Ticket -Bulk upload | backend issue | Functional | For bulk upload , System showing incorrect values for bulk upload , Through CSV user has provided the Priority field value as " High" however system displaying it as " Medium" | Preeti |  |  | Solved
65 | MTT | TT_MTT_65 | 2023-02-02 | 2 Medium | 2 Medium | Ticket | Task | backend issue | Functional | When user has created group task and it played for two people. Still total worked hours doesn’t reflect in user task report.
89 | MTT | TT_MTT_89 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | backend issue | Functional | “Total worked hours” are displays different that actual. | Priyanka |  |  | Solved
99 | UM | TT_UM_99 | 2023-02-07 | 1 High | 1 High | Master | My Ticket -Departmentwise | backend issue | Functional | I have added Ticket type show as Department wise as well as My Ticket however Departmentwise tab still not reflecting against username ( Preetib) | Preeti |  |  | Confirmation Required
109 | UTR | TT_UTR_109 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | backend issue | Functional | If somebody has marked to task as "completed" without playing the task, in report "Actual worked hours are displaying empty it is expected to display "00:00". | Priyanka |  |  | Solved
91 | UTR | TT_UTR_91 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | User Task Report | backend issue | Functional | Total worked hours doesn’t update when user has played the task second time. | Priyanka
102 | VR | TT_VR_102 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | backend issue | Functional | last updated time is not displaying proper. | Priyanka |  |  | FrontEnd
103 | VR | TT_VR_103 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | backend issue | Functional | A task got delayed so after editing task hours greater than "Actual worked hours", in variance report status is changed from "Delayed" to completed. | Priyanka |  |  | FrontEnd
105 | VR | TT_VR_105 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | backend issue | Functional | A "group activity" of 2 users but it has played only one user still it is displaying same "Actual working hours" for both the users. | Priyanka
192 | CSM | TT_CSM_192 | 2023-02-11 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | backend issue 2/20/2023 | Functional | System is allowing to create twice customer mapping with same Query and Department combination . How would system knows which approch needs to apply for ticket creation of specific department. Here Testing9027(Query) and IT testing(Department) with Approach - Ratio wise Testing9027(Query) and IT testing(Department) with Approach - Having Less Ticket | Preeti |  |  | Confirmation Required
182 | MT | TT_MT_182 | 2023-02-10 | 1 High | 1 High | Ticket | Edit Ticket | backend issue 2/20/2023 | Functional | User won't get OTP through WhatsApp and SMS channel | Preeti |  |  | Deffered
156 | NTF | TT_NTF_156 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 | Functional | Assigned to person is not receiving notification upon ticket assigning, when Assign to person assigns it to other person. | Amreen |  |  | Resolved 23-02-2023
189 | NTF | TT_NTF_189 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 | Functional | Notification is not being sent to ticket owner and task owner when any task been pending. | Amreen |  |  | Deffered
190 | NTF | TT_NTF_190 | 2023-02-11 | 1 High | 1 High | Ticket | Notification | backend issue 2/20/2023 | Functional | Notification is not being sent to ticket creator after masking ticket status as SOLVED. | Amreen |  |  | Solved
174 | PM | TT_PM_174 | 2023-02-10 | 1 High | 2 Medium | Ticket | Notification | backend issue 2/20/2023 | Functional | Project Owner not getting Ticket update related notification Project - Ticketing System, project owner - Preeti12(username) | Preeti |  |  | Development Not Done
175 | PM | TT_PM_175 | 2023-02-10 | 1 High | 2 Medium | Ticket | Notification | backend issue 2/20/2023 | Functional | Project owner won't get ticket creation notification as this field is not part of ticket create | Preeti |  |  | Development Not Done
146 | NTF | TT_NTF_146 | 2023-02-09 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | When passing authority passes a ticket, ticket creator should rcv notification stating "#PassingAuthorityName has passed #TicketId" | Amreen |  | 2/22/2023: Retested and failed | Resolved 23-02-2023
155 | NTF | TT_NTF_155 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | When sender mentions a user in comment, Ticket owner is not getting correct notification. Test data : Ticket owner is getting Notification : "Sender has mentioned you in TicketID" | Amreen |  | 2/22/2023: TT9368 | Resolved 23-02-2023
166 | NTF | TT_NTF_166 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Upon task creation, ticket owner not getting notification message. | Amreen |  | 2/22/2023: Retested Successfully and Reopened TT9368 | Resolved 23-02-2023
167 | NTF | TT_NTF_167 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Upon task creation for muliple user, task owners not getting notification message. | Amreen |  | 2/22/2023 : Monika kolpe has been created task for TT7400 and assigned to Amreen Shaikh -- TT received wrong , testing done on TT9368 | Resolved 23-02-2023
171 | NTF | TT_NTF_171 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Upon group activity creation, task owner not getting notification message. | Amreen |  | 2/22/2023 : Monika Kolpe has been created task for TT7400 and assigned to Amreen Shaikh -- TT id received wrong , testing done on TT9368, this is group activity --however notification says task | Resolved 23-02-2023
176 | NTF | TT_NTF_176 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Ticket owner not getting notification for task assigned to multiple users | Amreen |  | 2/22/2023: Retested and failed -- TT9368 | Resolved 23-02-2023
179 | NTF | TT_NTF_179 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Task completion notification not being sent to ticket owner | Amreen |  | 2/22/2023: Retested and failed -- TT9368 | Resolved 23-02-2023
180 | NTF | TT_NTF_180 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Mulple user -> task completion notification not being sent to to all user in that task | Amreen |  | 2/22/2023: Retested and failed -- TT9368 | Resolved 23-02-2023
186 | NTF | TT_NTF_186 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Notification is not being sent to ticket owner when any changes have been made in the Task | Amreen |  | 2/22/2023: Retested and Failed | Resolved 23-02-2023
187 | NTF | TT_NTF_187 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Notification is not being sent to Basket owner when any changes have been made by task owner / ticket owner in the Basket | Amreen |  | 2/22/2023: Retested and Failed | Resolved 23-02-2023
188 | NTF | TT_NTF_188 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 | Functional | Notification is not being sent to Task owner when any changes have been made by basket owner / ticket owner in the Task | Amreen |  | 2/22/2023: Retested and Failed | Resolved 23-02-2023
95 | CTBU | TT_CTBU_95 | 2023-02-06 | 1 High | 1 High | Ticket | Create Ticket - Bulk Uploading | Backend Issue Under Disscussion | Functional | While trying to do bulk upload user getting error as " Request Error" however user followed the downloaded file format. If there is any issue how would user know the things and how can he rectify the mistake. Kindly provide the descriptive details of error in user friendly language. | Preeti | Punam | 2/23/2023: Retested and Failed. upon getting error there is no error log generated which helps the customer to understand . what went wrong. | Solved

## Sheet2
Severity | (All)
Priority | (All)
Defect State | Count of Defect ID
Fixed - 2/15/2023 Retest - 2/16/2023-closed | 1
Backend Issue | 10
backend issue 2/20/2023 | 5
backend issue 2/20/2023 Closed - 2/22/2023 | 4
backend issue 2/20/2023 Partially fixed - 2/22/2023 | 1
backend issue 2/21/2023 | 1
backend issue Fixed-2/20/2023 Closed - 2/22/2023 | 1
Backend Issue Under Disscussion | 1
closed | 66
Closed | 2
Closed (Conditional Based) | 1
Confirmation Needed | 1
Data issue | 2
Data issue (Query Type ) | 1
Defect Not Replicate | 1
Fixed 2/23/2023 | 1
Front End | 1
Front-end | 2
New | 26
New Need to discuss 2/20/2023 | 8
New Fixed 2/21/2023 | 1
New Development | 2
New Closed | 1
New Deffred 2/22/2023 | 2
New Fixed - 2/15/2023 Closed - 2/17/2023 | 1
New Fixed - 2/15/2023 Reteste-2/16/2023-closed | 1
New Fixed - 2/15/2023 Reteste-2/16/2023-reopen | 1
New Fixed - 2/16/2023 | 1
New Fixed - 2/21/2023 Reopen - 2/22/2023 | 1
New Fixed -2/15/2023 Retest -2/16/2023-partially fail | 1
New Fixed -2/15/2023 Retest -2/16/2023-reopen | 1
New Fixed -2/15/2023 Retest-2/16/2023 Closed-2/16/2023 | 1
New Fixed -2/15/2023 Retest-2/16/2023-closed | 1
new Fixed 2/21/2023 | 4
New Fixed 2/21/2023 Closed - 2/22/2023 | 1
New Fixed 2/21/2023 Reopen - 2/22/2023 | 3
New Fixed 2/21/2023 Reopen - 2/22/2023 Fixed2/23/2023 | 1
New Fixed 2/22/2023 | 1
New Fixed 2/22/2023 | 1
New Not a Bug | 1
Not a Bug | 10
Observation ( Seems to be performance issue) | 1
Partially fixed | 5
Reopen | 16
Reopen Fixed - 2/16/2023 | 1
reopen Closed-2/22/2023 | 1
reopen Fixed - 2/15/2023 Retest - 2/16/2023-closed | 3
Suggestion | 4
Under Discussion | 2
(blank) | 1
New Fixed - 2/23/2023 Closed - 2/23/2023 | 1
backend issue - 2/20/2023 | 4
New Fixed - 2/16/2023 Closed-2/23/2023 | 1
New Fixed 2/22/2023 Reopen-2/23/2023 | 1
backend issue Partially fixed:--2/23/2023 | 1
Backend issue reopen:-2/23/2023 | 2
New Fixed 2/23/2023 | 2
New Fixed 2/23/2023 | 2
Backend Issue 2/23/2023 | 1
New Not a Bug 2/23/2023 | 1
New Not a Bug | 1
backend issue 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | 3
backend issue - 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | 1
backend issue 2/20/2023 Reopen- 2/23/2023 | 1
backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | 7
backend issue 2/20/2023 Reopen - 2/22/2023 Partially fixed - 2/23/2023 | 1
backend issue 2/20/2023 Reopen- 2/22/2023 | 1
Grand Total | 238

## Sheet5
SR No. | Identifier | Defect ID | Defect Raised Date | Severity | Priority | Module | Sub-Module | Defect State | Defect category | Defect Description | Tester | Assigned To | Remark | Remark by Dev | Defect Close Date | screenshots
82 | MTT | TT_MTT_82 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | New | Functional |  | Priyanka
141 | CSM | TT_CSM_141 | 2023-02-09 | 2 Medium | 2 Medium | Masters | Edit customer mapping | New | Functional | previously selected users are not displaying in edit customer mapping. | Priyanka
142 | CSM | TT_CSM_142 | 2023-02-09 | 2 Medium | 2 Medium | Masters | Edit customer mapping | New | Functional | Department wise usernames are not displaying in "select user" field. | Priyanka
143 | CSM | TT_CSM_143 | 2023-02-09 | 2 Medium | 2 Medium | Masters | Edit customer mapping | New | Functional | User is not able to update users in "select user" field. | Priyanka
151 | CSM | TT_CSM_151 | 2023-02-09 | 2 Medium | 2 Medium | Masters | create customer mapping | New | Functional | According to "user is having less ticket" approach ticket is not assigning. it is assigned to person who is not selected in "select user" | Priyanka
161 | NTF | TT_NTF_161 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification displayed on Notificatios page and under notification bell icon are different. | Amreen
162 | NTF | TT_NTF_162 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Chnages made on notification same should reflect on notification bell icon displaying different | Amreen
170 | NTF | TT_NTF_170 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon clicking on to the notification it should redirect to respective page. | Amreen
196 | CSM | TT_CSM_196 | 2023-02-11 | 3 Low | 3 Low | Customer Mapping | Create Customer Mapping | New | Functional | Though total ratio is 100% , still it is showing error “ Total should be 100” | Preeti
197 | CSM | TT_CSM_197 | 2023-02-11 | 3 Low | 3 Low | Customer Mapping | Create Customer Mapping | New | Functional | Ratio Wise - Total - displays 'Nan' instead of numerical figure. | Preeti
208 | UM | TT_UM_208 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Add user | New | Functional | User getting instruction and error simultaneously for one field. It is expected that user get error once the focus goes to other field. | Priyanka
209 | UM | TT_UM_209 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Add User | New | Functional | while entering whats app number second time when we select checkbox "same as contact number" it doesnt reflect in "whats app number" field. | Priyanka
213 | UM | TT_UM_213 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Export | New | Functional | If user is having multiple departments it doesnt display in downloaded file after export. | Priyanka
216 | MT | TT_MT_216 | 2023-02-14 | 2 Medium | 2 Medium | My Tickets | Manage Basket | New | Functional | User can not able to edit basket end date. | Priyanka
217 | MT | TT_MT_217 | 2023-02-14 | 1 High | 2 Medium | My Tcikets | Manage Basket | New | Functional | user can able to create backdated basket. basket date and ticket date is not synced properly. | Priyanka
218 | MT | TT_MT_218 | 2023-02-14 | 1 High | 2 Medium | My Tickets | Edit Ticket | New | Functional | ticket owner can not able to assign his ticket to another user. | Priyanka
219 | MT | TT_MT_219 | 2023-02-14 | 2 Medium | 2 Medium | My Tickets | Edit ticket | New | Functional | If assigned query type is deactivated still it is displaying in edit ticket | Priyanka
220 | MT | TT_MT_220 | 15/02/2023 | 2 Medium | 2 Medium | Ticket | My Tickets | New | Functional | project owner can able to view all projects even though he is not owner of that project. | Priyanka
221 | MT | TT_MT_221 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | My Tickets | New | Functional | Project owner doesnt have edit authority for ticket, basket and task. | Priyanka
225 | MT | TT_MT_225 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | My Tickets | New | Functional | When we filter any ticket it doesnt display action pop up properly. for example:-- after filtered records there are only 4 records are available on page. and if user want to edit last record then he can not able to view action pop up. | Priyanka
226 | MT | TT_MT_226 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | Manage task | New | Functional | user can create group activity of single user. It is expected that if user want to create group activtiy it requires minimum 2 users included. | Priyanka
227 | MT | TT_MT_227 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | Manage task | New | Functional | User is able to create the task greater than the Ticket "Expected Solve Date". Task end date should be less than Ticket Expected Solved date. | Priyanka
229 | MT | TT_MT_229 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | Manage task | New | Functional | For created "task" and "group activities" - play & pause button not there.(TT9043) | Priyanka
236 | NTF | TT_NTF_236 | 22/02/2023 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification not being sent to Ticket owner and basket owner when task owner is differ from Ticket owner and Basket owner | Amreen
237 | NTF | TT_NTF_237 | 22/02/2023 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | While ticket owner assigning ticket to other person , notification not being sent to Ticket creator and other person ( new Assign to person) | Amreen
238 | UM | TT_UM_238 | 2023-02-23 | 2 Medium | 2 Medium | User Master | Departments | New | Functional | user can make more than one department as dafault. It is expected that user can make at a time only one department as default. | Priyanka

## Sheet4
Severity | (ALL)
Priority | (ALL)
Defect State | Count of Defect ID
Fixed - 2/15/2023 Retest - 2/16/2023-closed | 1
Backend Issue | 10
backend issue - 2/20/2023 | 4
backend issue - 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | 1
backend issue 2/20/2023 | 5
backend issue 2/20/2023 Closed - 2/22/2023 | 4
backend issue 2/20/2023 Partially fixed - 2/22/2023 | 1
backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | 7
backend issue 2/20/2023 Reopen - 2/22/2023 Partially fixed - 2/23/2023 | 1
backend issue 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | 3
backend issue 2/20/2023 Reopen- 2/22/2023 | 1
backend issue 2/20/2023 Reopen- 2/23/2023 | 1
backend issue 2/21/2023 | 1
Backend Issue 2/23/2023 | 1
backend issue Fixed-2/20/2023 Closed - 2/22/2023 | 1
backend issue Partially fixed:--2/23/2023 | 1
Backend issue reopen:-2/23/2023 | 2
Backend Issue Under Disscussion | 1
closed | 66
Closed | 2
Closed (Conditional Based) | 1
Confirmation Needed | 1
Data issue | 2
Data issue (Query Type ) | 1
Defect Not Replicate | 1
Fixed 2/23/2023 | 1
Front End | 1
Front-end | 2
New | 26
New Need to discuss 2/20/2023 | 8
New Fixed 2/21/2023 | 1
New Fixed 2/23/2023 | 2
New Not a Bug | 1
New Development | 2
New Closed | 1
New Deffred 2/22/2023 | 2
New Fixed - 2/15/2023 Closed - 2/17/2023 | 1
New Fixed - 2/15/2023 Reteste-2/16/2023-closed | 1
New Fixed - 2/15/2023 Reteste-2/16/2023-reopen | 1
New Fixed - 2/16/2023 | 1
New Fixed - 2/16/2023 Closed-2/23/2023 | 1
New Fixed - 2/21/2023 Reopen - 2/22/2023 | 1
New Fixed - 2/23/2023 Closed - 2/23/2023 | 1
New Fixed -2/15/2023 Retest -2/16/2023-partially fail | 1
New Fixed -2/15/2023 Retest -2/16/2023-reopen | 1
New Fixed -2/15/2023 Retest-2/16/2023 Closed-2/16/2023 | 1
New Fixed -2/15/2023 Retest-2/16/2023-closed | 1
new Fixed 2/21/2023 | 4
New Fixed 2/21/2023 Closed - 2/22/2023 | 1
New Fixed 2/21/2023 Reopen - 2/22/2023 | 3
New Fixed 2/21/2023 Reopen - 2/22/2023 Fixed2/23/2023 | 1
New Fixed 2/22/2023 | 1
New Fixed 2/22/2023 | 1
New Fixed 2/22/2023 Reopen-2/23/2023 | 1
New Fixed 2/23/2023 | 2
New Not a Bug | 1
New Not a Bug 2/23/2023 | 1
Not a Bug | 10
Observation ( Seems to be performance issue) | 1
Partially fixed | 5
Reopen | 16
Reopen Fixed - 2/16/2023 | 1
reopen Closed-2/22/2023 | 1
reopen Fixed - 2/15/2023 Retest - 2/16/2023-closed | 3
Suggestion | 4
Under Discussion | 2
(blank) | 1
Grand Total | 238

## Defect Log
SR No. | Identifier | Defect ID | Defect Raised Date | Severity | Priority | Module | Sub-Module | Defect State | Defect category | Defect Description | Tester | Assigned To | Remark | Remark by Dev | Defect Close Date | screenshots
1 | LG | TT_LG_1 | 1/27/2023 | 2 Medium | 2 Medium | Login |  | closed | Functional | "with wrong password error message is displaying “Incorrect credentials” instead it should be displayed “password doesn’t match” |  | Rushikesh
2 | LG | TT_LG_2 | 1/27/2023 | 0 Blocker | 1 High | Login | Forget Password | reopen Closed-2/22/2023 | Functional | 2.when we clicked on forgot password otp is not received on mobile number and when user clicked on “Resend otp” blank page is displaying. |  | Rushikesh |  | 2/22/2023: At present System is not connected with Phone sevice
3 | LG | TT_LG_3 | 1/27/2023 | 2 Medium | 1 High | Login | Forget Password | closed | Functional | 3.While entering otp field should not be accepted characters.it should be accepted only numeric values. |  | Rushikesh
4 | LG | TT_LG_4 | 1/27/2023 | 3 Low | 3 Low | Login | Forget Password | closed | Functional | When we set password it doesn’t display any warning message like “your password should be at least 8 characters ” |  | Rushikesh
5 | LG | TT_LG_5 | 1/27/2023 | 2 Medium | 2 Medium | Login |  | closed | Functional | Eye button is not present to show and hide the password. |  | Rushikesh
6 | UP | TT_UP_6 | 1/27/2023 | 2 Medium | 2 Medium | Profile | Your Profile | Closed | Functional | 1.when user clicks on profile pop up is not closed. It should be closed when user clicks anywhere outside of the pop up. |  | Rushikesh | 2/3/2023: Retested and closed successfully
7 | UP | TT_UP_7 | 1/27/2023 | 1 High | 2 Medium | Profile | Your Profile | Closed | Functional | 2.User is not able to update the profile picture when clicked on dummy user image. |  | Rushikesh | 2/3/2023: Retested and closed successfully
8 | UP | TT_UP_8 | 1/27/2023 | 2 Medium | 2 Medium | Profile | Your Profile | Closed | Observation | 3.Contact no and whats app field doesn’t support for copy paste. |  | Rushikesh | 2/3/2023: Retested and closed successfully
9 | UP | TT_UP_9 | 1/27/2023 | 3 Low | 3 Low | Profile | Your Profile | Closed | Observation | While entering new password should be display error warning message like “your password should be at least 8 characters” |  | Rushikesh | 2/3/2023: Retested and closed successfully
10 | UP | TT_UP_10 | 1/27/2023 | 1 High | 1 High | Profile | Your Profile | closed | Functional | While changing the password system accepting old password |  |  |  | Resolved
11 | UP | TT_UP_11 | 1/27/2023 | 0 Blocker | 1 High | Profile | Your Profile | Closed | Functional | 6.When new password and confirm password is different and user clicked on update it displays “password updated ”pop up. |  | Rushikesh | 2/3/2023: Retested and closed successfully
12 | UP | TT_UP_12 | 1/27/2023 | 1 High | 2 Medium | Profile | Your Profile | Closed | Functional | 1.Profile is not displayed. |  | Rushikesh | 2/3/2023: Retested and closed successfully
13 | UM | TT_UM_13 | 1/27/2023 | 0 Blocker | 1 High | User Master | Add User | closed | Functional | 2.While editing the user, unable to add the department as “+” icon not there. It is expected Beside ‘Make Default’ there should be provision to add the department. |  | Rushikesh
14 | UM | TT_UM_14 | 1/27/2023 | 1 High | 3 Low | User Master | Edit User | closed | Functional | Contact number accepting as all 10 digit as ‘0’. it is expected as only accept 1to 9 digit and zero can be accepted at last digit. |  | suresh
15 | UM | TT_UM_15 | 1/27/2023 | 1 High | 3 Low | User Master | Edit User | Closed | Functional | 4.WhatsApp Number : Editable and allows user to enter more than 10 digits. It is accepting all ten digits as ‘0’. Expected result - it should accept 10 digits - 1 to 9 digit and zero can be accepted at last digit. |  | Suresh
16 | RM | TT_RM_16 | 1/27/2024 | 3 Low | 3 Low | Menu Management |  | closed |  | In menu management system upon click on Submit button , user get ire-relevant error “ Role or Tenant not found” |  | Rushikesh
17 | RM | TT_RM_17 | 1/27/2023 | 2 Medium | 2 Medium | Menu Management |  | Under Discussion | Functional | System is allowing to select child master (sub module ) however parent master ( module ) is not selected. It is expected if parent master is not selected then system should not allow to select child master .
18 | RM | TT_RM_18 | 1/27/2023 | 1 High | 1 High | Menu Management |  | closed | Functional | In case of user logged in and the user has all masters & menu access , if somebody revoke the access , still user allowed to see the masters . it is expected that user should not allow to view the masters. |  | Rushikesh
19 | UP | TT_UP_19 | 1/27/2023 | 2 Medium | 2 Medium | Login | Reset password | closed | Functional | On reset password screen , New Password & Confirm password field values are displayed. It should be masked and provide the provision to user to view by clicking “eye icon” if user wish. |  | Rushikesh
20 | LG | TT_LG_20 | 1/27/2023 | 1 High | 1 High | Login | Reset password | Fixed 2/23/2023 | Functional | I have created 2 users with same email id hence while resetting the pwd system has changed the password of last login user and allowed to login with changed password . However for 2nd user ( having the same email id ) does not allowed to login with changed password howevernor with old password user able to login . Please look into this on priority. |  | Rushikesh
21 | UM | TT_UM_21 | 1/27/2023 | 2 Medium | 3 Low | User Master | Create user | closed | Functional | User getting instruction and error simultaneously for one field. It is expected that user get error once the focus goes to other field. |  | Rushikesh
22 | UM | TT_UM_22 | 1/27/2023 | 2 Medium | 3 Low | User Master | Create user | closed | Functional | 10.Same issue observed for password field as well.( With respect to above) |  | Rushikesh
23 | UM | TT_UM_23 | 1/27/2023 | 2 Medium | 3 Low | User Master | Create user | closed | Functional | 11.For Pincode: user has not yet finished the pincode entry and system throwing error. Let user to finish the pincode then system throwing error seems to be meaningful. |  | Rushikesh
24 | UM | TT_UM_24 | 1/27/2023 | 2 Medium | 3 Low | User Master | Create user | closed | Functional | 12.Address field accepting unlimited characters , |  | Rushikesh
25 | UM | TT_UM_25 | 1/27/2023 | 1 High | 1 High | User Master | Grid View | Closed | Functional | 13. It has been observed that while creating the 3 user with same name ,the latest user is only displayed in grid view expected all users get displayed . |  | Rushikesh | Business Rule
26 | CNM | TT_CNM_26 | 1/30/2023 | 1 High | 3 Low | Country Master | Grid View | closed | UI | Grid view always changed column width vary time to time, it is expected to display at one glance all column values |  | Rushikesh
27 | UM | TT_UM_27 | 1/30/2023 | 3 Low | 3 Low | User Master | Edit User | closed | Functional | User Master, While Edit and Add user , country drop down list values are not sorted in ascending order |  | Rushikesh
28 | CM | TT_CM_28 | 1/30/2023 | 3 Low | 3 Low | Customer Master | edit Customer | closed | Functional | Customer Master, While Edit and Add user , country drop down list values are not sorted in ascending order |  | Rushikesh
29 | UM | TT_UM_29 | 1/30/2023 | 2 Medium | 3 Low | User Master | Edit User | Fixed - 2/15/2023 Retest - 2/16/2023-closed | Functional | While trying to change the department at edit user screen , system is not allowing . ( No action reaction seen after click on submit button) 1. select user for Edit 2. change the department 3. click on Submit button |  | Rushikesh |  | 2/15/2023: Suresh will pick up today
30 | CM | TT_CM_30 | 1/30/2023 | 1 High | 1 High | Tickets | Create Ticket | closed | Functional | Deactivated Query still reflecting in Query list box while create Ticket. |  | Rushikesh | 2/14/2023:-Retested and closed successfully.
31 | UM | TT_UM_31 | 1/31/2023 | 1 High | 2 Medium | User Master | Search | reopen Fixed - 2/15/2023 Retest - 2/16/2023-closed | Functional | Export function is not working properly. we have filtered the records with search string as "Preeti" , result received 1 record however upon export records recived 1 record with wrong values such as Sr no - , Name & Email field are populated with values as "undefined" |  | Rushikesh |  | 2/15/2023: Suresh will pick up today
32 | ALM | TT_ALM_32 | 1/31/2023 | 1 High | 2 Medium | All Master | Search | Partially fixed | Functional | Export function is not working properly.for All master. |  | Rushikesh |  | User master:-- Ticket type show values are not populating in downloaded file.
33 | TM | TT_TM_33 | 1/31/2023 | 3 Low | 3 Low | Tenant Master | Add Tenant | closed | UI | While trying to Add tenant , system opens Edit Tenant screen |  | Rushikesh
34 | TM | TT_TM_34 | 1/31/2023 | 2 Medium | 2 Medium | Tenant Master | Add Tenant | closed | Functional | While trying to Add tenant , Tenant Name Field not accepting space and number character. This field should support number and space character |  | Rushikesh | 2/14/2023:-Retested and closed
35 | CT | TT_CT_35 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Create Ticket | Reopen | Functional | When ticket is passed by authorized person notification is not received to entry user. |  |  |  | Resolved
36 | CT | TT_CT_36 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Edit Ticket | Reopen Fixed - 2/15/2023 Retest - 2/16/2023-closed | Functional | After passing a ticket by authorized person when “assigned to” person is trying to edit that ticket “entry user” field name is displaying empty. It is expected that ticket creator name should be displayed. |  | Rushikesh | 2/14/2023:-Retested and reopen | 2/15/2023: Suresh will pick up today
37 | CT | TT_CT_37 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Edit Ticket | closed | Functional | After passing a ticket by authorized person when “assigned to” person is trying to edit that ticket “project”, “Module”, and “Sub module” drop downs are not available. |  | Rushikesh | 2/14/2023:-Retested and closed
38 | CT | TT_CT_38 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Edit Ticket | Not a Bug | Functional | ”Business Analyst”, “Developer”, and “Tester” drop-downs are at “Edit Ticket” page is not required to display. |  | Rushikesh
39 | CT | TT_CT_39 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Edit Ticket | Not a Bug | Functional | After passing a ticket “assigned to” person is not able to assign the ticket to another user because “Assign to user” drop down is not available on “Edit ticket” page. |  | Rushikesh
40 | CT | TT_CT_40 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Edit Ticket | Reopen Fixed - 2/16/2023 | Functional | “Assigned to ” person is not able to delete the attachment on “Edit ticket” page. please note while editing only few files has been attached and out of that one file tried to remove however systen not allowed to do so |  | Rushikesh | 2/14/2023:-Retested and reopen | 2/15/2023: Suresh will pick up today
41 | CT | TT_CT_41 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Edit Ticket | closed | Functional | ”Expected solve date” field accepts wrong date. |  | Rushikesh | 2/14/2023:-Retested and closed
42 | CT | TT_CT_42 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Edit Ticket | closed | Functional | ”Assigned to” person is not able to edit the ticket because “project”, “module”, and “sub module” fields are mandatory which drop downs are not available to select the value. |  | Rushikesh | 2/14/2023:-Retested and closed
43 | CT | TT_CT_43 | 1/31/2023 | 2 Medium | 2 Medium | Ticket | Create Ticket | Closed | Functional | When user is trying create a new ticket and clicked on submit it displays alert pop up message “Please select customer” which is irrelevant. |  | Rushikesh
44 | CSM | TT_CSM_44 | 2023-02-01 | 2 Medium | 2 Medium | Customer Mapping | Create Customer Mapping | closed | Functional | While creating customer mapping On “Create Customer Mapping” page when user selects “Customer Type” drop down should be displayed active customer types only. |  | Rushikesh | 2/14/2023:-Retested and closed
45 | CST | TT_CST_45 | 2023-02-01 | 2 Medium | 2 Medium | Master | Customer Type | Defect Not Replicate | Functional | When user is trying to deactive any customer type it displays error message.”Customer type already exists.” |  | Rushikesh
46 | QM | TT_QM_46 | 2023-02-01 | 2 Medium | 2 Medium | Query Type Master | Add Query | Closed | Functional | when user is trying to deactive “query type” it is displaying alert pop up message “Please select form” even “select form” filed is optional. |  | Rushikesh
47 | QM | TT_QM_47 | 2023-02-01 | 2 Medium | 2 Medium | Query Type Master | Add Query | Not a Bug | Functional | when any error pop up message displays it is not required to display URL on pop up. |  | Rushikesh
48 | CSM | TT_CSM_48 | 2023-02-01 | 2 Medium | 2 Medium | Customer Mapping | Create Customer Mapping | Not a bug | Functional | User can select any form which is not against any query type. Consider a scenario:-- if user selects form “testing ”before selecting “query type” and after he selects query type “Program management” and form “testing” is not mapped against “program management” still it doesn’t display any error warning message. |  | Rushikesh
49 | CSM | TT_CSM_49 | 2023-02-01 | 2 Medium | 2 Medium | Customer Mapping | Filter | Reopen | Functional | When user clicks “Reset” button it displays irrelevant message “Record inserted”. |  | Rushikesh
50 | CSM | TT_CSM_50 | 2023-02-01 | 2 Medium | 2 Medium | Create Mapping Setting | Edit | Reopen | Functional | When user want to edit the user in “select user” field can not able to update. It displays alert that “Record not updated” . |  | Rushikesh
51 | CSM | TT_CSM_51 | 2023-02-01 | 2 Medium | 2 Medium | Create Mapping Setting | Edit | Closed | Functional | when user clicks on edit active and deactive radio buttons are displaying deselected. And when user wants to update the status it is not getting update. |  | Rushikesh
52 | CSM | TT_CSM_52 | 2023-02-01 | 2 Medium | 2 Medium | Customer Mapping | Grid View | closed | Functional | “created at” column doesn’t display date and time when record is created. |  | suresh
53 | CSM | TT_CSM_53 | 2023-02-01 | 2 Medium | 2 Medium | Customer Mapping | Grid View | closed | Functional | “created by” column displays random value it is expected that it should be displayed created by person name. |  | Suresh
54 | DFD | TT_DFD_54 | 2023-02-02 | 2 Medium | 2 Medium | Dyanic Form dropdown | Add dropdown | closed | Functional | Dropdown Name field accepting unicode characters |  | Rushikesh
55 | RM | TT_RM_55 | 2023-02-02 | 1 High | 1 High | Role Master | Add Access | closed | Functional | As delete functionality not yet developed in the system against User master hence kindly display it as disabled. | Priyanka | Rushikesh |  |  | 2023-02-08
56 | BT | TT_BT_56 | 2023-02-02 | 3 Low | 3 Low | Bill Transaction | Left side menu | Reopen | UI | "Bill checking transaction" sub menu text should be aligned |  | Rushikesh
57 | MT | TT_MT_57 | 2023-02-02 | 2 Medium | 2 Medium | Ticket | My Ticket | closed | Functional | when ticket creator is trying to confirm the ticket and clicked on “NO” it displays blank page. |  | Rushikesh | 2/15/2023:-Retested and closed.
58 | MT | TT_MT_58 | 2023-02-02 | 3 Low | 3 Low | Ticket | My Ticket | Closed | Functional | Ticket history:-- “Created at” and “updated at” values are not showing proper. |  | Rushikesh
59 | CT | TT_CT_59 | 2023-02-02 | 2 Medium | 2 Medium | Ticket | Create Ticket | Not a bug | Functional | .when we select bulk uploading it displays unnecessary alert pop up message”Select department and query type” though Department auto selected and Query Type value already selected |  | Rushikesh
60 | MT | TT_MT_60 | 2023-02-02 | 1 High | 1 High | Ticket | My Ticket | Data issue | Functional | When user edits a ticket “Assigned to user” drop down doesn’t display assigned to person name. Note:--This issue is not replicating in live. | Priyanka | Rushikesh
61 | MT | TT_MT_61 | 2023-02-02 | 1 High | 2 Medium | Ticket | Basket | reopen | Functional | When basket owner have access to play and pause the task of assigned users then when it is group task he is not able to play and pause the same task. | Priyanka | Rushikesh |  |  | 2023-02-08 | Sheet3!A95
62 | MT | TT_MT_62 | 2023-02-02 | 1 High | 2 Medium | Ticket | Basket | reopen | Functional | 5. When basket owner has created task for 3 people and he is not part of that task still he can play the and pause the task. It is expected that he should not be having authority to play the task or group activity of another user. He should be able to review task timings. | Priyanka | Rushikesh |  |  | 2023-02-08 | Sheet3!A120
63 | MTR | TT_MTR_63 | 2023-02-02 | 1 High | 1 High | Ticket | Regularization | closed | Functional | Regularization request is not received to ticket owner. | Priyanka | Rushikesh |  |  | 2023-02-08
64 | MTT | TT_MTT_64 | 2023-02-02 | 2 Medium | 2 Medium | Ticket | Sub-Task | closed | Functional | When user creates sub task under any task it displays previously added task. It is expected that when we add new sub task field should be cleared. |  | Rushikesh | 2/15/2023:-Retested and closed.
65 | MTT | TT_MTT_65 | 2023-02-02 | 2 Medium | 2 Medium | Ticket | Task | backend issue Partially fixed:--2/23/2023 | Functional | When user has created group task and it played for two people. Still total worked hours doesn’t reflect in user task report. |  |  | total worked time is reflecting but it doesnt display to both assigned users login. | Solved 23-02-2023
66 | MT | TT_MT_66 | 2023-02-03 | 3 Low | 3 Low | Ticket | Edit Ticket | closed | Functional | While Edit Ticket - submit the ticket without expected Solve date , system redirected focus to Expected solve date however user not acknowledged with any error message . If user get any user friendly message. This would be great. | Preeti | Rushikesh | 2/15/2023:-Retested and closed.
67 | MT | TT_MT_67 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | Edit Ticket | Under Discussion | Functional | Edit Ticket : Attached multiples files are not visible. | Preeti | Rushikesh
68 | CT | TT_CT_68 | 2023-02-03 | 1 High | 1 High | Ticket | Create Ticket | Closed (Conditional Based) | Functional | Deactive user is able to create the ticket. | Preeti | Rushikesh | 2/21/2023: Session need to be kill.
69 | UM | TT_UM_69 | 2023-02-03 | 3 Low | 3 Low | User Master | Edit User | reopen Fixed - 2/15/2023 Retest - 2/16/2023-closed | Functional | Edit user - Confirm Password field -password is not visible though click on eye button. | Preeti | Rushikesh | 2/7/2023: Retested and reopen as it is not working | 2/15/2023: Suresh will pick up today
70 | MT | TT_MT_70 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket - Export | Partially Fixed | Functional | While export it has been observed that On screen total ticket displays as 6 however while exporting 1.Total rows count is 20 however on screen it is 6. 2.the ticket number displayed on screen /page is different than export. 3.The status field value is mis match CUID depicted in Export sheet and is not present in Screen | Preeti | suresh | 2/17/2023: While export Created by me tab, - 3 rows extra has been seen ( preetib) at screen it was 118 however at export it is 121
71 | MT | TT_MT_71 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket - Export | Partially Fixed | Functional | With respect to above 5. Column heading not visible properly. | Preeti | Rushikesh | 2/17/2023: Your task -Assign To Dept heading not visible properly
72 | MT | TT_MT_72 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket - Export | Closed | Functional | 6.Search Result page coulmn header and Column values are not aligned properly same issue for other tabs as well ( Created by me, Department wise, Your task, Unpassed Ticket) | Preeti | Rushikesh
73 | MT | TT_MT_73 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket - Export | Closed | Functional | 7. Priority values need to be displayed with background colour in same size. | Preeti | Rushikesh
74 | MTB | TT_MTB_74 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Basket | Reopen | Functional | 1.While creating basket user is not able to select owner from dop down because drop down is not visible | Priyanka | Rushikesh
75 | MTB | TT_MTB_75 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Basket | Reopen | Functional | While creating basket start date field is accepting greater date than end date. Need validation to start date and end date. | Priyanka | Rushikesh |  | 2/14/2023: Fied by Suresh | 2023-02-08
76 | MTB | TT_MTB_76 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Basket | Closed | Functional | Basket Name, select user, start date and end date are mandatory fields are not having mandatory star mark. | Priyanka | Rushikesh |  | 2/14/2023: Fied by Suresh | 2023-02-08
77 | MTB | TT_MTB_77 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Basket | reopen | Functional | Added baskets are not arranged properly When screens size gets reduces basket alignment not arranged properlysqueeze | Priyanka | Rushikesh |  | 2/15/2023 : Suresh will look into this | 2023-02-08
78 | MTT | TT_MTT_78 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | Reopen | Functional | While creating task end date picker should not be accept smaller date than start date. | Priyanka | Rushikesh |  | 2/14/2023: Fied by Suresh | 2023-02-08
79 | MTT | TT_MTT_79 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | Data issue (Query Type ) | Functional | Edit ticket:--- when user is trying to assign ticket to another user that time it displays unnecessary error “Request error” message. | Priyanka |  |  | resolved
80 | MTBU | TT_MTBU_80 | 2023-02-06 | 1 High | 1 High | Ticket | My Ticket -Bulk upload | Backend Issue | Functional | For bulk upload , System showing incorrect values for bulk upload , Through CSV user has provided the Priority field value as " High" however system displaying it as " Medium" | Preeti |  |  | Solved 23-02-2023... Done from backend side
81 | MT | TT_MT_81 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Export | Closed | Functional | My Ticket , Export functionality is not working properly Upon Export it has been observed that export data is a subset of search result. | Preeti | suresh
82 | MTT | TT_MTT_82 | 2023-02-03 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | New | Functional |  | Priyanka
83 | MT | TT_MT_83 | 2023-02-03 | 3 Low | 3 Low | Ticket | My Ticket | Suggestion |  | Description alignment should be either left / right or justifable aligned . It is central aligned. | Priyanka
84 | MTT | TT_MTT_84 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | closed | Functional | when basket owner has created task to another user and he is not able to see "create task" option in "your task" tab. | Priyanka |  |  |  | 2023-02-08
85 | MT | TT_MT_85 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | Backend Issue | Functional | When task status is “In_Progress” it doesn’t reflect in basket owner’s login. It displays “not started”. | Priyanka |  |  | Bug not found
86 | UTR | TT_UTR_86 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | User Task Report | closed | Functional | Search task:-->search functionality is not working using enter key button. | Priyanka | suresh |  |  | 2023-02-08
87 | MTT | TT_MTT_87 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | closed | Functional | when we make “group activity” of already created task “play pause” button is getting removed. | Priyanka | Rushikesh |  |  | 2023-02-08
88 | MTT | TT_MTT_88 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | Closed | Functional | “status” doesn’t update when user played the task. | Priyanka |  |  | Resolved
89 | MTT | TT_MTT_89 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | Backend issue reopen-2/23/2023 Retested -2/24/2023 Closed-2/24/2023 | Functional | “Total worked hours” are displays different that actual. | Priyanka |  | 2/23/2023: Retested and failed. | Solved
90 | MTT | TT_MTT_90 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | Closed | Functional | “from” and “to date” field need validation. To date field accepts smaller date than from date. | Priyanka | Rushikesh |  | 2/14/2023: Fied by Suresh | 2023-02-08
91 | UTR | TT_UTR_91 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | User Task Report | Backend Issue | Functional | Total worked hours doesn’t update when user has played the task second time. | Priyanka |  |  | Solved 23-02-2023
92 | UTR | TT_UTR_92 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | User Task Report | closed | Functional | “updated at” column is not displaying time and date when anything is upadted in task. | Priyanka | Rushikesh |  |  | 2023-02-08
93 | UTR | TT_UTR_93 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | User Task Report | Not a Bug | Functional | Search filter is not working according to date. | Priyanka | Rushikesh |  | Its Complete working when checked
94 | UTR | TT_UTR_94 | 2023-02-06 | 2 Medium | 2 Medium | Ticket | export | closed | Functional | filtered record doesn’t export all data is exported in file. | Priyanka | suresh | 2/14/2023:-Retested and closed successfully. |  | 2023-02-08
95 | CTBU | TT_CTBU_95 | 2023-02-06 | 1 High | 1 High | Ticket | Create Ticket - Bulk Uploading | Backend Issue Under Disscussion | Functional | While trying to do bulk upload user getting error as " Request Error" however user followed the downloaded file format. If there is any issue how would user know the things and how can he rectify the mistake. Kindly provide the descriptive details of error in user friendly language. | Preeti | Punam | 2/23/2023: Retested and Failed. upon getting error there is no error log generated which helps the customer to understand . what went wrong. | Solved
96 | LG | TT_LG_96 | 2023-02-07 | 2 Medium | 2 Medium | Login | Login | Reopen | Functional | Incorrect Error message displayed, While trying to login through deactive user getting error as " username does not match" . If system displays " user does not exist" would be appropriate | Preeti |  |  | 2/17/2023: Now we are getting error as " Password does not match"
97 | CT | TT_CT_97 | 2023-02-07 | 1 High | 1 High | Ticket | Bulk - Upload | Backend Issue | Functional | For bulk upload Ticket creation, Assign to Field is not populated , Test data , Query Type - Program Management, User id - Preetib | Preeti | Punam | 2/23/2023: Unable to retest as with correct input as well system throwing error | Solved 23-02-2023
98 | CT | TT_CT_98 | 2023-02-07 | 1 High | 1 High | Ticket | Bulk - Upload | Backend Issue | Functional | While creating the ticket through Bulk Upload it has been observed that under department wise tab tickets created by bulk uploading are not reflecting . username - Preetib, Ticket no - same as created by me tab ( for yesterday's day ) display | Preeti | Punam | 2/23/2023: Unable to retest as with correct input as well system throwing error | Solved 23-02-2023
99 | UM | TT_UM_99 | 2023-02-07 | 1 High | 1 High | Master | My Ticket -Departmentwise | backend issue | Functional | I have added Ticket type show as Department wise as well as My Ticket however Departmentwise tab still not reflecting against username ( Preetib) | Preeti |  |  | Confirmation Required
100 | MT | TT_MT_100 | 2023-02-07 | 3 Low | 3 Low | Ticket | My Ticket - Your task | Reopen | Functional | Description field is seems to be central aligned , please make it left aligned and maintained constitancy through all tabs at my Ticket tabs | Preeti | Rushikesh
101 | DB | TT_DB_101 | 2023-02-07 | 3 Low | 3 Low | Dashboard | Upcoming Task | Not a bug | Functional | While continuously click twice on task , the 1st task stop playing as expected however next task started playing. | Preeti
102 | VR | TT_VR_102 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | backend issue | Functional | last updated time is not displaying proper. | Priyanka |  |  | FrontEnd
103 | VR | TT_VR_103 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | Backend issue | Functional | A task got delayed so after editing task hours greater than "Actual worked hours", in variance report status is changed from "Delayed" to completed. | priyanka |  |  | FrontEnd
104 | MT | TT_MT_104 | 2023-02-07 | 2 Medium | 2 Medium | Ticket | My Ticket - Search | Confirmation Needed | Functional | While selecting User , Department drop show should display department against mapped with user not displayed all. | Preeti |  |  | Need to confirm that whether it is required or not
105 | VR | TT_VR_105 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | Backend issue | Functional | A "group activity" of 2 users but it has played only one user still it is displaying same "Actual working hours" for both the users. | Priyanka
106 | MT | TT_MT_106 | 2023-02-07 | 2 Medium | 1 High | Ticket | My Ticket - Search | Closed | Functional | In Search Result View , Query Type Field is not populating | Preeti | Suresh
107 | MT | TT_MT_107 | 2023-02-07 | 1 High | 1 High | Ticket | My Ticket - Search | closed | Functional | In Search Result View , if result grid displays 3 record then user get ticket edit option however if more than 3 records then edit option is not avilable | Preeti | Rushikesh
108 | UM | TT_UM_108 | 2023-02-07 | 3 Low | 3 Low | Master | User master - Edit User | Partially Fixed | Functional | Contact number Validation is not applied for WhatsApp Number . Contact number validation should reflect for WhatsApp Number | Preeti | suresh | In reverse user selects checkbox ( same as contact no) Whatsapp no is not same as contact no | 2/14/2023: Fied by Suresh
109 | UTR | TT_UTR_109 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | Backend issue reopen-2/23/2023 | Functional | If somebody has marked to task as "completed" without playing the task, in report "Actual worked hours are displaying empty it is expected to display "00:00". | priyanka |  |  | Solved
110 | VR | TT_VR_110 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | closed | Functional | when we edit the group activity" of two people and add dependent task it doesnt display when we edit it next time. | Priyanka | Rushikesh |  |  | 2023-02-08
111 | UM | TT_UM_111 | 2023-02-07 | 2 Medium | 2 Medium | Masters | All master - Address | closed | Functional | Address Field is not accepting " Enter" key( new line). it should accept. | Preeti |  |  | 2/14/2023: Fied by Suresh
112 | VR | TT_VR_112 | 2023-02-07 | 2 Medium | 2 Medium | Reports | Variance report | Closed | Functional | While playing group activity when we clicked on "start timer" without selecting checkbox it doesnt display error warning message instead it removes the pop up. | Priyanka | Rushikesh
113 | CT | TT_CT_113 | 2023-02-07 | 2 Medium | 2 Medium | Ticket | Create Ticket - Bulk Uploading | New Fixed 2/21/2023 | Functional | For Bulk uploading though default department populated , still system throws error " please select department and Query Type" . User has to select the value from dropdown inspite of one or many department. | Preeti | Rushikesh
114 | CT | TT_CT_114 | 2023-02-08 | 3 Low | 3 Low | Ticket | Create Ticket - Bulk Uploading | New Not a Bug | Functional | For Bulk upload, user has to click 1st on 'Generate Bulk Format' and then click on 'Download file' then only user can proceed for Bulk uploading. Can we omit the 'Generate Bulk format' click on step. | Preeti | Rushikesh | 2/23/2023 We have to generate files according to querytype form and that is why we have to click it 2 times | Functionality is working
115 | MT | TT_MT_115 | 2023-02-07 | 2 Medium | 2 Medium | Ticket | Manage task | Backend Issue | Functional | All task total timing are displaying wrong. | Preeti |  |  | Bug not found
116 | VR | TT_VR_116 | 2023-02-07 | 2 Medium | 2 Medium | Reports | export | partially Fixed | Functional | "Completed at" column is not present in variance report grid still it is displayed in downloaded file. |  |  |  | 2/14/2023: Fied by Suresh
117 | RP | TT_RP_117 | 2023-02-08 | 2 Medium | 1 High | Reports | Resource planning | Observation ( Seems to be performance issue) | Functional | while selecting user in "select user" dropdown it redirects to blank page. | Priyanka |  |  | 2/14/2023: Fied by Suresh
118 | RP | TT_RP_118 | 2023-02-08 | 2 Medium | 2 Medium | Reports | Resource planning | suggestion | Functional | It would be better if task name displays with "Ticket Id". | Priyanka
119 | RP | TT_RP_119 | 2023-02-08 | 2 Medium | 2 Medium | Reports | Resource planning | suggestion | Functional | It would be better if task "added by person name" will display in report.in case another user has created task for us it will be more easy to understand that who is created task. | priyanka
120 | RP | TT_RP_120 | 2023-02-08 | 2 Medium | 2 Medium | Reports | Resource planning | suggestion | Functional | suggesting that "task status" also should be display in report. | priyanka
121 | RP | TT_RP_121 | 2023-02-08 | 2 Medium | 1 High | reports | Resource planning | Closed | functional | when we selects user in "select user" field and clicked on search it doesnt display report. | priyanka |  |  | 2/13/2023: Fied by Suresh
122 | RP | TT_RP_122 | 2023-02-08 | 2 Medium | 2 Medium | reports | resource planning | closed | functional | "from date", and "to date" fields are mandatory it is not having mandatory star mark. and if user left any field empty it doesnt display error warning message. | priyanka
123 | MT | TT_MT_123 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Manage task | Reopen | functional | when we edit task it doesnt load proper "Assign to user" and dependent task field. | priyanka |  |  | 2/14/2023: Fied by Suresh |  | Sheet3!A15
124 | RP | TT_RP_124 | 2023-02-08 | 2 Medium | 2 Medium | reports | resource planning | closed | functional | user names should be dislay in ascending order in "Select user" dropdown. | priyanka |  |  | 2/14/2023: Fied by Suresh
125 | RP | TT_RP_125 | 2023-02-08 | 2 Medium | 2 Medium | reports | resource planning | reopen | functional | without selecting "select user" if filter the records according to date user names are not displayed in proper order. | priyanka |  |  | 2/14/2023: Fied by Suresh
126 | MT | TT_MT_126 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Manage Task | new Fixed 2/21/2023 | functional | not working proper while play pause the group activity. | priyanka | Rushikesh
127 | MT | TT_MT_127 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Manage task | Front End | functional | when it is "group tasks" or "group activity" it is not arrranged properly. | priyanka |  |  |  |  | Sheet3!A42
128 | MT | TT_MT_128 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Manage task | backend issue 2/21/2023 | functional | when user have multiple baskets at a time different "group activities" are playing from "differnet baskets" of same user. | priyanka | Rushikesh |  |  |  | Sheet3!A71
129 | MT | TT_MT_129 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Manage task | new Fixed 2/21/2023 | functional | When user has created task and after it is edited with "group activity" play pause functionality is not working properly. | priyanka | Rushikesh
130 | MT | TT_MT_130 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Manage task | new Fixed 2/21/2023 | functional | when "basket owner" is not part of specific task he should not be having authority to send the regularization request. | priyanka | Rushikesh
131 | CB | TT_CB_131 | 2023-02-08 | 3 Low | 3 Low | Ticket | View - Chatbot | New Fixed 2/21/2023 Closed - 2/22/2023 | UI | Send button location is different from Edit view. | Priyanka | Rushikesh
132 | CB | TT_CB_132 | 2023-02-08 | 2 Medium | 2 Medium | Ticket | Edit View - Chatbot | New Fixed 2/21/2023 Reopen - 2/22/2023 | Functional | Mention text displays Twice | Preeti | Rushikesh
133 | CB | TT_CB_133 | 2023-02-08 | 3 Low | 3 Low | Ticket | Edit View - Chatbot | New Fixed 2/21/2023 Reopen - 2/22/2023 | Functional | Text is displayed in blue colour, expected to display in black colour | Preeti | Rushikesh
134 | MT | TT_MT_134 | 2023-02-09 | 0 Blocker | 1 High | Ticket | Create Ticket | New Fixed 2/21/2023 Reopen - 2/22/2023 | Functional | While creating the ticket it has ben observed that Ticket assigned to deactive user and further journey is not progressing. | Amreen | Rushikesh | 2/22/2023: Deactive user has been restricted in customer mapping sheet however for existing ticket assigned to deactiver user development is yet to be done.
135 | CT | TT_CT_135 | 2023-02-09 | 1 High | 1 High | Ticket | Create Ticket | New Development | Functional | Throughout the system there is no provision to see who has passing authority in specific department
136 | MT | TT_MT_136 | 2023-02-09 | 1 High | 1 High | Ticket | Create Ticket | New Development | Functional | Throughout the system there is no provision to see Which department which person has Assign To Authority.
137 | MT | TT_MT_137 | 2023-02-09 | 2 Medium | 1 High | Manage task | Task planner | closed | Functional | "planner" option should not be visible for completed tasks. | Priyanka |  | 2/14/2023: Fixed by suresh |  |  | Sheet3!A147
138 | MT | TT_MT_138 | 2023-02-09 | 2 Medium | 2 Medium | Manage task | Task planner | closed | Functional | user can enter the back date in planner."date" field should be disable. | Priyanka |  | 2/14/2023: Fixed by suresh
139 | MT | TT_MT_139 | 2023-02-09 | 1 High | 2 Medium | Manage task | Task planner | Reopen | Functional | If in planner "divided task hours" and "scheduled task hours" are not equal still task is getting updated. it doesnt display warning message. | Priyanka |  | 2/14/2023: Fixed by suresh
140 | MT | TT_MT_140 | 2023-02-09 | 2 Medium | 2 Medium | Manage task | Task planner | Reopen | Functional | If it is group task and I have edited "Assigned user" and assigned same user in planner it doesnt display any error message. | Priyanka |  | 2/14/2023: Fixed by suresh
141 | CSM | TT_CSM_141 | 2023-02-09 | 2 Medium | 2 Medium | masters | Edit customer mapping | New | Functional | previously selected users are not displaying in edit customer mapping. | priyanka
142 | CSM | TT_CSM_142 | 2023-02-09 | 2 Medium | 2 Medium | masters | Edit customer mapping | New | Functional | Department wise usernames are not displaying in "select user" field. | priyanka
143 | CSM | TT_CSM_143 | 2023-02-09 | 2 Medium | 2 Medium | masters | Edit customer mapping | New | Functional | User is not able to update users in "select user" field. | priyanka
144 | CSM | TT_CSM_144 | 2023-02-09 | 2 Medium | 2 Medium | masters | create customer mapping | Front-end | Functional | while creating customer mapping even though mapping is not done it displays successful message"Record inserted." | priyanka
145 | NTF | TT_NTF_145 | 2023-02-09 | 2 Medium | 2 Medium | Ticket | Create Ticket | backend issue Fixed-2/20/2023 Closed - 2/22/2023 | Functional | Passing Authority should receive notification if any user of the same department creates ticket the and that ticket should come under his unpassed ticket list. | Amreen |  |  | Resolved
146 | NTF | TT_NTF_146 | 2023-02-09 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | Functional | When passing authority passes a ticket, ticket creator should rcv notification stating "#PassingAuthorityName has passed #TicketId" | Amreen |  | 2/22/2023: Retested and failed 2/23/2023: Retested and failed | Resolved 23-02-2023
147 | NTF | TT_NTF_147 | 2023-02-09 | 2 Medium | 2 Medium | Ticket | Notification | backend issue - 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | Functional | When passing authority unpasses a ticket, ticket creator should rcv notification stating "#PassingAuthorityName has unpassed #TicketId" | Amreen |  | 2/22/2023: Retested and failed | Resolved 23-02-2023
148 | NTF | TT_NTF_148 | 2023-02-09 | 2 Medium | 2 Medium | Ticket | Create Ticket - Notification | backend issue 2/20/2023 Closed - 2/22/2023 | Functional | Upon Basket creation, basket owner didnt receive notification #TT9144 | Amreen |  | 2/22/2023 : New Basket has been created for TT9368 | Resolved
149 | CT | TT_CT_149 | 2023-02-09 | 1 High | 1 High | Ticket | Create basket - Notification | New Fixed 2/21/2023 Reopen - 2/22/2023 Fixed2/23/2023 | Functional | Basket owner (not ticket owner) should not have access to create basket. | Amreen | Rushikesh | 2/22/2023: Retested and failed | Now its Working
150 | MT | TT_MT_150 | 2023-02-09 | 1 High | 1 High | masters | My Tickets | Closed | Functional | Unable to add create mapping setting | Preeti
151 | CSM | TT_CSM_151 | 2023-02-09 | 2 Medium | 2 Medium | masters | create customer mapping | New | Functional | According to "user is having less ticket" approach ticket is not assigning. it is assigned to person who is not selected in "select user" | Priyanka
152 | DB | TT_DB_152 | 2023-02-09 | 2 Medium | 2 Medium | dashboard | My tasks | New Fixed 2/21/2023 | Functional | task name are not displaying proper. | Priyanka | Rushikesh
153 | NTF | TT_NTF_153 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Closed - 2/22/2023 | Functional | When there are more than one Ticket Passing Authority person, notification should be sent to all Passing Authority person, it being sent to only one person. | Amreen |  | 2/22/2023: Retested Successfully and closed TT9368 | Resolved
154 | NTF | TT_NTF_154 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Closed - 2/22/2023 | Functional | Notification should be received to basket owner while creation of basket. | Amreen |  | 2/22/2023: Retested Successfully and closed TT9368 | Resolved
155 | NTF | TT_NTF_155 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | Functional | When sender mentions a user in comment, Ticket owner is not getting correct notification. Test data : Ticket owner is getting Notification : "Sender has mentioned you in TicketID" | Amreen |  | 2/22/2023: TT9368 2/23/2023: TT9377 | Resolved 23-02-2023
156 | NTF | TT_NTF_156 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen- 2/23/2023 | Functional | Assigned to person is not receiving notification upon ticket assigning, when Assign to person assigns it to other person. | Amreen |  |  | Resolved 23-02-2023
157 | NTF | TT_NTF_157 | 2023-02-10 | 1 High | 1 High | Ticket | Notification | New Need to discuss 2/20/2023 | Functional | Upon creation of ticket where selecting query as "New Implementation" , Ticket not displaying at New Implementation user login. Test data : TT9172 | Amreen
158 | MT | TT_MT_158 | 2023-02-10 | 2 Medium | 2 Medium | Tickets | My tickets | New Need to discuss 2/20/2023 | Functional | Though passing authority passed the ticket however it is not reached to Assign To person bucket | Priyanka
159 | MTB | TT_MTB_159 | 2023-02-10 | 1 High | 1 High | Ticket | Basket | closed | Functional | created baskets doesnt display. | priyanka |  |  | Retested By Rushikesh and its Working
160 | MTB | TT_MTB_160 | 2023-02-11 | 1 High | 1 High | Ticket | Basket | New Fixed 2/23/2023 | Functional | user can create basket in another user's ticket. | priyanka | Rushikesh
161 | NTF | TT_NTF_161 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification displayed on Notificatios page and under notification bell icon are different. | Amreen
162 | NTF | TT_NTF_162 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Chnages made on notification same should reflect on notification bell icon displaying different | Amreen
163 | PM | TT_PM_163 | 2023-02-10 | 2 Medium | 2 Medium | Project master | Edit Project | New Fixed - 2/15/2023 Reteste-2/16/2023-closed | Functional | At project Master, Upon Edit, user field not populated
164 | PM | TT_PM_164 | 2023-02-10 | 2 Medium | 2 Medium | Project master | Edit Project | New Fixed - 2/15/2023 Reteste-2/16/2023-reopen | Functional | At project Master, Upon Edit, Description field not accepting Enter
165 | PM | TT_PM_165 | 2023-02-10 | 2 Medium | 2 Medium | Project master | Edit Project | New Fixed - 2/15/2023 Closed - 2/17/2023 | Functional | At project Master, Upon Edit, user field not populated
166 | NTF | TT_NTF_166 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | Functional | Upon task creation, ticket owner not getting notification message. | Amreen |  | 2/22/2023: Retested Successfully and Reopened TT9368 | Resolved 23-02-2023
167 | NTF | TT_NTF_167 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | Functional | Upon task creation for muliple user, task owners not getting notification message. | Amreen |  | 2/22/2023 : Monika kolpe has been created task for TT7400 and assigned to Amreen Shaikh -- TT received wrong , testing done on TT9368 | Resolved 23-02-2023
168 | NTF | TT_NTF_168 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Task | New Fixed - 2/21/2023 Reopen - 2/22/2023 | Functional | Upon task creation for mutiple user, task should be displayed all the user added under that task. Not displaying to all user. It is being displayed to only task owner. | Amreen
169 | CT | TT_CT_169 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Create Ticket |  |  | Project field is not associated with Create Ticket action however it is available with Edit action. In such case how would project owner get notified with ticket creation
170 | NTF | TT_NTF_170 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon clicking on to the notification it should redirect to respective page. | Amreen
171 | NTF | TT_NTF_171 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | Functional | Upon group activity creation, task owner not getting notification message. | Amreen |  | 2/22/2023 : Monika Kolpe has been created task for TT7400 and assigned to Amreen Shaikh -- TT id received wrong , testing done on TT9368, this is group activity --however notification says task | Resolved 23-02-2023
172 | NTF | TT_NTF_172 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New Fixed 2/22/2023 | Functional | In Your notification page -> Clear all option should be added | Amreen | Rushikesh |  | Not Resolved
173 |  | TT__173 | 2023-02-10 | 0 Blocker | 1 High | Code Deployment |  | New Closed | Functional | unstable environment getting so many issues, customer mapping create -edit, ticket create -edit, ticket creation ( things related to query mapping) - it seems to impact of yesterdays new code deployment
174 | PM | TT_PM_174 | 2023-02-10 | 1 High | 2 Medium | Ticket | Notification | backend issue 2/20/2023 | Functional | Project Owner not getting Ticket update related notification Project - Ticketing System, project owner - Preeti12(username) | Preeti |  |  | Development Not Done
175 | PM | TT_PM_175 | 2023-02-10 | 1 High | 2 Medium | Ticket | Notification | backend issue 2/20/2023 | Functional | Project owner won't get ticket creation notification as this field is not part of ticket create | Preeti |  |  | Development Not Done
176 | NTF | TT_NTF_176 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | Functional | Ticket owner not getting notification for task assigned to multiple users | Amreen |  | 2/22/2023: Retested and failed -- TT9368 | Resolved 23-02-2023
177 | NTF | TT_NTF_177 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New Need to discuss 2/20/2023 | Functional | Notification page -> all notification should dsiplay only recent 20 notifications are being displayed | Amreen | Rushikesh | 2/22/2023: need to discuss wth Monica abt its execution, Whether at one glance only 20 will displayed and upon clear another 20 will displayed
178 | NTF | TT_NTF_178 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | New Need to discuss 2/20/2023 | Functional | Notification page -> Page scroll bar not added | Amreen | Rushikesh | 2/22/2023: need to discuss wth Monica abt its execution, Whether at one glance only 20 will displayed and upon clear another 20 will displayed
179 | NTF | TT_NTF_179 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | Functional | Task completion notification not being sent to ticket owner | Amreen |  | 2/22/2023: Retested and failed -- TT9368 | Resolved 23-02-2023
180 | NTF | TT_NTF_180 | 2023-02-10 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | Functional | Mulple user -> task completion notification not being sent to to all user in that task | Amreen |  | 2/22/2023: Retested and failed -- TT9368 | Resolved 23-02-2023
181 | NTF | TT_NTF_181 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Closed - 2/22/2023 | Functional | Upon task creation, ticket owner not getting proper notification message. "Task has been assigned by Amreen Shaikh for TT9161". It should display "Task has been created by Amreen Shaikh for TT9161" | Amreen |  | 2/22/2023: Retested successfuly and closed | Resolved
182 | MT | TT_MT_182 | 2023-02-10 | 1 High | 1 High | Ticket | Edit Ticket | backend issue 2/20/2023 | Functional | User won't get OTP through WhatsApp and SMS channel | Preeti
183 | MT | TT_MT_183 | 2023-02-10 | 1 High | 1 High | 1 High | Edit Ticket | New Fixed - 2/16/2023 | Functional | While edit the ticket , if user changed the status from unsolved to Reject or other than Solved status, user gets Error " Request Error" | Preeti
184 | NTF | TT_NTF_184 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Partially fixed - 2/22/2023 | Functional | Notification is not being sent to ticket owner when any changes have been made in the Basket | Amreen |  | 2/22/2023 : Basket ID 3262 some changes has been done by Monika Kolpe --TT9368 | Resolved 23-02-2023
185 | MT | TT_MT_185 | 2023-02-10 | 3 Low | 3 Low | Ticket | Edit Ticket | New Fixed 2/22/2023 | Functional | For Solved Tickets, through Search Edit option is available however there is no submit button. For Solved tickets only view option should available and Comment section should not be there | Preeti | Rushikesh
186 | NTF | TT_NTF_186 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Partially fixed - 2/23/2023 | Functional | Notification is not being sent to ticket owner when any changes have been made in the Task | Amreen |  | 2/22/2023: Retested and Failed 2/23/2023: Receiving same message twice (ticket owner, task owner) | Resolved 23-02-2023
187 | NTF | TT_NTF_187 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Reopen-2/23/2023 | Functional | Notification is not being sent to Basket owner when any changes have been made by ticket owner in the Basket | Amreen |  | 2/22/2023: Retested and Failed | Resolved 23-02-2023
188 | NTF | TT_NTF_188 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 Reopen - 2/22/2023 Closed-2/23/2023 | Functional | Notification is not being sent to Task owner when any changes have been made by basket owner / ticket owner in the Task | Amreen |  | 2/22/2023: Retested and Failed 2/23/2023: Closed | Resolved 23-02-2023
189 | NTF | TT_NTF_189 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue 2/20/2023 | Functional | Notification is not being sent to ticket owner and task owner when any task been pending. | Amreen |  |  | Differ
190 | NTF | TT_NTF_190 | 2023-02-11 | 1 High | 1 High | Ticket | Notification | backend issue 2/20/2023 Reopen- 2/22/2023 | Functional | Notification is not being sent to ticket creator after masking ticket status as SOLVED. | Amreen |  | 2/23/2023: Retested and failed | Solved 23-02-2023
191 | CSM | TT_CSM_191 | 2023-02-11 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | Closed | Functional | Unable to edit the Customer Mapping | Preeti
192 | CSM | TT_CSM_192 | 2023-02-11 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | backend issue 2/20/2023 | Functional | System is allowing to create twice customer mapping with same Query and Department combination . How would system knows which approch needs to apply for ticket creation of specific department. Here Testing9027(Query) and IT testing(Department) with Approach - Ratio wise Testing9027(Query) and IT testing(Department) with Approach - Having Less Ticket | Preeti |  |  | Confirmation Required
193 | CSM | TT_CSM_193 | 2023-02-11 | 1 High | 1 High | Customer Mapping | Grid View | New Need to discuss 2/20/2023 | Functional | Approach name displayed in abbreviated form. | Preeti
194 | CSM | TT_CSM_194 | 2023-02-11 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | New Need to discuss 2/20/2023 | Functional | With Ratio Wise Customer mapping approach - Tickets are assigned to wrong person which are not included in the user list | Preeti
195 | CSM | TT_CSM_195 | 2023-02-11 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | New Fixed 2/22/2023 Reopen-2/23/2023 | Functional | Systeem allowing to do customer mapping with deactive user. In user select box - along with active user deactive user also populated. | Preeti | Rushikesh | 2/23/2023: Still we are able to see Deactive user in "select user" option
196 | CSM | TT_CSM_196 | 2023-02-11 | 3 Low | 3 Low | Customer Mapping | Create Customer Mapping | New | Functional | Though total ratio is 100% , still it is showing error “ Total should be 100” | Preeti
197 | CSM | TT_CSM_197 | 2023-02-11 | 3 Low | 3 Low | Customer Mapping | Create Customer Mapping | New | Functional | Ratio Wise - Total - displays 'Nan' instead of numerical figure. | Preeti
198 | MT | TT_MT_198 | 2023-02-11 | 1 High | 1 High | My Ticket | Created by me or Department wise | New Fixed - 2/23/2023 Closed - 2/23/2023 | Functional | Though customer has Ticket Type show , my Tickets or Department Tickets , user can see only Created by me tab only | Preeti
199 | NTF | TT_NTF_199 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue - 2/20/2023 | Functional | Buffer notifications is not being sent to task owner before the deadline to finish the task | Amreen |  |  | Confirmation Required
200 | NTF | TT_NTF_200 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue - 2/20/2023 | Functional | Buffer notifications is not being sent to Ticket owner before the deadline to finish the task | Amreen |  |  | Confirmation Required
201 | NTF | TT_NTF_201 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue - 2/20/2023 | Functional | Buffer notifications is not being sent to Basket owner before the deadline to finish the task | Amreen |  |  | Confirmation Required
202 | NTF | TT_NTF_202 | 2023-02-11 | 2 Medium | 2 Medium | Ticket | Notification | backend issue - 2/20/2023 | Functional | Buffer notifications is not being sent to Ticket owner before the deadline to finish the task | Amreen |  |  | Confirmation Required
203 | MT | TT_MT_203 | 2023-02-13 | 1 High | 1 High | My Task | Edit Basket/Task | New Fixed 2/23/2023 | Functional | Upon task creation for any other user, it been observed that other user have authority to create basket and new task, for other user create basket / create task should be disabled. |  | Rushikesh
204 | UM | TT_UM_204 | 2023-02-13 | 2 Medium | 2 Medium | User master | Departments | Not a bug | Functional | when user edit the department updated changes are not reflecting in edit user "Departments". | Priyanka
205 | RM | TT_RM_205 | 2023-02-13 | 2 Medium | 2 Medium | role master | edit role | New Deffred 2/22/2023 | Functional | if any role is deactivated it removes in "user master" who have already assigned. | Priyanka | Rushikesh |  | In Role history we user can see the details of user but that also have to develop and it is not possible to show both active and deactive user in same dropdown hence this bug is marked as Deffred
206 | UM | TT_UM_206 | 2023-02-13 | 2 Medium | 2 Medium | User master | Edit user | New Fixed -2/15/2023 Retest-2/16/2023 Closed-2/16/2023 | Functional | when we clicked on eye button of "confirm password" password field , the input visible here is similar to password field however user expected here to view Confirm password field input. | Priyanka
207 | DM | TT_DM_207 | 2023-02-13 | 2 Medium | 2 Medium | Designation master | Edit designation | New Deffred 2/22/2023 | Functional | if any designation is deactivated it removes in "user master" who have already assigned. | Priyanka | Rushikesh |  | In Role history we user can see the details of user but that also have to develop and it is not possible to show both active and deactive user in same dropdown hence this bug is marked as Deffred
208 | UM | TT_UM_208 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Add user | New | Functional | User getting instruction and error simultaneously for one field. It is expected that user get error once the focus goes to other field. | Priyanka
209 | UM | TT_UM_209 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Add User | New | Functional | while entering whats app number second time when we select checkbox "same as contact number" it doesnt reflect in "whats app number" field. | Priyanka
210 | UM | TT_UM_210 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Add User | New Fixed -2/15/2023 Retest-2/16/2023-closed | Functional | while entering "confirm password" it displays error for username field. | Priyanka
211 | UM | TT_UM_211 | 2023-02-14 | 2 Medium | 2 medium | User Master | Add User | New Fixed - 2/16/2023 Closed-2/23/2023 | Functional | user can able to add duplicate department against user. | Priyanka
212 | UM | TT_UM_212 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Add User | New Fixed -2/15/2023 Retest -2/16/2023-partially fail | Functional | When we enter wrong password it doesn't display any error warning message.and error messages are not handled properly. | Priyanka
213 | UM | TT_UM_213 | 2023-02-14 | 2 Medium | 2 Medium | User Master | Export | New | Functional | If user is having multiple departments it doesnt display in downloaded file after export. | priyanka
214 | CSM | TT_CSM_214 | 2023-02-14 | 2 Medium | 2 Medium | customer mapping | create mapping setting | New Fixed -2/15/2023 Retest -2/16/2023-reopen | Functional | "select user" dropdwon doesnt display all users in list. | priyanka | Suresh
215 | MT | TT_MT_215 | 2023-02-14 | 2 Medium | 2 Medium | My Tickets | Manage Basket | data issue | Functional | While creating basket "owner" dropdown is populating with duplicate usernames so from user's prospective it is difficult to understand whom to assign. | priyanka
216 | MT | TT_MT_216 | 2023-02-14 | 2 Medium | 2 Medium | My Tickets | Manage Basket | New | Functional | User can not able to edit basket end date. | priyanka
217 | MT | TT_MT_217 | 2023-02-14 | 1 High | 2 Medium | My Tcikets | Manage Basket | New | Functional | user can able to create backdated basket. basket date and ticket date is not synced properly. | priyanka
218 | MT | TT_MT_218 | 2023-02-14 | 1 High | 2 Medium | My Tickets | Edit Ticket | New | Functional | ticket owner can not able to assign his ticket to another user. | priyanka
219 | MT | TT_MT_219 | 2023-02-14 | 2 Medium | 2 Medium | My Tickets | Edit ticket | New | Functional | If assigned query type is deactivated still it is displaying in edit ticket | priyanka
220 | MT | TT_MT_220 | 15/02/2023 | 2 Medium | 2 Medium | Ticket | My Tickets | New | Functional | project owner can able to view all projects even though he is not owner of that project. | priyanka
221 | MT | TT_MT_221 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | My Tickets | New | Functional | Project owner doesnt have edit authority for ticket, basket and task. | priyanka
222 | MT | TT_MT_222 | 15/02/2023 | 2 Medium | 2 Medium | Ticket | Manage Basket | New Need to discuss 2/20/2023 | Functional | While creating multiple baskets user can not able to delete the basket entry. | priyanka
223 | MT | TT_MT_223 | 15/02/2023 | 2 Medium | 1 High | Ticket | Manage Basket | Backend Issue 2/23/2023 | Functional | user is not able to create multiple baskets. it displays error message "oops basket name already exists" even though the basket names are different. | priyanka
224 | UM | TT_UM_224 | 15/02/2023 | 2 Medium | 1 high | Ticket | Manage task | New Need to discuss 2/20/2023 | Functional | while creating new task it displays dependent tasks. It is expected that before adding task it should not be display dependent tasks. | Priyanka
225 | MT | TT_MT_225 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | My Tickets | New | Functional | When we filter any ticket it doesnt display action pop up properly. for example:-- after filtered records there are only 4 records are available on page. and if user want to edit last record then he can not able to view action pop up. | priyanka
226 | MT | TT_MT_226 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | Manage task | New | Functional | user can create group activity of single user. It is expected that if user want to create group activtiy it requires minimum 2 users included. | priyanka
227 | MT | TT_MT_227 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | Manage task | New | Functional | User is able to create the task greater than the Ticket "Expected Solve Date". Task end date should be less than Ticket Expected Solved date. | priyanka
228 | MT | TT_MT_228 | 15/02/2023 | 1 High | 1 High | Tickets | Manage task | New Not a Bug 2/23/2023 | Functional | newly created tasks are not displaying on dashboard.(TT9048) | priyanka | Rushikesh
229 | MT | TT_MT_229 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | Manage task | New Fixed 2/23/2023 | Functional | For created "task" and "group activities" - play & pause button not there.(TT9043) | priyanka | Rushikesh
230 | MT | TT_MT_230 | 15/02/2023 | 2 Medium | 2 Medium | Tickets | Edit Basket | Not a bug | Functional | while editing basket "select user" field is displaying empty. | priyanka | Rushikesh
231 | CP | TT_CP_231 | 22/02/2023 | 1 High | 1 High | Master | Customer mapping | New Fixed 2/23/2023 | Functional | While performing testing on customer mapping it been found that if we create new user against a new department (Customer Mapping Department). Then that user is not being displayed on customer mapping page after selecting same department (Customer Mapping Department). | Amreen | Rushikesh
232 | MT | TT_MT_232 | 22/02/2023 | 1 High | 1 High | Ticket | My Tickets -> Your Task | New Not a Bug | Functional | While ticket owner creating basket for a user, ticket and basket is not being displayed to basket owner (TT9366) . Basket Owner Priyanka Dupargude | Amreen | Rushikesh | If we create multiple usersid against same name and select another name while assign then it will not show to that login
233 | MT | TT_MT_233 | 22/02/2023 | 1 High | 1 High | Ticket | My Tickets -> Your Task | Not a Bug | Functional | Upon adding task to a user, where user is not basket owner nor he is ticket owner, that task is not being displayed to his/her login.(TT9366) | Amreen | Rushikesh | If we create multiple usersid against same name and select another name while assign then it will not show to that login
234 | MT | TT_MT_234 | 22/02/2023 | 1 High | 1 High | Ticket | My Tickets -> Your Task | Not a Bug | Functional | Upon adding group task to a user, where user is not basket owner nor he is ticket owner, that task is not being displayed to his/her login.(TT9366) | Amreen | Rushikesh | If we create multiple usersid against same name and select another name while assign then it will not show to that login
235 | MT | TT_MT_235 | 22/02/2023 | 1 High | 1 High | Ticket | My Tickets -> Your Task | New Fixed 2/23/2023 | Functional | Upon adding task, Play/pause button is not being displayed to task owner | Amreen | Rushikesh
236 | NTF | TT_NTF_236 | 22/02/2023 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification not being sent to Ticket owner and basket owner when task owner is differ from Ticket owner and Basket owner | Amreen
237 | NTF | TT_NTF_237 | 22/02/2023 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | While ticket owner assigning ticket to other person , notification not being sent to Ticket creator and other person ( new Assign to person) | Amreen
238 | UM | TT_UM_238 | 2023-02-23 | 2 Medium | 2 Medium | User master | Departments | New | Functional | user can make more than one department as dafault. It is expected that user can make at a time only one department as default. | Priyanka

## Sheet1 (hidden)
SR No. | Defect ID | Defect Raised Date | Severity | Priority | Module | Sub-Module | Defect State | Defect category | Defect Description | Tester | Assigned To | EFD | Remark | Defect Close Date | screenshots
Template Master is currently out of scope

## Sheet3
http://15.207.120.175/TechTicketDummy/