## Sheet1
Debtor Tracking Sysyem - Reports
Sr. No | Bugs
1 | "Due Date From" & "Due Date To" fields are missing | Filter
2 | Filter Button Label Should be "Search" | Filter
3 | "From Date" & "To Date" fields should be show Star Marks | Filter
4 | "From Date" field accepting Future date & "To Date" fields accepting Past date EX. From Date :14/04/2023 To Date : 03/04/2023 | Filter
5 | Sr No,Date & Remark Column is missing | Report
6 | Authorized Employee column showing Auth Emp Id | Report
7 | After Searching filter data , Reset button not visible | Report
8 | User Column showing Logged In Person Name , It should be show Employee Name selected while adding data | Report
9 | Remark column should be editable | Report
10 | Branch Filter not showing data , it showing error "No Data Available" | Report
11 | Pending days colum showing wrong data Pending days = current date - Due Date 10 = 19 - 12 | Report
12 | after click on Export , file not downloaded | Export
Testing from Sayali
Debtor List
Sr. No | Bugs
1 | Only csv, excel, pdf file format should accepted | Add
2 | It should show error message please upload csv,excel, pdf file | Add
3 | Upload CSV popup should not show previously added data | Add
4 | After uploading file it should fetch date automatically | Grid View
5 | Edit option should be present in action column | Grid View
6 | Authority Person, credit days fields are blank Column name should be Authority Employee | Grid View
7 | Due date should calculate automatically Due date = bill date + credit days Due date showing blank For -ve days it should show 0 | Grid View
8 | In Edit all fields should be editable except Customer name, Debit amount | Edit
9 | In Edit already added data should show | Edit
10 | After editing any field it should update the data | Edit
11 | In View, field name should be Cheque Number showing blank | View
12 | User field should be added | View
13 | Debit amt per = Debit Amt / Bill Amt *100 Ex: 44390*100/197315 = 22.50% Showing 1 | View
14 | Authority Employee field showing blank | View
15 | Credit days showing blank | View
16 | Due date should calculate automatically Due date = bill date + credit days Due date showing blank For -ve days it should show 0 | View
17 | Pending days = Current date - due date | View
Testing from Sayali
Debtor Tracking Sysyem - App bugs
SR NO. | BUGS
1 | Select employee, credit from date, credit to date, submit, reset buttons not added | debtor list
2 | Select branch search not working | barnch dropdown
3 | Edit option should be present | Edit
4 | In Edit, Only Remark field should be editable | Edit
5 | After editing it should update the changes | Edit
6 | Debit amt per = Debit Amt / Bill Amt *100 | View
Ex: 44390*100/197315 = 22.50%
Showing 1
7 | Authority Employee field showing blank | View
8 | Credit days, Cheque number fields are showing null | View
9 | Pending days = Current date - due date | View
showing 2
10 | Due date should calculate automatically, | View
Due date = bill date + credit days,
Due date showing 14/04/2023,
For -ve days it should show 0
11 | Bill date, due date fields should not be editable | View
12 | user field should show name of user | View
13 | Remark field is showing null | View
21/04/2023 Debtor Tracking system - Mapping list
Sr. No | Bugs
1 | Customer name column showing cust | Grid View
2 | Customer Number column showing Cust | Grid View
3 | Authorized column showing Authority | Grid View
4 | Cheque number misspell | Grid View
| cheque number column showing same cheque numbe | Grid View
5 | Bill Number showing Date & Time [2023/04/20 00:00:00 ] | Grid View
6 | Pending days colum showing wrong data Pending days = current date - Due Date 0 = 19 - 12 | Grid View
7 | User Column showing Logged In Person Name , It should be show Employee Name selected while adding data | Grid View
8 | Created By showing number | View
9 | Updated by Showing number | View
10 | It showing Two scroll bar | Grid View
11 | Status column not showing Proper status after uploading file | Grid View
12
21/04/2023 Debtor Tracking Sysyem - Reports
Sr. No | Bugs
1 | Showing only Filter button | Grid View
2 | It showing Two scroll bar | Grid View
3 | Status , Due Date from & Due Date To field missing | Filter
4 | Filter Button Label Should be "Search" | Filter
5 | Sr No, Date & Remark Column is missing | Filter
6 | Branch Filter not showing data , it showing error "No Data Available" | Filter
7 | Select branch search not working | Filter
8 | Employee Filter not showing data , it showing error "No Data Available" | Filter
9 | User Column showing Logged In Person Name , It should be show Employee Name selected while adding data | Grid View
10 | Status column not showing Proper status as per Date | Grid View
11 | Pending days colum showing wrong data Pending days = current date - Due Date 0 = 19 - 12 | Grid View
12 | Authorized Employee column showing Auth Emp Id | Grid View
13 | Bill Number showing Date & Time [2023/04/20 00:00:00 ] | Grid View
14 | Edit option should be present in action column | Grid View
15 | After Searching filter data , Reset button not visible | Grid View
16 | After click on View , it showing error | View
17 | Filter is not working so not able to Export data | Grid View
21/04/2023 APK - Debtor tracking system
Sr. No | Bugs
1 | Remove Sr No Field | View
2 | Status field is missing | View
3 | Cancel button not clickable | Filter
4 | Reset button is missing | Filter
5 | Pending days colum showing wrong data Pending days = current date - Due Date 0 = 20 - 12 | View
6 | Bill Number showing Date & Time [2023/04/20 00:00:00 ] | View
7 | cheque number column showing null | View
8 | Narration column showing null | View
9 | User Column showing number , It should be show Employee Name selected while adding data | View
10 | Employee Filter not showing data | Filter
11 | Branch Filter not showing data | Filter
12 | Filter is not working so not able to Export data | Export