## data
sr | ticket_id | task_owner | task_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at
1 | TT19422 | Dhiraj Chandel | create validation class Git online access | 2024-06-27 | 00:00:00 |  | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 15:24:37 | 2024-06-28 15:24:37
2 | TT19422 | Dhiraj Chandel | Daily Discussion... | 2024-06-27 | 00:00:00 |  | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 15:23:25 | 2024-06-28 15:23:25
3 | TT19422 | Dhiraj Chandel | MY CS HRMS integrate extra working api | 2024-06-28 | 04:00:00 | 04:00:00 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 15:22:50 | 2024-06-28 15:22:50
4 | TT19422 | Dhiraj Chandel | My cs approval api integration | 2024-06-28 | 01:00:00 | 01:00:00 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 15:48:44 | 2024-06-28 15:48:44
5 | TT19422 | Dhiraj Chandel | Daily Discussion.... | 2024-06-28 | 00:45:00 | 00:45:00 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 15:21:20 | 2024-06-28 15:21:20
6 | TT19422 | Dhiraj Chandel | split & share project android 14 file access | 2024-06-24 | 04:00:00 | 04:00:00 | 2024-06-24 |  | COMPLETED | DELAY | 2024-06-25 10:12:57 | 2024-06-25 10:12:57
7 | TT19422 | Dhiraj Chandel | search create validation class Git online access | 2024-06-25 | 03:00:00 | 03:00:00 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 17:20:24 | 2024-06-25 17:20:24
8 | TT19422 | Dhiraj Chandel | my cs form HRMS UI | 2024-06-24 | 03:00:00 | 03:00:00 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:14:05 | 2024-06-24 18:14:05
9 | TT19422 | Dhiraj Chandel | KT Devops | 2024-06-26 | 00:30:00 | 00:57:58 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 14:45:00 | 2024-06-26 14:45:00
10 | TT19422 | Dhiraj Chandel | team sync call | 2024-06-24 | 00:15:00 | 00:15:00 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:14:15 | 2024-06-24 18:14:15
11 | TT19422 | Dhiraj Chandel | code review | 2024-06-26 | 00:30:00 | 00:27:30 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 17:30:34 | 2024-06-26 17:30:34
12 | TT19422 | Dhiraj Chandel | Daily Discussion | 2024-06-24 | 00:45:00 | 00:28:34 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:14:24 | 2024-06-24 18:14:24
13 | TT19422 | Dhiraj Chandel | flutter learning how to make plugin | 2024-06-25 | 04:00:00 | 04:00:00 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 17:48:29 | 2024-06-25 17:48:29
14 | TT19422 | Dhiraj Chandel | sync call with team. | 2024-06-25 | 00:15:00 | 00:15:01 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 17:20:06 | 2024-06-25 17:20:06
15 | TT19422 | Dhiraj Chandel | Daily Discussion. | 2024-06-25 | 00:45:00 | 00:45:00 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 17:20:15 | 2024-06-25 17:20:15
16 | TT19422 | Dhiraj Chandel | team sync call.. | 2024-06-26 | 00:15:00 | 00:15:00 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 17:30:12 | 2024-06-26 17:30:12
17 | TT19422 | Dhiraj Chandel | sync call with team... | 2024-06-27 | 00:00:00 |  | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 15:23:18 | 2024-06-28 15:23:18
18 | TT19422 | Dhiraj Chandel | team sync call.... | 2024-06-28 | 00:00:00 |  | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 15:24:20 | 2024-06-28 15:24:20
19 | TT19422 | Dhiraj Chandel | Daily Discussion.. | 2024-06-26 | 00:45:00 | 00:45:00 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 17:18:38 | 2024-06-26 17:18:38
20 | TT19422 | Dhiraj Chandel | My CS HRMS API integration. | 2024-06-26 | 06:00:00 | 06:00:20 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:05:38 | 2024-06-26 19:05:38
21 | TT19422 | Govardhan Bollu | Devups Traning Session | 2024-06-26 | 01:00:00 | 02:04:42 | 2024-06-26 |  | COMPLETED | DELAY | 2024-06-28 11:42:37 | 2024-06-28 11:42:37
22 | TT19422 | Govardhan Bollu | Code Review | 2024-06-26 | 00:30:00 | 02:58:53 | 2024-06-26 |  | COMPLETED | DELAY | 2024-07-01 17:03:10 | 2024-07-01 17:03:10
23 | TT19422 | Govardhan Bollu | Daily Sync Call | 2024-06-26 | 00:15:00 | 00:57:55 | 2024-06-26 |  | COMPLETED | DELAY | 2024-06-28 16:09:36 | 2024-06-28 16:09:36
24 | TT22187 | Govardhan Bollu | B2B Image Upload app log in issue | 2024-06-26 | 01:30:00 | 17:13:52 | 2024-06-26 |  | IN_PROGRESS | DELAY | 2024-07-04 11:34:24
25 | TT19422 | Govardhan Bollu | Code Review - Pranjali | 2024-06-28 | 00:20:00 | 00:20:45 | 2024-06-30 |  | COMPLETED | DELAY | 2024-07-01 17:02:51 | 2024-07-01 17:02:51
26 | TT19422 | Govardhan Bollu | Daily Sync Call | 2024-06-28 | 00:20:00 | 00:16:22 | 2024-06-28 |  | COMPLETED | DELAY | 2024-07-01 17:03:02 | 2024-07-01 17:03:02
27 | TT19422 | Mustafa Siyam | 3rd party library | 2024-06-25 | 03:00:00 | 03:31:37 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 18:28:08 | 2024-06-25 18:28:08
28 | TT19422 | Mustafa Siyam | State Management | 2024-06-26 | 04:30:00 | 04:43:00 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:17:33 | 2024-06-26 19:17:33
29 | TT19422 | Mustafa Siyam | Quality Assurance | 2024-06-26 | 03:00:00 | 03:17:36 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:17:39 | 2024-06-26 19:17:39
30 | TT19422 | Mustafa Siyam | Version Control | 2024-06-27 | 00:00:00 |  | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 10:01:21 | 2024-06-28 10:01:21
31 | TT19422 | Mustafa Siyam | Flutter Sync Call | 2024-06-24 | 00:30:00 | 00:40:57 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 17:46:04 | 2024-06-24 17:46:04
32 | TT19422 | Mustafa Siyam | Flutter Sync Call Tuesday | 2024-06-25 | 00:30:00 | 00:17:18 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 18:27:55 | 2024-06-25 18:27:55
33 | TT19422 | Mustafa Siyam | Flutter Sync Call Wednesday | 2024-06-26 | 00:30:00 | 00:13:19 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:17:45 | 2024-06-26 19:17:45
34 | TT19422 | Mustafa Siyam | Firebase Storage | 2024-06-27 | 00:00:00 |  | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 10:01:50 | 2024-06-28 10:01:50
35 | TT19422 | Mustafa Siyam | Flutter Sync Call Thursday | 2024-06-27 | 00:00:00 | 00:00:00 | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 09:59:12 | 2024-06-28 09:59:12
36 | TT19422 | Mustafa Siyam | Native Integration | 2024-06-28 | 04:30:00 | 04:43:05 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 18:12:41 | 2024-06-28 18:12:41
37 | TT19422 | Mustafa Siyam | Flutter Sync Call Friday | 2024-06-28 | 00:30:00 | 00:30:25 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 18:12:52 | 2024-06-28 18:12:52
38 | TT19422 | Mustafa Siyam | Dynamic User Interface | 2024-06-28 | 03:00:00 | 02:56:20 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 18:12:48 | 2024-06-28 18:12:48
39 | TT19422 | Mustafa Siyam | Static User interface | 2024-06-24 | 04:30:00 | 04:06:56 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:11:19 | 2024-06-24 18:11:19
40 | TT19422 | Mustafa Siyam | Storages | 2024-06-24 | 03:00:00 | 03:00:00 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 17:48:05 | 2024-06-24 17:48:05
41 | TT19422 | Mustafa Siyam | Behaviour Components | 2024-06-25 | 04:30:00 | 04:45:01 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 18:28:02 | 2024-06-25 18:28:02
42 | TT19422 | Pranjali Maske | understanding flutter package | 2024-06-28 | 01:00:00 | 01:04:27 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 17:56:53 | 2024-06-28 17:56:53
43 | TT19422 | Pranjali Maske | Task scheduling | 2024-06-24 | 01:00:00 | 01:00:00 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 16:02:50 | 2024-06-24 16:02:50
44 | TT19422 | Pranjali Maske | implementing flutter package into code | 2024-06-28 | 01:00:00 | 01:00:35 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 19:08:50 | 2024-06-28 19:08:50
45 | TT19422 | Pranjali Maske | General Discussion | 2024-06-24 | 00:45:00 |  | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:23:57 | 2024-06-24 18:23:57
46 | TT19422 | Pranjali Maske | Team sync call & meeting with Gaurav sir | 2024-06-24 | 01:15:00 | 01:17:23 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 19:00:32 | 2024-06-24 19:00:32
47 | TT19422 | Pranjali Maske | understanding clean architecture | 2024-06-24 | 03:00:00 | 03:00:00 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:21:40 | 2024-06-24 18:21:40
48 | TT19422 | Pranjali Maske | B2B generating build and testing application with Mounika | 2024-06-25 | 02:00:00 | 02:00:45 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 19:28:31 | 2024-06-25 19:28:31
49 | TT19422 | Pranjali Maske | Team sync call. | 2024-06-25 | 00:15:00 | 00:15:00 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 19:26:10 | 2024-06-25 19:26:10
50 | TT19422 | Pranjali Maske | Custom theme integration | 2024-06-28 | 02:00:00 | 02:05:43 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 18:35:19 | 2024-06-28 18:35:19
51 | TT19422 | Pranjali Maske | understanding Feature Layer ,Domain Layer, Data Layer | 2024-06-24 | 00:15:00 | 00:16:12 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:23:18 | 2024-06-24 18:23:18
52 | TT19422 | Pranjali Maske | Team sync call.. | 2024-06-26 | 00:15:00 | 00:15:06 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 17:19:38 | 2024-06-26 17:19:38
53 | TT19422 | Pranjali Maske | B2B main page loading problem, Order placed barcodes from other tabs are being displayed issue checking | 2024-06-25 | 03:00:00 | 03:00:00 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 19:28:43 | 2024-06-25 19:28:43
54 | TT19422 | Pranjali Maske | Egold project checking | 2024-06-26 | 01:00:00 | 00:53:53 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:24:50 | 2024-06-26 19:24:50
55 | TT19422 | Pranjali Maske | B2B filter barcode testing | 2024-06-26 | 01:30:00 | 01:43:11 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:17:29 | 2024-06-26 19:17:29
56 | TT19422 | Pranjali Maske | General Discussion.. | 2024-06-25 | 00:45:00 | 00:49:11 | 2024-06-25 |  | COMPLETED | IN_TIME | 2024-06-25 19:28:18 | 2024-06-25 19:28:18
57 | TT19422 | Pranjali Maske | B2B place order | 2024-06-26 | 01:00:00 | 01:00:28 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:17:24 | 2024-06-26 19:17:24
58 | TT19422 | Pranjali Maske | General Discussion... | 2024-06-26 | 00:45:00 | 00:48:08 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 17:56:56 | 2024-06-26 17:56:56
59 | TT19422 | Pranjali Maske | B2B recrate image and sync process | 2024-06-26 | 01:30:00 | 01:39:36 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:18:14 | 2024-06-26 19:18:14
60 | TT19422 | Pranjali Maske | Team sync call... | 2024-06-27 | 00:00:00 |  | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 17:56:28 | 2024-06-28 17:56:28
61 | TT19422 | Pranjali Maske | B2B sync process checking | 2024-06-28 | 02:00:00 | 02:01:50 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 17:57:04 | 2024-06-28 17:57:04
62 | TT19422 | Pranjali Maske | Team sync call.... | 2024-06-28 | 00:15:00 | 00:50:41 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 17:56:39 | 2024-06-28 17:56:39
63 | TT19422 | Pranjali Maske | overview custom theme | 2024-06-27 | 05:00:00 | 04:29:07 | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 11:34:04 | 2024-06-28 11:34:04
64 | TT19422 | Pranjali Maske | General Discussion.... | 2024-06-27 | 00:45:00 | 00:46:15 | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 11:32:45 | 2024-06-28 11:32:45
65 | TT19422 | Pranjali Maske | code review | 2024-06-28 | 01:00:00 | 00:37:56 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 19:46:35 | 2024-06-28 19:46:35
66 | TT19422 | Pranjali Maske | General Discussion..... | 2024-06-28 | 00:45:00 | 00:50:43 | 2024-06-28 |  | COMPLETED | IN_TIME | 2024-06-28 17:56:44 | 2024-06-28 17:56:44
67 | TT19422 | Pranjali Maske | B2B sync services & testing | 2024-06-24 | 01:45:00 | 01:45:00 | 2024-06-24 |  | COMPLETED | IN_TIME | 2024-06-24 18:30:12 | 2024-06-24 18:30:12
68 | TT19422 | Pranjali Maske | B2B filter testing | 2024-06-25 | 02:00:00 | 02:00:00 | 2024-06-25 |  | COMPLETED | DELAY | 2024-06-26 12:51:38 | 2024-06-26 12:51:38
69 | TT19422 | Pranjali Maske | B2B firebase mismatch image checking | 2024-06-26 | 02:00:00 | 02:00:00 | 2024-06-26 |  | COMPLETED | IN_TIME | 2024-06-26 19:15:22 | 2024-06-26 19:15:22
70 | TT19422 | Pranjali Maske | B2B sync service | 2024-06-27 | 02:00:00 | 01:42:11 | 2024-06-27 |  | COMPLETED | DELAY | 2024-06-28 11:32:51 | 2024-06-28 11:32:51