## Summary
Version History | [5 empty] | Iteration Summary
Date | Author | Version | Approved by | Total Tcs. | Remark | Sub Module | Iteration category | Iteration Count | Start Date | End Date | Total Tcs | Total Defects | Remark
2024-05-28 |  | V0.1 |  |  | Initial draft | Test Draft | Initial Phase | 1 | 2024-06-01 | 2024-06-01 | 100 | 50 | 6/13/2024:
2024-05-29 |  | V0.2 |  |  | Severity and priority missing for 178 TCs. Functions missing for 14 TCs | Test Draft - Retesting | Retesting | 2 | 2024-06-13 | 2024-06-13
2024-06-01 |  | V0.3 |  |  | incorporated review comments | Test Draft-RAD iteration | RAD | 3 | 2024-06-14 | 2024-06-14
2024-06-01 |  | V1.1 |  |  | All ok | E2E | E2E | 4 | 2024-06-18 | 2024-06-18
2024-06-01 |  | V1.2 |  |  | Missing cases added

## TPM_Sheet
Ticket ID | TT24961 | Released Version
Project live Date |  | Project Name | My CS App
Module Name | Enrol new scheme | Test Cases Reviewed By
Testing Owner | Amreen | Ticket Owner | ####### | #######
Testing URL | ####### | Email / User Name | ####### | #######
Password
Description | New Scheme enrollment on My cs App
| 0 | 0 | 12 | 0 | 0 |  | 0 | 12 | 0 | 12 |  | 12 | 12 | 0
12 | 12 | 12 | 0 | 12 | 12 |  | 12 | 0 | 12 | 0 |  | 0 | 0 | 12
Case ID | Module | Submodule | Req Id | Function | Testing Type | Field | Test Description | Test steps | Expected Result | Actual Result | Screen Shot | Status Dt 24/06/2024 | Priority | Severity | Written Date | Review Remark | BA Remark | Developer Remark | Last Updated Date
TC-01 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Mobile no | Verfiy mobile no validation |  | This field should satisfy below validation 1.Accept only numeric values ( 10 digits long) 2.The first digit should contain numbers between 6 to 9. 3.The rest 9 digit can contain any number between 0 to 4. It should not accept duplicate mobile no 5 It should unique 6. Placeholder - Enter mobile no |  |  |  |  | Medium
TC-02 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Location | Verfiy Location validation |  | This field should satisfy below validation 1. It should be disabled. 2. It should fetch location / branch name of the logged in sales person from employee master. 3. It should be auto populated. |  |  |  |  | Medium
TC-03 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Employee ID | Verfiy emp id validation |  | This field should satisfy below validation 1. It should be disabled. 2. It should fetch emp id of the logged in sales person from employee master. 3. It should be auto populated. |  |  |  |  | Medium
TC-04 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Old Scheme Number | Verfiy old scheme no validation |  | Below validation should be satisfied by old scheme no : 1.Accept only characters , numbers & '-'. 2. It should not accept space. 3. It should not be unique 4. domain base must be at least 2 characters 5 domain extension must be at least 2, not more than 4 alpha 6. Placeholder - Enter old scheme number. |  |  |  |  | Medium
TC-05 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Name Of the Customer | Verfiy name of the Customer validation |  | This field should satisfy below validation 1. It should be disabled. 2. It should fetch emp name of the logged in sales person from employee master. 3. It should be auto populated. |  |  |  |  | Medium
TC-06 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Scheme Name | Verfiy scheme name validation |  | Below validation should be satisifed by platform : 1. It should fetch the value from padm. 2. It should allow to select only one value. 3. It should fetch only active schemes. 4. It should be dispalyed in cronological order. (alphabetical order) 5. Placeholder - Please select the scheme. Selected value should be displayed in field |  |  |  |  | Medium
TC-07 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Enrollment amount | Verfiy enrollment amount validation |  | This field should satisfy below validation 1.It should accept only numeric upto 1 - 50 digits. 2. It should be auto fetched for padm as per the scheme value set. 3. It should be auto populated. |  |  |  |  | High
TC-08 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Duration | Verfiy duration validation |  | Following data should be displayed in duration : 1. Duration in months it should be fetched from the master. 2. It should be in MM months format. 3. It should be disabled. 4. It should be auto populated |  |  |  |  | High
TC-09 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Extra month | Verfiy Extra validation |  | Following data should be displayed in duration : 1. Extra month it should be fetched from the master. 2. It should be in MM months format. 3. It should be disabled. 4. It should be auto populated |  |  |  |  | High
TC-10 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Maturity Date | Verfiy maturity date validation |  | Following data should be displayed in duration : 1. It should be in DD-MM-YYYY format. 2. It should be disabled. 3. It should be auto populated 4. Maturity month it should be fetched from the master. |  |  |  |  | High
TC-11 | Enroll new scheme | Enroll new scheme |  | Add | Functionality | Maturity Date | Verfiy maturity date validation |  | Following data should be displayed in duration : If todays date = 05/09/2024. Scheme duration 10 month. Extra month 1 month 1. Maturity date = 05/08/2025 |  |  |  |  | High
TC-12 | Enroll new scheme | Enroll new scheme |  | Add | Validation | Passbook Number | Verfiy passbook no validation |  | This field should satisfy below validation 1.It should accept only numeric. 2.It should accept upto 1 - 50 digit. 3.It should not accept duplicate passbook no 4. It should unique 5. Placeholder - Enter passbook number. |  |  |  |  | High
Note on H63: Amruta Kore:

## Report
Failed test case status | Severity |  |  |  |  | Status | New
Iteration 2 Status | High | Low | Medium | Very High | Grand Total
Fail | 31 | 7 | 43 | 1 | 82 | Defect status | Severity
Grand Total | 31 | 7 | 43 | 1 | 82 | Priority | High | Low | Medium | Grand Total
[6 empty] | High | 10 |  | 1 | 11
[6 empty] | Low |  | 5 |  | 5
[6 empty] | Medium | 1 |  |  | 1
[6 empty] | Very High |  | 1 |  | 1
[6 empty] | Grand Total | 11 | 6 | 1 | 18
Daily Summary Report - 6/10/2024
Test case execution status | Iteration 2 Status
Submodule | Fail | Pass | Grand Total
Function Master | 24 | 4 | 28
Review Comment Master | 3 | 26 | 29
Review test cases |  | 3 | 3
Reviewed Test Draft | 26 | 23 | 49
Test case Review |  | 19 | 19
Test Draft | 9 | 48 | 57
Testing group master | 8 | 21 | 29
Testing Type master | 12 | 17 | 29
Grand Total | 82 | 161 | 243

## TPM_MISC
Testing Type | Status | Priority / Severity | Tester remark | Developer remark | BA Remark | Functions | Req id | Req desc
Functionality | Pass | High | Closed | Resolved | Closed | Add | BR001 - with description
Intergration | Fail | Medium | Pending | Not a bug | Re-open | Edit | BR002 - with description
Validation | Not Executed | Low | Re-open | Deffered | Deffered | View
UI | Under Development | Very High | Blocker | In-Progress | Not a bug | Delete
Usability | Suggestion |  | Re-Test | Development Completed |  | Search
| NA |  |  |  |  | Gird view
Export
Custom Export
Filter
Pre-requisitis

## Defect log
Sr No | Defect ID | Raise on Date | Module | Sub Module | Function | Severity | Priority | Defect Description | Assign To | Tester Status | Tester comment | Dev Status | Dev comment | BA comment

## Sheet1 (hidden)
* |  |  | Testing | [11 empty] | Re-Testing | [10 empty] | RAD | [10 empty] | End To End Testing
Sr No | Submodule | Functions | Total no of test case (Module) | Start Date | End Date | No. of TC Executed | Passed TCs | Failed Tcs | Not Executed Tcs | Total no of Not Executed TC | High Severity | Medium Severity | Reviewed by | Review date | Total no of test case (Module) | Start Date | End Date | No. of TC Executed | Total no of Passed TC | Total no of Failed TC | Total no of Not Executed TC | High Severity | Medium Severity | Reviewed by | Review date | Total no of test case (Module) | Start Date | End Date | No. of TC Executed | Total no of Passed TC | Total no of Failed TC | Total no of Not Executed TC | High Severity | Medium Severity | Reviewed by | Review date | Total no of test case (Module) | Start Date | End Date | No. of TC Executed | Total no of Passed TC | Total no of Failed TC | Total no of Not Executed TC | High Severity | Medium Severity | Reviewed by | Review date
1 | PO |  | 15 |  |  | 0 | 5 | 5 |  | 4 | 2 | 3 | [5 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
[6 empty] | 4 | 2 | 2 |  | 0 | 1 | 1 | [5 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
2 | PO -edit |  | 20 |  |  | 20 | 10 | 5 |  | 5 | 2 | 3 | [5 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
3 | Po closer - add |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
4 | Po closer - view |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
5 | Po closer - History |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
6 | Po closer - History view |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
7 | Bill transaction add |  |  |  |  | 0 | [11 empty] | 22 | 5 | 8 | 9 | [7 empty] | 0 | [10 empty] | 0
8 | Bill transaction view |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
9 | Bill transaction edit |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
10 | GRN Add |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
11 | GRN View |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
12 | GRN delete |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
13 | GRN History |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
14 | GRN History view |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
15 | Po closer - edit |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
16 | GRN Edit |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
17 | Requisition add |  |  |  |  | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
[6 empty] | 0 | [11 empty] | 0 | [10 empty] | 0 | [10 empty] | 0
| Total No of Test cases |  | 35 |  |  | 24 | 17 | 12 |  | 9 | 5 | 7 |  |  | 0 |  |  | 22 | 5 | 8 | 9 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Consolidated Report
Date
2024-06-01 | Test case execution status Report - 6/1/2024 | [5 empty] | Remark
| TCs Status / Submodules | Pass Tcs | Fail Tcs | Other / Not Executed | Total Tcs
| Test Draft | 11 | 22 | 7 | 40
| Testing group master | 19 | 10 |  | 29
| Testing Type master | 19 | 10 |  | 29
| Grand Total | 49 | 42 | 7 | 98
| Failed test case status report - 6/1/2024 | [5 empty] | Remark
| Very High | High | Medium | Low | Grand Total
| 5 | 14 | 22 | 1 | 42
| Defect Status report - 6/1/2024 | [5 empty] | Remark
| Severity / Priority | High | Medium | Low | Very High | Grand Total
| High | 8 |  |  | 1 | 9
| Medium | 1 |  | 1 |  | 2
| Low |  | 4 |  |  | 4
| Very High |  | 1 |  |  | 1
| Grand Total | 9 | 5 | 1 | 1 | 16

## Test Case Quality
Attribute | Count | Percentage Completed | Percentage pending
TC Count | 12
Module | 12 | 100 | 0
Req Id | 0 | 0 | 100
Function | 12 | 100 | 0
Testing Type | 12 | 100 | 0
Test Description | 12 | 100 | 0
Test steps | 0 | 0 | 100
Expected Result | 12 | 100 | 0
Actual Result | 0 | 0 | 100
Priority | 0 | 0 | 100
Severity | 12 | 100 | 0
TC count as per the standards
%ofTest Cases | TCs Count | %
Functionality | 12 | 100
Usability | 0 | 0
UI/UX | 0 | 0