## Sheet1
Screens | UI | Delivery Time | Developer | Status
login, forgot password | Sign in - Gold size | 26/07/2023 | DC | Pending
| Verification page - line | 26/07/2023 | DC | Pending | size and width of all buttons should be same in all screens
| Verification page - logo pverlapping on verify button | 26/07/2023 | DC | Pending | size and height of all text fields should be same in all screens
| verification page - display red boxes and invalid line in case of incorrect code | 26/07/2023 | DC | Pending | UI, font, size, colour of billing information of all functionaliy should be same
| New password - bold title | 26/07/2023 | DC | Pending
| new password - reduce a bit font size of password rules | 26/07/2023 | DC | Pending
| help button should be below data / baterry/ camera line | 26/07/2023 | DC | Pending
| successful message after new password is updated successfully | 26/07/2023 | DC | Pending
Dashboard | dots for banners | 26/07/2023 | DC | Pending
| increase size of feature images, minimize space | 26/07/2023 | DC | Pending
| rate trigger and other button size adjusting | 26/07/2023 | DC | Pending
hamburger menu | menu size curve - increase size | 26/07/2023 | DC | Pending
| settings -sub menu | 26/07/2023 | DC | Pending
| offer icon | 26/07/2023 | DC | Pending
| change preference settings icon | 26/07/2023 | DC | Pending
SIP | text field height to be reduced | 26/07/2023 | DC | Pending
| display customer logo | 26/07/2023 | DC | Pending
| change line below duration field | 26/07/2023 | DC | Pending
| change line below rupees field | 26/07/2023 | DC | Pending
| underline period field after entering date and duration | 26/07/2023 | DC | Pending
| remove space after terms and condition line | 26/07/2023 | DC | Pending
| billing information - bold size title | 26/07/2023 | DC | Pending
| billing information sequence of details | 26/07/2023 | DC | Pending
| tenant logo needed in billing infor | 26/07/2023 | DC | Pending
| total billimg amount - bold | 26/07/2023 | DC | Pending
| bottom sheet to select bank - increase size of amount | 26/07/2023 | DC | Pending
| pay button needed | 26/07/2023 | DC | Pending
Buy | change line below text fields | 26/07/2023 | DC | Pending
| reduce height of text field | 26/07/2023 | DC | Pending
| billing info - dispay logo | 26/07/2023 | DC | Pending
| font size and colour of totall bill amount | 26/07/2023 | DC | Pending
| billing info - title bold | 26/07/2023 | DC | Pending
| display bottom sheet to select bank | 26/07/2023 | DC | Pending
| display successful message of purchase | 26/07/2023 | DC | Pending
Sell | weight balance - font size, bold and font colour of weight | 26/07/2023 | DC | Pending
| enter line after grams field - "Please enter value bewteen -- and --". | 26/07/2023 | DC | Pending
| enter line after amount field | 26/07/2023 | DC | Pending
| logo after continue button and screen should not be scrollable | 26/07/2023 | DC | Pending
| billing info - font size of title | 26/07/2023 | DC | Pending
| billing info - item price field is missing | 26/07/2023 | DC | Pending
| billing info - font size and colour of values | 26/07/2023 | DC | Pending
| font size and colour of 'total' word | 26/07/2023 | DC | Pending
| billing info - logo is missing | 26/07/2023 | DC | Pending
| bottom sheet of select bank - pay button is missing | 26/07/2023 | DC | Pending
Rate trigger | reduce text field height to enter amount | 26/07/2023 | DC | Pending
| Disclaimer ine should be within 2 lines | 26/07/2023 | DC | Pending
| remove space above save button | 26/07/2023 | DC | Pending
| outline for Table view of history | 26/07/2023 | DC | Pending
| width of save button should be more | 26/07/2023 | DC | Pending
| minimize and maximize of history table | 26/07/2023 | DC | Pending
| table / row line for each setting | 26/07/2023 | DC | Pending
| Date & Time should be in one line | 26/07/2023 | DC | Pending
| Buy rate field is missing | 26/07/2023 | DC | Pending
| cancelled rate triggers not getting displayed | 26/07/2023 | DC | Pending
| display cancelled text and it should not be clickable | 26/07/2023 | DC | Pending
Manage SIP | Title, tabs, field names - bold | 26/07/2023 | DC | Pending
| Customer name shoul be capital and bold | 26/07/2023 | DC | Pending
| draw line after SIP details , cance sip tab | 26/07/2023 | DC | Pending
| : for al field names | 26/07/2023 | DC | Pending
| view action-> customer name should be caital and bold | 26/07/2023 | DC | Pending
| view action -> display cpount of sip in 'total paid sip' field | 26/07/2023 | DC | Pending
| editaction -> ispaly entire card of SiP details | 26/07/2023 | DC | Pending
| edit action -> diplay reasn field after clicking on cancel checkbox | 26/07/2023 | DC | Pending
| Display pop-up box after cliking on save button after cancel reason is mentioned | 26/07/2023 | DC | Pending
| CANCEL SIP ENTIRE PAGE IS NOT DONE | 26/07/2023 | DC | Pending
Notifications | right aligmment for date and time | 26/07/2023 | DC | Pending
| Dispay red colour if notification is not read | 26/07/2023 | DC | Pending
| notification page title should be bold | 26/07/2023 | DC | Pending
| after reading notification -> text / content is not displayed properly (there is space at right) | 26/07/2023 | DC | Pending
Your trades | title - bold | 26/07/2023 | DC | Pending
| weight balance' in card should be small | 26/07/2023 | DC | Pending
| Gold' and 'silver' in card should be big size and bold | 26/07/2023 | DC | Pending
| /gm in card should be small and in black colour | 26/07/2023 | DC | Pending
| reduce height of filter and export button | 26/07/2023 | DC | Pending
| draw line after each transaction | 26/07/2023 | DC | Pending
| , after date is needed (before time) | 26/07/2023 | DC | Pending
| transaction title as buy / sell should be bold | 26/07/2023 | DC | Pending
| transaction amount colour should be different | 26/07/2023 | DC | Pending
| Filters -> all should be displayed in box | 26/07/2023 | DC | Pending
| filters -> apply button is missing | 26/07/2023 | DC | Pending
| filters -> type : drop-down should be within box and should not overlap | 26/07/2023 | DC | Pending
| export -> file is not getting exported | 26/07/2023 | DC | Pending
Bank account settings | Title size bold | 27/07/2023 | DC | Pending
| text font size | 27/07/2023 | DC | Pending
| bank name should be displayed field instead select dropdown | 27/07/2023 | DC | Pending
| validation error messages bold | 27/07/2023 | DC | Pending
| Add button size | 27/07/2023 | DC | Pending
| app logo | 27/07/2023 | DC | Pending
Preference settings | Title size should be in bold | 27/07/2023 | DC | Pending
| communication order sequence | 27/07/2023 | DC | Pending
| all input field of call timings size should be dsplayed same | 27/07/2023 | DC | Pending
| communication language dropdown | 27/07/2023 | DC | Pending
| notification permissions :- space in buttons | 27/07/2023 | DC | Pending
| notification permissions :- checkbox colour | 27/07/2023 | DC | Pending
| allignment of all preference setting details | 27/07/2023 | DC | Pending
| save button size, and it should be in upper case character | 27/07/2023 | DC | Pending
| app unlock recognition slider color | 27/07/2023 | DC | Pending
| app logo | 27/07/2023 | DC | Pending
Delivery | title should be in bold | 27/07/2023 | DC | Pending
| In grams field :- rupees lable color | 27/07/2023 | DC | Pending
| country, state , city, id proof placeholder | 27/07/2023 | DC | Pending
| continue button size | 27/07/2023 | DC | Pending
Help Desk | mobile number is not required | 27/07/2023 | DC | Pending
| select type dropdown | 27/07/2023 | DC | Pending
| submit and cancel button size | 27/07/2023 | DC | Pending
| successful message after submit | 27/07/2023 | DC | Pending