## Sheet1
Sr No | Application | Phase | Status of data (Bmt Division) | Transfer Date | Remark
1 | Padm Current Year DB | 1 | Done
2 | Padm Current Year Application | 1 | Done |  | E-Invice Issue PENDING
3 | Padm Last Year DB | 1 | Pending-FY22-23.
4 | Padm Last Year Application | 1 | Pending-FY22-23.
5 | Infinity Last Year DB | 1 | Done
6 | Infinity Last Year Application | 1 | Done
7 | Connect Us 1.0 DB | 1 | Done
8 | Connect Us 1.0 Application | 1 | Done |  | Issues in current Modules
9 | Crm App | 1 | Pending
10 | S3-B2B | 1 | Pending
11 | My CS App | 1 | Pending
12 | D2D | 1 | Pending
13 | Refinery | 1 | Pending
14 | BDD | 1 | Pending
15 | Antivirus | 1 | Pending
16 | All App Backups | 1 | Pending
17 | HRMS | 1 | Pending
18 | AWS-Metal Booking | 1 | Pending
19 | Website payment | 2 | Pending
20 | Connect Us Desktop DB | 2 | Pending
21 | Connect Us Desktop Application | 2 | Pending
22 | LMS | 2 | Pending
23 | Xtrem Media | 2 | Pending
24 | AWS-Xtreme Media | 2 | Pending
25 | S3-User Data | 2 | Pending
26 | S3-Back year | 2 | Pending
27 | S3-Connect Us Image | 2 | Pending
28 | S3-Acme ftp | 2 | Pending
29 | S3-Weekly backup | 2 | Pending
30 | Link shifting | 2 | Pending
31 | Email | 3 | Pending
32 | AWS-Ecommerce | 3 | Pending
33 | S3-URD DVR Data | 3 | Pending
34 | S3-Ecommerce | 3 | Pending
35 | S3-Customer KYC | 3 | Pending
36 | S3-Mongo DB 2019 | 3 | Pending
37 | S3-Old PST | 3 | Pending
38 | S3-Voice Logger | 3 | Pending
39 | Azure | NA | Pending
40 | Connect Us 2.0 | NA | Pending
41 | AWS-CU 2.0 | NA | Pending
42 | NAS Server | NA | Pending

## Task
Sr No | Task ID | Task | Sub Task | Start Date | End Date | Remark
1 | 9 | Crm App | Develop Side Changes | 2023-10-23 | 2023-10-25
2 | 9 | Crm App | Testing | 2023-10-25 | 2023-10-27
3 | 9 | Crm App | Bug Solving & Retesting | 2023-10-30 | 2023-10-31
4 | 9 | Crm App | Google Play Store Upload | 2023-11-01 | 2023-11-11 | This is subjective it may take less or more time
5 | 10 | S3-B2B | Copy Data to your AWS | 2023-10-23 | 2023-10-24 | 750 GB Data
6 | 10 | S3-B2B | Develop Side Changes | 2023-11-01 | 2023-11-03
7 | 10 | S3-B2B | Testing | 2023-11-04 | 2023-11-06
8 | 10 | S3-B2B | Bug Solving & Retesting | 2023-11-07 | 2023-11-08
9 | 10 | S3-B2B | Google Play Store Upload | 2023-11-09 | 2023-11-19 | This is subjective it may take less or more time
10 | 11 | My CS App | Develop Side Changes | 2023-11-09 | 2023-11-15
11 | 11 | My CS App | Testing | 2023-11-16 | 2023-11-17
12 | 11 | My CS App | Bug Solving & Retesting | 2023-11-20 | 2023-11-21
13 | 11 | My CS App | Google Play Store Upload | 2023-11-22 | 2023-12-02 | This is subjective it may take less or more time
14 | 12 | D2D | Develop Side Changes | 2023-11-22 | 2023-11-24
15 | 12 | D2D | Testing | 2023-11-27 | 2023-11-29
16 | 12 | D2D | Bug Solving & Retesting | 2023-11-30 | 2023-12-01
17 | 12 | D2D | Google Play Store Upload | 2023-12-02 | 2023-12-12 | This is subjective it may take less or more time
18 | 13 | Refinery | Copy Database to BMT Server | 2023-10-23 | 2023-10-23
19 | 13 | Refinery | Restore Database at BMT Server | 2023-10-23 | 2023-10-23
20 | 13 | Refinery | Change point & solve issue if any | 2023-10-23 | 2023-10-25
21 | 14 | BDD | Can Say on this as Approval is pending from your end
22 | 15 | Antivirus | Pending from BMT IT Team
23 | 16 | All App Backups | Show how to take backup of ftp, connectus, padm, bdd, attachment | Already Shown to Sagar Gote
24 | 18 | AWS-Metal Booking | Create server of Metal Booking | 2023-10-24 | 2023-10-25
25 | 18 | AWS-Metal Booking | Testing of Application | 2023-10-26 | 2023-10-27
26 | 16 | All App Backups | Show how to take backup of HRMS, metal booking & b2b | 2023-11-20 | 2023-11-20
27 | 17 | HRMS | Check the setting given by BMT Team | 2023-10-30 | 2023-10-30 | Assuming the required configuration is make properly
28 | 17 | HRMS | Do the required changes | 2023-10-31 | 2023-11-02
29 | 17 | HRMS | Do the required setting in Connect Us | 2023-11-03 | 2023-11-07
30 | 17 | HRMS | Testing | 2023-11-08 | 2023-11-09
31 | 17 | HRMS | Changes if required | 2023-11-10 | 2023-11-15