## data
sr | ticket_id | task_owner | task_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at
1 | TT19189 | Asmita Margaje | working on live ticket solved date and ticket solved by defect | 2024-03-12 | 01:00:00 | 02:37:12 | 2024-03-12 |  | COMPLETED | DELAYED | 2024-03-13 14:54:18 | 2024-03-13 14:54:18
2 | TT19189 | Asmita Margaje | Dynamic Form Defect Solving | 2024-03-06 | 03:00:00 | 02:43:48 | 2024-03-06 |  | COMPLETED | COMPLETED | 2024-03-06 18:46:51 | 2024-03-06 18:46:51
3 | TT18190 | Asmita Margaje | Meeting with BA | 2024-03-20 | 00:17:00 | 00:27:29 | 2024-03-20 |  | COMPLETED | COMPLETED | 2024-03-20 11:26:33 | 2024-03-20 11:26:33
4 | TT19189 | Asmita Margaje | bill checking bug solving | 2024-03-12 | 01:00:00 | 20:08:25 | 2024-03-12 |  | COMPLETED | DELAYED | 2024-03-13 14:58:03 | 2024-03-13 14:58:03
5 | TT19189 | Asmita Margaje | my ticket and play pause button bug solving | 2024-03-13 | 02:00:00 | 01:54:24 | 2024-03-13 |  | COMPLETED | COMPLETED | 2024-03-13 14:55:06 | 2024-03-13 14:55:06
6 | TT18767 | Asmita Margaje | RND - Task and ticket type new development | 2024-03-27 | 02:15:00 | 02:07:24 | 2024-03-27 |  | COMPLETED | COMPLETED | 2024-03-27 18:49:16 | 2024-03-27 18:49:16
7 | TT19189 | Asmita Margaje | Dynamic form edit view component defect solving | 2024-03-13 | 02:00:00 | 01:49:22 | 2024-03-13 |  | COMPLETED | COMPLETED | 2024-03-13 16:45:17 | 2024-03-13 16:45:17
8 | TT18991 | Asmita Margaje | dynamic form all fields development | 2024-03-01 | 04:00:00 | 08:51:01 | 2024-03-01 |  | COMPLETED | DELAYED | 2024-03-11 12:42:22 | 2024-03-04 09:18:03
9 | TT19189 | Asmita Margaje | Entire module code cleaning - BillChecking,Dashboard,SigIn Forgot Password,Notification | 2024-03-14 | 03:30:00 | 03:11:39 | 2024-03-14 |  | COMPLETED | COMPLETED | 2024-03-14 18:47:13 | 2024-03-14 18:47:13
10 | TT19189 | Asmita Margaje | Go Live - ticketing Rewamp | 2024-03-13 | 04:00:00 | 00:00:00 | 2024-03-13 |  | COMPLETED | DELAYED | 2024-03-27 15:03:48 | 2024-03-27 15:03:48
11 | TT18991 | Asmita Margaje | User master bug solving | 2024-03-07 | 01:00:00 | 01:19:37 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-11 12:42:22 | 2024-03-08 23:06:30
12 | TT18991 | Asmita Margaje | E2E testing bug solving | 2024-03-04 | 04:00:00 | 04:17:25 | 2024-03-04 |  | COMPLETED | DELAYED | 2024-03-11 12:42:22 | 2024-03-08 23:06:44
13 | TT19189 | Asmita Margaje | march 8th E2E bug solving | 2024-03-13 | 01:00:00 | 01:14:44 | 2024-03-13 |  | COMPLETED | DELAYED | 2024-03-20 14:53:49 | 2024-03-20 14:53:49
14 | TT18991 | Asmita Margaje | In group activity task if task is played for 2 users then in dashboard of this users task is shown as played but users- solving defect | 2024-03-07 | 01:00:00 | 00:58:35 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-11 12:42:22 | 2024-03-08 23:06:16
15 | TT18991 | Asmita Margaje | In group activity task if task is played for 2 users then in dashboard of this users task is shown as played but users- solving defect | 2024-03-07 | 01:00:00 | 02:47:45 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-11 12:42:22 | 2024-03-08 23:05:58
16 | TT18991 | Asmita Margaje | HRMS Employee joining KT session | 2024-03-07 | 01:00:00 | 00:00:00 | 2024-03-07 |  | COMPLETED | COMPLETED | 2024-03-11 12:42:22
17 | TT19189 | Asmita Margaje | Live support | 2024-03-28 | 03:00:00 | 02:22:35 | 2024-03-28 |  | IN_PROGRESS | IN_PROGRESS
18 | TT20380 | Asmita Margaje | General Discussion with Amit Sir 21-03-2024 | 2024-03-21 | 00:08:00 | 00:05:44 | 2024-03-21 |  | COMPLETED | COMPLETED | 2024-03-21 11:49:47 | 2024-03-21 11:49:47
19 | TT19189 | Asmita Margaje | March E2E 14-03 testing - bugs solving | 2024-03-15 | 05:00:00 | 00:22:26 | 2024-03-15 |  | COMPLETED | DELAYED | 2024-03-20 14:52:59 | 2024-03-20 14:52:59
20 | TT19873 | Asmita Margaje | Tech Ticket System Data Export issue | 2024-03-07 | 02:10:00 | 02:06:05 | 2024-03-08 |  | COMPLETED | COMPLETED | 2024-03-08 23:04:46 | 2024-03-08 23:04:46
21 | TT19189 | Asmita Margaje | Revamp Sync Meeting with Pritam Sir | 2024-03-15 | 01:00:00 | 00:43:14 | 2024-03-15 |  | COMPLETED | COMPLETED | 2024-03-15 17:53:56 | 2024-03-15 17:53:56
22 | TT18991 | Asmita Margaje | Select Master: Selected master data source is not displaying- defect solving | 2024-03-07 | 02:00:00 | 03:26:00 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-11 12:42:22 | 2024-03-08 23:05:34
23 | TT19189 | Asmita Margaje | UAT@Softlaunch Defect Solving | 2024-03-25 | 06:00:00 | 07:45:44 | 2024-03-25 |  | COMPLETED | DELAYED | 2024-03-26 19:41:57 | 2024-03-26 19:41:57
24 | TT19189 | Asmita Margaje | Bug solving | 2024-03-11 | 04:00:00 | 05:18:45 | 2024-03-11 |  | COMPLETED | DELAYED | 2024-03-13 14:58:10 | 2024-03-13 14:58:10
25 | TT19189 | Asmita Margaje | General meeting | 2024-03-11 | 00:15:00 | 00:59:57 | 2024-03-11 |  | COMPLETED | COMPLETED | 2024-03-11 14:53:49 | 2024-03-11 14:53:49
26 | TT19189 | Asmita Margaje | Live support | 2024-03-25 | 05:00:00 | 04:29:06 | 2024-03-27 |  | COMPLETED | COMPLETED | 2024-03-27 18:48:35 | 2024-03-27 18:48:35
27 | TT19189 | Asmita Margaje | Bug defects /Low Priority defect | 2024-03-25 | 03:00:00 | 04:55:21 | 2024-03-27 |  | COMPLETED | COMPLETED | 2024-03-27 18:48:58 | 2024-03-27 18:48:58
28 | TT19189 | Asmita Margaje | Testing bill checking modules | 2024-03-18 | 02:00:00 | 01:42:41 | 2024-03-18 |  | COMPLETED | COMPLETED | 2024-03-18 16:54:03 | 2024-03-18 16:54:03
29 | TT19189 | Asmita Margaje | UAT Bug solving | 2024-03-18 | 09:00:00 | 25:33:35 | 2024-03-20 |  | COMPLETED | DELAYED | 2024-03-27 15:03:58 | 2024-03-27 15:03:58
30 | TT19189 | Asmita Margaje | Live bug solving | 2024-03-12 | 04:00:00 | 00:00:05 | 2024-03-13 |  | COMPLETED | DELAYED | 2024-03-20 14:53:35 | 2024-03-20 14:53:35
31 | TT19189 | Asmita Margaje | bill payments defect solving | 2024-03-12 | 01:00:00 | 00:14:18 | 2024-03-12 |  | COMPLETED | COMPLETED | 2024-03-12 10:07:08 | 2024-03-12 10:07:08
32 | TT19189 | Priyanka Satpute | Final testing bug solving | 2024-03-06 | 05:00:00 | 05:33:56 | 2024-03-06 |  | COMPLETED | DELAYED | 2024-03-11 11:37:21 | 2024-03-11 11:37:21
33 | TT19296 | Priyanka Satpute | Ts bulk uploaded implementation | 2024-03-06 | 06:00:00 | 06:13:26 | 2024-03-08 |  | COMPLETED | DELAYED | 2024-03-13 14:55:18 | 2024-03-13 14:55:18
34 | TT18190 | Priyanka Satpute | Task And Ticket type master KT | 2024-02-06 | 01:03:00 | 00:00:00 | 2024-03-06 |  | COMPLETED | DELAYED | 2024-03-13 16:44:57 | 2024-03-13 16:44:57
35 | TT19296 | Priyanka Satpute | listen the recording TS Bulk upload | 2024-03-07 | 01:00:00 | 01:07:32 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-11 18:57:45 | 2024-03-11 18:57:45
36 | TT19296 | Priyanka Satpute | Ts bulk Upload Bug solving | 2024-03-28 | 02:00:00 | 00:45:20 | 2024-03-29 |  | IN_PROGRESS | IN_PROGRESS
37 | TT19296 | Priyanka Satpute | Syn Call 28-03-2024 | 2024-03-28 | 00:15:00 | 00:00:06 | 2024-03-28 |  | COMPLETED | COMPLETED | 2024-03-28 12:42:39 | 2024-03-28 12:42:39
38 | TT20380 | Priyanka Satpute | General Discussion with Amit Sir 21-03-2024 | 2024-03-21 | 00:08:00 | 00:26:11 | 2024-03-21 |  | COMPLETED | COMPLETED | 2024-03-21 11:49:47 | 2024-03-21 11:49:47
39 | TT18190 | Priyanka Satpute | Cleaning the codes for the entire ticketing system. All masters are included. | 2024-03-14 | 03:00:00 | 03:13:52 | 2024-03-14 |  | COMPLETED | COMPLETED | 2024-03-14 18:40:05 | 2024-03-14 18:40:05
40 | TT19296 | Priyanka Satpute | Go Live Ticketing System | 2024-03-08 | 01:04:00 | 02:02:03 | 2024-03-26 |  | COMPLETED | DELAYED | 2024-03-27 17:10:34 | 2024-03-27 17:10:34
41 | TT19919 | Priyanka Satpute | Ticketing System : In user master not Able to Save Entry | 2024-03-07 | 01:00:00 | 17:08:23 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-11 11:38:20 | 2024-03-11 11:38:20
42 | TT18190 | Priyanka Satpute | End to End testing bug solving | 2024-03-04 | 08:00:00 | 07:14:22 | 2024-03-05 |  | COMPLETED | DELAYED | 2024-03-11 11:34:48 | 2024-03-11 11:34:48
43 | TT18190 | Priyanka Satpute | March E2E 14-03 testing - bugs solving | 2024-03-15 | 05:00:00 | 43:12:16 | 2024-03-15 |  | COMPLETED | DELAYED | 2024-03-18 18:22:56 | 2024-03-18 18:22:56
44 | TT18190 | Priyanka Satpute | Customer View CR KT Session | 2024-03-05 | 01:00:00 | 00:00:00 | 2024-03-05 |  | COMPLETED | DELAYED | 2024-03-13 16:42:43 | 2024-03-13 16:42:43
45 | TT18190 | Priyanka Satpute | Live support | 2024-03-25 | 03:00:00 | 03:37:07 | 2024-03-27 |  | COMPLETED | COMPLETED | 2024-03-27 18:50:23 | 2024-03-27 18:50:23
46 | TT18190 | Priyanka Satpute | HRMS Employee joining doc reading | 2024-03-05 | 01:00:00 | 00:00:00 | 2024-03-05 |  | COMPLETED | DELAYED | 2024-03-13 16:36:52 | 2024-03-13 16:36:52
47 | TT19189 | Priyanka Satpute | Revamp Sync Meeting with Pritam Sir | 2024-03-15 | 01:00:00 | 00:43:00 | 2024-03-15 |  | COMPLETED | COMPLETED | 2024-03-15 17:53:56 | 2024-03-15 17:53:56
48 | TT18190 | Priyanka Satpute | HRMS Employee joining KT session | 2024-03-07 | 01:00:00 | 00:00:00 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-13 16:35:11 | 2024-03-13 16:35:11
49 | TT18190 | Priyanka Satpute | Bug defects /Low Priority defect | 2024-03-25 | 03:00:00 | 03:50:03 | 2024-03-27 |  | COMPLETED | COMPLETED | 2024-03-27 18:51:55 | 2024-03-27 18:51:55
50 | TT18190 | Priyanka Satpute | Testing bill checking modules | 2024-03-18 | 02:00:00 | 02:31:33 | 2024-03-18 |  | COMPLETED | COMPLETED | 2024-03-18 18:20:36 | 2024-03-18 18:20:36
51 | TT18190 | Priyanka Satpute | Procurement Doc reading | 2024-03-06 | 01:00:00 | 00:00:00 | 2024-03-06 |  | COMPLETED | DELAYED | 2024-03-13 16:43:23 | 2024-03-13 16:43:23
52 | TT19189 | Priyanka Satpute | Meeting with Pritam Sir | 2024-03-18 | 00:30:00 | 00:00:00 | 2024-03-18 |  | COMPLETED | COMPLETED | 2024-03-18 14:07:41 | 2024-03-18 14:07:41
53 | TT19189 | Priyanka Satpute | General meeting | 2024-03-11 | 00:15:00 | 00:40:31 | 2024-03-11 |  | COMPLETED | COMPLETED | 2024-03-11 14:53:49 | 2024-03-11 14:53:49
54 | TT18190 | Priyanka Satpute | Procurement KT | 2024-03-06 | 01:00:00 | 00:00:00 | 2024-03-06 |  | COMPLETED | DELAYED | 2024-03-13 16:36:01 | 2024-03-13 16:36:01
55 | TT19189 | Priyanka Satpute | Bug Solving Ticketing system | 2024-03-11 | 08:00:00 | 09:30:03 | 2024-03-13 |  | COMPLETED | COMPLETED | 2024-03-13 16:40:32 | 2024-03-13 16:40:32
56 | TT18190 | Priyanka Satpute | Go live the TS bulk Upload | 2024-03-06 | 02:00:00 | 00:00:00 | 2024-03-06 |  | TO_DO | DELAYED | 2024-03-27 17:11:36
57 | TT18190 | Priyanka Satpute | Bulk upload Doc Reading | 2024-03-07 | 01:00:00 | 00:27:04 | 2024-03-07 |  | COMPLETED | DELAYED | 2024-03-13 16:34:33 | 2024-03-13 16:34:33
58 | TT18190 | Priyanka Satpute | UAT bug solving :-17-03-2024 | 2024-03-18 | 09:00:00 | 24:10:12 | 2024-03-19 |  | COMPLETED | DELAYED | 2024-03-26 19:43:04 | 2024-03-26 19:43:04
59 | TT18190 | Priyanka Satpute | Daily Sync call 4/3 to 8/3 | 2024-03-04 | 02:30:00 | 01:15:28 | 2024-03-08 |  | COMPLETED | DELAYED | 2024-03-11 11:34:14 | 2024-03-11 11:34:14
60 | TT18190 | Priyanka Satpute | Meeting with BA | 2024-03-20 | 00:17:00 | 00:26:22 | 2024-03-20 |  | COMPLETED | COMPLETED | 2024-03-20 11:26:33 | 2024-03-20 11:26:33
61 | TT8878 | Somyaranjan Sethy | TT-8878 HRMS Go Live | 2024-03-26 | 00:00:00 | 00:00:00 | 2024-06-03 |  | TO_DO | TO_DO
62 | TT20380 | Somyaranjan Sethy | R&D for CI/CD for different different platform | 2024-03-20 | 04:30:00 | 04:08:28 | 2024-03-20 |  | COMPLETED | DELAYED | 2024-03-22 16:19:40 | 2024-03-22 16:19:40
63 | TT8878 | Somyaranjan Sethy | HRMS - UI/Interview Master[Landig page,Add step,Edit step] | 2024-03-27 | 05:30:00 | 06:30:20 | 2024-03-27 |  | COMPLETED | COMPLETED | 2024-03-27 20:09:44 | 2024-03-27 20:09:44
64 | TT20380 | Somyaranjan Sethy | Scrum Call | 2024-03-20 | 01:00:00 | 00:00:00 | 2024-03-20 |  | TO_DO | DELAYED
65 | TT8878 | Somyaranjan Sethy | HRMS - UI/Candidates List [Landing page, Add data, Otp verification, Resend Otp] | 2024-03-27 | 05:00:00 | 04:03:08 | 2024-03-28 |  | IN_PROGRESS | IN_PROGRESS
66 | TT20380 | Somyaranjan Sethy | KT On masters to Somya | 2024-03-20 | 04:05:00 | 00:00:00 | 2024-03-22 |  | COMPLETED | DELAYED | 2024-03-25 10:38:06 | 2024-03-25 10:38:06
67 | TT20380 | Somyaranjan Sethy | Document reading on ticketing and bill checking | 2024-03-20 | 07:20:00 | 04:15:30 | 2024-03-22 |  | IN_PROGRESS | DELAYED | 2024-03-20 12:56:51
68 | TT8878 | Somyaranjan Sethy | R&D for field array | 2024-03-28 | 00:45:00 | 00:00:00 | 2024-03-28 |  | TO_DO | TO_DO
69 | TT8878 | Somyaranjan Sethy | HRMS KT Session | 2024-03-22 | 01:00:00 | 02:24:12 | 2024-03-22 |  | COMPLETED | COMPLETED | 2024-03-22 19:57:12 | 2024-03-22 19:57:12
70 | TT8878 | Somyaranjan Sethy | Hrms planning and discussion | 2024-03-25 | 00:45:00 | 00:00:00 | 2024-03-25 |  | COMPLETED | COMPLETED | 2024-03-25 13:34:35 | 2024-03-25 13:34:35
71 | TT8878 | Somyaranjan Sethy | R&D steper, custom date picker and giving estimation | 2024-03-25 | 05:00:00 | 20:21:15 | 2024-03-25 |  | COMPLETED | DELAYED | 2024-03-26 12:35:12 | 2024-03-26 12:35:12
72 | TT8878 | Somyaranjan Sethy | HRMS - Interview master / candidate joining implementation | 2024-03-26 | 00:00:00 | 00:00:00 | 2024-04-04 |  | COMPLETED | COMPLETED | 2024-03-26 18:29:34 | 2024-03-26 18:29:34

## Sheet1
The selection you're trying to copy and paste is too large. Select a smaller set of data and try again.
MODULE NAME | TEST SCENARIO ID # | TEST SCENARIO DESCRIPTION | EXPECTED RESULT | PRIORITY | NOTES
Sprint | 1 | The sprint should allow add, view and edit functionalities | The system should allow the add, view and edit functionalities. | High
Example:
The add functionality to add the sprint into the system
The view functionality to view the sprint added or updated
The edit functionality to update the sprint in the system
Sprint | 2 | Duplication of data should not be allowed | The duplication of the sprint name is not allowed in a single ticket. | High | backend
Example:
The sprint name should be different.
Sprint | 3 | Error messages | The system should check the validations as per the documentation. | High | backend
Example:
If the user entering any invalid data, error message to be displayed
Sprint | 4 | Add sprint | The sprint can be added either by the project owner and the ticket owner. | High | frontend
Sprint | 5 | Edit sprint | The sprint can be edited only by the project owner. | High | frontend
Sprint | 6 | View sprint | The sprint can be viewed to all the users who are assigned to the ticket i.e., project owner, ticket owner, basket owner and the task owner or the task assigned users. | High | frontend
Sprint | 7 | Sprint view | The sprint can be viewed as a single or multiple. | High
Sprint | 8 | Sprint view | If there is only single sprint, directly the sprint is viewed. | High
Sprint | 9 | Sprint view | If there are multiple sprints, the view can be viewed either all the sprints at a time or single sprint based on the selection made in the sprint dropdown. | High
Sprint | 10 | Previous button | The previous button to view the previous sprint if there are multiple sprints. | High | frontend
Sprint | 11 | Next button | The next button to view the next sprint if there are multiple sprints. | High | frontend
Sprint | 12 | Sprint view | The sprint view consist of the baskets and the tasks added in the specific time frame in between the start date and the end date of the sprint. | High | frontend
Sprint | 13 | Sprint graph | The view of the sprint can be viewed either weekly or monthly or yearly. | High
Sprint | 14 | Sprint graph | The graph can be zoomed in and zoom out for better user experience. | High
Sprint | 15 | Sprint graph | The colour combination for each and every basket created in the sprint is viewed in the graph | High
Sprint | 16 | Sprint graph | The red colour when the sprint or the task missed the end date in the graph | High
Sprint | 17 | Sprint graph | Each task in the time frame is viewed in the sprint. | High
Sprint | 18 | Sprint graph | The specific view of the task in the graph when the user points the task | High
Sprint | 19 | Sprint report | The report is generated based on the sprint selection in the drop down | High
Sprint | 20 | Sprint report | The data to be exported based on the data fetched in the grid view | High
Sprint | 21 | Variance report | The status field to be updated both in the report and the exported data. | High
Sprint | 22 | Actual status in variance report | To do - When the task is created but not played yet and the end date is not exceeded. | High | backend
Sprint | 23 | Actual status in variance report | In progress - When the task is created and started playing and the end date is not exceeded. | High
Sprint | 24 | Actual status in variance report | Completed - When the task is marked completed on or before the end date. | High
Sprint | 25 | Actual status in variance report | Slightly delayed - When the task is marked completed after the end date but within the sprint end date ends. | High
Sprint | 26 | Actual status in variance report | Highly delayed - When the task is marked completed after the end date but after the sprint ends. and also when any task got delayed and the tasks in the sprint got delayed, the delayed tasks in that sprint will be shown as highly delayed. | High
Sprint | 27 | Hamburger Menu | The ticket owner or project owner can add the sprints from the hamburger menu. | High | frontend
Sprint | 28 | Project owner | The project owner can add, edit and view the sprints. | High | frontend
Sprint | 29 | Ticket owner | The ticket owner can add and view the sprints. | High | frontend
Sprint | 30 | Basket owner | The basket owner can only view the sprints. | High | frontend
Sprint | 31 | Task owner | The task owner can only view the sprints. | High | frontend
Sprint | 32 | Task users | The task users can only view the sprints. | High | frontend
Sprint | 33 | Sprint View | By default, all the tasks to be displayed which includes all the tasks and the sprints. | High
Sprint | 34 | Sprint view | The sprint selected from the drop-down can be viewed. If de-selected, all tasks page is displayed. | High
Sprint | 35 | Sprint graph | The dark red colour when the sprint date is missed for that particular task. And if any task missed the deadline and the sprint crossed, then that will be displayed in the dark red colour. | High
Sprint | 36 | Sprint graph | The view of the tasks in the sprint. | High
Sprint | 37 | Sprint graph | The played task will be displayed in the cross lines. | High
Sprint | 38 | Sprint graph | Division of the sprints is even shown. | High
Sprint | 39 | Actual status in variance report | Delayed - When the task is delayed but the sprint not yet completed. | High
Sprint | 40 | Sprint task status | To do - When the task is created but not played yet and the end date is not exceeded. | High
Sprint | 41 | Sprint task status | In progress - When the task is created and started playing and the end date is not exceeded. | High
Sprint | 42 | Sprint task status | Completed - When the task is marked completed on or before the end date. | High
Sprint | 43 | Sprint task status | Delayed - When the task is delayed but the sprint not yet completed. | High
Sprint | 44 | Sprint task status | Slightly delayed - When the task is marked completed after the end date but within the sprint end date ends. | High
Sprint | 45 | Sprint task status | Highly delayed - When the task is marked completed after the end date but after the sprint ends and also when any task got delayed and the tasks in the sprint got delayed, the delayed tasks in that sprint will be shown as highly delayed. | High
Sprint | 46 | Sprint Calendar | The view of the daily, weekly and monthly. | High
Sprint | 47 | Sprint Calendar | The colour combination for each and every status is shown in the sprint | High
Sprint | 48 | Sprint Calendar | The red colour when the task missed the end date | High
Sprint | 49 | Sprint Calendar | The dark red colour when the sprint date is missed for that particular task. And if any task missed the deadline and the sprint crossed, then that will be displayed in the dark red colour. | High
Sprint | 50 | Sprint Calendar | The view of the tasks in the sprint. | High
Sprint | 51 | Sprint Calendar | The specific view of the task when the user points the task | High
Sprint | 52 | Sprint Calendar | Division of the sprints is even shown. | High