## data
sr | ticket_id | task_owner | sprint_name | sprint_start_date | sprint_end_date | task_name | type_name | task_start_Date | task_scheduled_Hours | task_actual_worked | task_delivery_scheduled | task_last_update | task_status | task_actual_status | task_updated_at | task_completed_at
1 | TT24206 | Digvijay Tulse | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Digvijay about connect us 2.0 (Masters , except customer mapping ) | Internal KT/cross KT | 2024-10-07 | 02:00:00 | 01:56:19 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 14:11:10
2 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Weekly sync call with Gaurav Sir | Meeting with PH | 2024-10-03 | 00:00:00 | 00:00:00 | 2024-10-10 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 13:31:36
3 | TT23495 | Preeti Bokade | - | - | - | Footer / Setting Discussion KT | KT Session | 2024-10-07 | 00:30:00 | 00:58:55 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 13:21:38 | 2024-10-07 13:21:38
4 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Resource planning Report analysis | Performance analysis and improvement plan | 2024-10-07 | 00:24:00 | 00:57:15 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-08 15:00:48
5 | TT24180 | Preeti Bokade | Oct-2024 | 2024-10-01 | 2024-10-31 | Support from Gaurav sir | Query clarification | 2024-10-07 | 00:24:00 | 00:00:00 | 2024-10-31 |  | TO_DO | TO_DO
6 | TT24206 | Preeti Bokade | Testing_KT_Oct24_Wk1 | 2024-09-30 | 2024-10-06 | KT to Digvijay about connect us 2.0 (Masters , except customer mapping ) | Internal KT/cross KT | 2024-10-07 | 02:00:00 | 01:30:21 | 2024-10-08 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-07 14:11:10
7 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Conflit meeting against task scheduling | Testing Team Meeting | 2024-10-07 | 00:30:00 | 00:00:00 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 19:07:17 | 2024-10-07 19:07:17
8 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Monthly meeting with Gaurav sir | Meeting with PH | 2024-10-07 | 01:00:00 | 01:02:12 | 2024-10-07 |  | COMPLETED | IN_TIME | 2024-10-07 17:40:34 | 2024-10-07 17:40:34
9 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:07:47 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS | 2024-10-06 23:48:07
10 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:47 | 2024-10-06 23:46:47
11 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:20 | 2024-10-06 23:45:20
12 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:45:10 | 2024-10-06 23:45:10
13 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:00:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:46:59 | 2024-10-06 23:46:59
14 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Gokul | Query clarification | 2024-10-07 | 00:15:00 | 00:00:00 | 2024-10-11 |  | COMPLETED | IN_TIME | 2024-10-06 23:43:31 | 2024-10-06 23:43:31
15 | TT24303 | Preeti Bokade | Testing_GM_Oct_2024_Wk1 | 2024-09-30 | 2024-10-04 | Support to Sayali | Query clarification | 2024-10-07 | 00:15:00 | 00:28:35 | 2024-10-11 |  | IN_PROGRESS | IN_PROGRESS