## TPM
Sr No | Project | Module | Sub-module | Platform | Function | field | Testing Type | Testing Group | Severity | Test Description | Steps | Expected Result | Actual Status 10/07/2024 | Actual Status 10/13/2024 | Status:10/07/2024 | Status: 10/13/2024 | Screenshot 10/07/2024 | Screenshot 10/13/2024 | Actual Status 10/17/2024 | Final Testing:10/17/2024 | Screenshot 10/17/2024 | Actual Status 10/20/2024 | Final Testing: 10/20/2024 | Screenshot 10/20/2024 | Actual Status 22/10/2024 | Testing Status 22/10/2024 | Screenshot 22/10/2024
TC_1 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | View |  | UI | Smoke | Medium | Verify that the page loads correctly without any UI issues. |  | The page should load all elements correctly without errors. | Add button + icon is not awailable(All browser) | As Expected | Fail | Pass | SS!A1 |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | SS1!A70
TC_2 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | View |  | UI | Smoke | Medium | Verify all fields and buttons UI |  | All Input fields and buttons should be well aligned as per figma-i.customer Name/Mobile ii.store iii.Net amount iv. Remark | Remark Feild alignment is not as per figma |  | Fail | Need to discuss | SS!A70 |  | Remark field Text box size is large and there is no Provision For save remark, unable to Save remarrk | Need to discuss | SS1!J17 | As Expected | Pass |  | As Expected | pass | SS1!A70
TC_3 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | Gift Card type | Validations | Regression | Medium | Verify Gift Card type drop-down |  | Drop-down should be clickable with hard-coded options-1.Physical Gift card 2.E-Gift card 3.Paper Gift card 4.Auto generated | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | SS!A85
TC_4 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | Reference Number | Validations | Regression | low | Verify Reference number field |  | Should accept integer only | Accepting Characters , negative number also | Reference number field accepting -ve value, character and special characters | Fail | Fail | SS!AT3 | SS1!A2 | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | SS!A102
TC_5 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add |  | Validations | Regression | Medium | Verify item Id Drop-down |  | GC item category vise Item id should reflect | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | SS!A102
TC_6 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add |  | Validations | Regression | Medium | Verify Variant ID drop-down |  | According to item release product variant should reflect | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_7 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | Denomination | Validations | Regression | Medium | Verify Denomination field |  | User will get denomination value as per setted variant value and it should not be editable in physical gift card case | As Expected | Denomination field is editable in case of physical gift card case | Pass | Fail |  | https://share.nmblc.cloud/bc67dcb8 | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/5775fb3c
TC_8 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | No. of gift card | Validations | Regression | Medium | Verify Number of gift card issued field |  | Number of gift card field should be accept only integer values, negative value should not allow | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/3a5fc267
TC_9 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | Expiry date | Validations | Regression | Medium | Verify Expiry date field |  | 1.Expiry date should be reflect first according to item expiry date. 2.If Expiry date of item is not given then it will consider from as per jewellery parameter setting. | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/6ac05e6b https://share.nmblc.cloud/2d9ef2eb
TC_10 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | Customer name | Validations | Regression | Medium | Verify Customer Account drop-down |  | Should reflect all available customers from account receivable -> all customers | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_11 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | View | Customer name | Validations | Regression | Medium | Verify Customer Name/Mobile Number field |  | Customer Name/Mobile Number will get as per selection of customer | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | SS1!A70
TC_12 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  | Store | Validations | Regression | Medium | Verify Store field |  | User will get From cash registry location (store from which user logged in will reflect) | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | SS1!A70
TC_13 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Gift voucher popup | Functional | Regression | Medium | Validate add Process |  | After clicking on add button gift voucher pop-Up will reflect with-Quantity, Starting Number,Gift Card Name,Gift Card Category,Ending No,Rate,Amount,GV Validity Date fields. | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_14 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Quantity | Validations | Regression | Medium | Verify Quantity field |  | 1. User should able to add numberic data 2. Shouldn't add negative and alpha numeric values 3. shouldn't be zero (0) | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_15 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Starting Number | Validations | Regression | Medium | Validate Starting number field |  | User should be able to add starting number of Gift Card | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_16 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Starting Number | Validations | Regression | Medium | Validate quantity & starting number field limit |  | quantity and startring number field should have limit Quantity accepting : 89764513206546462454651465465165468656456165455646546546545646545646545646546545648465156 | accepting any value : ex GCG10000532354894651451656653156132545612 |  |  | Suggestion |  |  | Suggestion | Suggestion |  |  | Suggestion |  |  | Suggestion
TC_17 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Gift Card Name | Validations | Regression | Medium | Verify Gift card Name field |  | As per 'starting number' gift card name will show.This is non editable field. | As Expected | As per document value column Item Id should reflect in gift card name field | Pass | Fail |  | SS1!A4 | BA Comment:As per jewellery parameter gift card item name show | Pass |  | As Expected | Pass |  | As Expected | pass
TC_18 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Gift Card Category | Validations | Regression | Medium | Verify Gift Card category |  | As per "starting number" gift card category will show.This is non editable field. | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_19 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Ending No | Validations | Regression | Medium | Verify Ending Number |  | As per the starting number and quantity, the ending number will be shown. | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_20 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Rate | Validations | Regression | Medium | Verify Rate field |  | As per Gift card rate will be display. | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_21 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Validations | Regression | Medium | Verify Amount = rate * quantity |  | In amount field value will reflect as per Rate * quantity | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_22 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Validations | Regression | Medium | Verify GV Validity date |  | GV validity will reflect as per item validity GV validity = current date + (Expiry Days against item Id if set / jewellery parameter Gift card Expiry Days) | As Expected | For physical gift card Fetching wrong GV validity date. | Pass | Fail |  | SS1!A6 | BA & dev:Deffered | Deferred |  |  | Deferred |  |  | Deferred
TC_23 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | High | Verify Save button |  | Button should clickable and after clicking detailed line will reflect on Gift Card sale bill page | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | Pass
TC_24 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | cancel |  | Functional | Regression | High | Verify Cancel process |  | After Clicking on cancel button user will not able to proceed and navigate to home page and clear entered data | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | Pass
TC_25 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add |  | Functional | Regression | High | Verify User Can perform sale gift card process with already used Gift card number |  | User should not allow already used GC number and User will get error as "gift Card is already issued." | As Expected | Error should be meaningful if user reissue any GC. "Gift Card is already issued." | Pass | Fail |  | SS1!A8 | BA:Not required | Not required |  | As Expected | Not Required |  |  | Not Required
TC_26 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add |  | Functional | Regression | High | Verify Gift card creation-"Customer account field " if selected by user |  | If the user selects a customer during gift card generation, the gift card can only be sold to that specific customer | As Expected | The user can issue a GC to any customer, even if the GC was generated for a specific customer | Pass | Fail |  | gift voucher | Still Persist | Deferred | https://share.nmblc.cloud/1ce96271 |  |  |  | As Expected | pass | https://share.nmblc.cloud/03f84f5c https://share.nmblc.cloud/62a81b7a
TC_27 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | High | Verify Gift card creation-Customer account field if not added by user |  | If the user hasn't selects a customer during gift card generation, the gift card can be sold to that any customer | As Expected | As Expected | pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass | https://share.nmblc.cloud/f960ec6e | If the user hasn't selects a customer during gift card generation, the gift card can be sold to that any customer, getting error "DataAreaId Is not ValidStore Is not Valid " | fail | https://share.nmblc.cloud/fd9e52ac https://share.nmblc.cloud/cc202abb
TC_28 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | High | Verify Stores |  | User should be able to issue gift card only for that specific store | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/f9457638
TC_29 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Payment |  | Functional | Regression | High | Verify User Can perform payment by cash |  | user should make payment by cash | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/224f258e
TC_30 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Payment |  | Functional | Regression | High | Verify User Can perform payment by card |  | user should make payment by card | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/224f258e
TC_31 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Payment |  | Functional | Regression | High | Verify User Can perform payment by UPI |  | user should make payment by UPI | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/224f258e
TC_32 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Payment |  | Functional | Regression | High | Verify User Can perform payment by advance |  | user should make payment by using advance | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/7e467943
TC_33 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Payment |  | Functional | Regression | low | Verify working of payment mode back button |  | after clicking on payment mode back button it should show previous page (GC sale bill) |  | payment mode back button not present |  | Fail |  | SS1!A10 | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/ed3154eb
TC_34 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | High | Verify User can sale expired GC |  | User Shouldn't sale expired gift card | As Expected | user is able to issue expired GC, and Once it is issued it is updating expiry date in D365 against that GC | Pass | Fail |  | SS1!A12 | BA:User can issue expired gift card but user can not redeem the expired gift acrd.Not a bug. | Deferred |  |  | Deferred
TC_35 | Microsoft Dynamic D365 | D365 & POS | Gift Voucher sale | Web | Add |  | Functional | Regression | High | Verify Gift Card generation Process for Paper gift card | 1.Open Gift Card details page & Click on generate Gift card. 2.Select Gift Card type as paper gift card 3.Add item & Variant Id 4.Add denomination 5.Add No of gift card and proceed 6.On Gift card Sale bill PEWS-click on add 7.Add require data with rate and click on save | 1.Generate Gift Card popUp will reflect with fields-Gift card type, reference number,item id , variant id, denomination,no of gift card issued,Expiry date and customer account. 2.Should be selectable 3.User should able to add item and variant id 4.User should be able to add/edit value for denomination feild(Paper Gift card). 5.As per added information it will proceed 6.User will get gift voucher popup 7.Paper gift card case rate Should be editable and after clicking on save it will navigate to home page . | 7.Rate is not editable in POS | As Expected | Fail | Pass | SS!A288 |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_36 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add |  | Integration | Regression | High | Verify rate field in paper Gift card Case |  | If user changed rate from POS Rate field that should be reflect in D POS | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/83963cc2
TC_37 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | View |  | Integration | Regression | Medium | Verify paper Gift Card POS Reflection |  | As per created gift card all data should Reflect in POS from D POS | Unable to Edit Rate | For paper gift card Fetching wrong GV validity date. | Pending | Fail |  | SS1!A14 | BA:This is deferred. | Deferred |  |  | Pass |  | As Expected | pass | https://share.nmblc.cloud/83963cc2
TC_38 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Usability | Regression | Low | Verify Behavior if user clicked go to payment without adding sale bill |  | User Shouldn't go for further process will get error as"Please add data" | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/a697b838
TC_39 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | View |  | UI | Smoke | Medium | Verify Mandatory fields are Marked with asterik |  | All Mandatory fields should be marked with asterik | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_40 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  | Starting Number | Usability | Regression | Medium | check behavior without adding Starting number field |  | User should get error as"Please enter starting number" | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/bc99dabf
TC_41 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  | Starting Number | Validations | Regression | High | Verify PAN card field for Tax Page |  | The pancard should be below mentioned format : First 5 characters: alphabets (e.g., ABCXY) Next 4 characters: digits (e.g., 1116) Last 1 character: alphabet (e.g., G) EX :"ABCXY1116G" | Not getting Page for upload pan and adhaar for more than 2 lakhs gift card value | As Expected | Fail | Pass | gift voucher |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/0a3ddd5f
TC_42 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | High | Verify Cash limit |  | If user crossed daily cash limit then user should not able to proceed by cash | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/22a18b77
TC_43 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | High | Verify Tax information Page |  | If User creating GC more than 2 lakhs amount user will get Tax information Page User Need to attache atleast i.Pan card ii.form 60 iii.form 61 and validate | Not getting Page for upload pan and adhaar for more than 2 lakhs gift card value |  | Fail | Pass | gift voucher |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass | https://share.nmblc.cloud/0a3ddd5f
TC_44 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | Medium | Verify back button functionality |  | If the user enters PAN card details with an attachment, validates it, and moves to the payment mode, clicking the back button from the payment mode should redirect the user to the PAN details page, and the entered data should remain intact |  | If the user enters PAN card details with an attachment, validates it, and moves to the payment mode, clicking the back button from the payment mode should redirect the user to the PAN details page, and the entered data should remain intact |  | Fail |  | https://share.nmblc.cloud/5bc6d9df | CR | Deferred |  |  | Deferred |  |  | Deferred
TC_45 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional | Regression | High | Verify Advance Utilization for GC Creation |  | User can utilize URD and blanket advance for GV sale process | As Expected | For URD advance getting posting error 00000048-090688 | Pass | Fail |  | SS1!A18 |  | Need to discuss |  |  | Need to discuss |  |  | NA
TC_46 | Microsoft Dynamic D365 | D365 | Gift Voucher sale | Web |  |  | Validations | Regression | low | Validate Number sequence For GC |  | User will get As per selected Item name Number sequence | As Expected | As Expected | Pass | Pass |  |  | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_47 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | Variant id | Functional |  | Medium | Verify that the Variant ID drop-down is cleared after changing the Item ID. |  | If the user selects an item ID and a corresponding variant based on that item ID, the variant field should be cleared whenever the item ID is changed |  | When the user selects an item ID and a corresponding variant based on that item ID, the variant field does not clear when the item ID is changed |  | Fail |  | https://share.nmblc.cloud/3c8fb9a8 | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_48 | Microsoft Dynamic D365 | D365 | gift card details | Web | Add | Denomination | Validations | Regression | Medium | Verify Denomination field accepting zero (0) |  | Denomination field should not accept zero (0) and negative value for both physical and paper gift card |  | Denomination field should not accept zero (0) for both physical and paper gift card GS0320 / GCG1000074 |  | Fail |  | https://share.nmblc.cloud/bc67dcb8 | As Expected | Pass |  | As Expected | Pass |  | Denomination field Accepting -ve values | Fail | https://share.nmblc.cloud/e8c13afe
TC_49 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Ending No | Functional | Regression | Medium | Verify Ending Number updating after user change quantity |  | Based on the starting number and quantity, the ending number will be displayed. If the user changes the quantity after scanning the GC, the ending number should be updated accordingly |  | If the user changes the quantity after scanning the GC, the ending number not updating |  | Fail |  | https://share.nmblc.cloud/fe660b20 |  | Deferred |  |  | Deferred |  |  | Deferred
TC_50 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add | Amount | Functional | Regression | Medium | Verify Amount updating after user change quantity |  | Based on the rate and quantity, the amount will be displayed. If the user changes the quantity after scanning the GC, the amount should be updated accordingly |  | If the user changes the quantity after scanning the GC, the amount not updating |  | Fail |  | https://share.nmblc.cloud/930fb77f |  | Deferred |  |  | Deferred |  |  | Deferred
TC_51 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web | Add |  | UI |  | Medium | Verify print format |  | All details should reflect from gift sale bill |  | On print format Net amount is wrong(in numbers and in words) Amount paid by payment method reflecting wrong amount |  | Fail |  | SS1!A20 | As Expected | Pass |  | As Expected | Pass |  | As Expected | pass
TC_52 | Microsoft Dynamic D365 | Inventory management - | on hand list | Web |  |  | Functional |  | High | Verify inventory effect after GC issued to any customer (after posting) |  | If user issue any gift card to any customer then inventory must be deducted from that store | [12 empty] | If user issue any gift card to any customer then inventory must be deducted from that store | Fail | https://share.nmblc.cloud/01534b6b https://share.nmblc.cloud/73b791cf
TC_53 | Microsoft Dynamic D365 | Jewellery | gift card details | Web | grid |  | Functional |  | Medium | Verify that latest record showing on top of grid |  | latest record should reflect on top | [12 empty] | after generating gift card it should refelct on top | Fail | SS1!A118 | https://share.nmblc.cloud/4aeba6a5
TC_54 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Validations |  | low | Verify fields are clearing after user scan GC and click anywhere or not |  | After GC scan if user clicks any where on screen it should clear fields as popup is closing | [12 empty] | After GC scan if user clicks any where on screen it should clear fields as popup is closing | Fail | https://share.nmblc.cloud/571c3d15
TC_55 | Microsoft Dynamic D365 | POS | Gift Voucher sale | Web |  |  | Functional |  | Medium | Verify whether, when a user creates a gift card (GC) in D365 and runs the job without transferring it to any store, and later transfers the same GC to a specific store and scans it there, all the details are properly retrieved for that GC at the store. |  | when a user creates a gift card (GC) in D365 and runs the job without transferring it to any store, and later transfers the same GC to a specific store and scans it there, all the details are properly retrieved for that GC at the store. | [12 empty] | when a user creates a gift card (GC) in D365 and runs the job without transferring it to any store, and later transfers the same GC to a specific store and scans it there, then getting "DataAreaId Is not ValidStore Is not Valid" error | Fail | https://share.nmblc.cloud/54384e21

## Report (hidden)
Defect Status@071024 | New
Count of Defect ID | Priority
Severity | High | Low | Grand Total
High | 3 |  | 3
Medium |  | 3 | 3
Grand Total | 3 | 3 | 6
Defect Status: 10/13/2024 | New
Count of Defect ID | Priority
Severity | High | Low | Medium | Grand Total
High | 3 | 1 |  | 4
Medium |  |  | 10 | 10
Low |  | 2 |  | 2
Grand Total | 3 | 3 | 10 | 16
Test case execution status: 10/13/2024 | Status: 10/13/2024
Sub-module | Fail | Pass | Suggestion | Need to discuss | Grand Total
gift card details | 5 | 6 |  |  | 11
Gift Voucher sale | 11 | 27 | 1 | 1 | 40
Grand Total | 16 | 33 | 1 | 1 | 51
Count of Defect ID |  | Priority
Severity | Defect Status: 10/17/2024_2 | High | Low | Medium | Grand Total
High |  | 3 | 1 |  | 4
| Closed | 1 | 1 |  | 2
| Deferred | 1 |  |  | 1
| Need to discuss | 1 |  |  | 1
Medium |  |  |  | 11 | 11
| Closed |  |  | 5 | 5
| Deferred |  |  | 3 | 3
| Need to discuss |  |  | 3 | 3
Low |  |  | 2 |  | 2
| Closed |  | 2 |  | 2
Grand Total |  | 3 | 3 | 11 | 17
Count of Final Testing | Final Testing:10/17/2024
Sub-module | Pass | Need to discuss | Deferred | Not required | Suggestion | Grand Total
gift card details | 10 |  | 1 |  |  | 11
Gift Voucher sale | 32 | 2 | 4 | 1 | 1 | 40
Grand Total | 42 | 2 | 5 | 1 | 1 | 51
Count of Defect ID |  | Priority
Severity | Defect Status 20/10/2024 | High | Low | Medium | Grand Total
High |  | 3 | 1 |  | 4
| Closed | 1 | 1 |  | 2
| Deferred | 1 |  |  | 1
| Need to discuss | 1 |  |  | 1
Medium |  |  |  | 11 | 11
| Closed |  |  | 4 | 4
| Deferred |  |  | 7 | 7
Low |  |  | 2 |  | 2
| Closed |  | 2 |  | 2
Grand Total |  | 3 | 3 | 11 | 17
Count of Final Testing: 10/20/2024 | Final Testing: 10/20/2024
Sub-module | Deferred | Need to discuss | Pass | Suggestion | Grand Total
gift card details | 1 |  | 10 |  | 11
Gift Voucher sale | 6 | 1 | 32 | 1 | 40
Grand Total | 7 | 1 | 42 | 1 | 51

## Defect Log
Sr No | Defect ID | Raise on Date | Module | Sub Module | Function | Severity | Priority | Defect Description | Assign To | Defect Status 10/07/2024 | Defect Status 10/13/2024 |  |  | Tester comment | BA comment for 10/07/2024 | Dev Status for 10/07/2024 | Dev comment
1 | TC_1 | 2024-10-07 | POS | GiftVoucher |  | Medium | Low | On gift card sale bill page Add button + icon is not awailable(All browser) |  | New | Closed |  |  |  | alredy given | Solved
2 | TC_2 | 2024-10-07 | POS | GiftVoucher |  | Medium | Low | On gift card sale bill page Remark Feild alignment is not as per figma |  | New |  |  |  |  | Not a bug
3 | TC_4 | 2024-10-07 | POS | GiftVoucher |  | Medium | Low | For reference number in D-while creating GC Accepting Characters , negative number also |  | New | New |  |  |  | Bug
4 | TC_33 | 2024-10-07 | POS | GiftVoucher |  | High | High | On gift voucher popup Rate is not editable in POS |  | New | Closed |  |  |  | alredy given | Solved
5 | TC_39 | 2024-10-07 | POS | GiftVoucher |  | High | High | Not getting Page for upload pan and adhaar for more than 2 lakhs gift card value |  | New | Closed |  |  |  | Bug | Solved
6 | TC_41 | 2024-10-07 | POS | GiftVoucher |  | High | High | Not getting Page for upload pan and adhaar for more than 2 lakhs gift card value |  | New | Closed |  |  |  | Duplicate
Sr No | Defect ID | Raise on Date | Module | Sub Module | Function | Severity | Priority | Defect Description 10/13/2024 | Assign To | Defect Status: 10/13/2024 | Screenshot 10/13/2024 | Defect Status: 10/17/2024 | Screenshot 10/17/2024 | Tester comment | BA comment for defect raised on 10/07/2024 | Dev Status for defect raised on 10/07/2024 | Dev comment(17-10-2024) | Tester Comments 17/10/2024 & 18/10/2024 | BA Remark (19/10/2024) | Defect Status 20/10/2024 | Tester Comments 20/10/2024 | Defect Status 22/10/2024 | Screenshots 22/10/2024 | Tester Comments 22/10/2024 | BA Remark 22/10/2024 | Tester comment 22/10/2024 after 10 PM | BAcomment 22/10/2024 after 10 PM
1 | TC_4 | 2024-10-13 | D365 | gift card details | Add | Low | Low | Reference number field accepting -ve value, character and special characters |  | New | SS1!A2 | Closed |  |  | Bug (It accept character , number and "-" and space) |  | Resolved |  |  | Closed
2 | TC_7 | 2024-10-13 | D365 | gift card details | Add | Medium | Medium | Denomination field is editable in case of physical gift card case |  | New | https://share.nmblc.cloud/bc67dcb8 | Closed |  |  | Bug |  | Resolved |  |  | Closed
3 | TC_17 | 2024-10-13 | POS | Gift Voucher sale | Add | Medium | Medium | As per document value column, Item Id should reflect in gift card name field |  | New | SS1!A4 | Deferred |  |  | As per jewellery parameter gift card item name show |  |  | We will consider it as CR | Document update and send on mail. | Deferred | CR
4 | TC_22 | 2024-10-13 | POS | Gift Voucher sale |  | Medium | Medium | For physical gift card Fetching wrong GV validity date. |  | New | SS1!A6 | Deferred |  |  | This is deferred. |  |  |  |  | Deferred | CR
5 | TC_25 | 2024-10-13 | POS | Gift Voucher sale | Add | High | Low | Error should be meaningful if user reissue any GC. "Gift Card is already issued." |  | New | SS1!A8 | Closed |  |  | Not required. |  |  |  |  | Closed
6 | TC_26 | 2024-10-13 | D365 | gift card details | Add | High | High | The user can issue a GC to any customer, even if the GC was generated for a specific customer |  | New | https://share.nmblc.cloud/1ce96271 | Closed | gift voucher |  | Bug |  | As per discussed with Baliram Sir, the point has to not being solved by D- Team | https://share.nmblc.cloud/519b9e44 |  | Closed
7 | TC_33 | 2024-10-13 | POS | Gift Voucher sale | Payment | low | Low | payment mode back button not present |  | New | SS1!A10 | Closed |  |  | Remove all payment lione then back button is enable. |  |  |  |  | Closed
8 | TC_34 | 2024-10-13 | POS | Gift Voucher sale |  | High | High | user is able to issue expired GC, and Once it is issued it is updating expiry date in D365 against that GC |  | New | SS1!A12 | Deferred |  |  | User can issue expired gift card but user can not redeem the expired gift acrd.Not a bug. |  |  | We will consider it as CR | Need to discuss | Deferred | CR
9 | TC_37 | 2024-10-13 | POS | Gift Voucher sale | View | Medium | Medium | For paper gift card Fetching wrong GV validity date. |  | New | SS1!A14 | Deferred |  |  | duplicate. same condition will apply on any gift card for experiy. |  |  | We will consider it as CR | In the document this condition is already add. development team working on it. | Deferred | CR
10 | TC_44 | 2024-10-13 | POS | Gift Voucher sale |  | Medium | Medium | If the user enters PAN card details with an attachment, validates it, and moves to the payment mode, clicking the back button from the payment mode should redirect the user to the PAN details page, and the entered data should remain intact |  | New | https://share.nmblc.cloud/5bc6d9df | Deferred |  |  | Bug |  | CR | CR | For this CR sanika will working on it. and it is applicabple to all type of transactions. | Deferred | CR
11 | TC_45 | 2024-10-13 | D365 | Gift Voucher sale |  | High | High | For URD advance getting posting error 00000048-090688 |  | New | SS1!A18 | Need to discuss |  |  | Bug |  | Not Bug (As per our discussion with Divya Ma'am, this is not related to the gift card ) |  |  | Need to discuss
12 | TC_47 | 2024-10-13 | D365 | gift card details | Add | Medium | Medium | When the user selects an item ID and a corresponding variant based on that item ID, the variant field does not clear when the item ID is changed |  | New | https://share.nmblc.cloud/3c8fb9a8 | Closed |  |  | Bug |  | Resolved |  |  | Closed
13 | TC_48 | 2024-10-13 | D365 | gift card details | Add | Medium | Medium | Denomination field should not accept zero (0) for both physical and paper gift card GS0320 / GCG1000074 |  | New | https://share.nmblc.cloud/bc67dcb8 | Closed |  |  | Bug |  | Resolved |  |  | Closed
14 | TC_49 | 2024-10-13 | POS | Gift Voucher sale | Add | Medium | Medium | If the user changes the quantity after scanning the GC, the ending number not updating |  | New | https://share.nmblc.cloud/fe660b20 | Need to discuss |  |  | Not a bug. Click on ">" sign then this is update. |  |  | The ending number should update based on changes in quantity, rather than when the starting number button is clicked | Quantity is added and click on “>” this button then quantity field is disable. Document update and send on mail. | Deferred | CR
15 | TC_50 | 2024-10-13 | POS | Gift Voucher sale | Add | Medium | Medium | If the user changes the quantity after scanning the GC, the amount not updating |  | New | https://share.nmblc.cloud/930fb77f | Need to discuss |  |  | Not a bug. Click on ">" sign then this is update. |  |  | The amount should update based on changes in quantity, rather than when the starting number button is clicked. | Quantity is added and click on “>” this button then quantity field is disable. Document update and send on mail. | Deferred | CR
16 | TC_51 | 2024-10-13 | POS | Gift Voucher sale |  | Medium | Medium | On print format Net amount is wrong(in numbers and in words) Amount paid by payment method reflecting wrong amount |  | New | SS1!A20 | Closed |  |  | Bug |  | Solved |  |  | Closed
17 | TC_02 | 2024-10-13 | POS | Gift Voucher sale |  | Medium | Medium | On gift card sale bill page-Remark field Text box size is large and there is no Provision For save remark, unable to Save remark |  | New | SS1!J17 | Need to discuss | SS1!J17 |  |  |  |  | In document no details about this field. Hence we will consider it as CR | Document update and send on mail. | Deferred | CR
18 | TC_52 | 2024-10-22 | Inventory management | on hand list |  | High | High | If user issue any gift card to any customer then inventory must be deducted from that store | [13 empty] | New | https://share.nmblc.cloud/01534b6b https://share.nmblc.cloud/73b791cf | Need updated document | CR
| TC_48 | 2024-10-22 | D365 | gift card details |  | Medium | Medium | Denomination field Accepting -ve values | [13 empty] | New | https://share.nmblc.cloud/e8c13afe |  |  | Date : 22/10/24 https://share.nmblc.cloud/c3e5f598 Bug has been resolved on UAT | closed
| TC_53 | 2024-10-22 | Jewellery | gift card details |  | Medium | Medium | after generating gift card it should refelct on top | [13 empty] | New | SS1!A118 | https://share.nmblc.cloud/4aeba6a5 |  | Date : 22/10/24 https://share.nmblc.cloud/c3e5f598 Bug has been resolved on UAT | closed
| TC_54 | 2024-10-22 | POS | Gift Voucher sale |  | Low | Low | After GC scan if user clicks any where on screen it should clear fields as popup is closing | [13 empty] | New | https://share.nmblc.cloud/571c3d15 |  |  | https://share.nmblc.cloud/c736c01f | Bug exist
| TC_55 | 2024-10-22 | POS | Gift Voucher sale |  | Medium | Medium | when a user creates a gift card (GC) in D365 and runs the job without transferring it to any store, and later transfers the same GC to a specific store and scans it there, then getting "DataAreaId Is not ValidStore Is not Valid" error | [13 empty] | New | https://share.nmblc.cloud/54384e21 |  |  | https://share.nmblc.cloud/9f77807f | closed
| TC_27 | 2024-10-22 | POS | Gift Voucher sale |  | High | High | If the user hasn't selects a customer during gift card generation, the gift card can be sold to that any customer, getting error "DataAreaId Is not ValidStore Is not Valid" | [13 empty] | New | https://share.nmblc.cloud/fd9e52ac https://share.nmblc.cloud/cc202abb |  |  | https://share.nmblc.cloud/c86140ee | https://share.nmblc.cloud/8c6efb3c | closed

## SS1
=DISPIMG("ID_2BDA9EAD87594BF89814B95E2EE2E739",1)
=DISPIMG("ID_D6E61E0AE59F48D1BCFBFB7901B74FBC",1) | =DISPIMG("ID_259D34E3825640E2965D53DF3E2C69EF",1) | =DISPIMG("ID_73F2FDD7B52C417F8E5533F0D6ABB280",1)
=DISPIMG("ID_DFB8058AFA21439CB4B433AEF4554C6E",1) | =DISPIMG("ID_8A06A8EED3D5449DA583AD5EDEFCE6A5",1) | =DISPIMG("ID_F49990EFDBA0430C819BF7BF6796B9C1",1) | =DISPIMG("ID_2633991B966F4DF19690D77A58A20408",1)
=DISPIMG("ID_F17E24050C1C4BAABD833DE470D325E6",1)
=DISPIMG("ID_6228E537EEAF4E9D8EC8D1BFF962FEA1",1)
=DISPIMG("ID_64E57730CBE84048ABF684970248E01A",1) | =DISPIMG("ID_4CC6A2E5A279472EA9A991CF77A6D8FE",1) | =DISPIMG("ID_461110F358974C7B897D10071BB3F6C7",1) | =DISPIMG("ID_DBD212FD9082407BBCC60FD1E8286B4D",1) | =DISPIMG("ID_4881196655D64F41A7FD433C407CADEF",1)
=DISPIMG("ID_3B032316FF564573B1C2C3319908AE23",1)
=DISPIMG("ID_E294526CFE5C4B8E98129B2778DE05A0",1)
=DISPIMG("ID_D8113446CE5A4D3DB5DDABA810149B0D",1) | =DISPIMG("ID_05CF879B92964DE19A2F3211DCEC50A7",1)
=DISPIMG("ID_C198845CCEC140439C22168B10EC28BB",1)